SNG Annual Review 2016 - Summary Sheet

Title: Sub National Governance Programme
Programme Value: £38.1 million		Review Date: 5 - 23 March 2016
Programme Code: 202367	Start Date: 8 April 2013	End Date: 30 September 2017

Summary of Programme Performance

Year	2014	2015	2016
Programme Score	A	A	A+
Risk Rating	Severe	Severe	Major

Summary of progress and lessons learnt since last review:
The Sub-National Governance programme (SNG) has now been running for three years and is well established as a planning and finance reforms support mechanism in both Punjab and Khyber Pakhtunkhwa. In year three, some of the programme’s key successes were:
- Agreement and roll out of a Public Financial Management (PFM) strategy in Punjab in line with the provincial Finance Minister’s reform agenda, which also led to the restructuring of the Finance Department with significant functional improvements;
- Successful piloting of Geographical Information System (GIS) as a planning and monitoring tool with early signs of evidence-based decision making at the district level and a clear government appetite to adopt this technology;
- Improved budget transparency through the publication of citizen budgets and an overall improvement in provision of budget information;
- Increased budget allocations in health and education in 12 SNG districts through better needs based assessments and output based budgeting with potential benefits for 25 million citizens;
- Finalisation of rules of business, budgeting and other key functions for the new local governments in Khyber Pakhtunkhwa, which enabled timely release of devolved development expenditure (30% of total development expenditure for the province) to all districts;
- Government’s agreement to adopt 5 pilots to improve public service delivery in health and education under the Challenge Fund with intended benefits for more than 250,000 people in the next 12 months; one specific pilot on “Broad Class – Listen to Learn” that uses interactive radio instructions to improve learning outcomes for primary school girls in two districts in Khyber Pakhtunkhwa was recognised by the Global Development Network as the ‘Most Innovative Development Project’;
- Established a Strategic Support Unit in the Chief Minister Khyber Pakhtunkhwa’s office to drive key government priorities by setting up a routine of high level stocktakes. The Unit established itself within six months and is seen as a driver of reform by the Chief Minister and the governing political party.

Key lessons learnt were:
- Experiences of the PFM reform strategy in Punjab and Strategic Support Unit in Khyber Pakhtunkhwa point to the criticality of working politically;
- Digital innovations provide long term opportunities to improve planning and management in the public sector, which should be further explored;
- In public sector reforms programmes, it is important to monitor improvements in government outcomes and tangible benefits for citizens;
- Local governments will remain in transition requiring the programme to take a flexible approach to support and embed devolution over time.

Summary of recommendations for the next year:
- In its final 18 months, the programme should focus on consolidation and prioritisation of its work i.e. the log frame should be revised to capture the programme results in four core outputs: i) innovations in service delivery and planning; ii) improving public financial management; iii) supporting devolution; and iv) supporting delivery units.
- The programme should look to do more on supporting devolution, embedding GIS and improving budget oversight with clearer linkages between the spend and service delivery outcomes.
- The scope of final impact evaluation should focus on: a) improvement in government planning and finance functions and outcomes; b) tangible benefits for the citizens; and c) lessons learnt for future programming on public financial management and planning reforms

These recommendations will be reflected in the 2016-17 workplans, followed up through the provincial steering committees and tracked through the SNG delivery plan.

Acronyms

ADP Annual Development Plan / BTR Budget Transparency Review / DEA District Education Authority / DFID Department for International Development / DHA District Health Authority / DSD Directorate of Staff Development / EFOs Externally-Financed Outputs / FATA Federally Administrated Tribal Areas / GIS Geographical Information System / GoKP Government of Khyber Pakhtunkhwa / GoP Government of Pakistan / GoPb Government of Punjab / ICT Information and Communication Technology / KP Khyber Pakhtunkhwa / KPI Key Performance Indicators / M&E Monitoring and Evaluation / MDGs Millennium Development Goals / MoU Memorandum of Understanding / MTBF Medium Term Budgetary Framework / MTFF Medium Term Fiscal Framework / OBB Output Based Budgeting / OBI Open Budget Index / OPM Oxford Policy Management / PEFA Public Expenditure and Financial Accountability / PETS Public Expenditure Tracking Survey / PFM Public Financial Management / PFM Public Financial Management / PKR Pakistani Rupee / PLSM Pakistan Living Standards Measurement / PPA Partnership Principles Assessment / SMU Special Monitoring Unit / SNG Sub-National Governance programme / SSU Strategic Support Unit / VfM Value for Money

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/

Outline of the Programme

DFID Pakistan’s £38.1 million Sub-National Governance programme (SNG), 2013-2017, responds to the challenge of weak governance in Khyber Pakhtunkhwa (KP) and Punjab - the two focus provinces of DFID Pakistan’s portfolio. The programme aims to contribute towards stable democracy in Pakistan by supporting the improvement of government service delivery through strengthening the finance and planning functions in 12 districts, six each in Khyber Pakhtunkhwa and Punjab, working closely with the respective provincial governments. The Oxford Policy Management (OPM) led consortium is the key implementing partner and provider of the technical assistance.

Services better meet the needs of poor people in Khyber Pakhtunkhwa and Punjab
Increased government capability and responsiveness to deliver services
Improved state-society relations / more stable democracy in Pakistan
SNG Theory of Change
(Simplified from the Business Case)

In the first three years of the programme, there have been six areas of SNG activity.

Technical Assistance on public financial management, planning and local governance at both provincial and sub-provincial levels.

Piloting Geographical Information System (GIS) at district level to strengthen evidence-based planning and monitoring using adequate socio-spatial data.

Supporting the establishment of effective and viable Delivery Units in Punjab and Khyber Pakhtunkhwa to improve service delivery in selected departments of both provincial governments: Special Monitoring Unit (SMU) in Punjab and Strategic Support Unit (SSU) in Khyber Pakhtunkhwa.

Challenge Funds in both provinces to pilot innovative service delivery interventions at sub-provincial levels. The first round focused on education and the second round focused on health. Following the second annual review and mid-term impact evaluation, it was decided not to plan any future rounds and focus instead on consolidation of ongoing work within the programme timeframe.

Conditional Grants for the Construction of Missing Facilities in Health and Education in Khyber Pakhtunkhwa through the provision of ear-marked budget support in 6 districts. The programme is currently focusing on gaps in the construction quality of the schools; DFID will not make any further disbursements to the Government of Khyber Pakhtunkhwa until these issues are addressed.

Work with the World Bank, primarily in Punjab, on three Externally-Financed Outputs (EFOs) on Information and Communication Technology (ICT); Right to Information legislation; and a Public Expenditure and Financial Accountability (PEFA) assessment of Pakistan’s Federally Administered Tribal Areas (FATA). This component is completed.
Synergies with Health and Education programmes

As a cross-cutting governance programme, SNG directly contributes to improving health and education outcomes in both focus provinces. SNG works with DFID sector programmes to support institutional improvements at the provincial level. This is enhanced at the district level, where SNG focuses on implementing and embedding PFM and planning reforms in the 12 target districts. Similarly, SNG’s work on service delivery and planning innovations, under the Challenge Fund and GIS components, also contributes towards better education and health outcomes.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The programme’s outcome, as set out in the business case, aims at an improved service delivery at the district level and is measured through the levels of household satisfaction of and access to improved primary health and basic education services. Outcome indicators rely on three sources: the Pakistan Living Standards Measurement survey (PLSM), Punjab Education Statistics and Expanded Programme on Immunization Coverage Survey. At the time of reporting, none of these sources have provided updated information on these indicators but it is likely that more data will be available in the next six months. The review therefore cannot comment on specific levels of progress at the outcome level at this stage but judges a positive trajectory against outcome targets on the basis that the programme is on track against all output level milestones.

Over the last three years, the programme has delivered a number of strong results in improving finance and planning functions and in providing innovative service delivery models. Going into year four, the programme is delivering at pace with strong government buy in and pockets of excellence exist across the outputs. SNG remains relevant to the context and the project interventions are delivered at a high quality generally. As the programme moves towards its closure, a focus on consolidation and institutionalisation of key successes will make a sustainable positive outcome more likely.

An independent mid-term impact evaluation, which was conducted last year, confirmed that the programme remains relevant to the context, the needs of the government and the intended beneficiaries and that the Theory of Change holds true. The review recognises the constraints of the current log frame to capture the outcome of the programme and recommends that the outcome must be carefully and thoroughly assessed in the final impact evaluation. This may require commissioning additional evidence in the final 18 months of the programme.

Overall output score and description

Overall the programme scored an ‘A+’ – Moderately Exceeding Expectations. The scores against each of the outputs are as follows:
Log frame output	Punjab	KP	Risk
Output 1. Decisions by sub-national governments are based on robust evidence (30%)	A+		Substantial / (revised to moderate)
1.1 Need Based Budgeting	A+	A+
1.2 Service Delivery Pilots (Challenge Fund)	A+	A
1.3 Geographical Information System to enable Evidence-Based Planning	A+	A+
Output 2 - Sub-national government services are more responsive to peoples' needs (30%)	A		Substantial / (revised to moderate)
2.1 Increase Non-Salary Budget Allocation	A	A++
2.2 e-Governance Pilots	Not scored	N/A
2.3 Improve Budget Transparency	A	A
Output 3 Strengthened sub-national government capability to deliver basic services. (40%)	A+		Major / (no change)
3.1 Performance based budgets	A	A
3.2 Expenditure Tracking System to improve Financial Flows and Controls	A+	A+
3.3 Increase Fiscal Space	A++	A+

Key lessons

- Experiences of PFM strategy in Punjab and the Strategic Support Unit in Khyber Pakhtunkhwa point to the criticality of working politically. Going forward, SNG must see how it can further incentivise political ownership for its wider set of technical interventions while appreciating the different operating contexts of both provinces.
- Digital innovations have clear potential and traction to improve public sector decision making and service delivery as proven by various challenge fund pilots and GIS work. A problem driven approach using champions is right in the short term, but the long term approach should focus on socialising technology as a default planning and management tool in a participatory manner.
- In public sector reform programmes, monitoring project interventions alone is not sufficient to gauge both the impact and sustainability; programmes must allocate resources to monitor improvements in government outcomes and tangible benefits for citizens.
- The complex political context means that, for the time being, local governments will remain in transition while elected representatives negotiate their fiscal and administrative space with various stakeholders. This requires the programme taking a flexible approach to supporting the transition process to embed devolved service delivery and increased local accountability.

Key Actions

- Revise the log frame in view of the recommendations below.
- Design an impact evaluation that addresses the difficulties of measuring the programme outcome and captures lessons to provide a springboard for future programming.
- Treat critical school repairs under conditional grants as a key priority and establish a routine for regular follow up.
- Building on the success of first three years, the programme should identify opportunities to engage more on GIS, devolution and budget execution.
- Develop and rollout an exit strategy with the underlying principles of consolidation and institutionalisation of SNG’s success in the last 18 months of the programme.
- Encourage and facilitate mutual lesson learning between both provinces on areas such as PFM strategy, where Punjab has been more successful, and support to devolution, where Khyber Pakhtunkhwa is at more advanced stage.
- Ensure that the government counterparts are part of the discussions around log frame revisions, workplan prioritisation and design of the impact evaluation. This will give them a substantial opportunity to make proactive inputs in SNG delivery as the primary client and will also improve the communication loop.

Has the log frame been updated since the last review?

The log frame was updated after last year’s annual review.
Log frame recommendations

- With a view to consolidate and prioritise programme delivery in the final 18 months, the log frame should be revised to capture the programme results in four core outputs: i) innovations in service delivery and planning; ii) improving public financial management; iii) supporting devolution; and iv) supporting provincial delivery units.
- Outcome level indicators should also be revisited to capture how the programme contributes to the high level context on finance and planning. Alternate baselines such as PEFA, DFID Fiduciary Risk Assessments and Country Governance Assessments may be considered, which can also reduce the attribution challenges.

## C: DETAILED OUTPUT SCORING

Output 1	Decisions by sub-national governments are based on robust evidence
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicators Punjab	Milestones	Progress
Output indicator 1.1: District budgets based on evidence of people’s needs	Evidence based lobbying - with a focus on the needs of women, girls and marginalised groups - results in institutionalising need based planning and budgeting in 3 districts	Moderately exceeding expectations (A+): / Evidence based budget proposals adopted for 6 SNG districts (against the target of 3 districts) with potential benefits for 16 million citizens in primary health care
Output indicator 1.2: Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	2 pilots assessed and recommended for adoption and 2 pilots made operational benefitting 120,000 people with a focus on women, girls and marginalized groups	Moderately exceeding expectations (A+): / 2 pilots from round 1 and 1 pilot from round 2 recommended for adoption with more than 150,000 potential beneficiaries. / Four pilots from round 2 are operational with an outreach of 459,000 beneficiaries ( 260,000) women, girls and marginalised)
Output indicator 1.3: Government uses Geographic Information Systems (GIS) to monitor and plan quantity and quality of services	GIS operational in 6 districts for service delivery monitoring, with a focus on health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.	Moderately exceeding expectations (A+): / 6 GIS cells are operational in 6 districts of Punjab; strong evidence of traction and utility within upper tiers of district management for monitoring, planning and decision-making / Strong evidence of success: trebling of district revenue (from a low base) and improvement of constituency delimitation by alignment of population pockets. / Wide use of GIS technology across areas such as police, elections, revenue, municipal services, land registry etc which is on the top of originally targeted health and education services
Indicators KP	Milestones	Progress
Output indicator 1.1: District budgets based on evidence of people’s needs	Evidence based lobbying - with a focus on the needs of women, girls and marginalised groups - results in institutionalizing need based planning and budgeting in 3 districts	Moderately exceeding expectations (A+): / SNG supported 6 districts (against the target of 3 districts) administrations and councils in Annual Development Plan preparation process on the basis of community needs and evidence with potential benefits for 9 million citizens in primary education.
Output indicator 1.2: Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	2 pilots assessed and recommended for adoption and 2 pilots made operational benefitting 120,000 people - with a focus on women, girls and marginalized groups	Meeting expectations (A): / Government agreed to scale up 2 pilots from round 1, which will benefit more than 80,000 people directly. / Two pilots from round 2 are operational with an outreach for one million beneficiaries ( at least 600,000 women, girls and marginalised)
Output indicator 1.3: Government uses Geographic Information Systems (GIS) to monitor and plan quantity and quality of services	GIS operational in 6 districts for service delivery monitoring, with a focus on health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.	Moderately exceeding expectations (A+): / 6 GIS cells are operational in six districts of Khyber Pakhtunkhwa; strong evidence of traction and utility within upper tiers of district management for monitoring, planning and decision-making / Representative success stories include mapping of flood affected areas for a timely response and improved coverage of basic health services through improved access analysis. / Government of Khyber Pakhtunkhwa moving towards scale up of GIS in 8 additional districts

Evidence-based budgeting at the district level

This year the programme was successful in embedding need-based budget assessments across all 12 SNG districts in both provinces. As a result, the district budgets better reflected the needs of the community through more rational forecast and improved allocations towards primary health and primary education with improved access and coverage for potentially 25 million citizens (16 million in Punjab and 9 million in Khyber Pakhtunkhwa). It is also significant that SNG developed a need assessments toolkit and trained more than 250 district officials to use it. As a result, evidence based budgeting was mainstreamed in SNG districts enabling district governments to undertake needs-based assessment themselves. This is an early sign of sustainability.

Service Delivery Pilots

The SNG challenge fund was designed as a space to test and experiment alternate service delivery models, which if successful could be scaled up by the partner governments. Following a slow start in the first two years, the challenge fund came together in year 3 providing some really good stories around various service delivery innovations in health and education. For example, one specific pilot on “Broad Class – Listen to Learn” that uses interactive radio instructions to improve learning outcomes for primary school girls in two districts in Khyber Pakhtunkhwa, was recognised by the Global Development Network as the ‘Most Innovative Development Project’ in a global competition. Similarly, a pilot to streamline immunisation coverage using electronic records through low-cost mobile technology has already made a compelling case for adoption at scale in Punjab.

Altogether 14 pilots have been funded, 8 focusing on primary education and 6 on primary health, in both provinces. These pilots cater to more than 2 million beneficiaries already (at least 1.4 million women, vulnerable and marginalised). By the spirit of the design, the review will judge the success of these pilots primarily by adoption at scale by the government and/or other development partners. Learning Boost, a pilot that used low cost android tablets to increase learning outcomes at primary school level, is now being scaled up to three more districts in Punjab.

There is a strong buy in and excitement around the ongoing technology based experiments to increase immunisation and to provide remote maternal health care, but more evidence is required before any scale up commitment. In Khyber Pakhtunkhwa, the government decided that the Tele Taleem and Science Camp projects will be gradually scaled up in the selected districts; however scale up across the province will be the true measure of challenge fund’s success. Altogether, 5 pilots are seeing a partial scale up with more in the pipeline which suggests that this component is more than on track.

Geographical Information System (GIS)

GIS is a computer system that helps manipulate, analyse and present (visualize) information that is tied to a spatial location. GIS work under SNG is a strong example of how technology can enable efficient and evidence-based decision making. SNG successfully piloted GIS cells in four districts, two each in both provinces, and then scaled up in all 12 SNG districts proving both its VFM and its potential for transformative impact at district level.

Success stories include district revenue almost trebling (albeit from a very low base) simply by revising urban-area ratings on the basis of population density and improved disaster response by better damage assessment. On multiple occasions, constituency delimitation was done in a more rational way by alignment of population pockets on the basis of geographical neighbourhood and population density rather than political incentives.

The Government of Khyber Pakhtunkhwa has already budgeted scale up of GIS in 8 additional districts, while Punjab is also likely to follow suit. GIS is arguably the signature result under this output with a strong multiplier effect.

Recommendations

- Need based budgeting – Going forward focus should be on ensuring that funds are released in accordance with allocations, which in turn are translated in improved budget execution. Next year’s milestone should capture improved budget execution in addition to developing need-based budgets and ensuring minimum sectoral allocations.
- Challenge Fund – SNG and DFID could do more to capture and communicate the lessons learnt from various service delivery innovations, which are particularly relevant for the partners and programmes in health and education. The programme should continue to support the demand for adoption of successful pilots at scale by government.
- Geographical Information Systems – Further expand the use of GIS at the district level, enabling elected local government officials to understand and use GIS for planning and monitoring purposes. Provide GIS access to education and health departments at the district level to help further mainstream the use of GIS in evidence-based decision making. Continue to track (preferably independently) to see how GIS reports are actually being used for better planning and monitoring of service delivery. The focus of SNG should be on making GIS sustainable, effectively used by officials and building the capacity of a critical mass of mid-tier officials at District level in each department who understand how to use GIS.

Output 2	Sub-national government services are more responsive to peoples' needs
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicators Punjab	Milestones	Progress
Output indicator 2.1: Proportion of budget allocated to primary health and primary education at district level	Share of non-salary recurrent budget in primary health and primary education allocated to the district level is 60%	Meeting expectations (A): / The proportion of non-salary recurrent budget allocated to primary health and education in the six SNG districts rose to 61% in the budget 2015-16 from a base of about 58% in 2012-13.
Output indicator 2.2: Number of Departments / districts using smart information communication technology	No milestones for this year as related interventions were concluded in the previous reporting year.	N/A.
Output indicator 2.3: Provincial Open Budget Index score	Provincial Open Budget Index (OBI) score improved by 15% (63 from 55)	Meeting expectations (A): / OBI score increased to 63
Indicators KP	Milestones	Progress
Output indicator 2.1: Proportion of budget allocated to primary health and primary education at district level	Share of non-salary recurrent budget in primary health and primary education allocated to the district level is 26%	Strongly exceeding expectations (A++): / Allocation of non-salary recurrent budget to primary health and education in six focus districts for FY 2015/16 rose to 48% from the baseline of 22% in FY 2012-13
Output indicator 2.3: Provincial Open Budget Index score	Provincial Open Budget Index (OBI) score improved by 25% (55 from 44)	Exceeding expectations (A): / OBI score increased to 60

Non- Salary Budget

International experience suggests that it is extremely difficult to increase allocations towards non-salary budget therefore it is commendable that SNG has enabled a shift in such allocations by 26% upwards in Khyber Pakhtunkhwa. This gives district government significant space for spending on critical area of operations and maintenance, which if not done properly can substantially hold back service delivery. In Punjab, where the baseline is already high, the 3% increase is still meaningful and has positive dividends for public expenditure.

Budget Transparency

On budget transparency, SNG has done well to conduct the first ever sub-national baselines using the Open Budget Index in both provinces. Initiatives such as Citizen Budgets, which present lengthy budget documents in a 20 page summary, have increased budget legibility and were used by the parliamentarians to have a meaningful budget debate at the macro level at least. Both provinces have responded well to the baselines and are placed significantly above the national score of 43/100. This year, the budget strategy paper has been shared with parliamentarians four months in advance of budget finalisation; enabling a critical window for pre-budget public steer and inputs which the Finance Minister has pledged to take into account in the final budget.

Earmarked Conditional Grants for missing health and education facilities

DFID agreed a £9 million earmarked financial aid package with Government of Khyber Pakhtunkhwa through conditional grants – an expenditure model in which government and donor money is channelled through communities to construct missing health and education facilities. Following the disbursement of first tranche of £2.5 million in 2013, DFID discovered gaps in management and construction controls. The programme is currently focusing on addressing these gaps and making repairs to poorly constructed facilities. DFID will not make any further disbursements to the Government of Khyber Pakhtunkhwa until these issues are addressed. This decision was communicated and agreed at the steering committee level.

SNG will take forward the repairs of 272 sub-standard school classrooms built from DFID funds given the urgency of the repairs needed. This year, OPM after thoroughly testing the market identified a commercial arrangement to take forward repairs to 52% of these classrooms, while plans are underway to respond to the remaining 48% class rooms. Repair work will start on the ground in May 2016. Repairing all sub-standard class rooms is a programme priority for 2016/17.

Recommendations

- Non-Salary Budget – There are two main challenges that SNG should continue to address; one is to help government maintain this momentum and make it irreversible by embedding good planning and budgeting practices and second to shift the focus more to improving the rate and quality of non-salary expenditure. The programme should also monitor the impact in service delivery as a result of increased non-salary budget.
- Budget Transparency: SNG should get the OBI score independently peer reviewed as a core requirement of the methodology. Citizens budgets at provincial levels are a good start at macro level budget transparency, the important next steps remain improved budget transparency and reporting at the district level and also in overall budget utilisation.
- Prioritise Conditional Grants Schools Repairs: Pick up the pace of delivery on Conditional Grants School Repairs, so that this can be concluded in the final leg of the programme.

Output 3	Strengthened sub-national government capability to deliver basic services.
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators Punjab	Milestones	Progress
Output indicator 3.1: Sub-national planning is more performance orientated (especially for health and education)	Performance based budgets with service delivery targets (including targets for women and girls) approved in primary health and education for 2 districts.	Meeting expectations (A): / Key performance indicators agreed with 2 SNG districts leading to first ever Performance Budget Statements at the district level for health to inform the budget for FY 2016-17 / Robust support in drafting the rules and structures of newly proposed District Health Authorities and District Education Authorities. / Education’s performance budget work deprioritised by SNG as it is being led by PESP (Punjab Education Support Programme)
Output indicator 3.2: Percentage of budget reaching service delivery units	At least 25% of recommendations from Public Expenditure Tracking Survey (PETS) implemented in all 6 SNG districts	Moderately Exceeding expectations (A+): / 40% of PETS recommendations being implemented across all 6 SNG districts, with better fund flows to Basic Health Units leading to preliminary 32% increase in outpatient numbers.
Output indicator 3.3: Increased provincial resources to finance services	Expenditure saving / revenue raising activities deliver efficiency savings of £7m	Exceeding expectations (A++): / This is a cumulative target, with total potential savings of £18.9 million to date. / £11.6 million saving materialised in implementation this year
Indicators KP	Milestones	Progress
Output indicator 3.1: Sub-national planning is more performance orientated (especially for health and education)	District OBB targets agreed for health and education in 6 focus districts (including targets for women and girls)	Meeting expectations (A): / Medium-term OBB targets for health and education in six focus districts have been set and agreed with district governments.
Output indicator 3.2: Percentage of budget reaching service delivery units	Expenditure tracking system established in one pilot district for one sector	Moderately exceeding expectations (A+): / Public expenditure tracking system for health sector established in two pilot districts – Haripur and Dera Ismail Khan. / Has led to better accounting for £2.2 million budget across 94 health facilities benefitting population coverage of 140,000.
Output indicator 3.3: Increased provincial resources to finance services	Expenditure saving / revenue raising activities deliver efficiency savings of £7m	Moderately exceeding expectations (A+): / This is a cumulative target, with total potential savings of £10.52 million to date. / £3.56 million savings materialised in implementation this year

Performance Oriented Budgeting

SNG is aiming to shift the governments away from incremental budgeting by bringing a long term results focus to the budget cycle. This is done through initiatives such as Output Based Budgeting (OBB), Medium Term Budgeting Framework and performance based budget statements. In Khyber Pakhtunkhwa, OBB targets for health and education for the financial year 2016-17 have been agreed in all SNG districts. In Punjab, SNG initiated work on piloting OBB at provincial level in two Education and Livestock Departments as well as in two publicly owned enterprises – Saaf Paani Company (Clean Water) and Lahore Waste Management Company. These will also be reflected in the financial year 2016-17.

SNG introduced a structured approach to performance based budgeting for primary healthcare in 2 districts using key performance indicators, which will account for over 80% of the non-recurrent health allocation in these districts. This will provide the framework when setting up next year’s budget with particular focus for district priorities on access of various health care facilities.

In Khyber Pakhtunkhwa, SNG helped establish a comprehensive performance monitoring system in the Chief Secretary’s office, covering all service delivery departments at the district. A routine of monthly performance reporting on key performance indicators has brought some key improvements such as increase in polio vaccination coverage. All data is also made public leading to greater citizen engagement and greater transparency.

SNG also revised the Annual Development Plan guidelines for both provinces bringing further results focus for development expenditure at the district level. Consideration for gender and other social indicators, for instance, has appeared for the first time as a legal requirement.

Public Expenditure Tracking

Last year, SNG conducted Public Expenditure Tracking Surveys (PETS) in four districts, two districts in each province, with a particular focus on primary health care. The objective was to help government counterparts get a better handle on the financial flows particularly below the sub-district level down to the service delivery unit. This directly responds to some of the gaps in current accounting mechanisms. To take the findings and recommendations forward, SNG came up with a PETS implementation plan in Punjab for all six SNG districts. 40% of these recommendations have already been implemented. For example adopting an improved system for budgeting and expenditure tracking for 400 Basic Health Units has led to a substantial increase in medicine supplies with 32% increase in patients’ outturn.

In Khyber Pakhtunkhwa, SNG came up with a comprehensive automotive expenditure tracking system that disaggregates all the expenses at the health care facility level and links with the central accounting system. This is already being piloted in Haripur and D.I. Khan covering 94 health facilities with approximately £2.2 million traceable health budget between them for financial year 2015-16. This has contributed to improved medicine supplies for approximately 140,000 citizens in the pilot districts. In the next 18 months, SNG will be aiming to embed this expenditure tracking system across the province by working closely with the health sector programme.

Improving Fiscal Space/ Efficiency Savings

Efficiency savings are significant in the way that they make more provincial resources available to finance key public services. SNG has delivered exceptionally well in this area making a strong VFM case on the basis that the improved fiscal space in government budgets is equal to the total programme costs.

In both Punjab and Khyber Pakhtunkhwa, SNG has helped materialise efficiency savings and additional revenues of over £15.1 million to date. Examples include identification of £10 million efficiency savings through a payroll audit, covering 400,000 education sector employees, of which £3 million have been delivered in FY 2015-16. In Khyber Pakhtunkhwa, SNG identified new areas of tax and non-tax revenue enabling government to raise an additional £1.75 million. By enhanced scrutiny of the budget, the Government of Khyber Pakhtunkhwa was able to save a further £1.76 million in the reporting year. SNG is also supporting the Punjab Provincial Revenue Authority with a survey to identify 10,000 additional businesses in five key urban centres and thereby potentially increase the tax base.

Additional Results

The programme also delivered the following additional results, which are not directly captured by the log frame, but are relevant to the output and significant for the overall programme objectives:

The PFM Roadmap and the Restructuring of Finance Department in Punjab. Support to this initiative has allowed Punjab to have a consolidated and cohesive strategy to take the PFM reform agenda forward and monitor progress through a prioritised action plan. If implemented as planned, it has the potential to unlock Punjab’s true potential in achieving inclusive broad based growth. This also led to a major restructuring of the Finance Department with a clearer division of labour by separating the functions of budgeting and resources and expenditure and investment. The new structure also includes specialist units for Corporate Finance and Debt Management. Such modernisation effort of a finance department in unprecedented in the Pakistani context and is likely to have a multiple efficiency gains and a national demonstration effect.

Support to devolution, particularly in Khyber Pakhtunkhwa, focused on devising rules of business, budgeting, human resources and other critical functions for the newly formed local government which enabled timely release of the 30% devolved development budget to all districts. Similarly, training and resource management support in addition to support to select districts in devising output/needs based district budgets has helped Government of Khyber Pakhtunkhwa in delivering on its critical commitment of devolution which, we expect, is a prerequisite for improved and needs based service delivery.

Established a Strategic Support Unit in the Chief Minister Khyber Pakhtunkhwa’s office to drive key government priorities by setting up a routine of high level stocktakes through timely and high quality technical assistance. The Unit established itself within six months and is seen as a key driver of reform by the Chief Minister and the governing political party. It is further seen as huge value for money providing top class technical assistance support to the Chief Minister for delivering priorities across government.

These high value results justify the value for money of the programme and further reinforce an A+ score for this output.

Recommendations

- Embedding Output Based Budgeting – SNG support in preparing in-year and end-year OBB implementation reports to establish a stronger link with the annual budgets. This will help embed a routine of using these documents which are currently treated as a one-off activity with little relevance to budget execution.
- Improved Fiscal Space – SNG must keep up the good work and continue to follow up on the identified potential savings so that they are delivered at scale in the budget implementation. Similarly, it will be critical that the findings of the ongoing tax survey are actioned.
- PFM Strategy in Khyber Pakhtunkhwa – It has remained in draft for the last six years and has also been picked up in the latest Fiduciary Risk Assessment. The review recommends taking a similar approach to Punjab by working politically to take this agenda forward.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The total spend to date on the SNG is approximately £17.9 million (47%) out of a total programme budget of £38.1 million. The component breakdown of spend suggests a 78% expenditure incurred on technical assistance and innovations under the challenge fund and the GIS, 13% financial aid to government, 8% on externally financed outputs through the World Bank and 1% on design and monitoring. The largest spending continues to be on the technical assistance contract managed by OPM. As a core technical assistance programme, these trends are assessed to be reasonable.

SNG remains on track to spend all programme funds over the next 18 months / two financial years on technical assistance and innovation. The £6.5 million, which are committed to the Government of Khyber Pakhtunkhwa for financial aid ‘Conditional Grants’, can only be disbursed once critical school repairs are complete and more robust management and construction quality controls are in place.

Recommendation

DFID to explore programming options for the funds allocated to financial aid for school construction in Khyber Pakhtunkhwa.

VfM performance compared to the original VfM proposition in the business case

The SNG Business Case recognised that the programme interventions at provincial and sub-national levels would lead to both tangible and intangible benefits and social outcomes whose attribution to the programme may not be easily quantified. However, using conservative assumptions, selected tangible benefits were quantified at the business case stage – including increased productivity of the government and ultimate welfare gains enjoyed by end users of services (such as longer life and higher income).

The programme has been implemented for three years now and as evident in the assessment below, DFID funded inputs have started to yield returns in terms of efficiency gains and savings for the government through better planning and budgeting. These benefits are discussed in detail below. There is however, a need to capture information on how these benefits are being converted to benefit the end user. This would allow a clearer comparison with the proposition in the business case. This could potentially be done through the impact assessment.

The programme has already helped both provinces deliver efficiency savings of £15.1 million in implementation with another £10 million identified, which suggests a break even with regards to the programme’s actual costs and benefits.

Assessment of whether the programme continues to represent value for money

It is challenging to make an overarching assessment that the programme is delivering VFM for three reasons. Firstly, although the log frame milestones have been met, it is still unclear (including attribution challenges within the delivered outputs) if the outputs are effectively being converted into outcomes. Secondly, a partial but significant part of the programme needed to focus on district level planning and execution with direct link to service delivery; evidence of this has only picked up in the third year of implementation (with preliminary results starting to surface now). Lastly, and most importantly, overall intended outcome/impact expects that the reform initiatives introduced under this programme will not be reversed after DFID funding concludes, which needs to be further tested.

That said there are three major components of the programme where DFID funded interventions have continued to demonstrate VFM, at least at the output level. Selected illustrations are discussed below:

Under output 1, there is evidence available which suggests that the direction of travel is encouraging and that decisions by sub national governments are based on robust evidence:

- Needs assessments have influenced budget proposals in 12 districts of Khyber Pakhtunkhwa and Punjab, with potential benefits for 25 million people (16 million in Punjab and 9 million people in Khyber Pakhtunkhwa).
- More specifically, there has been a 34% increase in non-salary allocations in primary health care in 6 districts in Khyber Pakhtunkhwa as a result of needs-based budgeting supported by SNG. If utilised as intended, for every £1 spent by SNG there has been an increase of £0.35 in allocations to primary health care across the 6 pilot districts to date.

There are good VFM illustrations under output 2, which focuses on ensuring that sub-national government services are more responsive to people’s needs:

SNG’s investment has played a significant role in ensuring that Government of Khyber Pakhtunkhwa and Punjab stick to their commitment of increasing the non-salary budget for education and health sectors. In Khyber Pakhtunkhwa, the share of the total non-salary budget allocated to the health and education sectors was increased to 48% in 2015-16, compared to a target of 26% in 2014-15 and a baseline of 22% in 2012-13. Similarly, in Punjab, budget allocated to the health and education sectors increased to 61% in 2015-16, 3% higher compared to a baseline of 58% in 2012-13. Precise increases, if utilised as planned, have the potential of converting each £1 SNG investment to £2.60 additional money available in non-salary budgets for education and health in 2015-16.

VFM is the strongest under output 3, which aims to strengthen sub-national government capability to deliver basic services:

- With the support of SNG funded technical assistance, efficiency savings of £3.51 million have been realised (with another £6.5 million identified) in Khyber Pakhtunkhwa, while in Punjab efficiency savings of £11.6 million were realised. Overall a total of £15.1 million efficiency savings realised, which is directly attributable to SNG investment. This suggests a saving cost ratio of 12:1 i.e. every £1 investment led to £12 savings/revenue.
- SNG support to draft local government rules enabled timely release of 30% devolved budget across Khyber Pakhtunkhwa, which further demonstrates the strong enabling effect and positive VFM for the programme.

Quality of financial management

The programme is input based and over FY 2015/16, the programme spend has been broadly in line with forecasts, with discrepancies fairly small where they took place. The main spend is on the Challenge Fund which has picked up pace in its second round. The programme has demonstrated strong financial management controls for downstream partners with due diligence, spot checks and audit processes in place. Monthly invoicing quality has gradually improved over the past year. Invoices are supported by a narrative report along with a budget tracker and support documents which are reviewed by DFID before processing the disbursements. Cost efficiencies are achieved through continuous negotiation between DFID and OPM.

Recommendation

The programme may benefit from a prioritisation exercise to seek further budget efficiencies.

Date of last narrative financial report	09 March 2016
Date of last audited annual statement	04 December 2015

## E: RISK

Overall risk rating: Major

The programme has been rated as a major risk programme due to the complex context, operating environment and difficult political economy in both Punjab and Khyber Pakhtunkhwa. Successive ‘A’ ratings in previous annual reviews suggest that good mitigating measures are in place. There is a view that the delivery risk is moderate in Punjab while major in Khyber Pakhtunkhwa specifically on the conditional grants component. The review acknowledges that despite consistent delivery, the programme operates in a conflict-prone context with high levels of political uncertainty in Khyber Pakhtunkhwa; the overall risk rating has been revised to major.

Overview of programme risk

The annual review recognises that in principle SNG’s provincial programmes in Khyber Pakhtunkhwa and Punjab are relatively different and separate from each other, because of separate political settings. The major risks are:

Uncertainty around devolution: The local government elections are completed in Khyber Pakhtunkhwa and Punjab. While Khyber Pakhtunkhwa local government systems have started to progress slowly, Punjab has not yet come to a decision on how power will be devolved to the lower tiers of government. Uncertainty around this may hinder the programme’s ambitions in the districts. This should be mitigated through more engagement with the local government and other relevant departments to implement the local government rules in true spirit.

Sustainability: There is a risk that some of the governance reforms influenced by SNG may not be sustainable beyond the life of the programme. This needs to be mitigated through greater government ownership, lower government staff turnover and matching capacity building alongside the technical assistance. The programme must carefully and closely support the institutionalisation of the reforms along with developing and rolling out an exit strategy and framework for possible future programme directions.

Security and conflict: This remains a challenge for DFID and OPM staff, particularly in South Khyber Pakhtunkhwa. DFID’s ability to visit Khyber Pakhtunkhwa remains restricted with OPM staff having fewer access issues. The OPM security team is vigilant and have regular liaison with British High Commission. The findings of the conflict-mapping exercise for Khyber Pakhtunkhwa districts should now be mainstreamed.

Low evidence base: The absence of a robust mechanism to provide assurance and independent view of SNG interventions at outcome level will be mitigated by putting in place third party monitors and a robust final impact evaluation.

Outstanding actions from risk assessment

The programme has done well to complete the final audit of conditional grants pertaining to Education and Health sectors. The action on taking forward the rectification work has started, however the delay in the start of the reconstruction work is disappointing. A robust contingency plan is in place to avoid further delays.

Government counterparts, implementing partners and DFID must develop a shared approach on risk mitigation with clearer accountability and regular communication channels beyond the steering committees.
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Delivery against the work plan is monitored and reported on a monthly basis using the monthly dashboard meetings and reports. This provides an opportunity to look into the upcoming challenges, identifying risks and real time solutions. Quarterly progress reports help monitor the log frame milestones. The programme is mainly on track; delivery against the work plan has been behind schedule on some areas such as the PFM strategy in Khyber Pakhtunkhwa and rollout of some of the challenge fund milestones. The reconstruction work under the conditional grant component has not been efficiently addressed; OPM needs to improve this through following tight timelines and robust implementation of the rectification work.

Recommendation

Include the timeline of conditional grants school repairs in the delivery plan and set up a routine of weekly follow up.

Performance of partnership (s)

Performance of technical assistance and innovations contract:

OPM is consistent and proactive in delivering the programme outputs and objectives. The risk mitigation and financial management has been good, and OPM has responded well to the recommendations of last year’s annual review. The grant management side of service delivery innovations under the challenge fund, which is Coffey’s lead, has also been robust. OPM has also been very proactive in managing the government counterparts, their expectations from the programme and drawing them into opportunities to deliver on the objectives of the programme. OPM have capable international and national staff, though the international quality assurance can be made more consistent across the programme, particularly in Khyber Pakhtunkhwa. The review team also found the three offices of the SNG (Islamabad, Lahore and Peshawar) could be joined up better with efficient communication. The review has looked into the role of the SNG Islamabad office, which was supposed to be a coordination hub but given strong sub-national focus merits a revisit. The steering committees, co-chaired by DFID and the government counterparts, provide for a key governance mechanism and forum to review programme progress and take key decisions.

Recommendations

- OPM may consider scaling down the Islamabad office and shift resources closer to the delivery in the provinces and districts.
- Establish a communication routine beyond steering committees, where government counterparts can more regularly input into the workplan formulation and prioritisation.

Coordination with other programmes

SNG is a cross cutting programme and has strong linkages with budget support programmes on education and health as well as demand side programmes on education and peace building. One of SNG’s objectives is to create synergies between all these programmes and build better coordination. SNG has worked closely with education sector teams to embed payroll audits in both provinces. SNG has also started to build more coordination with Aawaz, which is DFID’s key voice and accountability programme, in the districts common to both programmes. On PFM roadmap in Punjab, SNG works closely with other donors such as the World Bank and GIZ. However there is still room to improve on this coordination especially with health sector programmes as there are opportunities to engage and leverage the challenge fund initiatives in the health department through effective lobbying with the stakeholders. This should be done proactively and sensitively and government counterparts should also be brought in so that duplication of efforts can be avoided and the results can be maximised.

Recommendation

At both provincial and district levels, coordination should be further strengthened with health and education sector teams and with the voice and accountability teams, through regular sharing of work plans and lesson learning. This coordination should also take place among the DFID teams managing these programmes.

Asset monitoring and control

DFID team conducted three assets spot checks (Lahore, Sheikhupura and Vehari, Hafizabad) over the course of the year. It was found that the OPM team maintains a robust asset register with all assets properly reflected and coded. A significant sample of items was physically verified and labelling was cross checked with coding on the register during these spot checks. Spot checks of procurement documents and vehicle log books were also conducted and found that adequate controls are in place. Best practice has been followed by OPM in procurement of all office equipment i.e. for all purchases above PKR 50,000 (GBP 300) a minimum of 3 quotes was obtained from suppliers. A complete record of the bids, quotations and the award process has been maintained by the team. This provides a comprehensive audit trail and also enables Value for Money analysis.

Recommendation

Carefully consider asset disposal plans for the assets under the use of challenge fund grantees considering that many grants will be coming to a close this year.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The majority of the UK’s investment in SNG is technical assistance to the Governments of Punjab and Khyber Pakhtunkhwa with an additional element of earmarked budget support to the Government of Khyber Pakhtunkhwa. SNG is part of the wider aid relationship between the UK and Pakistan which is based on an assessment of Government’s commitment to our Partnership Principles. DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the Partnership Principles. DFID can therefore continue to deliver on SNG programme activities.

H: MONITORING & EVALUATION

Evidence and evaluation

The programme went through its mid-term evaluation in the last year which gave an interim sense of programme performance and partial validation of the theory of change. The programme is shifting its focus to districts and more on budget execution and service delivery. The programme’s final evaluation is planned for the beginning of 2017, before the Programme Completion Review due in September 2017.

SNG has undertaken a citizens perception survey, using the qualitative monitoring package - Sense Maker, to gather beneficiary perceptions of basic public services within selected SNG districts. The study was carried out in two districts in Punjab, Sheikhupura and Vehari, with the sample size of 1,830. Going forward, it is important for the programme to follow up these studies with a policy response and monitor tangible outcomes for citizens in both districts.

The current log frame and monitoring tools do not establish a clear link between the project outputs and the project outcome from the perspective of citizens. This can be addressed through revising the log frame and broadening the beneficiary feedback loop to the citizens benefitting from the programme.

Monitoring progress throughout the review period

SNG maintains a robust monitoring, evaluation and reporting framework. The programme has a log frame, which was updated in view of the last annual review. The log frame is complemented by the annual work plan, relevant to the needs of the operating context, which is maintained by the programme’s provincial M&E advisers (one each for Khyber Pakhtunkhwa and Punjab). In addition to the provincial M&E advisers, the teams are also supported by the national M&E manager who maintains the oversight and ensures quality.

DFID and OPM engage on a monthly basis through a work plan based tool in the shape of Monthly Progress Dashboard. The monthly progress dashboard template has evolved in the past and as of September 2015 has been revised to reflect the strategic and thematic level reporting as the programme is now moving towards its fourth year of implementation.

OPM also shares the comprehensive quarterly and annual progress reports with DFID which captures progress against the log frame. To integrate gender and social development in the results framework, the programme has also developed gender and social development indicators to complement the SNG log frame demonstrating beneficiary outreach at a macro level. To track the performance throughout the year, the progress against each indicator is documented in the quarterly as well as the annual report. In order to streamline these, the indicators were also embedded in the revised log frame for year 3, under outputs 1 and 3.

As a follow-up of the last year’s annual review recommendations, the programme was successful in arranging joint monitoring visits with the government counterparts in Challenge Fund and GIS components. The provincial teams have easy and frequent access to the government offices and are able to engage directly at the intervention level. DFID also undertook monitoring visits throughout the year and as part of the annual review process. The case studies and success stories of the programme are very well documented and have become an on-going feature of the programme. The case studies on areas such as GIS, service delivery pilots, evidence based budgeting and expenditure tracking are well documented and published on the SNG website for a wider audience.

Recommendation

In line with the above, DFID, OPM and the government partners need to work together to design a robust impact evaluation that provides a conclusive narrative on the outcome and impact of the programme and also a springboard for future programming – a possibility that we are considering.