ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Appui au Système de Santé en République Democratic du Congo (ASSR) – Support to the health system in the Democratic Republic of Congo (DRC)
Country or region targeted	Democratic Republic of Congo
Type of cost extension (if applicable)	N/A
Original project budget	£39,000,000
Original project start and end dates	Start: 01/04/2019 / End: 30/09/2020
Cost extension value (if applicable)	N/A
New project end date (if applicable)	31/03/2021 (6 months extension)
Business Case Quest Document No.	46440933

INFORMATION
What is the project’s purpose?
This 24-month intervention will provide a bridge between the current health programme ASSP (Access to Primary Healthcare) and a new longer-term health programme in DRC. The proposed programme will ensure continued support to health systems strengthening and delivery of basic services in 50 health zones out of 516 nationally, in four of the 26 provinces in DRC. There are approximately 9.7 million people living within supported health zones who would benefit from having improved access to healthcare. The programme will continue to focus on improving maternal, newborn, child and adolescent health by addressing key health issues such as nutrition, family planning, maternal care and prevention and management of childhood illness (including malaria). The programme also proposes to include a new component that will be set up to support global health security preparedness and response work. / The project will be delivered through 3 components: / Component 1. Health systems strengthening and support for delivery of basic services (up to £35m) across four provinces of DRC with a population of approximately 9.7 million people. Programme expenditure will focus on essential medicines and commodities, equipment, training and supervision, as well as targeted technical assistance to national, provincial, local and community health structures to strengthen systems and to improve the sector’s overall management. / Component 2. Global Health Security (up to £3m) – A health preparedness and response mechanism will be set up to support global health security preparedness and response work (including outbreaks of infectious disease) and to provide the facility to flex and respond to new health needs in supported programme areas (for example spikes in malnutrition rates). / Component 3. A third-party monitoring and operational research mechanism (up to £1m) will be put in place to provide ongoing, high quality, critical constructive review of the ASSR programme, and to work with programme providers to improve any areas of weakness identified. This component will also deliver a limited number of high-quality pieces of operational research. This facility will support the programme to deliver against DFID compliance expectations around due diligence, fraud and safeguarding.
What is the objective of the cost extension or other changes?
There are two main objectives of the changes proposed: / Delivery mechanism – to change the proposed delivery mechanism of Component 1 (Health Service delivery) from an accountable grant into a commercial contract. / Time Extension – to extend the length of time in the business case by an additional six months to take into account a slight delay in starting implementation as planned (1st April) and a closeout/ handover/ lesson learning period anticipated at the end of the programme.
What is the additional and total support the UK will provide?
No additional support is being requested. The total budget for the programme remains the same, as was outlined in the original business case – £39,000,000.
What are the expected results?
The expected results remain the same as outlined in the original business case. The additional time (6 months) being requested would be used to deliver on a responsible and organised closeout plan of the current programme as well as handover/ transition into a new long-term health business case expected to be starting from October 2020. Specific results/ targets for this additional period will be defined closer to the end date and will depend on the timing/ overlap required with the new long-term business case.
What is the approach to implementation?
Change in delivery mechanism – Component 1 / This addendum seeks to change the delivery instrument for Component 1 from an “Accountable Grant” as stated in the original Business Case, to a “Commercial Contract”. This proposed change is based on further advice received from DFID’s Procurement and Commercial Department (PCD) following the formal approval of the business case. / Given the market constraints in the DRC, the heightened humanitarian and political situation as well as the ongoing health shocks, the programme design team had previously pursued a non-contractual route to market with a call for proposals targeted at NGO and multilateral partners. Following extensive engagement, two proposals were received from consortiums led by IMA World Health and another from a Multilateral Organisation working in the DRC. Following analysis of the proposals received, IMA World Health were deemed to have provided the most comprehensive proposal which aligned with the programme requirements. The focus of the other proposal in comparison was too niche and did not cover the full breadth of the terms of reference issued. / Our call for proposals process identified a consortium of highly capable and experienced NGO’s with significant expertise in delivering health care in the DRC. Given the proposed consortia is being led by IMA World Health, who were previously under a legally binding contract for the ASSP programme; the advice from PCD is to award a contract for the bridging period to them. PCD agree and endorse the award of a new commercial contract and have subsequently engaged the market through publication of a Voluntary Ex Ante Transparency (VEAT) notice issued in the official Journal of the European Union; signalling our intent to award a contract to IMA World Health for delivery of Health Services in the DRC for this bridging phase. The timeline on this has now expired without any challenge from the market and we can therefore proceed to contract IMA World Health once Ministerial approvals are granted. / No changes in approach are proposed for Components 2 and 3 of the programme.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
Time Extension (6 months extension to overall business case period) / In addition to the proposed change in approach on the delivery mechanism described above, the programme team is also proposing an overall extension of the programme timeframe from 18 months to 24 months. / The change of delivery mechanism for the largest component of the programme means that we have less flexibility as offered previously by an accountable grant mechanism in terms of quick mobilisation and adapting changes quickly. In light of this, the programme team deem that is prudent to extend the programme for a further 6 months to ensure that there is sufficient time for an orderly closeout/ handover period from the bridging programme to the new long-term package of support that is expected succeed ASSR. The additional time will also be spent documenting any lessons learnt from the bridging phase. / It is also likely that the new programme will have an extended inception phase period to account for a full needs assessment in the provinces that DFID plans to operate in and therefore the additional 6 months on this bridging programme can be used to provide necessary critical support during the set up of systems for the new long-term programme. / No other changes are proposed at this stage.
[note] ASSP - Accès aux Soins de Santé Primaires
[note] ASSP was supporting 52 health zones until September 2018. After this time DFID stopped support to Tshopo province (3 health zones) as part of the DFID DRC plan to reduce and focus its provincial footprint; one other health zone, Dekese, is planned to be added to ensure full-province coverage in Kasai province.
[note] In July 2015, further to the approval of several legal texts, the government announced that it was proceeding with découpage, with the 11 ‘old’ provinces now split into 26 smaller units.
[note] Kasai, Kasai-Central, Nord-Ubangi and Maniema