Good Governance Fund

Phase 2
2016/17 – 2020/21

Conflict, Stability and Security Fund (CSSF) Programme Document

Good Governance Fund Joint Unit
14 July 2016

Summary

What support will the UK provide?

The first phase of the Good Governance Fund (GGF) was approved in June 2015 and was fully operational by November 2015. It is a highly responsive, adaptive, demand-led fund, largely focused on the provision of technical assistance in support of governance and economic reform in Ukraine, Georgia, Moldova, Serbia and Bosnia and Herzegovina (BiH). Specific areas the fund supports include; anti-corruption measures, improving the business environment, judicial reform, key sector reforms (e.g. banking and energy), strengthening the rule of law and supporting an independent media. These interventions support states to become more resilient to external and internal shocks, both political and economic, and support poverty reduction, growth and stability. The first phase was funded by DFID (up to £20m). The second phase will be funded by the Conflict, Stability and Security Fund (CSSF); The Strategic Defence and Security Review (SDSR), the 2015 UK Aid Strategy and the 2016/17 – 2020/21 Spending Review committed up to £180m to the GGF from the CSSF over the Spending Review period.

Why is UK support required?

Since the early 1990s the initial five partner countries have worked to develop stronger economies and democratic institutions, to support poverty reduction and growth. There has been success but many challenges remain which could undermine progress and may lead to development reversals. UK support will help prevent these states regressing and in turn boost resilience to economic and political shocks. These countries are classed as (lower and upper) middle income countries by the OECD and are ODA eligible. The UK is well placed to provide fast, flexible assistance which can respond to local needs and priorities.

At the launch of the GGF the then Prime Minister said:
[note] https://www.gov.uk/government/news/new-uk-funding-to-help-build-stronger-and-more-democratic-nations-in-the-eastern-neighbourhood-and-balkans

“Ensuring we have strong partners on the EU’s border is not only essential for Britain’s security but our long term prosperity. UK expertise can play a crucial role in bringing about the reforms needed to build lasting stability in the region, especially in the face of Russian intimidation, and it is right we that we step up our efforts alongside international partners”.

The GGF’s innovative, adaptive model is in line with DFID’s strategic approach to building resilience in fragile states. The GGF helps deliver the UK’s objectives to support a prosperous and stable region in the European neighbourhood.
[note] See DFID’s Building Stability Framework 2016
[note] Georgia, Moldova and Ukraine have signed Association Agreements (AAs) and Deep and Comprehensive Free Trade Agreements (DCFTAs) with the EU and the EU has committed to support the implementation of reforms. The GGF complements this support. Serbia opened accession negotiations with the EU in 2014. Bosnia and Herzegovina is a potential candidate for EU accession.

When will funding start and when will it end?

Phase one of the GGF was funded by DFID. An extension to the first phase Business Case until September 2016 has been funded by the CSSF since 1 April 2016. This second phase Business Case will cover the remainder of the Spending Review Period, from September 2016 – March 31 2021.

How will the programme be delivered and by whom?

The GGF provides flexible, responsive support, mainly focused on technical assistance, but also including procurement of goods where needed, to support the creation of open societies and open economies in the target countries. It operates through three delivery channels:

International Financial Institutions (IFIs), multilaterals and other donors: agreements have already been established with the European Bank for Reconstruction and Development (EBRD), the World Bank (WB), the European Investment Bank (EIB), the International Finance Corporation (IFC), the United Nations Development Programme (UNDP) and Deutsche Gesellschaft fur Internationale Zusammenarbeit (GIZ). Existing institutional assessments and proportionate local due diligence assessments ensure we work with trusted, capable partners to support achievement of the GGF’s objectives.
[note] https://www.gov.uk/government/publications/multilateral-aid-review-update-2013

A commercially provided Managed Fund: A commercial supplier was contracted under phase one for three (plus one) years to provide a flexible, responsive, demand led facility, focused on technical assistance but providing other support where appropriate to support reform priorities.

Strategic Support Fund: A grants facility is being managed at post, setting up agreements with local non-governmental, civil society, academic and think tank organisations. This may also involve some support to commercial and governmental bodies. Where support is provided to governmental bodies the partnership principles will be considered. Due diligence assessments are conducted to ensure all partners have financial, management and delivery competencies.
[note] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/358341/how-to-partnership-principles-march2014a.pdf

The GGF will largely operate at the national level, but will also look for regional approaches. These work streams will be delivered through a combination of IFI, multilateral, other donor and Managed Fund partners.

The GGF is led through UK Embassies in each country, with support from a central, DFID/FCO Joint Unit providing advisory and programme management support, and managing overall MoUs, contracts and agreements and regional work.

What are the expected results?

Phase two of the GGF will deliver targeted technical assistance in areas where governments show progress in implementing meaningful reform. It is designed to be highly responsive and adaptable, mobilising support rapidly to unblock reform and leverage support and investment from larger donors and IFIs. Results for the five year Spending Review period are not defined up front. The portfolio will develop throughout each year of implementation, responding to demand, reform opportunities and project performance. Country teams in Embassies will work with beneficiaries and the DFID/FCO GGF Joint Unit to identify specific deliverables based on the strategic objectives of the GGF throughout the programme cycle. Planning and delivery will be aligned to CSSF planning and delivery cycles.

The hypothesis underpinning the GGF is that well targeted, adaptive technical assistance provided to GGF countries will support reform in priority areas, strengthen demand-side accountability, and leverage wider resources and political commitment to support reform. This hypothesis will be tested throughout GGF implementation, including through the GGF’s monitoring and evaluation strategy.

The GGF results framework identifies the key strategic priorities for each country. Additionally the GGF will consider gender issues in the development of all programmes.

The impact of the GGF will be that countries are increasingly resilient and prosperous as the result of economic growth and transparent, responsive and effective governance institutions held to account by informed and active populations.

To support this, the GGF will pursue a range of interventions according to country priorities, including support for:

- Reform to regulation of the business environment and economic governance to bring target countries closer to international standards which can support the growth of small and medium-sized enterprises and attract foreign investment to improve prospects for broad-based economic growth and job creation.
- Institutional capacity building to develop more effective governance, public administration and management of public finances in order that government in target countries can become increasingly transparent, accountable and responsive to the needs of citizens.
- Anti-corruption measures and judicial reform to strengthen the rule of law, reduce opportunities for corruption and increase the ability of target countries to address corruption where it does occur.
- Modernisation of key sectors such as energy, banking and reform of state-owned enterprises to strengthen target countries’ transition to market driven, vibrant, modern economies.
- Stronger and more independent media and civil society to ensure the public has the ability to engage in active, informed debate and to enable to government to resist external pressure and effectively communicate the benefits of reforms to their citizens.

What are the key risks to the success of the programme?

There are risks beyond the UK’s control, including political or economic shocks which could disrupt delivery of the reform agendas. We have sought to manage this by selecting countries with more committed reform agendas, where FCO colleagues overseas (“missions”) work with key interlocutors and GGF advisers to ensure early warning of such issues. We have used extensive political economy and other analysis to refine country focus, shape portfolios, agree projects and monitor overall performance. This will help to ensure we are working in the right areas and to adjust the programme to address challenges, to scale up more effective elements and to scale down others.
[note] See Table 5: Risk Matrix (p54) for further detail.

Risks within the programme’s control include: the proliferation of small, low impact programmes; weak programme management; supply led portfolios (Principal Agent Problem); failure to deliver adaptive programming; fraud or corruption in the programme. These risks will be mitigated by ensuring sufficient staff resources are in place to deliver the programme and good complementarity with other donors’ work. The proliferation of small programmes will be managed through the development of clear criteria for GGF support (including results and value for money). Firm oversight and monitoring will ensure a demand led approach focused on strategic priorities. Robust systems and use of evidence and feedback/learning outcomes will deliver adaptive programming.

Strategic Case

Context and need for the proposed intervention

  1. In March 2015 the then UK Prime Minister announced the creation of a multi-year, joint FCO/DFID Good Governance Fund (GGF) - a package of support for economic reform and good governance initiatives initially in Ukraine, Moldova, Georgia, Serbia and Bosnia and Herzegovina (BiH). At the launch it was noted that the programme might be extended to other countries. Each of the initial five countries has positive economic and governance reform agendas intended to create more open societies and open economies. However each country also faces substantial challenges that could undermine reform and earlier advances on poverty reduction, growth and stability.
    [note] https://www.gov.uk/government/news/new-uk-funding-to-help-build-stronger-and-more-democratic-nations-in-the-eastern-neighbourhood-and-balkans

  1. All of the GGF’s target countries have suffered violent conflict over the last two decades which continues to affect their economic, social and political development. Causes of conflict are largely unresolved and continue to represent vulnerabilities which increase the risk of future violence. Ukraine is the most acute – and recent – example, whilst Georgia and Moldova each have unresolved conflicts, and BiH and Serbia, to varying degrees, struggle with ongoing post-conflict tensions. DFID’s Building Stability Framework recognises that aid can contribute to long-term stability through a variety of interventions which support the ‘building blocks’ of stability including fair power structures, effective and legitimate institutions and inclusive economic development. While conflict is present in all societies, development interventions can put in place accessible systems to resolve conflicts peacefully, give people a credible economic stake in a future without violence, and strengthen bonds between communities and governments.

  1. A cross-country comparison of governance using the six Worldwide Governance Indicators (WGI) for 2004, 2009 and 2014 shows an uneven profile across GGF countries. Although GGF countries each have their own specific (non-linear) reform trajectory there are common themes in terms of the political and governance contexts, for example the legitimacy of political and governance systems risks being undermined by personalised party politics; institutions can be weakened by political influence, the public sector is inefficient, expensive and public sector reform meets with resistance; the private sector’s role in the economy is constrained by cumbersome regulation, state-owned enterprises are inefficient and may have poor economic governance; corruption is endemic (in Ukraine and Moldova) and exacerbates popular discontent (and protest); civil society is largely free from regulatory constraint but weak; media is relatively free from regulatory constraint but may be subject to political pressure and self-censorship, populations are increasingly frustrated, disenfranchised, apathetic and resentful.
    [note] The World Bank Worldwide Governance Indicators (WGI) project reports aggregate and individual governance indicators for 215 economies over the period 1996–2014, for six dimensions of governance. http://www.govindicators.org

  1. GGF countries exhibit uneven and often non-inclusive economic development. This can stall progress towards poverty reduction or in some cases may worsen the situation. Apart from infrastructure deficiencies and often experiencing a skills mismatch, GGF countries face challenges of a narrow economic base, constrained private sector and relatively low levels of structural sophistication in the economy; all of which increases their vulnerability to shocks. In addition GGF countries lack institutions capable of providing good governance, rule of law and transparency. These give confidence to both foreign and domestic investors that their investments are safe and that challenges involved in diversifying and growing the economy, building the infrastructure, and delivering education and training will all be properly addressed. Over the last two decades all of the countries covered by the GGF have implemented reforms to support higher rates of growth, with some success (see Economy below), but all of the countries need to go further to develop diversified, job-creating economies. With the notable exception of Georgia, all of the countries covered have a low rank in the World Bank’s Doing Business report, and three of the five GGF countries have experienced recession over the past three years. Limited job creation and high rates of (youth) unemployment risk social dissatisfaction and unrest, which could create further instability.

  1. The UK has an opportunity to help support reform, and through this encourage accelerated and sustained progress towards growth and stability. Whilst other donors are active in GGF countries there is a clear need identified by government partners, other key stakeholders and donors, for fast, responsive, flexible technical and other assistance to unblock reform, decisively step in to respond to reform opportunities, and complement the larger programmes of other donors. Many donors’ programmes operate over longer time periods and cannot rapidly adjust priorities in year. These countries have rapidly evolving reform environments. The GGF is designed to respond to these evolving priorities, step in rapidly, scale up or scale down as necessary, and focus on delivering with a view to securing longer term support from donors with larger budgets.

  1. At the Fund’s launch the International Development Secretary said:

A stronger, more democratic and more successful Eastern neighbourhood is in all our interests. That is why we will provide targeted assistance to help these countries make tough but necessary reforms to help strengthen their economies, fight corruption and better serve their people.

  1. The Foreign Secretary said:

Recent events have brought into sharp focus the challenges faced by our eastern neighbours. We all have a stake in their stability, resilience and prosperity. This new fund will support the efforts of our neighbours to reform their governance, economies and societies. And, in doing so, Britain is helping to build Europe’s security and prosperity in the 21st century.

REGIONAL CONTEXT

Economy

  1. Over the last decade two of the five GGF target countries (BiH and Georgia) have benefited from more consistently positive growth rates, whilst the other three have experienced more significant fluctuations (Ukraine, Serbia and Moldova). Each of the countries needs to go further to develop diversified, job-creating economies with inclusive, sustainable growth.

  1. The World Bank’s annual “Doing Business” indicators show a mixed picture on investment climate. Out of 189 countries, Georgia performs best at 24th (stable), Moldova 52nd (down from 49th the year before), Serbia 59th (up from 68th), Bosnia and Herzegovina 79th (up from 82nd) and Ukraine at 83rd (up from 87th).
    [note] Data from 2016.

  1. Georgia: following economic growth of 4.6% in 2014, growth is estimated as 2.8% in 2015 and forecast to be 2.5% in 2016; unemployment was 12.4% in 2014. Unemployment has been fuelled by lower economic activity in the region, and lower remittances from Russia impacting on growth. Georgia’s ability to boost foreign investment and achieve export-led growth will be important in determining future growth. The currency (lari) could weaken further this year, as remittance inflows remain subdued.
    [note] IMF World Economic Outlook April 2016
    [note] Economist Intelligence Unit

  1. Moldova: has the lowest per capita income of all five countries and the economy shrank by an estimated 1.1% in 2015; due to a combination of significant bank fraud in late 2014 and associated damage to confidence from this, as well as political uncertainty and the recession in Russia. The bank fraud has increased fiscal constraints and led to a sharp rise in public debt due to a related bank bail-out. The economy is forecast to return to modest growth of 0.5% in 2016, followed by growth of 2.5% in 2017. The weak currency (leu) continues to put upwards pressure on inflation and the unemployment rate was estimated at 4.9% in 2015.
    [note] IMF World Economic Outlook April 2016
    [note] IMF WEO April 2016

  1. Serbia: the economy grew by an estimated 0.7% in 2015; driven by a rebound in fixed investment and export-led production and despite fiscal consolidation under the IMF programme. This followed Serbia experiencing a recession for a third time in ten years in 2014 and contracting by 1.8%. Growth is forecast to remain positive between 2016 and 2021. Unemployment rates have been falling from a peak of 24.6% in 2012 to an estimated 18.5% in 2015, with women’s general participation rate at 38.3%. Following an election in April 2016 further fiscal consolidation and structural reform are planned under the IMF stand-by arrangement, which is currently on track and runs through to early 2018.
    [note] Statistical Office of the Republic of Serbia
    [note] IMF WEO April 2016

  1. Bosnia and Herzegovina (BiH): following a double-dip recession in 2012, real GDP growth has been positive and modest since 2013. Growth was estimated at 2.3% in 2015 and is forecast to pick up to 3% in 2016 and 3.2% in 2017. The pick-up in growth in 2015 is largely attributed to private consumption growth of 2.5% combined with rising external demand and low oil prices. However unemployment remains very high (estimated at 27.7% in 2015 and forecast to fall to 24% by 2021).
    [note] IMF WEO April 2016
    [note] IMF WEO April 2016

  1. Ukraine: the economy contracted by an estimated 6.5% in 2014 and contracted by a further estimated 10% in 2015, but is forecast to return to positive growth, of 1.5%, in 2016 and 2.5% in 2017[10]. The IMF programme estimated Ukraine’s financing needs to be $40 billion over 2015-2018. The IMF has put in place a $17.3 billion programme with the remainder of the $40 billion financing gap filled through debt restructuring and contributions from bilateral and multilateral donors. Ukraine faces significant challenges including in implementing the IMF led reform programme. The hryvnya depreciated by almost 46% in 2015 but has shown signs of stabilising in 2016. The unemployment rate is estimated at 9.1% in 2015; up from 7.3% in 2013 and forecast to fall to below 8% by 2021.

Governance, conflict and the political economy

Ukraine

  1. Ukraine’s performance on governance indicators is weak. The key areas of concern for governance in Ukraine remain control of corruption (with some modest progress on the Transparency International Corruption Perceptions indicator in 2015/16 but still down at 130 out of 168 countries), political instability, regulatory effectiveness and rule of law.

  1. Deep societal and political transformations have taken place in Ukraine since the autumn of 2013. The Euromaidan protests, leading to the Revolution of Dignity, were followed by early elections for a new president and parliament in 2014. Political and civic activists, energised by the magnitude of political change, pushed for major legislative reforms. The overhaul of the political system, however, has proved challenging, and many Ukrainians have been dissatisfied with the pace of reform and frustrated by the mounting economic crisis.

  1. The Government of Ukraine is simultaneously having to manage the conflict in the East and undertake root-and-branch reforms. Key reform areas include: constitutional reform and decentralisation; corruption; justice sector reform; police reform; and civil service reform. Ukraine has achieved more on reforms in the past two years than in the previous two decades, including drafting a number of reform initiatives and passing laws. But much remains to be done.

  1. Many believe that Ukraine’s second attempt at transition in a decade must succeed and that time is short. Failure, or even perceived failure, could be a trigger for further instability. There is widespread demand for urgent large scale assistance to support changes at all levels. The Ukraine crisis remains fast-moving. However, while short-term events are unpredictable, longer-term dynamics change less rapidly and any sustainable resolution will require addressing such underlying factors. We must therefore remain flexible and responsive to the current context, while targeting programming on longer-term drivers of conflict.

  1. Ongoing corruption has played an important part in motivating citizens to demand change and this combines with a sense that now is the unique opportunity for the country to make a decisive break with the past. Supporting those who have shown genuine commitment to meaningful reform, in spite of the challenges they face, will be critical to seizing this opportunity.

Georgia

  1. Georgia experienced its first peaceful transfer of power in the highly competitive parliamentary elections of October 2012. Georgia has made the most progress on governance indicators amongst the five GGF target countries. Significant progress was made in tackling corruption and improving regulatory quality. There has been less progress on political stability and absence of violence and Georgia scores poorly on political and social integration issues. High expectations of socio-economic improvements and justice have led to some disappointment as the economy contracted and did not provide an expected increase in employment. Economic reform which supports inclusive growth and creates jobs will be important to sustain public appetite for reforms.

  1. Parliamentary elections are due in October 2016 and a National Democratic Institute March 2016 poll shows that 61% of the population are as yet undecided as to which political party they would support, indicating a potential disengagement from political parties and their policies. Political forces are highly polarised and there remains a risk that perceived restrictions on public debate, particularly at key stages of the electoral cycle, could spark civil unrest.

  1. Georgia has two unresolved conflicts on its territory, Abkhazia and South Ossetia. Despite performing relatively well on a range of development and governance indicators, Georgia continues to face challenges to maintaining peace and stability. South Ossetia and Abkhazia remain outside the control of the Georgian government. Economic development is uneven and some social groups face challenges in accessing employment opportunities.

  1. Governance is dominated by personalised party politics and issues-based policy is often hijacked by these dynamics, which alienate the population.

Moldova

  1. Moldova scores poorly on control of corruption, independence of the judiciary and political and social integration issues. The country continues to suffer from political instability with mass street demonstrations in late 2015 leading to a change in Government in January 2016. Citizens came out on the street in protest at levels of corruption and bank fraud on a massive scale. In November 2014, Moldova's central bank took control of Banca de Economii, the country's largest lender, and two smaller institutions, Banca Sociala and Unibank. Investigations into activities at these three banks had uncovered a large-scale theft by means of fraudulent loans to business entities controlled of funds worth about 1 billion U.S. dollars. The first direct Presidential elections in twenty years are due in autumn 2016 (the President has been elected by the Parliament since 2001).

  1. Moldova remains the poorest country in Europe. An impoverished and disenfranchised population has little ability to participate in the political process. Recent elections pointed to a divided political landscape in which few candidates enjoy substantial support. Much needed reforms to strengthen rule of law, governance and democratic institutions are within reach but must challenge vested self-interests in a country used to the status-quo.

  1. Although voice and accountability and government effectiveness are the areas where most progress has been made, the ‘demand-side’ of reform, through the media and civil society, is weak with limited room for meaningful public debate or scrutiny of government actions. Support to civil society organisations, local governments and other mechanisms to provide a means through which political institutions can actually respond to citizen’s needs are badly needed to develop confidence in the ability of government to provide for the public.

  1. The southern, Russian-speaking and relatively industrialised region of Transnistria declared independence from the rest of Moldova and following a brief war has existed as a de-facto separate state since 1992. The existence of an ill-defined internal border incentivises corruption and smuggling which further deplete government resources and deters investors.. Further, the loss of Transnistria renders the rest of Moldova more dependent on its agricultural sector leading to an undiversified economy vulnerable to external shocks. While the conflict shows little sign of renewed violence, the presence of Russian troops on Moldovan territory remains a critical strategic vulnerability. Without significant progress in implementing reform and developing the economy it is unlikely that the government in Chisinau will be able to incentivise a lasting settlement with the South.

Bosnia and Herzegovina (BiH)

  1. BiH experiences political instability, a lack of institutional capacity and low levels of Government effectiveness. The Constitutional arrangements give rise to a de-centralised but extremely complex government and public administration structures.

  1. At the national level there are two entities: the Bosnian Federation and Republika Srpska (RS). State, entity and cantonal level institutions have complex, bureaucratic and expensive administrative structures. Parallel governance and security apparatus both maintain peace in the short-term but also promote the proliferation and duplication of offices, long-term inefficiency and undermine the consolidation of a multi-ethnic state and identity. Many entity administrations run large budget deficits but political constraints make it difficult for the central state to enforce fiscal discipline. This both encourages competition for the authority and resources vested in these offices and impedes any coherent decision-making.

  1. Frustration with the socio-economic situation led to protests and violence in February 2014. The economy is held back by political stalemate, inefficient regulations, weak integration with regional markets, and limited access to finance.

Serbia

  1. EU accession is driving institutional and economic reform and the development of democratic values. Additionally, Serbia’s deepening cooperation with NATO through the adoption of the NATO Individual Partnership Action Plan (IPAP) ties Serbia and its armed forces into the wider international security architecture and increases regional defence cooperation. Overall, these reforms have contributed to a significant increase in stability and a generally low risk of serious internal conflict.

  1. Serbia has the highest GGF country score in terms of voice and accountability. It has made progress on government effectiveness and regulatory quality issues. The judiciary operates relatively independently but its functions are still hindered. Serbia scores poorly on freedom of expression. Although freedom of expression was generally respected, the independence and pluralism of the media is constrained. The government has embarked on an anti-corruption campaign leading to the arrests of several influential businessmen and politicians, public opinion surveys indicate that citizens continue to believe that high-level corruption is common within politics, healthcare system and judicial system. Reforms may become more difficult as and when they challenge personal vested interests[1]. While state institutions remain on the whole resilient, work to increase their transparency and accountability would contribute to further progress on transition.

  1. Serbia faces a difficult economic situation: lack of economic growth entails high levels of unemployment especially among youth – who are increasingly alienated and drawn to emigrate, causing a brain drain. Public debt accounts for 64.4% of GDP. There are as many pensioners as employees, and the public sector is oversized; with 780,000 employees. However, economic and fiscal reform – especially downsizing the public sector and privatisation of major state-owned enterprises – is proving difficult. Stronger private sector development requires reforms to strengthen the banking system, improve efficiency of contract enforcement systems, making infrastructure improvements, increasing renewable energy capacity, and developing better skills. Pension and wage cuts under the PM’s austerity plan, remain the largest source of dissatisfaction[2]. The continued presence of the International Community in Serbia are a driver of stability and forms one of the factors contributing to the country’s resilience.

STRATEGIC CONTEXT

  1. The GGF operates alongside other HMG funding in the regions in which it operates, most significantly additional Conflict Security and Stabilisation Fund (CSSF) funding, as well as other funds such as the Bilateral Programme Budgets and the Magna Carta fund.

  1. The GGF is a country-led model, which supports Embassies to deliver against agreed strategic priorities, and works in conjunction with other HMG Funds. Practically, this means that in GGF countries the CSSF focuses more directly on conflict and stability, whilst the GGF focuses on longer-term structural issues such as economic and governance reform.

  1. This Business Case does not seek to narrow down a set of priorities for each country. Rather, the dynamic, responsive planning process will lead to limited priorities for each country, agreed on during annual planning processes.

The GGF Theory of Change and results framework set the context for operation.

At the country level these strategic documents are combined with country level Political Economy Analysis (PEAs), scoping studies, Joint Analysis of Conflict and Stability (JACS), Inclusive Growth Diagnostic (IGDs), national reform priorities, Embassy priorities and advisory and programme management inputs from the GGF Joint Unit. The GGF draws on all of this to help agree on prioritisation as well as assessments of likelihood of success of each key area for each country.

The GGF uses a problem driven iterative approach and so effective implementation requires strong evaluation throughout. This helps to ensure lesson learning both on project design and on where there is traction to narrow down the range of priorities for GGF support in each country.

A portfolio is developed and an overall approach and project selection that delivers against the agreed focus and priorities. Lessons from portfolio development and project implementation are fed back into the process, as are broader lessons fed back into the overall strategic approach.

  1. This process runs in alignment with broader CSSF programming, to ensure a coherent, joined up approach that tackles key challenges in country.

Getting the politics right – ways of working

  1. GGF programmes are designed to be complementary to broader CSSF programmes. To build responsive, capable institutions underpinned by inclusive economic growth, GGF programmes compliment traditional CSSF activities in areas such as peacebuilding and security-sector reform to produce a comprehensive approach to building stability which address both short-term triggers and consequences of conflict in parallel to underlying structural vulnerability.

  1. GGF Unit advisers and programme teams in Embassies work closely with FCO counterparts, regional conflict advisors and research analysts to ensure that project design and quality-assurance is informed by ongoing political monitoring and analyses to mitigate the risk that assistance is manipulated to strengthen conflict-generating tendencies, such as exclusionary economic dynamics. It is important that lessons are also learned from technical assistance provided in the past where support may have contributed towards ‘crony capitalism’ or elite capture. The nature of the Joint Unit approach means that DFID and FCO teams are embedded and GGF therefore benefits from regular access to political reporting as well as analysis generated by the FCO’s research analysts and Regional Conflict Advisers.

UK comparative advantage

  1. Georgia, Ukraine, Moldova, BiH and Serbia have each achieved a great deal in the past 20 years. However they still face significant challenges. Whilst existing development support from other donors is substantial, the UK can play an important role in helping to accelerate reform, generate growth, promote open and market-based economies and support stability. Existing multilateral partners in the region tend to operate larger, multi-year programmes, with longer term commitments making it harder for them to adjust quickly to changing circumstances.
    [note] Usually partners such as EU, IMF, WB set out funding commitments over long periods e.g. 2014-2020

  1. The UK’s comparative advantage in the region with development work includes:

- The availability of strong in-house (HMG) professional expertise, particularly in economic reform, governance and private sector development;
- Strong experience of contracting flexible programmes through high quality external suppliers;
- Proven programme management capacity;
- Emphasis on value for money and impact;
- Flexible, responsive programmes, with rapid decision making;
- Willingness to support innovation, combined with a readiness to accept and manage higher risks where there are prospects of high impact returns.

  1. In addition, the UK’s existing support to the region enhances our credibility and comparative advantage:

Eastern Neighbourhood (including Ukraine, Moldova and Georgia) – existing UK support

a) The UK provides bilateral programme support through FCO programme funds and the CSSF, focused on areas such as confidence building in areas of conflict, judicial reform, anti-corruption, capacity building and human rights through the CSSF.

b) Additionally the UK delivers significant support in the region through the EU’s Eastern Partnership (EaP), established in 2009 in Georgia, Moldova, Ukraine, Armenia, Azerbaijan and Belarus. The EaP seeks to encourage economic, political and institutional development based on international standards. The EaP includes practical co-operation in areas including economic integration, good governance, private sector development and energy security.

Western Balkans (including Serbia and BiH) – existing UK support

c) Since the end of the conflict in the 1990s, UK policy has focussed on building stability and security in the region by addressing the region’s weak governance, including poor rule of law and corruption. In March 2013, the European Council agreed to open accession negotiations with Serbia, while in June 2015 BiH’s Stabilisation and Association Agreement with the EU came into force.

d) The UK also deploys over 100 troops to the EU’s peace-keeping mission – European Union Force in BiH. On the diplomatic front the UK, with Germany, launched a process to normalise relations between Serbia and Kosovo (with negotiations between the two parties continuing). In November 2014, the UK and Germany launched a new initiative to inject momentum into BiH’s EU accession path, which had been stalled for almost a decade.

Impact, outcome and results that we expect to achieve

  1. GGF interventions will help countries to become increasingly resilient and prosperous as the result of economic growth and transparent, responsive and effective governance institutions which are held to account by informed and active populations.

  1. By providing well-targeted, adaptive technical assistance to GGF countries in support of reforms in priority areas we can strengthen demand-side accountability, leverage wider resources from donors and governments and help sustain the political commitment for reform (Outcome).

  1. The hypothesis underpinning the programme is that well targeted, adaptive TA provided to GGF countries will support reform in priority areas, strengthen demand-side accountability, and leverage wider resources and political commitment to support reform.

  1. We will support achievement of the outcomes and impact through a range of interventions according to country priorities aligned to one or more of the following priority areas:

- Reform to regulation of the business environment and economic governance to bring target countries closer to international standards which can support the growth of small- and medium-sized enterprises and attract foreign investment to improve prospects for broad-based economic growth and job creation.
- Institutional capacity building to develop more effective governance, public administration and management of public finances in order that government in target countries can become increasingly transparent, accountable and responsive to the needs of citizens.
- Anti-corruption measures and judicial reform to strengthen the rule of law, reduce opportunities for corruption and increase the ability of target countries to address corruption where it does occur.
- Modernisation of key sectors such as energy, banking and reform of state-owned enterprises to strengthen target countries’ transition to more market-driven, vibrant, modern economies.
- Stronger and more independent media and civil society to ensure the public has the ability to engage in active, informed debate and to enable to government to resist external pressure and effectively communicate the benefits of reforms to their citizens.

  1. This is a demand-led, responsive and adaptive programme; observable and measurable results in each country will be determined in line with country-specific priorities, tracked and adapted throughout the course of programme delivery, and over time will become increasingly targeted in areas where governments demonstrate a commitment to implementing meaningful reforms and where the GGF adds value. Specific interventions and activities will be developed on an ongoing basis in consultation with beneficiaries and delivery partners, with successful interventions scaled up (with support from the UK or others), and less successful interventions adapted or closed.

Moving from start up to steady state

  1. The GGF has moved quickly to re-establish programmes in countries from which DFID has been absent for several years and where the FCO had very limited programming. We have had to build the knowledge and evidence base. To do this, we have opted to work predominantly through established partners (i.e. IFIs and a competitively tendered managed fund) with proven track records of delivery in these countries. This rationale is set out in greater detail in the appraisal case. Our approach has been to establish our presence and credibility, and to begin to build relationships with a variety of beneficiaries and within the donor community, by developing a portfolio of “quick wins” in the first year of the GGF’s operation. Early outputs, evidence and lessons learned from this approach are informing ongoing programme development.

  1. The TA provided will be demand led and make use of GGF analysis of the political economy; rather than being supply driven. The GGF will work through an iterative learning process building on experience of working effectively to support reforms in Ukraine. The annual planning processes will hone in on areas where evidence suggests traction. The evidence will be built with forthcoming evaluation of work in Ukraine and the wider GGF.

  1. Over time, country programmes will develop a sharper, more strategic focus, with a stronger understanding of the context in a few key areas, and will consolidate and deepen our implementation relationships with committed beneficiaries. The DFID Ukraine technical assistance programme from 2014-16 (which is now integrated into the GGF) followed this pattern; the first annual review acknowledged a need for better prioritisation and consolidation of programme delivery in fewer areas. This approach has been followed, with some intervention areas scaled down, and others scaled up as appropriate.

Box 1: Scaling Up - Support to the National Anti-Corruption Bureau of Ukraine

Progress on fighting corruption is the top demand from citizens and civil society as well as a Government priority. We identified an early opportunity to help ensure the credibility and effectiveness of the newly established National Anti-Corruption Bureau (NABU). In NABU’s early days, it needed fast and flexible support to set out a roadmap for its organisational structure and recruitment plan to develop its capacity to launch effective investigations. UK assistance identified the need to bring in regional expertise through Georgian anti-corruption know-how and Ukrainian project management skills. As NABU grew and established itself as credible and effective, we continued to support its needs through a phased approach, responding to specific needs such as its external communication strategy. NABU is now fully operational, and as of end January 2016, had initiated 56 criminal proceedings, seized significant pre-trial investigation funds and filed claims to the amount of UAH 346,200,000 (nearly £10m). We are continuing to support NABU on a series of strategic initiatives to build NABU’s operational capacity. Our support has helped unlock a large scale EU intervention which has been slow to get off the ground but should now be operational by the end of 2016.

  1. This process – demand led, responsive, and able to scale up or down or stop projects during implementation – means the GGF has a dynamic portfolio which will change over time. The Managed Fund will amend and change throughout the year, as will new grants under the Strategic Support Fund. In the longer term, we will keep delivery modalities under review, not least as our understanding of market development options such as private sector suppliers and SME`s develops. For example, an increased GGF budget from 2018 onwards, combined with more focussed country priorities, may allow us to move from technical assistance into longer term developmental approaches, e.g. service delivery pilots including through the private sector. Alternatively, we may apply lessons and experience to new GGF programmes in other reform-minded countries in the region.

  1. This flexible, adaptive approach is intended to ensure impact in the short and longer term, including through immediate support to government to support reform, by bringing other donors in to support longer term programmes, by influencing government and donor policy, and by unlocking significant additional resources and investments from other sources. This will ensure long term impact, and will deliver multiplier effects, including in terms of financing where GGF interventions will leverage in significantly greater investment from other donors.

Key stakeholders and consultation

  1. The Good Governance Fund was developed in close consultation with Embassies and key partners in the region, including partner governments, bilateral and multilateral donors and other international and national partners. Aside from recipient governments, international financial institutions and other donor partners have been key partners, including the European Bank for Reconstruction and Development (EBRD), the World Bank (WB), the International Finance Corporation (IFC), the European Investment Bank (EIB), the EU, GIZ (German technical cooperation), United Nations Development Programme (UNDP) and USAID. Their knowledge and experience has been invaluable in supporting the strategic framing for the GGF.

## 2. Appraisal Case

What are the feasible options that address the need set out in the Strategic Case?

Building on the GGF Phase One Business Case, there are five possible options to achieve the intended impact:

1. No funding but broader lobbying efforts – further targeted lobbying specifically on governance and economic reforms;
2. Strategic Support Fund – small grants fund managed at post;
3. Managed fund(s) – commercially contracted managed fund delivering a variety of interventions across all five countries;
4. Support to International Financial Institutions (IFIs), multilaterals and other partners such as the EBRD, the World Bank, UNDP and other donor programming in-country;
5. Variety of delivery models – a mixture of in-house programming (option B) managed fund (option C) and upscaling of partnering with IFIs and other donors in country (option D), combined with targeted lobbying.

  1. Option A: No funding but continued and broader lobbying efforts. This would see an end to the current technical assistance programmes in the five GGF countries, with the UK focusing on advocating for inclusive growth and transparent and accountable government. Policy dialogue and political interactions would continue between the UK, other donors and partner governments.

  1. This option would not address the need for additional, responsive technical assistance and additional funds to unblock reforms or scale up successful interventions. In addition, it would see the current high performing support the UK has started to provide through the GGF wound down. Ending support would undermine progress to date and could result in some reform areas stalling, and would have reputational issues. This could be mediated if others step in to provide support, but other donors do not have a similarly fast paced, flexible, responsive instrument as the GGF, and the reputational down sides could make it hard to lobby others to step in. The current programme would be hard to replace.

  1. The UK would not benefit from the deeper understanding of specific problems and opportunities for each of the countries that comes with delivering programmes. We would therefore add less value in terms of policy dialogue with government. No additional funding would therefore risk reforms stalling, leaving the countries less resilient to internal and external threats, risks damage to the reputation of the UK and would see the UK have a limited impact on poverty reduction, growth and enhanced stability in the five countries.

  1. Option B: Strategic Support Fund – this would see funds directly managed by UK Embassies through grants to local NGOs, think tanks, commercial organisations and others. This would ensure the programme was well grounded with local knowledge, led by Embassies and their staff. It would further enable a range of relationships to be developed with key local partners enhancing UK access and influence, and ensuring the UK understood the development context. It would also build on existing skills and capacity (as developed for the CSSF and other small grants programmes).

  1. However, this would require Embassies to enhance capacity to scale up programming, which would incur substantial additional costs for HMG. It would not be possible to scale up sufficiently to absorb proposed funding, limiting the ability of the UK to maximise the benefits of the financing allocated under the Spending Review. Furthermore, whilst posts have excellent access to key partners, they would not bring the specific technical credibility and expertise of International Financial Institutions or be resourced to draw on the networked capacity and expertise of an international commercial supplier (as would be the case with the Managed Fund option).

  1. Finally, a proliferation of smaller scale projects and programmes would introduce risks into the programme in terms of oversight and management. Combined with the high overhead costs in terms of management and monitoring, this option requires shrewd selection and strong management and would best be used strategically for a small selection of targeted support in country. Examples of where this might be the best approach include: small scale, targeted and time bound technical assistance support; testing innovative approaches; trialling interventions before scaling up (e.g. by another donor, government or through an alternative GGF mechanism); testing assumptions and building an evidence base; or developing critical delivery relationships. All these approaches could see scale up or rapid scale down depending on performance and lessons learnt. See paras 5.6 to 5.8 in the Management Case for further information on oversight and monitoring.

  1. Option C: managed fund(s) – Under this option one (or more) service providers would be contracted to respond to requests for technical assistance from partner governments and Embassies for specific reform areas. A multi-year contract has already been established and is operational under the GGF phase one Business Case. This approach is demand led with requests coming from government, working to GGF strategies in country. The service provider will help to identify reform opportunities, scoping projects, working up and agreeing terms of reference with partners and then providing or subcontracting the relevant expertise and advice.
    [note] The GGF was always anticipated to be a multi-year programme, and so a 3 + 1 year contract was let to the successful bidder. Only the first year budget was defined in line with programme approvals at that time, and break clauses were included to enable contract end if the GGF did not continue into future years.

  1. A Managed Fund offers the opportunity to draw on existing local, regional and UK expertise. The current supplier operates through a consortium that includes three to five local organisations in each country, which, with Embassy and GGF expertise, helps to guarantee deep local knowledge. It can also operate in a flexible, adaptive and responsive way, drawing on rapid deployment of expertise to meet partner government and others priorities. Capacity to manage a diverse portfolio with rigorous programme management, allowing scaling up and down is also a benefit. This approach would reduce the staff resource needed in London and in Embassies as the provider scopes, implements and manages programme delivery. This model was used as part of the approach under the DFID bilateral programme in Ukraine where its fast and flexible technical assistance offer delivered high quality results that were welcomed by the Government. Under the GGF Phase One Business Case this approach has rapidly established itself as a highly credible approach with partner governments.
    [note] The Georgian Prime Minister Kvirikashvili specifically thanked the UK for support from the GGF to the Parliamentary Budget Office of Georgia and the UK Office of Budget Responsibility at the 2016 London Anti-Corruption Summit. Embassies in Georgia and Moldova have reported on the value their partner governments have placed on the Managed Fund.

  1. However, relying solely on a managed fund with limited supporting HMG staffing carries a number of risks, including: that the fund won’t necessarily have the access or leverage at a high level with partner governments that HMG, IFIs and other donors enjoy; in addition, limited capacity at post means there is a risk that implementation at the country level would be supply driven (Principal Agent Problem); furthermore, without deeper knowledge of the development challenges in country the fund will be less able to identify key reform opportunities. This option would also limit UK opportunities to build partnerships with larger actors in the region, and support the work of key donor partners.

  1. To manage these risks the GGF would ensure support from a managed fund is rooted in country context – drawing on the Managed Fund’s own expertise, but led by GGF and Embassy analysis and HMG priorities. It will ensure adequate oversight, including at post, and through firm performance management from the GGF Joint Unit. It will direct the managed fund to deliver HMG priorities. This will seek to address the Principal-Agent Problem. Robust oversight from specific advisory and programme management staff in the GGF as well as local knowledge and regular interaction of staff in Embassies will help to ensure that the programme delivers value for money throughout. The risk is further mitigated by pursuing a demand led approach in TA provision; and an adaptive implementation strategy.

  1. Option D: support to International Financial Institutions (IFIs), multilaterals and other donor partners in-country - this option presents the opportunity to work with well-established partners, supporting existing programmes that are already addressing key reform issues as well as developing new programmes with partners. The IFIs offer unique advantages to the GGF through their access to high level officials in country, their ability to link conditionality, and technical assistance to relatively large lending operations, deliver technical expertise in specific areas, international reputation, and political neutrality. The GGF will aim to influence wider IFI programming and policy narrative through its programmes with them, supported by UK directors on their boards. Much of this is not possible through the managed fund or SSF. It also avoids potential overlap of our interventions by collaborating with partners already working in a specific area needing more support.

  1. This option requires less staff resource in London and in Embassies than the managed fund and much less in Embassies than the SSF model; IFIs, multilateral and bilateral donors will work closely with HMG to scope, implement and monitor programmes. These programmes will on average be larger than managed fund programmes. IFI country offices and local partners working with IFIs guarantee deep local knowledge of the politics and practicality of reform. GGF staff will have quarterly update meetings with partners to monitor progress and suggest tweaks to the programmes.

  1. However, relying solely on this approach could hamper our ability to provide flexible, rapid and responsive technical assistance to unblock key reforms and potentially to bring in UK expertise; with the SSF and Managed Fund particularly well placed to do the latter. IFIs and other donors tend to operate over longer time periods through focused programmes. What has been established in Ukraine and in other GGF countries over the phase one period is the importance of moving quickly to provide technical assistance to unblock reforms in these countries.

  1. We need a proactive, well-resourced process to ensure IFI programmes deliver against GGF objectives and are not supply led (Principal Agent Problem, as noted above). This process has been developed through the DFID Ukraine programme and through the phase one of the GGF. The process gives us the opportunity to challenge any projects put to us through IFIs and other partners to ensure they are not only in line with our strategic priorities for each country but also do not duplicate the work of others, are sound projects which reflect best practice and offer good value for money.

Box 2: Working with International Financial Institutions (IFIs)

When the GGF was first set up the Fund approached the World Bank and EBRD to scope possible collaboration in the areas of the GGF strategic priorities for each country. The GGF and Embassies investigated each potential project using local knowledge and a limited selection of the much longer list of projects put to the GGF by the IFIs was then agreed. Due diligence assessments, flexible agreements, results framework and quarterly meeting cycles were then put in place to ensure GGF oversight of the projects. / The GGF has subsequently undertaken more detailed analysis and scoping work and identified further priorities and looked to develop some larger projects. Such priorities include local business support and business registration reform in BiH and support for access to finance for SMEs in Ukraine, Moldova and Georgia. The GGF has scoped options for providing support in these areas and are now planning to work through the IFC and EIB respectively. / Another example is, following analysis and scoping missions to Georgia and close discussions with Embassy colleagues we identified Government of Georgia political will to support public administration reform. We identified this as an area where the UK could support and build on an existing UNDP TA programme, co-funded by Swedish SIDA. The GGF is putting in place a £4.5m agreement with UNDP to support this over the next four years; having pro-actively influenced the overall design of the UNDP programme. This will allow for a strategic, longer term and sizeable programme to run alongside more flexible support to governance reform.
[note] Access to finance was identified as a key binding constraint to growth in the DFID Ukraine Inclusive Growth Diagnostic

  1. Option E: a variety of delivery models - this option involves a mixture of Options B, C and D to maximise flexibility and impact. The UK would work through three delivery channels, enhancing our credibility in continuing to lobby in the region and internationally to accelerate reforms. Stability and resilience depends on a range of support and this approach would allow us to be flexible in each country across each area of reform. This option allows us to increase UK visibility and influence in-country whilst spreading the risk of under-performance across a variety of models. Delivery channels would include:

- a managed fund – providing flexible and responsive technical assistance;
- partnering with IFIs/multilateral institutions and other donors – ensuring new partnerships are built and successful longer term systemic reform programmes are supported, and;
- retaining some modest funding in house to take advantage of opportunities as they emerge to provide small scale support to local and other organisations.

Assess the strength of the evidence base for each feasible option including delivery routes

  1. The evidence base for how to deliver technical assistance effectively is fairly strong. Important lessons have also been generated from previous experience, including the DFID Ukraine bilateral programme, the UK’s Arab Partnership, the Know How Fund and recent GGF experience thorough the first phase of operations.

  1. The ability to provide rapid and responsive technical assistance support is crucial to enable the GGF to build countries’ capacity. Evidence shows that technical assistance (TA) is an effective tool in this regard. A World Bank study found that three quarters of the countries that received technical assistance showed improvements in governance. The study also highlighted that such a support is more likely to show results in middle-income countries – all of GGF countries are middle income. Others have emphasised increasing country ownership, shorter interventions, focusing on capacity building and improving coordination.
    [note] Webb, S. et al (2008) ‘Public Sector Reform: What works and why?’ IEG Evaluation Report.
    [note] GSDRC Report (2009): Changing approaches to technical assistance.

  1. TA aimed at developing capacity works best when adapted to local institutional and political realities; involves local knowledge sources; integrates with informal institutions; develops and maintains legitimacy in the eyes of citizens; and understands local needs, systems, and capacities. Context assessment is usually best done by people with inside knowledge of the country – either local staff, or people with experience in the country who can not only assess needs and deficiencies, but also identify motivation, committed people and opportunities for supporting institutional change. It is also acknowledged that capacity development in fragile and conflict-affected states can be better guided by adaptation and communication, rather than by comprehensive planning.
    [note] Baser, H. (2011). Capacity Development in Fragile Situations. Learning Network on Capacity Development.
    [note] Petersen, B., & Engberg-Pedersen, L. (2013). Capacity Development of Central State Institutions in Fragile Situations. Danish Institute for International Studies

  1. Drawing upon the above evidence, instead of designing large and rigid reform programmes, TA support through the GGF will be based on the principles of adaptive programming; will be informed by local context; will ensure that interventions are politically supported and practically implementable; are small and flexible allowing for experimentation; and include feedback loops for lesson learning.
    [note] Pritchet, L. et al (2012). ‘Escaping Capability Traps through Problem-Driven Iterative Adaption’ Harvard.

  1. The ability to deploy TA in a nimble manner should facilitate rapid response, maximum flexibility and broad access to respond to emerging priorities of different governments. TA proposals will be solicited in a demand-led process and will be assessed by technical advisory staff in Embassies and in London (and in delivery partners, depending on the model chosen) to assess suitability. Proposals will be evaluated to ensure that these support government reform priorities. HMG will take final decisions on which projects to support based on strategic and government partner priorities. During implementation, staff and implementing partners will quality-assure the outputs produced to verify they meet expected standards. They will regularly seek feedback from stakeholders and beneficiaries about the progress of activities, their strategic value and short- and long-term results. This feedback will then inform follow up action, if required.

Box 3: Lessons from Ukraine

DFID established a bilateral programme in Ukraine in April 2014 after a six year gap. Design for the GGF drew on this recent experience, and the Ukraine programme became part of the GGF. In Ukraine support was delivered through a variety of methods, including a managed technical assistance fund (run by an external supplier) and by working with partners who are established and influential in-country such as Germany, the World Bank and the European Bank for Reconstruction and Development (EBRD). Underpinned by a clear strategy, the Ukraine programme has been able to deliver quick wins, whilst establishing longer term interventions. The UK’s programming in Ukraine has been able to support crucial reforms and operates in a space where some other donors struggle (delivering fast, responsive, adaptable programmes – see Box 6 below), whilst ensuring complementarity with the work of other development partners. DFID is recognised for providing timely, valued interventions. The managed fund model, our humanitarian funding and support for improved donor coordination have enabled the UK to play a major role in offering fast, flexible and responsive support in a range of sectors. The last Annual Review of the programme, including the managed fund, scored an A+ and noted that the Government of Ukraine (Ministers and Deputy Ministers) praised its flexibility and how this support enabled reforms to be implemented swiftly and comprehensively.

Box 4: Lessons from the Arab Partnership

The Arab Partnership was a joint FCO and DFID initiative that supported political and economic reform in the Middle East and North Africa region, to build a more inclusive, accountable MENA region. The AP included diplomatic support for political reform, and bilateral funding to finance locally-led reform projects, and influencing work through multilateral organisations, including the European Union, World Bank and International Monetary Fund, to build support for the region. / Lessons from the Arab Partnership include that flexibility is key, but that a strong strategic focus is also essential to ensure maximum impact. Some of the benefits of the Arab Partnership included: greater flexibility to support development interventions; increased impact through pooling funds with other donors; enhanced access to support reforms that otherwise would not be supported; the importance of signalling support for transition in the region. Other lessons included that having too many small programmes can increase the likelihood of overlap and decrease the impact of the overall programme. It also puts a serious strain on limited staffing resources. Good coordination and a clear strategy are necessary to minimise these risks.
[note] https://www.gov.uk/guidance/arab-partnership

Box 5: Lessons from the Know How Fund

The design of the Good Governance Fund took account of the experience of the Know How Fund (KHF), which was set up in 1989/90 to provide assistance to central and eastern European countries and, after 1991, to the countries of the former Soviet Union in their transition to market economies and pluralist democracies. At its height the KHF was spending around £40 million in the region. The context for the GGF differs from the KHF in a number of important ways. In the early 1990s the primary need was perceived to be for basic advice in how to set up market-based systems which simply did not exist in the former Eastern Bloc. The focus was largely on privatisation and financial sector restructuring, and latterly on establishing social safety net systems. While the latter two are still key areas of need today, the issues are now around improved governance to reduce corruption and supporting the business climate through reforming existing systems, rather than building systems from scratch. The KHF worked best where it supported wider incentives for reform and the GGF can learn from this and look for drivers for reform and ensure incentives align with and support larger programmes e.g. IMF programmes. It is therefore critical for the GGF to have a keen understanding of the political economy in each country.

Box 6: Lessons from GGF Phase One

Lessons have been drawn on what works best from the first phase of the Good Governance Fund. We have found that a combination of the Managed Fund’s fast and responsive technical assistance, combined with longer term and strategic support through the IFIs and other donors has worked very well in supporting Ukraine (as noted above). The same model has been effective in the new GGF countries where – despite relatively modest budgets – the UK has quickly become an influential and highly credible donor, working closely with partner governments to deliver reform.

  1. Building on the experience and lessons outlined above the GGF is designed to deliver demand led TA and primarily based on needs highlighted by respective country authorities. This approach requires the recipient country and its institutions to be able to articulate their needs with a clear understanding of the problem and the gaps; domestic commitment and capacity to absorb the TA; and well defined objectives. Such an approach is built through applying good analytics and facilitating an informed dialogue about what TA is needed for, how it should be deployed and by whom.
    [note] Tilley, H. et al (2014). ‘Demand and supply of technical assistance and lessons for the health sector’. Overseas Development Institute, UK.

  1. The evidence base for interventions that would be supported through options B, C, D and E above is moderate to fairly strong (depending on the intervention area).

  1. The GGF priority areas are:

1. Improvements to the business climate;
2. Anti-corruption measures;
3. Modernisation of key sectors such as energy and banking;
4. Reform of justice systems;
5. Strengthening independent media.

Assessment of risks and opportunities for impact on climate change and the environment

  1. The GGF presents limited risks but appreciable opportunities for climate mitigation from supporting reforms and enabling investments in the energy sector.

  1. Risks: Activities promoting economic growth can have an adverse environmental impact; a simple result of increased resource use and motivation to take advantage of economic and livelihood opportunities in the workplace and community. This can partly be offset by raising awareness of sustainable development issues both of the government and other related organisations as well as by exploiting opportunities mentioned below. Throughout all programming we will consider any possible risk to the climate and environment to ensure the programme does no harm to either.

  1. Opportunities:

a) Opportunity to use Strategic Support Fund Projects (SSF) projects to engage on urgent environment issues. Posts could engage reputable local organisations and actors to strive for positive environmental outcomes through small but targeted interventions.

b) Opportunity through the Managed Fund to deliver technical assistance for energy sector reform, increasing energy efficiency, and promoting renewable energy. The Managed Fund will be able to deliver flexible technical assistance which responds to need of shorter term programmes requiring quick mobilisation. This could include support to key actors in the energy sector, including legislative bodies, government ministries and state-owned energy companies. Support would focus on areas where UK has expertise and leadership i.e. electricity and gas market regulation, corporate governance, transparency and accountability of the public institutions, coal sector restructuring.

c) Opportunity to unlock substantial investments in the energy sector from IFIs by unblocking key barriers. Other development partners including IFIs are active in energy sector in GGF countries, working on energy security by diversifying energy sources, building energy infrastructure, investing in renewable energy and supporting energy efficiency programmes at the national and municipal level.

Selecting an option for appraisal

  1. A preferred option has been selected using a multi-criteria decision analysis, comparing each option against a weighted set of practical delivery and potential impact criteria. These criteria take into account the overall objectives of the Good Governance Fund. The criteria were:

1. value for money (VfM)
2. speed of delivery
3. allows for innovation
4. use of local expertise
5. using international expertise on best practice
6. delivering long term systemic change
7. costs of management and oversight for GGF time.

  1. The criteria were determined by a panel of DFID and GGF officials, and were weighted based on their importance and then marked on scale of 0 – 5 based on how well they performed against each of the weighted criteria. Officials independently assigned weights and scores, which were then averaged to give a collective weight and score. Weights are between 0 and 1, while scores are between 1 (low) and 5 (high). Weighted scores were calculated by multiplying each score by the relevant weight. The weighted scores were then summed and these sums used to rank options. This analysis is presented in table 1.
    [note] 0 demonstrating that an option does not deliver against a particular criterion and 5 indicating the option is fully successful in delivering success. Scores are multiplied by the weighting and then totalled to give an overall mark out of 5 per option.

  1. Option E has been assessed as the preferred way to deliver on the GGF’s objectives. Option E scores at least as well as the other options against all of the key criteria except for criteria seven on GGF oversight and management time, and so Option E would remain the preferred option unless there was a very significant increase in the weighting on criteria seven. The score on oversight and management is lower for this option because there are more programmes to manage under this option which is more complex in terms of management oversight and time for GGF staff. It would therefore require an appropriately higher investment in management oversight than an alternative of only one of the delivery options.

  1. Option E scores highly due to the potential to achieve a set of locally informed, mutually reinforcing improvements that give an aggregate effect greater than the sum of its parts. Given experience delivering the first phase of the GGF we now have greater certainty that this option performs better than Options B, C or D on their own.

  1. Having selected a preferred option the below sets out the potential costs and benefits in more detail drawing comparison to Option A (to provide no more funding). Due to uncertainty over the exact projects within each delivery mechanism the analysis is necessarily qualitative in nature but does provide examples of existing and planned projects.

Table 1: Multi-criteria Decision Analysis of Options

		Intervention Options
		Score				Weighted Score
Criteria	Weighting	Option B	Option C	Option D	Option E	Option B	Option C	Option D	Option E
1. Delivers value for money	0.2	2	4	4	4	0.4	0.8	0.8	0.8
2. Speed of delivery	0.2	3	3	3	4	0.6	0.6	0.6	0.8
3. Allows for innovation	0.1	2	4	3	4	0.2	0.4	0.3	0.4
4. Supports the use of local expertise	0.1	4	3	3	4	0.4	0.3	0.3	0.4
5. Leveraging international expertise on best practice	0.1	2	3	4	4	0.2	0.3	0.4	0.4
6. Delivers long term systemic change	0.2	2	2	4	4	0.4	0.4	0.8	0.8
7. Costs of management and oversight time for GGF team (high score represents less time required)	0.1	2	3	3	2	0.2	0.3	0.3	0.2
Total						2.4	3.1	3.5	3.8
Key / Option A - No additional funding / Option B – Small grants fund / Option C - Managed Fund only / Option D - Scale up through IFIs/other donors only / Option E - Variety of delivery methods from options B, C and D

What are the costs and benefits of the preferred option?

  1. Costs: the costs incurred by Good Governance Fund come from the planned £180 million of support over five years as part of the Spending Review (£134 million in present value, discounted at 10% per annum) to interventions that seek to enhance economic and governance reforms in each GGF country. This includes all GGF staff (programme management and adviser) costs, in line with CSSF programming.
    [note] Discounting is a process that adjusts values through time due to the increasing uncertainty that grows the further into the future we look. It considers the rate of change that would be required to compensate society for forgoing consumption today to have consumption in the future and keep people indifferent between the two. In this way it is similar to an interest rate. The greater the uncertainty over the future, the higher the level of compensation required to delay consumption. The discount rate used across the GGF countries is 10%.
    [note] A maximum of 5% of programme costs can be used for all staffing and associated costs.

Table 2: GGF Programme Costs

UK financial year	Value
2016/17	£30m
2017/18	£30m
2018/19	£40m
2019/20	£40m
2020/21	£40m
Total	£180m

  1. Based on 2016/17 country planning, the GGF is currently planning the following breakdown across the three delivery mechanisms within Option E:

Table 3: Indicative Breakdown for FY16/17

Option E Budget line	Spend in FY 2016/17	Expected percentage of spend
Strategic Support Fund	£1.9m	6%
Managed Fund	£12.5m	42%
Working through International Financial Institutions, multilateral organisations and other donor partners	£14.1m	47%
Operational costs	£1.5m	5%
Total	£30.0m	100%

  1. The breakdown in Table 3 could be adjusted within the year as new priorities emerge, the situation changes on the ground, programmes are discontinued due to underperformance or on the basis of new analysis on key drivers of inclusive growth and stability.

  1. The GGF Joint Unit will assess how each delivery mechanism, and project within, is performing in each country and in each area of work, working with staff in Embassies and with delivery partners. The GGF monitors all programmes closely, including through monthly reporting from the Managed Fund and SSF projects and quarterly reporting and meetings with the IFIs, multilaterals and other donors.
    [note] See paras 5.5 – 5.9 for further detail on oversight and monitoring.

  1. Programming decisions will be based on performance reviews, together with need and demand. Decisions will be agreed at formal country programme boards and by the head of the GGF Joint Unit, and reported through NSC Regional Boards.
    [note] See paras 5.1 – 5.4 for further details on management and governance

  1. The costs for each project will be assessed as new projects are considered by the GGF Joint Unit together with Embassies and based on strategic priorities in country. Administration fees will be agreed between the GGF and delivery partners. Where necessary this will involve a negotiation to ensure rates are competitive and offer sound value for money. For the Managed Fund, a competitive process was followed that secured good value for money and excellent technical delivery. In all cases the benefits of the projects should be considered in relation to the costs of delivery.
    [note] See commercial case for more detail
    [note] See paras 3.10 – 3.19 for further information on the Managed Fund

  1. Under phase one, GGF staff (both in Embassies and London) spend around the same amount of time on each of the three delivery mechanisms. Given the respective size of the delivery channels, this suggests the SSF has much higher overhead costs than the Managed Fund or IFIs (this also takes account of management fees levied by delivery partners). This can be justified given the particular benefits of working through the SSF (para 2.7, the SSF is well suited to small scale, targeted and time bound technical assistance support; testing innovative approaches; trialling interventions before scaling up (e.g. by another donor, government or through an alternative GGF mechanism); testing assumptions and building an evidence base; or developing critical delivery relationships). The GGF will keep a close eye on the SSF work strand to ensure it continues to represent value for money.

  1. Benefits: This economic appraisal seeks to compare the net benefit of action to the net benefit of inaction, accounting for all costs and benefits, not just those incurred by the GGF. In this case inaction (option A) may lead to costs being incurred by society. These costs would manifest if the challenges identified in this programme are not addressed, including: the countries become less stable with increased risk of violence; corruption continues, impacting on public services and state capability; and expectations of change among the population in GGF countries reduces, slowing further reforms, or increasing frustration and discontent. The potential costs from these risks materialising to any degree are very difficult to determine. The proposed intervention reduces the risk that these costs materialise and these avoided costs are major benefits from the proposed intervention.

  1. This analysis focuses on the specific GGF priority areas and the evidence of their impact in the five GGF countries. This analysis shows that there will be a broad range of direct and indirect benefits from the programme, including stemming from the GGF leveraging additional funds into the GGF countries through support to technical assistance programmes supporting IFI lending. Wider benefits also stem from, for example, a reduction in the costs to set up a business, money not lost through corruption, time saved by government through more efficient systems and increased investor confidence. Moreover inefficiencies and corruption damage the delivery of services to citizens, slowing the countries’ human and economic development, and leading to wider indirect costs; but the causes of all these costs are inherently unobservable making the estimation of the value of costs avoided by Option E beyond the scope of this document.

  1. The evidence points to wide ranging and diverse impacts from the different GGF priorities. For example:
    [note] For more details see fuller literature review at Annex B

a) Improvements to the business climate (e.g. tax reform, reduction of red tape)

Reforms to improve the business climate can strengthen a country’s institutions such as strengthening the rule of law and enabling political stability which, in turn, can lead to greater investment and stronger economic growth as the political and social situation becomes more predictable. A healthy business environment is essential for growth and poverty reduction. Havrylyshyn et al. (1998) looked at determinants of growth in transition economies and found that macroeconomic stabilisation and structural reforms helped achieve sustainable growth. De Melo et al. (2001) stressed that: “economic liberalisation is the most important factor determining differences in growth”. Carstensen and Toubal (2004) examined the determinants of foreign direct investment (FDI) into Central and Eastern European countries and their study suggests that a rise of the market share of private businesses by 1% leads, on average, to additional 242 million dollars bilateral FDI into a country in the short run (300 million in the long run). Djankov et al. (2006) suggested that if a country reformed significantly to move from the bottom quartile to the top quartile of the Doing Business ranking, it would add 2.3% to its annual growth rate.

b) Modernisation of key sectors such as energy and banking.

Modernisation of the energy sector – the literature shows that energy plays a crucial role in the sustainable development of a country and a region and that energy insecurity is associated with costs that hinder that development. Overall, higher competition levels leads to higher output, capacity and labour productivity (Zhang et al., 2002). However, studies have shown that the success of energy reforms highly depends on other factors. Zhang et al. (2008) found that privatisation is beneficial for growth but only if it is accompanied by a high quality and independent regulatory framework. Bohi and Toman found that if energy-exporting countries behave in a non-competitive manner, importer countries are likely to face unpredictable changes in the affordability of energy. Empirical evidence on the costs of energy insecurity is limited, but a key economic consequence of energy insecurity is related to price shocks, an effect that some researchers have attempted to show using cross-country data. For example, Hamilton (2005) points out that nine of the last ten recessions since WWII have been preceded by an increase in oil prices and found that there is a negative relationship between oil price and economic activity (Hamilton, 2003). Other economists have focused on the demand-side to explain the effects of oil shocks. Bernanke (2006) suggested that an increase in energy prices would primarily slow economic growth through its effects on consumers’ expenditure based on the rationale that fluctuations in prices create uncertainty to which consumers are likely to respond by increasing their precautionary savings and postponing purchases of energy-intensive goods such as cars.

Modernisation of the financial sector - there is a large empirical literature that examines the relationship between financial development and economic growth. Most studies conclude that financial development, together with a more efficient banking system, accelerated economic growth but the size of the effect varies with the indicators, estimation method, data frequency and functional form (see Levin (2005) for an extensive review). Levine and Zervos’s (1998) analysis implies that a one-standard-deviation increase in initial stock market liquidity (0.30) would increase per capita GDP growth by 0.80 percentage points per year. Caporale et al. (2009) used data from ten new EU members from the CEE region over 1994-2007 and found that the stock and credit markets are still underdeveloped in these economies and that their contribution to economic growth is limited owing to a lack of financial depth. By contrast, a more efficient banking sector is found to have accelerated growth. Using the example of Poland between 1994 and 2004, Kenourgios and Samitas (2007) found that credit to the private sector has been one of the main forces in Polish economic growth. Eschenbah et al. (2000) conclude that financial sector openness stimulates economic development though increasing financial sector competition, and Bekaert and Haevry (2003) provide similar evidence for the liberalisation of stock markets.

c) Reform of justice systems

The literature supports the existence of a positive correlation between the rule of law and entrepreneurial activity at the firm-level as well as growth and investment levels at the country-level. However, there is less evidence on which legal institutions and what specific interventions are needed to create and support this environment. Using firm-level data, there are studies that support claims that property rights incentivise investment and increase productivity through enabling individuals to start a business, hire and fire workers as well as protecting investors by enforcing contracts. There are also studies that suggest such a link is dependent on the type of property and investment and the available markets for land, credit and other inputs. Lorenzani and Lucidi (2014) showed that a 10% decrease in the courts to population ratio is associated with a 0.51 percentage points increase in firms’ entry rate and a 0.05 percentage points increase in net FDI inflows as a share of GDP. At the macro-level, there is a widespread literature on the role of institutions in economic growth, especially the role of property rights in fostering investment and growth. Kaufman and Kraay (1997) found that an increase on one point on their 6-point rule of law index was associated with between 2½ and 4-fold improvement in income per capita and a 15-25% increase in literacy. Acemoglu and Johnson (2005) found that property rights have an effect on long-run economic growth, investment and financial development.
[note] The entry rate is a measure of entrepreneurial activity and is defined as the ratio of new firms to the total number of firms in a sector. Net FDI inflows measure new investment inflows from foreign investors (less disinvestment) in the reporting economy in a certain year.
[note] Countries with greater constraints on politicians and elites and more protection against expropriation by these powerful groups are substantially higher income per capita (i.e. higher long-run growth rates), greater investment rates, and more developed stock markets.

d) Strengthening independent media

Case studies from around the world show that, over the long term, there is a positive and strong relationship between independent and free media and economic growth, largely due to the role that an independent and free media can have in fostering greater accountability and transparency in public institutions, critical factors for generating public and international confidence in governments and markets they oversee. Djankov et al. (2003) found that state ownership of media is associated with lower levels of political rights, civil liberties, security of property, and quality of regulation and higher levels of corruption and risk of confiscation. The performance of media institutions is also closely dependent on external economic conditions. In one of the most rigorous studies to attempt an empirical analysis of press freedom and economic and social indicators, Guseva et al. (2008) concluded that “all findings confirm the importance of press freedom for development. A free press always has a positive influence, whether it be on poverty and its various aspects, on governance, on violence and conflict issues”.

e) Anti-corruption measures
[note] There are various anti-corruption measures that countries can introduce (e.g. establishment of Anti-corruption Bureaus, criminalisation of corruption and ensuring enforcement and measures to prevent corruption in public administration and the business sector). Investigating the differential impact of different types of anti-corruption measures was out of scope for this Annex. Please refer to the OECD report on “Anti-corruption Reforms in Eastern Europe and Central Asia: Progresses and Challenges, 2009-2013” for a useful guide to which measures work best under different contexts.

The evidence suggests that corruption is likely to have a negative effect on a country’s overall governance environment, undermining the regulatory environment and the efficiency and legitimacy of state institutions by distorting incentives and decision-making processes which, in turn, are likely to have an adverse effect on economic development and the rule of law, through the channels discussed above. There are a number of channels through which corruption may affect economic growth directly and indirectly through its effects on governance and the institutional environment. These include the impact of corruption on investment, taxation, public revenue and expenditure, human development and institutions such as the justice system. Other studies have confirmed FDI to be positively correlated with governance indicators such as rule of law, control of corruption, regulatory quality, among others (Gani, 2007). Ugur and Dasgupta (2011) concluded that corruption has a negative direct and indirect effect on per-capita income growth. In addition, they found that, indirectly, corruption is associated with lower investment and human capital. Economic theory suggests that corruption can act as a barrier to investment by increasing the cost of doing businesses and causing uncertainty and this is supported by empirical evidence (Zurawicki and Habib, 2010). According to Lambsdorff (2003), an increase in corruption by one point on a scale from 0 (highly clean) to 10 (highly corrupt) is found to lower productivity by 4% of GDP and decrease net annual capital inflows by 0.5% of GDP. The literature suggests that corruption not only lowers the tax to GDP ratio, but also causes long-term damage to the economy by increasing the size of the underground economy, distorting the tax structure and corroding the tax morality of taxpayers, which is likely to reduce further the tax revenue base of a country (Attila, 2008). Corruption affects the progressivity of the tax system, creating biased tax systems favouring the rich and well connected (Gupta et al., 2002).

  1. A DFID-commissioned evidence paper “Why corruption matters: understanding causes, effects and how to address them” (January 2015) looked at the effects of corruption on growth and broader development and concluded:
    [note] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/406346/corruption-evidence-paper-why-corruption-matters.pdf
- The effect of corruption on macroeconomic growth remains contested, and corruption has not been a determining factor constraining growth.
- Corruption has a negative effect on both inequality and the provision of basic services, so it affects poor people disproportionately.
- Lack of trust, reduced legitimacy and lack of confidence in public institutions can be both a cause and an effect of corruption.
- Corruption has a negative effect on domestic investment and tax revenues.
- At the micro level, corruption imposes additional costs on growth for companies, especially in terms of their performance and productivity.
- The relationship between corruption and fragility varies: it can be a source of conflict but has also been an important stabilising factor in some settings.
- Corruption has negative consequences for the environment.

  1. The DFID paper also examines which anti-corruption measures are effective and concludes:
- Not all types of corruption are the same, therefore differing responses are needed depending on the context (one size does not fit all).
- Anti-corruption measures are most effective when other contextual factors support them and when they are integrated into a broader package of institutional reforms.
- Public financial management reforms are effective in reducing corruption.
- In the right circumstances, supreme audit institutions, social accountability mechanisms and organised civil society can be effective in combating corruption.

  1. A full economic appraisal is not possible because GGF programmes are designed to be flexible, demand led and cover a wide range of different interventions. Assessing the potential impact of GGF reforms in each of the five GGF countries is additionally complicated by the five GGF priority areas often overlapping and being inter-dependent; and because there will be activities funded and/or implemented by other partners/donors in the countries and by the governments themselves, which could affect the overall impact of GGF reforms.

  1. It is highly likely that the overall net benefits from the interventions will at least equal the present value of the costs and most likely will significantly outweigh the costs. This is further enhanced by the benefits that will come from GGF interventions leveraging in substantial resources from other donors (examples below) that will ensure the GGF is able to secure larger financial benefits for the countries concerned than the cost to the UK.

Examples of existing and Planned GGF Programmes

  1. Examples taken from existing GGF programmes in GGF countries are outlined below. They include examples from Ukraine, where the GGF has the longest running programmes. As Ukraine is going through political and structural reforms there is a high chance that that such reforms can support macroeconomic stabilisation and economic growth at the impact level. As mentioned in the literature (Havrylyshyn et al. 1998), in Annex B one of key determinants of sustainable growth in transition economies is political stabilisation and structural reforms. This strengthens the probability of success for GGF interventions in the areas of business climate, economic reform and anticorruption.

Box 7: Example of Anti-Corruption Programming in Ukraine

Corruption has been identified as one of the key structural drivers for political instability and one of the factors leading to the 2014 Maidan. We have prioritised the following combination of GGF TA interventions: / So as to reduce discretion in the management of public resources and services, and improve scrutiny of public expenditure, we are: strengthening checks and balances in public financial management; including through support from the UK NAO; supporting greater budget transparency; supporting transparency of State Owned Enterprises; supporting a World Bank led multi-donor Public Expenditure and Financial Accountability assessment for the Ministry of Finance; automating processes through support to the roll out of electronic procurement; strengthening parliamentary oversight through support to financial analysis / In order to enhance scrutiny of individual wealth and conflicts of interest, we are: assisting the development of an electronic asset/ income declaration registry for public officials. / In order to support more effective law enforcement against corruption-related offences, we are: building capacity to investigate and prosecute corruption through institutional support to the National Anti-Corruption Bureau of Ukraine. / In order to improve access of citizens to information and build collective demand for accountability, we are: providing support to the Business Ombudsman Office to act as a conduit for business to channel and investigate complaints, with a strong focus on anti-corruption; supporting independent media and civil society to raise awareness of corruption / In addition, we work closely with other UK Government Departments, in particular the National Crime Agency,

Box 8: GGF work with the International Finance Corporation (IFC)

The GGF plans to provide the IFC with financing of around £3.28m over 3 financial years to undertake business registration reform in Bosnia and Herzegovina (BiH). The project aims to reduce time required for business registration in Republic of Seprska and the Federation of BiH (FBiH) to 3 days from 67 days (for business + VAT registration); reduce the number of steps needed to register a business by 50% in the FBiH by creating a “One-Stop-Shop” for businesses; and reduce the costs of business registration by 15% across entities. The cumulative effect of these reforms should be to increase the number of newly registered businesses in the BiH by 15% in 1.5 years rather than 2 years with significant positive impact on the economy.

Box 9: GGF work with the European Investment Bank (EIB)

The GGF plans to provide up to £5million of technical assistance (TA) through EIB support over 3 financial years. The project is designed to improve the productivity of agri-food sector in the Ukraine, Moldova and Georgia by enabling financial intermediaries to lend to businesses facing difficulties accessing finance. The project will help to improve the capacity of 22 financial institutions and around 4500 small and medium sized enterprises (SMEs) in relatively deprived areas and support inclusive, job creating growth. The EIB identified a need for significantly greater levels of technical assistance to support these loans. This TA will help to provide the knowledge and expertise which the intended beneficiaries need to access the loans, as well as supporting expertise in the financial intermediaries to better assess bids for loans from SMEs. GGF support (50% of the total TA provided) will improve the ability of small and medium sized enterprises (SMEs) to access €620m of funding which is available across Moldova, Georgia and Ukraine.

Box 10: GGF work with the European Bank for Reconstruction and Development (EBRD)

The GGF has supported the establishment of the new Ukraine Business Ombudsman institution in Ukraine through support to EBRD and using UK expertise. The UK has contributed £250,000 a year in FY 2014/15 and 2015/16. The Business Ombudsman’s office carried out 342 investigations on behalf of businesses in Ukraine and made 123 recommendations to government agencies in 2015. Going forward the GGF plans to support the Business Ombudsman for another year. In addition the GGF is developing a range of programmes delivered by EBRD to support the investment climate and governance reform measures in the other four GGF countries. Planned work through EBRD includes supporting Investment Councils to work with government and business and cut red tape (Georgia, Moldova), supporting good corporate governance enhancements in State Owned Enterprises in Serbia and capacity building of the Competition Commission in Georgia.
[note] Under the precursor to the GGF, the DFID Ukraine bilateral programme

Box 11: GGF work with the World Bank and IFC

The GGF has established a trust fund with the World Bank across the GGF countries and planned projects include tax legislation revision in Moldova, public procurement reform in Georgia and Serbia and financial sector strengthening and modernisation work in BiH. A results framework and quarterly meeting schedule has been established with the World Bank to monitor al elements of the work. The Trust Fund has been designed to allow new projects to be approved and included as the need and demand from government counterparts are identified. All such projects will be reviewed by GGF advisers and approved by Embassy programme boards and the head of GGF unit.

Box 12: GGF and the Anti-Corruption Summit

The GGF unit worked closely across DFID, FCO, the Cabinet Office, National Crime Agency and the Serious Fraud Office in the lead up to the PM’s Anti-Corruption Summit on 12th May 2016. Two GGF countries participated in the Summit: Ukraine and Georgia. The GGF unit provided analytics of corruption, identified key priorities and worked closely with political leads to ensure that both countries signed up to ambitious commitments. One of the GGF projects, a partnership between the UK Office of Budget Responsibility and the Parliamentary Budget Office of Georgia was highlighted by the Prime Minister of Georgia Kvirikashvili at the Summit. Anti-Corruption programmes remain a key priority for GGF programming, in particular for Moldova and Ukraine.

  1. Given the challenges in estimating costs and benefits of the whole programme the GGF has developed a robust monitoring framework (see management case). The GGF team will recruit a Monitoring and Evaluation Adviser to ensure that results are captured and lessons learnt throughout implementation.

Theory of Change for the preferred option

  1. The GGF is seeking to achieve the following impact: GGF countries are increasingly resilient and prosperous as the result of economic growth and transparent, responsive and effective governance institutions held to account by informed and active populations.

  1. To achieve this, the GGF will support activities that lead to three major outcomes:

- Governments deliver reform in priority areas;
- Technical Assistance catalyses further investment in reform;
- Increased civil society engagement in reform.

  1. To achieve these outcomes, the GGF will support reforms in targeted areas where beneficiary countries demonstrate reform commitment, including in terms of:

- Support for regulatory reform and capacity building to improve economic governance;
- Training and expertise to develop greater professionalism and technical capacity in the public sectors of GGF countries, such as in financial management and public administration;
- Supporting reform of key sectors including banking, energy, state-owned enterprises and judicial institutions;
- Developing stronger institutional capacity and supporting legislative change to address the challenge of corruption;
- Helping to develop a stronger independent media and civil society, as well as supporting governments’ ability to provide information and communicate with their citizens.

Figure 3: Theory of Change Diagram

  1. The GGF is a relatively modest fund compared to other donors in the region. However, its demand led flexibility will enable it to move quickly to support governments to deliver reforms, and to bring other donors in to support longer term objectives. Its success is predicated on partner governments being committed to reform in areas being supported. Governance reform is complex, and often non-linear. Achieving the outcomes and impacts noted above will not be a short term success. However, there is strong evidence to show that the planned intervention areas are well correlated with positive economic and other governance changes.

What measures can be used to monitor Value for Money for the preferred intervention?

  1. There is uncertainty over precise activities across the lifetime of the GGF programme, and so overall outputs from the GGF are currently not all known making it harder to develop cost-efficiency and cost-effectiveness indicators. However based on current programming the GGF will develop robust and flexible monitoring tools to ensure that UK funding is tracked to deliver agreed outputs and outcomes and achieving the maximum return. Value for money assessments, as well as monitoring and evaluation, will be undertaken against each of the three delivery mechanisms, and within this each programme through IFIs, multilaterals or bilateral donors, to ensure all deliver results and consistently represent sound value for money.

  1. As the GGF will consist of a range of interventions with separate partners it is more challenging to consider value for money in aggregate for ongoing performance management. The approach to value for money should consider explicitly defining trigger points for the re-appraisal of an intervention’s performance. This approach should be employed to reduce sunk cost bias, where money already committed creates a bias to continue spending on interventions that are performing less well. Careful monitoring should enable the overall net value of the programme to be assessed as the programme progresses. Detailed Programme Delivery Plans for each delivery mechanism (and each delivery partner within this for the IFIs, multilaterals and other donors), which include monitoring value for money, will be used to monitor value for money. Agreements with suppliers and partners stipulate specific value for money requirements including on economy, effectiveness and efficiency.

  1. DFID’s regular Multilateral Aid Review (MAR) has also assessed the value for money of potential IFI delivery partners. It concluded that the European Bank for Reconstruction and Development (EBRD) and the United Nations Development Programme (UNDP) offer “Good value for money for UK Aid” while the World Bank offers “very good value for money for UK Aid”. We will ensure that any weaknesses identified in the MAR are integrated into programme design, where relevant, and will put a strong monitoring framework in place throughout the life of the programme. Additionally due diligence assessments will be undertaken for each delivery partner and for each country, where appropriate.

Summary Value for Money statement for the preferred option

  1. Option E – using a variety of delivery methods – should offer the greatest value for money of all of the options because a variety of interrelated delivery models should achieve the greatest impact for the same amount of money. Additionally supporting and working with IFIs, multilaterals and other donors should ensure the UK’s relatively small investment uses the expertise built up by others and leverages greater effect, and this will be supported by the managed fund, a flexible and responsive mechanism enabling assistance to be provided at speed as it is needed to help move reforms forward. A small grants fund will also enable new approaches to be tested which can then be scaled up to increase impact. This approach will also ensure the best use of staff resources available across DFID and FCO to support the GGF. The GGF will capitalise on Embassy know how at posts through the delivery of a small grants scheme and strategic policy advice from London and posts on the politics of the region, while DFID has regular and strong engagement with the IFIs and other donors, alongside sound in-house programme management and economics, private sector development and governance expertise. As a country led fund with leadership from Embassies, the Managed Fund and IFI work streams will also be firmly rooted in country context and local intelligence and understanding.

  1. Although the uncertainty over the precise activities across the GGF mean that undertaking a quantitative appraisal has not been possible, the scale of the costs that the programme seeks to address (e.g. the countries becoming less stable with increased risk of violence; corruption continues; and the opportunity presented by expectations of change are not exploited and significant reforms are delayed), compared to the relatively low cost of the programme, strongly suggests that the GGF should achieve good value for money.

  1. By using a variety of methods we can learn lessons to apply across the wider programme and spread risk, as well as ensure we have a range of alternative options to support interventions in line with the evolving local context. Additionally the GGF is designed so that it is operating through three delivery mechanisms and a range of partners and has the ability to take action and terminate activities that are not preforming well and provide additional support to those areas which are and need further funding.

Gender appraisal

  1. To comply with the International Development (Gender Equality) Act 2014, gender inequality has been considered in the development of this business case and throughout the development of the GGF programme.

  1. In comparison to many countries in which DFID operates, the GGF target countries perform relatively well in UNDP gender equality indices. However, women continue to face significant barriers in accessing employment and other economic opportunities – reflected in considerably lower rates of labour force participation compared to male counterparts. Overall evidence tells us that poor governance, instability, corruption and conflict have a disproportionate impact on women and girls. The GGF is working to build programmes which target gender inequality in country and has commissioned analysis to help support this work. Additionally the GGF is already working to promote transparent, accountable and responsive political institutions, and to promote competitive, vibrate and dynamic economies should be of particular benefit to vulnerable and marginalised populations among all genders.

Table 4: Summary of Priority Gender Issues in Each GGF Country – with Consideration to Gender and Governance (Summary of work commissioned by the GGF)

Bosnia and Herzegovina (BiH)	Despite progress being made towards achieving gender equality in BiH, gender stereotyping and discrimination against women remain widespread – and more needs to be done to overcome ingrained socio-cultural attitudes. While gender mainstreaming is integrated into a range of national policies, legislation, institutional structures and social and economic strategies, and progress is underway to reform or strengthen many systems, significant barriers still exist which limit women’s economic opportunities, equal participation in public life and decision-making, and exercise of human rights. These barriers disadvantage women, and reduce the growth potential, productivity, and performance of the economy as a whole (Cancho and Elwan, 2015; World Bank, 2015a). This report focuses on gender issues, with particular focus on sociocultural conditions and economic impacts on women; however it is acknowledged that gender analyses implies inclusion of men and boys.
Georgia	The gender context in Georgia reflects deep-rooted biases concerning gender roles and equality. Gender stereotyping and discrimination continue - largely due to traditional cultural values, the legacy of Soviet policy on gender equality, and social and economic uncertainties caused by the transitional country context (ADB, 2014; UNECE, 2014; UN, 2015; Duban, 2010; CEDAW, 2013). Recent policy and legal reforms that ensure equal rights and opportunities to women and men and protection of women against violence provide an essential groundwork for improving gender equality and women’s empowerment. But implementation of the laws and policies is weak, and more effort is needed for transformation of persistent patriarchal attitudes (ADB, 2014; CEDAW, 2013).
Moldova	The gender context in Moldova reflects persistent biases and discriminating practices concerning gender roles and equality. Recent policy and legal reforms that ensure equal rights and opportunities to women and men, and protection of women and girls against violence, provide a favourable environment supporting gender equality and women’s empowerment. But implementation of laws and policies across social, economic and political sectors is lagging largely due to slowness on the part of those responsible, deep-seated patriarchal norms, resistance to change, budgetary constraints and subsequent over-reliance on donors (UNWOMEN website, n.d.,; Cozzarelli, 2011; CEDAW, 2013; Sattar et al., 2014; World Bank, 2013). A range of partners are working with government and civil society to promote gender equality and women’s and girls’ empowerment in diverse areas, including broadening economic opportunities, supporting gender-sensitive democratisation by increasing women’s representation in government and public financing, and implementing measures to combat gender-based violence (UNWOMEN website, n.d., UNDP website, 2016).
Serbia	Serbia greatest successes in terms of gender equality have been achieved in the area of power and decision making, showing that the introduction of quotas for women’s political participation has been successful (Babović, 2016, p. 2). However, the gender pay gap is still high in Serbia compared to other European countries and women’s and men’s equal access to the labour market needs to be improved (Babović, 2016, p. 20). Serbia is the first country outside the EU to introduce the EU Index of Gender Equality. The gender equality index in the Republic of Serbia is 40.6, compared to the 52.9 average for the EU Member States, not yet half-way to gender equality (Babović, 2016, p. 2, 22). This places it at 22nd place in Europe. The Index also illustrates regional differences, with Belgrade the best performing region, South and East Serbia the regions with the lowest scores in domains of work, money, time, and Vojvodina the region with lowest score in domain of health (Babović, 2016, p. 50).
Ukraine	Ukraine has made some progress towards gender equality and is above average when it comes to women in education, healthcare, and the labour market, but lagging far behind in women's political representation, while gender stereotypes and discrimination remain. The 2014 Maidan protests and conflict in eastern Ukraine have impacted on progress towards gender equality both negatively and positively. / Key issues include that although the Ukrainian legal and policy architecture is favourable to gender equality although there are problems with implementation and there is a lack of political will to advance gender equality; the stereotypes prevalent in the media are a major challenge to achieving gender equality; women’s political participation is limited and there are no effective mechanisms for improving women’s access to power and decision making; women have lower participation in the labour market and a gender pay gap exists; and there are high levels of sexual and gender based violence.

  1. The GGF commissioned gender analysis to inform programming across all five countries to support a better understanding of the impact on women and girls in the strategic areas in which the GGF engages (a summary of this analysis is in the table above). The analysis had a strong focus on gender and governance issues. The analysis for each country includes the legal and policy environment, institutional environment, the media, public financial management: gender-responsive budgeting (GRB) as well as priority issues towards women’s empowerment including political empowerment, economic empowerment, sociocultural attitudes and gender stereotyping, and gender based violence. This analysis will now help the GGF to develop a robust evidence-base programme of support on gender issues and provide gender-sensitive programming.

  1. Additionally the GGF team will ensure that all project proposals and terms of reference for GGF-funded projects include a gender appraisal assessment to ensure that constraints and blockages affecting particular genders are considered. Wherever possible the GGF will disaggregate results by gender so that we can monitor the impact of the programme on different groups and ensure that development reaches the most vulnerable, allowing the GGF to take action if the benefits of our work do not reach certain groups.

Box 13: Examples of GGF Programmes Delivering Gender Priorities

The GGF is designing programmes to improve gender inequality and designing programmes with gender disaggregated reporting as appropriate. For example: / The planned £4.5m UNDP-led Governance Reform Fund programme in Georgia will address key challenges identified in Georgia’s Gender Equality Policies National Action Plan, ie limited resources, a lack of coordination and indequate comprehension of gender equality and mainstreaming concepts and principles in the public sector. / We are also considering a potential programme with the National Democratic Institute focusing on political empowerment of women in Georgia and Ukraine. / The Local Investment-friendly Environment (LIFE) programme with the IFC in BiH will have a specific focus on gender; including gender analysis as a part of an enterprise survey and focusing on raising awareness of female business owners in new procedures and more transparent processes, as well as seeking business women’s feedback. The GGF is agreeing the gender element of a planned further IFC project in BiH on Business Registration. This project will see gender aspects of the intervention assessed and will endeavour to reduce gender inequalities. / More generally GGF programmes with other institutions including the World Bank and EBRD, which contain a number of projects across the GGF countries, have been designed to include gender disaggregated results; and we are working with each IFI to develop a robust strategy and approach to gender. / The EBRD programme across GGF countries includes gender components in relevant programmes including the projects to strengthen alternative dispute resolution, commercial mediation and arbitration in Moldova and Serbia.

3. Commercial Case

3.1. Paragraphs in the Appraisal Case set out the case for using CSSF resources to support a mixed portfolio of three delivery channels. These are:
1. A Managed Fund: technical assistance projects delivered by a commercially procured service provider;
2. IFI projects: longer term strategic interventions delivered by international financial institutions who have a comparative advantage and presence in country; and
3. SSF projects: short term responsive projects delivered through a variety of partners.

3.2. GGF will adopt a proactive commercial approach which regularly assesses value for money, comparative advantage, continued relevance and impact of the chosen delivery channels. This will be done through a mixture of mechanisms including ad hoc daily interactions and more formal monthly, quarterly and annual review processes. Similarly end of project reviews will be used to test the continued value for money of the delivery channels throughout the year.

3.3. GGF Joint Unit programme managers and the Commercial Adviser are currently preparing a draft GGF Commercial Delivery Plan. This will initiate a commercial capability review beginning with a self-assessment of the GGF Unit’s and Posts’ current capability. The resulting commercial “roadmap” will be agreed between the Commercial Adviser, the Head of GGF and Procurement and Commercial Department (PCD). Priority actions identified are likely to include the need for commercial awareness training (provisionally planned for the autumn) across the joint DFID and FCO teams; improving market knowledge at country level, appointing commercial champions, agreeing and implementing commercial metrics and dashboard reporting, and the introduction of local key supplier management where this adds value. These activities will ensure the Commercial Delivery Plan adds value and demonstrates clear attention to the efficiency, economy and effectiveness of each delivery channel.

3.4. Activities undertaken so far to improve the programme delivery channels can be separated into lessons from similar and related programmes run elsewhere and lessons from activities already undertaken as part of first phase of the GGF. Lessons drawn from related activities including the DFID Ukraine programme and other joint programmes such as the Arab Partnership. These have demonstrated that flexible technical assistance projects combined with a strong strategic focus can deliver real impact by providing added complementarity between activities, increasing the impact of each individual output and therefore increasing value for money overall. This is borne out by the analysis in paras 2.17 to 2.22 of the Appraisal Case, i.e. that technical assistance aimed at developing capacity works best when adapted to local institutional and political realities; involves local knowledge sources; integrates with informal institutions; develops and maintains legitimacy in the eyes of citizens; and understands local needs, systems, and capacities.

3.5. Recognising this, GGF countries are developing country strategies that focus on delivery of GGF priorities, aligned to CSSF activities, where the UK offers strategic impact and adds value to the wider donor effort in that specific country context. For example in Ukraine there is now a focus on anti-corruption and public financial management reform. In Bosnia there is a focus on investment climate reform. In Georgia there is a focus on economic governance and public administration reform. Our commercial approach of using three different delivery channels adds flexibility to deliver these strategic objectives using the best delivery mechanism in a constantly evolving arena, maintaining and in places enhancing, value for money as posts utilise the best mechanism for their ultimate beneficiaries.

3.6. Lessons have also been learnt from GGF phase 1 (June 2015 to September 2016) where interventions have been strategically targeted, but improvements have been identified and made in governance and reporting of delivery channels across the piece. Continued awareness of potential gains in efficiency, economy and effectiveness will continue to deliver targeted and value for money projects.

3.7. Similarly, as the GGF Team’s knowledge of in country markets increases and the programme becomes increasingly focussed on a few key strategic areas and beneficiary relationships, the choice of delivery mechanism may change (see para 1.65 – 1.69 on the GGF’s approach to moving from start up to steady state). Our market knowledge in country is supported by that of Embassies on the ground and our approach to date, informed by the four Partnership Principles, has been to minimise risk by working with known and trusted partners. This is particularly important as the effectiveness of the delivery partners (and therefore the activities) is impacted by their pre-existing relationships with government and other local interlocutors. We will consider country-specific early market engagement exercises as necessary, particularly with a view to broadening access to local private sector suppliers with relevant expertise.

3.8. Further adaptation is also likely following key analysis points, for example end of project reviews and formal DFID reporting processes. An upcoming annual review of the Managed Fund for example will identify early outcomes and explore opportunities to further improve the way the Fund operates; the delivery partner welcomes this. Value for money continues to be tested as programmes start to deliver results. The GGF will continue to access the different delivery channels flexibly, use more of the most appropriate modality to deliver specific outputs, and consider alternative delivery channels as the programme develops.

3.9. The following section goes into further detail about each of the channels.

Which suppliers/implementing partners are expected to deliver the programme?

Managed Fund:
3.10. Under Phase one of the GGF, a commercial supplier was contracted to deliver the Managed Fund. The contract was competitively sourced within the past 12 months through the Fragile and Conflict Affected States framework agreement. This route was taken following advice from PCD. Early Market Engagement (EME) was carried out before the competitive process to build and assess market interest. The EME allowed the GGF Joint Unit to clarify a series of important factors to consider when assessing delivery partners, including: presence and experience in country and a strong relationship with posts, coordination with other donors, ability to provide TA directly as well as source it locally and regionally. Payment by Results was ruled out for this procurement because of the need for adaptive, short term delivery.
3.11. As part of the competitive process there was a rigorous assessment and negotiations of the fees and rates proposed. The preferred bidder was selected as their proposal was strongest, both technically and commercially. The bid delivered value for money (VFM), including by providing economies of scale savings through taking advantage of synergies from the existing Managed Fund in Ukraine and the provision of pro-bono technical advice.
3.12. The chosen supplier is experienced, having already implemented the similar Managed Fund mechanism in Ukraine, and were able to draw on a network of expertise as well as existing infrastructure throughout the Good Governance Fund region. Furthermore their ability to mobilise local, regional and international expertise was seen as a key strength of the bid. Their bid highlighted a clear existing understanding of the region as well as broader expertise across our identified key sectors. This bid placed stronger emphasis on concrete actions and deliverables than the other bid received. Lastly, the chosen supplier is a trusted partner to DFID and participates in the Key Supplier Management programme.
3.13. The contract terms of reference provided flexibility to adapt to changes that may occur during the life of the programme. Specifically, it allowed the scaling up or down of the programme over its lifetime and included the potential to make changes to programme scope, geographical and country reach and contract value. The key review points for following the initial inception phase are at each financial year end.

3.14. With advice from PCD a three year contract with annual break points and the possibility of a one year extension was agreed, allowing flexibility to adapt the programme as necessary throughout the life of the contract.

3.15. At the outset, only the first year’s budget was included in the contract (funded from the DFID funded GGF phase one Business Case). This was made explicit in the contracting documents, with provisions for loading future years’ budgets into the contract when multi-year CSSF funding was confirmed. This arrangement was approved by PCD.

3.16. The first year’s funding cycle is coming to an end, and a draft contract amendment has been developed with PCD. This will allow budgets to be allocated across the remaining programme implementation period once this Business Case is approved.

3.17. As outlined in Table 15, Terms of Reference (ToRs) for sub-projects are assessed by GGF advisors and staff in country for relevance to strategic priorities, risks and outcomes as determined in the logframe, and against VFM criteria including agreed fee rates. Once satisfactory ToRs have been developed they are submitted for formal approval by the Head of the GGF Unit (above £250k) or Embassies (below £250k) before implementation is allowed to commence.

3.18. As noted, the current supplier is part of DFID’s Key Supplier Management programme and managed the separate Managed Fund for Ukraine since July 2014. Ukraine contract reviews have resulted in good performance ratings of 78% and 79% respectively. The GGF team have also established effective performance management arrangements, with weekly progress meetings with the Fund’s Coordinating Unit, and formal monthly and quarterly reporting to provide assurance on delivery. Close scrutiny of performance is also fed up through Embassies to the central GGF Team on a more ad hoc basis.

3.19. The first annual review of the Managed Fund is now underway. Performance will continue to be reviewed throughout the life of the contract, with measures taken wherever necessary to ensure and improve performance. A decision will be taken after the second annual review on whether to continue with the Managed Fund approach. The GGF team, in coordination with PCD, will then consider whether this is continued value and therefore whether to go out to the market for a new contract, or to extend the current contract. Evidence of impact to date and value of money criteria will be central to this assessment, as will a further early market engagement exercise. We will seek advice from PCD on any steps taken on contract extension or on a new tender process.

IFIs:

3.20. Various International Financial Institutions, multilaterals and bilateral partners will continue to deliver a range of interventions under the GGF. These will be focussed on longer term development impacts where the partners have: proven expertise in a given outcome area; an established track record of delivery in the region; and a clearly defined comparative advantage within the donor community. To date, MoUs and contribution agreements have been established with:

- The European Bank for Reconstruction and Development (EBRD) http://www.ebrd.com/home
- The European Investment Bank (EIB) http://www.eib.org/
- The World Bank (WB) http://www.worldbank.org/
- The International Finance Corporation (IFC) http://www.ifc.org/
- The United Nations Development Programme (UNDP) http://www.undp.org/

3.21. Each agreement is approved by the Head of the GGF Unit in consultation with Heads of Mission in relevant embassies, on the basis of a submission which sets out: the background and context for the intervention; the rationale for the choice of delivery partner including evidence of previous performance, whether core funded or through other donor contributions; alignment with the overarching GGF business case and expected contribution to BC outcomes; risks and mitigations including due diligence; gender considerations; Overseas Security and Justice Assessment requirements (if relevant); and management arrangements including value for money criteria and cost drivers. Each agreement is required to have its own results framework and risk register, which cross-refers to the overarching GGF Logframe.

3.22. Terms of Reference (ToRs) and MoUs are concluded with delivery partners using DFID templates and frameworks. Agreements include options to adjust support upwards or downwards as required in the programme, often identifying key break points aligned to programme funding to make adjustments. Quarterly disbursements and financial and progress reports requirements are specified where possible. Some partners however have centrally agreed framework agreements which allow for six-monthly disbursements. At each disbursement point checks are conducted to ensure payment whilst in advance is not in advance of need, with partners needing to demonstrate current level of disbursement and up to date work plans before further disbursement is approved.

3.23. Competence of delivery institutions will be assessed through existing instruments such as the Multilateral Aid Review and Due Diligence Assessments, using existing assessments where possible. We will supplement these with assessments of previous performance in relevant GGF countries, Commercial Expertise Reviews (to be taken forward in parallel to annual reviews), and other evidence of their understanding of local markets, ability to allocate and manage risk, cost drivers and management of downstream partners. These assessments will focus on the partner’s capability to perform appropriate procurement, financial and risk tasks ensuring they have key mechanisms in place to deal with such issues as corruption and fraud. MoUs also will detail key performance indicators to measure and manage performance.

3.24. Given the relatively recent establishment of IFI/multilateral agreements, none have yet been subject to an annual review, and the GGF’s understanding of partners’ delivery capacity and capabilities is therefore still developing. A key area for consideration is local market conditions and how partners manage downstream supply chains; this will be a focus of commercial capability development under the forthcoming GGF Commercial Delivery Plan. Overhead costs are assessed against criteria in DFID’s framework agreements with IFIs and multilaterals. All agreements include break clauses, and allow adaptive programming flexibility, including measures for closing unsuccessful approaches.

Strategic Support Fund (SSF):

3.25. The SSF brings together development and diplomatic approaches by working collaboratively between Embassies in GGF countries and the GGF Unit. This funds fast and flexible small grants for innovative policy engagement activities and pilot interventions, primarily to local organisations. These projects are delivered on a short timescale (usually within a year), and are catalytic in nature. Proposals are submitted by applicants for review and endorsement by programme boards at Post, on which the GGF Unit is represented, using a project template adapted from that used for the CSSF. Non-profit, public and for-profit organisations are eligible to apply. Organisations applying for funding will be required to meet similar criteria to Managed Fund sub-projects, including: how they will apply value for money principles; appropriate use of local expertise and innovation; and alignment of proposed projects with GGF strategic objectives. Specific SSF criteria have also been established including proportionate due diligence and risk assessments arrangements.

3.26. Individual projects are approved by the Head of the GGF Unit following a formal scrutiny process as requested by Ministers. Once approved, SSF projects will be monitored by the Embassy and accounted for using FCO systems. Heads of Mission will remain accountable to the Head of the GGF Unit for the use of SSF resources, and spend will be monitored centrally by the GGF unit programme management team. In addition the GGF Unit will maintain oversight whilst also working to up-skill FCO staff in Posts in programme management and commercial awareness competencies, and ensure that DFID’s SMART rules are adhered to in managing the SSF budget.

3.27. As the day to day management of SSF projects is undertaken in country by Embassies, an annual transfer of funds from DFID to the FCO will be arranged at Main Estimates, at the start of each financial year. Adjustments may be made in the winter Supplementaries round if required.

## 4. Financial Case

What are the anticipated Cost Drivers?

4.1. For the Managed Fund, key costs include international expertise (fee rates), the operating environment and running Programme Management Units in focus countries. International fee rates and programme costs were evaluated against framework rates during the mini-competition described in paras 3.10-3.19, local fee rates were benchmarked against market knowledge including DFID’s recent experience in Ukraine, in particular the Ukraine-specific Managed Fund, and alongside existing CSSF work. The preferred bidder’s costs were further negotiated to maximise value for money. The GGF Joint Unit scrutinises individual ToRs to ensure the relevant level of expert and number of days are provided. We will continue to assess fee rates to ensure ongoing value for money and will review these against updated market information in the forthcoming contract extension.
[note] Project documentation is available from the GGF Joint Unit.

4.2. Programme delivery costs via third party multilateral organisations include cost recovery rates, plus any administration and management costs. Costs are checked against and aligned with framework arrangements where DFID has these in place, eg UNDP, World Bank, EBRD and the IFC. Elsewhere, we have negotiated these as appropriate to drive further value for money. The GGF Joint Unit negotiates fees and overheads when putting in place accountable grants e.g. when putting in place an agreement with NDI Washington for work in Georgia, Ukraine and Moldova. Embassies negotiate contracts with SSF partners as they have a good knowledge of local market rates.

4.3. We have sought to drive down costs in both the Managed Fund and IFI strands by using local expertise whenever possible; such knowledge and skills are high-quality. Not only does this often demonstrate better value for money in terms of immediate costs, but by using local expertise we are more likely to cement government buy-in and produce more sustainable results from the GGF. Furthermore, beyond the immediate local capacity there is also significant experience in neighbouring countries that have had successful reform programmes e.g. Poland and Lithuania. These countries are regarded by other regional players as exemplars to achieving long standing governance and economic reforms. This expertise should also be drawn on where appropriate to ensure the GGF interventions are effective and achievable.

Who are the recipients of all proposed payments?

4.4. There are three delivery channels: working through IFIs/multilateral/other donors; the Managed Fund; and a small grants fund (SSF).

4.5. Payments to the Managed Fund will be made in arrears to the managing agents, who manage subsequent payments to subcontracted providers where appropriate and are responsible for due diligence of their subcontractors.

4.6. For IFIs, multilaterals, and other donors, the main recipients will be: UNDP, WB, IFC, EBRD, WB, EIB. Each of these organisations have significant financial and technical capacity and capability, and each have been reviewed through Multilateral Aid Review (MAR), central due diligence assessments and other reviews including reviews of previous performance. We will conduct proportionate country level DD assessments to supplement central DDAs as appropriate; these will focus on organisations’ capacity to manage downstream delivery and their approach to risk management and allocation.
[note] https://www.gov.uk/government/publications/multilateral-aid-review-update-2013. The 2015/16 MAR is currently being under taken.

4.7. In the case of the small grants Strategic Support Fund (SSF), recipients will be a variety of local organisations in country, including NGOs and civil society organisations, academic institutions and think tanks, some commercial suppliers where appropriate and some government institutions. Projects will be managed in line with CSSF guidance and criteria; most payments are expected to be in arrears but if advance payments are agreed on grounds of need, recipients will be required to account for previous tranches before the next is disbursed. No financial aid is planned to any government institutions. If there were to be a strong case for this for a particular project then the GGF Unit would seek guidance from DFID on whether this might be appropriate and on the need to undertake a fiduciary risk assessment.

4.8. We will also look to work with local organisations who have relevant expertise and who satisfy our due diligence requirements. We recognise the particular risks of small grants funding, e.g. striking a balance between rigorous due diligence and Embassy capacity to manage oversight of multiple suppliers, developing a market in specialist local expertise in countries with corruption risks. Project documents are required to include a risk assessment and mitigations; we expect to develop this further, e.g. through supporting Embassies to better assess their risk appetite and review/termination trigger points.

What is the profile expenditure?

4.9 When the GGF was announced there was a clear ambition to grow our engagement in Eastern Europe and the Western Balkans. A commitment was made in the Strategic Defence and Security Review (SDSR) and UK Aid Strategy that we would double the size of the GGF by the end of the Spending Review period. The allocations below enable the UK government to meet this commitment:

Table 5: GGF Annual Budget

Year	Amount
2016/17	£30m
2017/18	£30m
2018/19	£40m
2019/20	£40m
2020/21	£40m
Total	£180m

4.10. As a demand led fund, country allocations will depend on a combination of need and absorptive capacity. Need can broadly be assessed against the following criteria:

- GDP/capita
- Population
- Fragility and risk of instability
- Transparency International Transparency and Corruption indices
- World Bank Doing Business Indicators

4.11. Absorptive capacity will depend on presence of other donors, how ‘aided’ the country is and whether there are policy/thematic gaps which align with GGF priorities, and institutional commitment and capacity to deliver reform. We have not developed a rigid resource allocation model, but will assess need, demand and absorptive capacity through an iterative process during planning stages.

4.12. For 2016/17 indicative allocations are in Table 6.
[note] As agreed at the GGF Board meeting January 2016. This was the last GGF Board meeting. The GGF will operate through NSC governance procedures in future. The GGF Board meeting has been replaced by a GGF Stakeholder Forum.

Table 6: Indicative Country Allocations 2016/17

Country
Ukraine	£11.7m
Bosnia	£4.2m
Serbia	£4.2m
Moldova	£4.2m
Georgia	£4.2m
Administrative costs (5%)	£1.5m
Total	£30m
[note] CSSF guidance is that no more than 5% of programme funds should be used for administrative costs. Staffing need has been assessed and agreed with the CSSF Joint Secretariat.

4.13. Disbursements will broadly be split as follows:

- Managed Fund payments are made monthly in arrears, upon receipt of correct, itemised invoices. We are working with the managing agent to improve the accuracy of their financial forecasting and budget profiling (this has been identified as an issue in recent Key Supplier Management reviews for this supplier). In general, we expect payments to be fairly evenly split throughout the year based on the current trajectory of Managed Fund projects.
- IFI payments will be quarterly or six monthly, depending on the individual agreement and an assessment of need. Agreements have been set up with the World Bank and EBRD to deliver projects across the five GGF countries with EIB for Georgia, Ukraine and Moldova, and with the IFC in BiH; all agreements have been approved by the Head of the GGF Unit. We are planning agreements with GIZ in Ukraine and UNDP in Georgia which will follow a similar format.
- SSF payments will be made quarterly, upon receipt and agreement by Embassies of financial utilisation reports from implementers. Amounts will be aligned with timelines of programme activities and will therefore vary. We are working with Embassies to improve the accuracy of financial forecasting and profiling, which will be informed by their own rigorous monitoring of implementers.

4.14. This disbursement model will help the GGF manage calendar year and financial year spend depending on the split between Managed Fund and IFI delivery channels. To date the highest risk of variance against forecast has been on the Managed Fund, given its relative complexity (managing a range of subcontractors delivering activities across five countries). We have discussed our forecasting requirements in detail with the managing agent and will continue to review their spending profile monthly. In comparison, IFI payments are generally made against a predetermined schedule, with payments conditional on the receipt of financial and progress reporting for the previous disbursement period demonstrating that 80% of resources provided have been utilised.

What is the assessment of financial risk and fraud?

4.15. GGF countries score relatively poorly on corruption indicators. We will take a strongly risk-averse approach to fraud and corruption, and keep our approach under regular review. Our principal criteria are:

- No financial aid will be used; no payments will be made to government institutions. Payments to delivery partners will only be made after submission and review of project and financial reporting,
- All funding is to be channelled through trusted partners with an established track record of delivery and where there is evidence of sufficient financial management and oversight capabilities. Funding agreements will specify a requirement to have robust fraud and fiduciary risk management policies and procedures in place, consistent with DFID standards.
- Where we are less familiar with partners’ financial systems and procedures in country, we will be conducting local level due diligence assessments before any agreement to fund is finalised, and will monitor closely any actions arising from these assessments. Funding will not be disbursed if we have concerns about an organisation’s track record.
- We will use political economy analysis and lessons learnt from past programming to understand incentives and risks in working with government agencies and anti-corruption institutions and particularly in relation to any work around privatisation and restructuring of state owned enterprises, to avoid elite capture and misuse of aid resources.

How will expenditure be monitored, reported and accounted for?

4.16. Disbursement of GGF funds is split between DFID, which will have the lead responsibility for the Managed Fund and IFI components, and the FCO for the SSF. The exact division will be agreed on an annual basis, but for 2016/17 £27m has been allocated to DFID for the IFIs and Managed Fund components and £1.5m has been allocated to the FCO for the Strategic Support Fund. Funds have been transferred from DFID to FCO at main estimates and adjustments will be made at the winter Supplementaries round.

4.17. £1.5m has been reserved for frontline delivery costs, in line with CSSF guidance that allows for up to 5% of programme funds to be used for this purpose. Over 90% of delivery costs will be payroll, ie staff costs for the London-based GGF Joint Unit and for programme staff in Embassies; workforce planning has been agreed with DFID and FCO respectively.

4.18. The GGF will be monitored in line with CSSF processes and procedures, DFID’s SMART Rules (for the Managed Fund and IFI components on the DFID baseline) and FCO systems (for the SSF). Monitoring arrangements have been established for each component. These are explained in more detail in the management case, but broadly: weekly, monthly and quarterly review meetings are held with the Managed Fund provider, with monthly written updates and quarterly formal reporting; quarterly review meetings have been established with IFIs/multilateral partners, again with quarterly reporting requirements. The Managed Fund and IFI components will each have their own results framework and risk register, which will be aligned with the overall programme logframe and risk register. These are reviewed monthly and updated regularly. A single Delivery Plan for the GGF has been established and is regularly monitored. Small grants partners in country agree reporting cycles with Embassies and project completion reviews.
[note] https://www.gov.uk/government/publications/dfid-smart-rules-better-programme-delivery

4.19. In country the post programme board overseas progress on all projects, including CSSF and GGF. They then report to the GGF Joint Unit for GGF activity. The Joint Unit reports to the Eastern Europe and Central Asia Directorate (EECAD) and Western Balkans and Europe (WBE) Programme and Regional Boards. These in turn report to the National Security Secretariat. The Joint Unit also reports jointly to respective FCO and DFID Directors (for the Eastern European and Central Asia Directorate, and Asia, Caribbean and Overseas Territories Division) and up to FCO and DFID Ministers.

4.20. DFID’s ARIES financial management system will be used through 2016/17 for the DFID allocation. FCO’s PRISM system will be used for the FCO component. This arrangement will be regularly reviewed.

4.21. We will use existing tools to monitor and report on financial and project performance (including progress on delivery) to senior management on a monthly basis. These processes will allow us to identify and flag any risks or issues of concern as well as ensure compliance with best practice.

Will the programme include assets or equipment owned by HMG?

4.22. The majority of programme activity will be technical assistance, which will not generate assets. However, some assets will be purchased where there is a strong case, for instance IT hardware where needed to make progress on key reforms. Procurement of such assets will normally be undertaken locally, using a mini-tender or three quotations process, and final purchase approved by the SRO for the relevant project component.

4.23. All projects will have their own asset registers. Regular spot checks will be carried out by programme staff in the relevant Embassy with oversight from the GGF Joint Unit. At the end of project activities, a decision will be taken on whether to transfer ownership to the partner. Where the assets will continue to be used for the intended purpose, and the Embassy and Joint Unit are confident that the partner has adequate capacity and capability to maintain assets, the normal outcome will be to transfer assets. If there are concerns, a decision will be taken between the Embassy and the Joint Unit on what to do with assets (including whether to transfer them to another partner).

5. Management Case

What are the management arrangements for implementing the programme?

5.1. The GGF programme is managed by a DFID/FCO Joint Unit, led by a DFID Deputy Director as Head of the GGF Unit and an experienced FCO staff member as Deputy Head (at A1 equivalent). This team sits and interacts as a single unit within the FCO, embedded in the EECAD. The team comprises 11 DFID and two FCO members of staff: senior management, programme management and advisers. In addition, the GGF funds 17 FCO Locally Engaged (LE) and UK-based programme management and advisory posts in its five priority countries to increase programme and project management and advisory capacity and to join up local and central knowledge and reporting. All posts are funded from within a ring-fenced delivery costs budget of £1.5m (i.e. 5% of the GGF annual budget, in line with CSSF rules on delivery costs).

5.2. The GGF Joint Unit is accountable to a) DFID and FCO Ministers and b) as with all CSSF funded activity to the National Security Adviser through the National Security Secretariat Joint Programme Hub. Practically this means that the GGF reports to FCO and DFID Regional Directors and through them up to Ministers to keep them informed of progress. The GGF follows DFID’s SMART Rules, and accounts through DFID for all spend related to the IFI and Managed Fund delivery channels, ensuring compliance and programme management best practice. The Strategic Support Fund is managed through the FCO and uses FCO systems, reporting through Ambassadors to the head of the GGF Joint Unit. Departmental accountability is important for high quality programme and financial management, advisory inputs and policy engagement.

5.3. As a CSSF funded programme, the GGF is accountable to the National Security Adviser (the CSSF SRO) through the National Security architecture: the NSC Regional Boards for Eastern Europe and Central Asia, and for Western Balkans and Europe. Regional Boards are accountable to the National Security Secretariat. These boards bring together key HMG colleagues working in the region and provide strategic oversight of the GGF programme portfolio and its alignment with broader NSC objectives.

5.4. The Head of the GGF Unit is the Senior Responsible Owner (SRO) for the overall GGF portfolio but other members of the GGF Joint Unit have day to day responsibility for individual project components. This approach will be reviewed later this year to ensure that it represents the best way of working.

Strategic and portfolio development, oversight and monitoring

5.5. The GGF Joint Unit works with the CSSF, with Embassies and with delivery partners to ensure appropriate strategic and portfolio development, project selection and oversight, monitoring, project completion and lessons learnt. The GGF Joint Unit will ensure very clear oversight throughout, to tackle effectively the challenges identified earlier in this submission: the need for a clear focus and limited priorities; shrewd and robust project selection and monitoring; Principal Agent challenges; the risk of supply-led portfolio development; and the need for evidence and lessons to feed back into the GGF planning process and beyond. As the diagram shows, the Joint Unit works with Embassies to ensure all three delivery channels are proactively managed to deliver HMG priorities.

5.6. Strategic level relationships with IFIs and other multilaterals will be led by the GGF Joint Unit through MoUs and regular monitoring and reporting. The Joint Unit will hold and directly manage the Managed Fund contract. The Strategic Support Fund will be administered at post in accordance with FCO accounting requirements, with additional programme and advisory support from the Joint Unit where necessary.

What are the risks and how will these be managed?

5.7. The GGF Joint Unit will actively manage risk at programme, portfolio and corporate level. Risks will be escalated through the above management chain, with risk management at all levels complying with a common set of principles and approaches that are being finalised. Our appetite for risk within different delivery mechanisms will be outlined in the GGF Risk Management Strategy later this year. Risk management is central to how the GGF JU will manage the various programme streams with lessons learnt between countries and mitigations adapted as the context or risk evolves.

5.8. Detailed risk matrices have been agreed with individual partners which will be monitored closely on an ongoing basis. Key over-arching risks are set out in Table 5 below.
Key:
- Likelihood – 5, almost certain; 4, likely; 3, possible; 2, unlikely; 1, rare
- Impact – 4, severe; 3, major 2, moderate; 1, minor

Table 5: GGF Risk Matrix

Risk	Gross		Mitigation	Net
	Impact	Likelihood		Impact	Likelihood
External/Contextual Risks
External political or economic shocks disrupt delivery of reform agendas.	4	3	HMG diplomatic and GGF programme builds resilience and helps countries deal with internal and external shocks. / GGF uses HMG analysis and early warning to inform strategic and adaptive programme delivery.	3	3
Host Governments over ambitious reform plans raise unrealistic expectations and exacerbate instability or tensions.	4	3	HMG encourages Govt to have conflict sensitive, focused, realistic reform priorities.	3	3
Worsening socio-economic conditions and disillusionment, undermines public demand for reform.	3	3	Technical assistance complimented by ongoing advocacy and communication strategies to communicate the benefit of reforms.	3	2
Programme Management/Delivery Risks
Fund is not sufficiently strategic.	4	2	Regular political dialogue; work in sectors with UK added-value; ensure a focused, PEA informed and conflict sensitive approach; work in partnership with other donors where appropriate.	4	1
Weak donor coordination undermines impact	2	3	Effective engagement with other donors, including considering secondments where appropriate. Explore potential to work in partnership with other donors to improve their programme effectiveness.	2	2
Too many initiatives result in limited overall impact.	3	3	Retain focus on long-term impact and use JU oversight to develop value-added, focused portfolios whilst remaining open to new opportunities.	2	1
Principal-agent problem results in supply-led portfolio with poor VFM.	3	3	Effective and engaged oversight and monitoring of delivery partners ensures demand-led, strategic approach.	2	1
Inadequate capacity and/or capability of staff reduces ability to provide sufficient oversight and assurance.	3	2	Plan for and recruit sufficient staff, build capability and set effective standards through adherence to Smart rules.	1	1
Inadequate capacity and/or capability of advisory staff prevents advisory unit from providing and drawing upon analysis of local context and political economy.	3	3	Plan for and recruit sufficient advisory staff and build capability. Pursue close engagement with XWH policy teams.	2	1
Insufficient monitoring and evaluation, evidence and/or oversight undermines delivery of adaptive programming.	3	2	Generate and use effective feedback, lesson learning and timely evidence to support adaptive programming. Sufficient resources to provide robust M&E.	1	1
Changes in primary stakeholders leads to diminished engagement in reform work.	3	2	Development of deep and broad delivery relationships with key government counterparts. Continued political engagement and close monitoring of overall local context.	4	2
Financial Risks
Fraud or corruption leads to misuse of UK taxpayer money	3	3	Robust financial systems; strong fiduciary controls; no use of financial aid; adequate training of staff and application of DFID policies, including proportionate due diligence.	2	1
Insufficient oversight or management leads to resource and programme slippage	3	3	Strategic over-programming; rigorous financial profiling and variance management; engagement with partners to ensure timely delivery.	2	2

5.9. The risk matrix is aggregated across all GGF countries and country specific risk matrices will be developed. Detailed risk matrices for individual programme components (projects) are being included in delivery plans and used for day-to-day risk management.

5.10. The GGF programme portfolio includes projects supporting security and justice institutions. A process will be established to ensure Overseas Security and Justice Assessments (OSJA) are undertaken as required to assess human rights implications and mitigate associated risks. These will be completed by the end of 2016 and then on an ongoing basis.

How will the programmes incorporate the Partnership Principles?

5.11. A key factor that will impact the effectiveness of GGF programmes will be the approach and commitment of recipient governments. In order to assess this, the GGF Joint Unit, in close coordination with Embassies, will use the four Partnership Principles to assess and monitor this element of the country context. This will include considering the recipient government’s commitment to:

1. Reducing poverty and achieving the Sustainable Development Goals (SDGs);
2. Respecting human rights and other international obligations
3. Strengthening financial management and accountability and reducing the risk of funds being misused through weak administration or corruption
4. Strengthening domestic accountability

MONITORING AND EVALUATION

Purpose and Overall Objective

5.12. GGF Joint Unit will monitor and evaluate the GGF to support the implementation of the programme. The objective is a) to ensure accountability of all funds spent, and b) to learn what works best across the fund, focusing on key evidence gaps. Given the adaptive nature of the fund, evidence generated throughout implementation will help ensure adaptations and responses to the context and emergent risks over the coming years are grounded in rigorous evidence.

M&E Governance

5.13. The GGF as a whole will be monitored against its fund-level logframe. Work will continue to refine the logframe over the next three months. This will be a living document and will be updated when an intervention is undertaken, and after each annual review as needed. The logframe reflects the Theory of Change for the intervention. Implementing partners of each component are expected to develop separate but nested Theories of Change and logframes for each of the projects, with results aggregated up to the programme logframe via the below governance structures. The relevant GGF Joint Unit lead adviser and programme manager is responsible for ensuring these are congruent with the fund-level logframe.

5.14. There will be three groups of stakeholders in the collection, analysis and reporting of monitoring and evaluation data:

- The GGF Joint Unit, with leadership from the newly recruited GGF Monitoring and Evaluation Adviser
- Managed Fund managing agent, IFIs and other implementing partners
- An independent monitoring, evaluation and learning (MEL) provider will be contracted as a programme component, to help DFID and partners to learn about what works in the GGF, how and why, and to provide a depth of analysis and independent assessment not currently available to the GGF Joint Unit.

5.15. The Monitoring, Evaluation and Learning (MEL) provider will work at the programme and project level, providing the following services:
- Help the GGF to finalise an integrated M&E system for gathering data and information to assess implementation progress across the components, including support at the start of the programme to help finalise the fund-level ToCs and strengthen the overall programme logframe;
- Identify and further develop key evidence gaps across the GGF during inception.
- Quality assure and consolidate monitoring reports from the implementing partners into single compact programme reports and provide feedback to the implementing partners and DFID. The reporting should help DFID to monitor progress against target results as set out in the Business Case and programme logframe;
- Based on the above, regularly test and update the programme-level Theory of Change, including key assumptions;
- Inform DFID-led annual reviews with evidence from the above;
- Carry out deep dive evaluations at the project level (as directed by the GGF M&E adviser), providing real-time learning on what works, how, and why in selected adaptive projects;
- Help DFID facilitate learning events across the GGF as appropriate, building on evidence from the above;
Conduct a mid-term and final evaluation at the fund level, if deemed useful by key stakeholders, building on existing monitoring and other data.

5.16. Delivery partners will be responsible for the collection of data under each project, and for producing and submitting this to the GGF Joint Unit. The external MEL provider will regularly report progress made against the relevant logframe. Wherever possible, data will be disaggregated by gender, age, and income quintile. The GGF Joint Unit will verify the satisfactory delivery of agreed outputs through regular field visits, incorporating beneficiary feedback.

5.17. The GGF will put in place more detailed governance arrangements for GGF MEL processes over the next three months. As the different components are interdependent, good coordination and knowledge sharing between them, the GGF Joint Unit, beneficiaries and the external MEL provider, is crucial to achieve the GGF objectives. As part of this, the GGF Joint Unit will prepare an M&E plan for the GGF outlining the roles and responsibilities related to the MEL activities in more detail across levels, including on how adaptive decisions will be made based on evidence.

5.18. In seeking to improve outcomes for beneficiaries in GGF countries whilst being a highly responsive and adaptable programme, specific interventions and activities will be developed on an ongoing basis in consultation with delivery partners and beneficiaries, with successful interventions scaled up (with support from the UK or others), and less successful interventions adapted or closed. These decisions will be based on rigorous evidence, and the M&E plan will consider explicit defining trigger points for the re-appraisal of an intervention’s performance, for example where there is insufficient assurance of improvement for poor performing projects or a major change in the regional economic and political context of GGF countries.

Monitoring Activities

5.19. Monitoring activities will take place at the fund and project-level, and across the stakeholders specified above and will include the following activities:

Results monitoring (project and fund level): Each funding arrangement will set out progress reporting requirements and timings for the delivery of key milestones. Reporting will be aligned to the overall Logframe framework. Results reporting requirements will be designed in such a way that they allow for adaptive programming, where relevant. The above governance arrangements will facilitate aggregation of results monitoring at the fund level, and will allow for effective decision making in DFID. This will also feed into DFID Annual Reviews, led by the GGF Monitoring and Evaluation Adviser.

Portfolio monitoring (fund level): Through monthly portfolio performance meetings, the GGF Unit will assess portfolio development against delivery plans, conduct risk reviews and spots check of results for individual projects. This will also ensure compliance with the Smart rules. Project reporting from partners, post programme boards and beneficiaries will create an understanding of how activities are being delivered, allowing for appropriate monitoring against delivery plans.

Situation/context monitoring (fund and project level): Continued political engagement and close monitoring of overall regional context will allow for an adaptive and flexible approach bolstered by break clauses in contracts. Through regular reporting from implementing partners, and continued close monitoring of overall economic and political situation by posts there will be examination of the operating environments of GGF countries, horizon scanning for changes to the assumptions that underline our results framework and potential risks.

Evaluation Activities

5.20. The evidence base for the overall Theory of Change is considered medium to fairly strong, so the GGF M&E Adviser and MEL provider will further develop the evidence base in these areas through evaluative activities to be specified by November 2016.

5.21. Key strategic aspects of the GGF will be evaluated at the fund and project level, these will link directly to the GGF Theory of Change, testing assumptions and strengthening the evidence base. Questions could include:

Fund level
  1. How can we measure the quality of our technical assistance?
  2. How can GGF supported reforms be best targeted to benefit populations in target countries?

Project level
  1. Is there a link between technical assistance and continued government commitment to reform?
  2. Does investing in demand side accountability promote government-led reform?
  3. What incentives are most likely to stimulate meaningful government-led reform?

5.22. More detailed, country specific questions will be developed during inception.

5.23. The MEL provider will answer the above questions through targeted, robust evaluation(s), which will be agreed upon during the next three months, and might include impact, performance and process evaluation reports at fund or project level. The GGF Joint Unit will manage and quality assure the evaluation reports from the external MEL provider. Evaluations will help influence key decision makers across the GGF.

5.26. Evaluation activities will be done in line with DFID’s evaluation policy, and may be submitted to the DFID independent quality assurance mechanism. Final reports that pass independent quality assurance will be published on devtracker.

Annexes

TABLE OF CONTENTS

Annex A	Worldwide Governance Indicators (WGI) for GGF countries (for 2004, 2009 and 2014) and Freedom House indicators
Annex B	Literature Review on the potential benefits of GGF priorities

Annex A: Worldwide Governance Indicators (WGI) for GGF countries (for 2004, 2009 and 2014) and Freedom House indicators

Indicator 1: Political Stability and Absence of Violence and Terrorism

With the exception of Serbia, which displays a positive trajectory, political stability and absence of violence emerges as the most uneven trajectory over time across the other four GGF countries, indicating a need to focus on political institutions of power and managing both internal conflict as well as conflict resulting from external pressure.

Indicator 2: Control of Corruption

Both Moldova and Ukraine display very low indicators of Control of Corruption, suggesting a continued focus on supporting progress in this area in both countries. Bosnia and Herzegovina has slightly higher indicators but has made little progress

Indicator 3: Government Effectiveness

According to Government Effectiveness indicators, Georgia and Serbia have relatively capable government institutions, with Bosnia and Herzegovina, Moldova and Ukraine displaying uneven and slower progress. There is uneven progress between GGF countries.

Indicator 4: Rule of Law

Ukraine displays a negative trajectory and low level on Rule of Law indicators, Bosnia and Herzegovina, Serbia and Georgia show gradual progress with Moldova a more mixed performer.

Indicator 5: Voice and Accountability

Voice and Accountability is an area where all GGF countries display similar, limited, progress from 2004 to 2014

Indicator 6: Regulatory Quality

Ukraine displays a negative trajectory and low level on Regulatory Quality indicators, whilst all four other GGF countries making positive progress with Georgia emerging as the clear leader.

Freedom of Information

Scores on ‘freedom of press’ are mixed across the GGF countries and shows that there is still room for improvement with the majority of countries ranked ‘partly free’ in 2014.
[note] Freedom House has published an assessment of the media landscape in 195 countries since 1980. Its 23 questions address the legal, political, and economic environments of countries. Individual country reports asses the degree of print, broadcast, and internet freedom in all 195 countries and then rates the country’s media as “Free”, “Partly Free” or “Not Free”. [* Serbia rating prior to 2007 is rating of “Serbia and Montenegro”]

All countries show progress compared to the early 2000s with Serbia outperforming its peers and BiH and Ukraine showing some decline since 2008, partly due to the financial crisis. Ukraine’s improvement in media independence had stalled since 2008 but showed improvement in 2014.

Serbia is ranked best in terms of ‘freedom of press’ with Georgia coming second, closely followed by BiH, Moldova and Ukraine.
Annex B: Literature Review on the potential benefits of GGF priorities

GGF reform area: Economic and governance benefits
Improvements to the business climate (e.g. tax reform, reduction of red tape)
There are a wide range of studies assessing the impact of business climate reforms on the economy and, more specifically, the role of macroeconomic stabilisation in economic growth. Despite agreement that a healthy business environment is essential for growth and poverty reduction there is less consensus on how the impact of business reforms might be associated with factors such as the country’s legal and institutional framework, quality of governance and political regime. Havrylyshyn et al. (1998) looked at determinants of growth in transition economies over 1990–97. They found that macroeconomic stabilisation (including fiscal restraints) and structural reforms helped achieve sustainable growth. While reforms might have depressed output initially, long-term growth was associated with sustained reform performance. They found the role of adverse initial conditions, i.e. the point at which countries began the transition process, to be negative but small. Similarly, Fischer et al. (1998) found that more successful stabilisation measures (resulting in lower inflation and more stable exchange rates), and faster and more comprehensive structural reforms were associated with better growth outcomes during this period. While initial conditions seem to have mattered at the start, this effect wore off over time. De Melo et al. (2001, p. 1) stressed that: “economic liberalisation is the most important factor determining differences in growth”. However, although agreeing on the importance of economic liberalisation, Campos and Coricelli (2002, p. 825) noted that price liberalisation and tight macroeconomic policies are not sufficient to foster growth. They noted that “institutions enabling the functioning of a market economy are a fundamental precondition, particularly relating to financial markets and social safety nets.”
Carstensen and Toubal (2004) examined the determinants of foreign direct investment (FDI) into Central and Eastern European countries. Empirical models showed that the traditional determinants such as market potential (attractiveness to FDI), low relative unit labour costs and a skilled workforce have significant effects on investment. In addition, transition-specific factors such as the level and method of privatisation and country risk, play important roles in determining the flows of FDI into the countries and help to explain the differing attractiveness of the individual countries to foreign investors. For example, they found that relatively high corporate tax rates exert pressure on profits and have an adverse effect on FDI flows to Central and Eastern Europe. However, the estimated parameter value is small and not significant at the 5% level. A decrease of the nominal corporate tax rate in the host countries by 1 percentage point increases bilateral FDI flows by only 2 million dollars in the first year. This small impact may be due to the fact that the authors do not take into account the special tax regimes designed to attract FDI. Another finding from this study suggests that a rise of the market share of private businesses by 1% leads, on average, to additional 242 million dollars bilateral FDI into a country in the short run (300 million in the long run). Moreover, Gross (2005) examined the relationship between FDI inflows in Central and Eastern Europe and institution building, particularly governments' efforts to create a more favourable FDI environment, by reducing uncertainty and, as a result, costs associated with long-term capital investments. They concluded that corruption and a measure of political risk were negatively (and significantly) related to inward FDI, while the presence of bilateral investment treaties and the level of restrictions on repatriation of earnings of CEE affiliates were positively (and significantly) related to inward FDI. Finally, Djankov et al. (2006) suggested that if a country reformed significantly to move from the bottom quartile to the top quartile of the Doing Business ranking, it would add 2.3% to its annual growth rate. In summary, reforms to improve the business climate can strengthen a country’s institutions such as the strengthening the rule of law and enabling political stability which, in turn, can lead to greater investment and stronger economic growth as the political and social situation becomes more predictable.
It is important to note that business climate reforms are political and tends to involve all sectors of an economy, from both the private and public sphere, and, therefore, the GGF should take account of the political context and support for reform by engaging key stakeholders and making sure they own the reforms to ensure successful implementation and sustainability of business climate interventions.

Anti-corruption measures
[note] There are various anti-corruption measures that countries can introduce (e.g. establishment of Anti-corruption Bureaus, criminalisation of corruption and ensuring enforcement and measures to prevent corruption in public administration and the business sector). Investigating the differential impact of different types of anti-corruption measures was out of scope for this Annex. Please refer to the OECD report on “Anti-corruption Reforms in Eastern Europe and Central Asia: Progresses and Challenges, 2009-2013” for a useful guide to which measures work best under different contexts.

Economists and political scientists have long identified a number of channels through which corruption may affect economic growth directly and indirectly through its effects on governance and the institutional environment. These include the impact of corruption on investment, taxation, public revenue and expenditure, human development and institutions such as the justice system. Macro-level studies have used cross-country data to explore the relationship between governance and economic indicators and have consistently found that corruption significantly decreases economic growth and development. Ugur and Dasgupta (2011) conducted a review of the evidence available (115 studies) on the effect of corruption on economic growth and concluded that, overall, corruption has a negative direct and indirect effect on per-capita income growth. In addition, they found that, indirectly, corruption is associated with lower investment and human capital. Moreover, they found that corruption is expected to be more detrimental in countries with higher levels of per capita income and institutional quality. Focusing on indicators of human development, Holmberg and Rothstein (2011) used cross-sectional data from more than 120 countries and found that corruption is correlated with lower growth rates, GDP per capita, economic quality and lower levels of human development across countries.
Economic theory suggests that corruption can act as a barrier to investment (e.g. FDI) by increasing the cost of doing businesses and causing uncertainty and this is supported by empirical evidence (Zurawicki and Habib, 2010). According to Lambsdorff (2003), an increase in corruption by one point on a scale from 0 (highly corrupt) to 10 (highly clean) is found to lower productivity by 4% of GDP and decrease net annual capital inflows by 0.5% of GDP. Wei (2000) found corruption to be a significant factor in reducing FDI in the host country. A 2008 study, looking at US FDI outflows in relation to levels of corruption in 42 host countries, also indicated that US firms are less likely to invest in countries where corruption is widespread (Sanyal and Samanta, 2008). Consistent with these findings, other studies have confirmed FDI to be positively correlated with governance indicators such as rule of law, control of corruption, regulatory quality, among others (Gani, 2007). The link between corruption and FDI comes through the channel of increased investment costs when corruption is high. A survey of 350 international companies based in seven jurisdictions: the UK, the US, Germany, France, the Netherlands, Brazil and Hong Kong carried out by Control Risks and Simmons & Simmons in 2006 revealed that a quarter of its respondents claimed that corruption increased their costs of international investment by up to 5%, and nearly 8% of respondents claimed that it increased their costs by 50% (Control Risks and Simmons & Simmons, 2006). Cuervo-Cazura (2006) found that corruption not only results in a reduction in FDI but also in a change in composition of country or origin of FDI. Their results indicate that corruption in host countries results in less FDI from countries that criminalise corruption abroad, which are the largest source of FDI, and more FDI from countries with higher levels of corruption which implies that laws against bribery may act as a deterrent to bribery in foreign countries.
The literature suggests that corruption not only lowers the tax to GDP ratio, but also causes long-term damage to the economy by increasing the size of the underground economy, distorting the tax structure and corroding the tax morality of taxpayers, which is likely to reduce further the tax revenue base of a country (Attila, 2008). Similarly, Tanzi and Davoodi (2000) found that corruption has a statistically significant negative correlation with individual income taxes, taxes collected from VAT, sales tax and turnover tax. More recently, a 2010 paper, using panel data for firms in Asian countries, found that public sector corruption has a large negative impact on corporate tax payments, suggesting that reduction in public sector corruption could have a significant impact on a country’s tax capacity (Fuest, Maffini and Riedel, 2010). The study indicated that this is especially true for small and medium-sized national firms that may try to reduce their tax burden in corrupt environments. Large multinationals, however, react to public sector corruption by investing in other countries, therefore pointing to the opportunity costs of corruption.
Moreover, corruption has an impact on economic welfare as indicated by inequality. An IMF paper provides empirical evidence of the impact of corruption on inequality and identifies one of the mechanisms leading to these results. Corruption affects the progressivity of the tax system, creating biased tax systems favouring the rich and well connected (Gupta et al., 2002). As corruption facilitates tax evasion, ill-functioning tax administrations, and exemptions that favour the wealthy and well connected, this undermines the effectiveness of the tax base and the government’s capacity to ensure equitable wealth redistribution from the rich to the poor.
Finally, researchers have investigated the impact of corruption on a country’s governance environment. Andreev (2008) investigated the relationship between citizen’s perceptions of corruption and the quality of rule of law and the political system in the CEE region and Latin America and found that perceptions of corruption are key determinants of government legitimacy across countries. Similarly, Seligson (2003) found similar results for four Latin America countries. Using survey data from 80 countries, Jong-Sung You (2005) found that freedom from corruption; income equality and mature democracy are positively associated with social trust.
In summary, the evidence suggests that corruption is likely to have a negative effect on a country’s overall governance environment, undermining the regulatory environment and the efficiency and legitimacy of state institutions by distorting incentives and decision-making processes which, in turn, are likely to have an adverse effect on economic development and the rule of law, through the channels discussed above.

Modernisation of key sectors such as energy and banking
Modernisation of the energy sector
The rationale of interventions to modernise the energy sector is based on the assumption that reforms will lead to higher efficiency levels and stronger governance environment (e.g. energy security) and, thus, stimulate economic growth. Common interventions include regulatory reforms, restructuring, market liberalisation and privatisation.
The effect of increased competition (e.g. through market liberalisation or privatisation) has been analysed in many sectors. Overall, higher competition levels leads to higher output, capacity and labour productivity (Zhang et al., 2002). However, studies have shown that the success of energy reforms highly depends on other factors. Zhang et al. (2008) look at 36 transition and developing countries and conclude that regulatory reforms to enable competition and privation in the energy sector are not sufficient to increase electricity generation. They showed that privatisation is beneficial for growth but only if it is accompanied by a high quality and independent regulatory framework. Similarly, Lenz and Prsa (2005) look at differences in the impact of energy sector reform in the EU-15 (old Member States) and the EU-12 (new Member States) and conclude that successful reform models require an appropriate level of institutions, which transition and post-transition countries may be lacking, to be successful in improving the efficiency of electricity generation and, therefore, economic growth. In summary, this strand of the literature points towards a strong positive correlation between electricity production and economic growth in both developed and developing countries. However, the success of interventions is highly dependent on the macro-economic environment including strength of institutions and regulatory quality.
More recently, economists and policy makers have analysed issues related to energy security with countries across the world putting in place measures to reduce energy insecurity. Energy security is seen as a way to address concerns on energy dependence that is driven by growing energy demands, the significant share of fossil fuels in energy systems and the significant geographical concentration of hydrocarbons.
Economists have used economic theory to define the costs of energy security. Bohi and Toman (1996) defined energy security as the loss of welfare resulting from a change in the price or physical availability of energy. In an earlier paper, they used the theory of externalities to discuss the costs of energy security. More specifically, they considered two potential externalities: (i) those related to changes in the volume of oil imports, and (ii) those related to price volatility (Bohi and Toman, 1993). The externalities related to the price of oil are present due to the market power of exporters, e.g. organisations such as OPEC, who may be able to keep the market price of oil above the competitive level. If energy-exporting countries behave in a non-competitive manner, importer countries are likely to face unpredictable changes in the affordability of energy. Moreover, energy-related externalities arise due to energy cost fluctuations when the rest of the economy is slower in its adjustment to energy cost changes. For example, in the labour market, a rise in energy prices can increase unemployment due to wage rigidities and similarly, a rise in energy prices can have an effect in capital markets through its effect in energy-intensive capital (Markandya and Hunt, 2004).
Empirical evidence on the costs of energy insecurity is limited, partly due to the difficulty in measuring energy security. A key economic consequence of energy insecurity is related to price shocks, an effect that some researchers have attempted to show using cross-country data. For example, Hamilton (2005) points out that nine of the last ten recessions since WWII have been preceded by an increase in oil prices and found that there is a negative relationship between oil price and economic activity (Hamilton, 2003). However, it is unclear how the price of oil affects economic activity. Other economists have focused on the demand-side to explain the effects of oil shocks. Consistent with Hamilton’s (2005) finding that higher uncertainty about future energy prices is the main mechanism through which energy shocks affect the economy, Bernanke (2006) suggested that an increase in energy prices would primarily slow economic growth through its effects on consumers’ expenditure based on the rationale that fluctuations in prices create uncertainty to which consumers are likely to respond by increasing their precautionary savings and postponing purchases of energy-intensive goods such as cars. In summary, the literature shows that energy plays a crucial role in the sustainable development of a country and a region and that energy insecurity is associated with costs that hinder that development.
Modernisation of the financial sector
There is a large empirical literature that examines the relationship between financial development and economic growth using panel data or time-series data for individual countries. Most studies conclude that financial development, together with a more efficient banking system, accelerated economic growth but the size of the effect varies with the indicators, estimation method, data frequency and functional form (see Levin (2005) for an extensive review). Goldsmith (1969) was the first empirical study to show, graphically, a positive association between financial development and GDP per capita compiling a dataset on 35 countries over 1860 to 1963. During the late 1990s, researchers included stock markets in their analysis with Levine and Zervos (1998) analysis implying that a one-standard-deviation increase in initial stock market liquidity (0.30) would increase per capita GDP growth by 0.80 percentage points per year. Accumulating over 18 years, this implies real GDP per capita would have been over 15 percentage points higher by the end of the sample. Interestingly, Levine et al. (2000) found that development of financial intermediation affects growth positively, and that cross-country differences in legal and accounting systems largely account for different degrees of financial development. The GGF and other donor activities should consider inter-linkages and inter-dependencies between the GGF areas of intervention such as the modernisation of key sectors in the economy and strengthening institutions, including the justice system as well as improving the business climate.
More recently, researchers have looked at the CEE region and other countries in transition to investigate the role of the financial sector, one of the first sectors to transition from a heavily regulated industry to a key player in the market economy. Caporale et al. (2009) used data from ten new EU members from the CEE region over 1994-2007 and found that the stock and credit markets are still underdeveloped in these economies and that their contribution to economic growth is limited owing to a lack of financial depth. By contrast, a more efficient banking sector is found to have accelerated growth. Using the example of Poland between 1994 and 2004, Kenourgios and Samitas (2007) found that credit to the private sector has been one of the main forces in Polish economic growth. Eschenbah et al. (2000) conclude that financial sector openness stimulates economic development though increasing financial sector competition, and Bekaert and Haevry (2003) provide similar evidence for the liberalisation of stock markets. Hagmayr et al. (2007) investigated the finance-growth nexus in four emerging economies of Southeastern Europe for 1995-2005 and found a positive and significant effect of bond markets and the capital stock on growth, given that legal and supervisory frameworks work properly. Lastly, supporting the evidence that the relationship may differ depending on the wider institutions in place, Fink et al. (2005) looked at 22 market economies and 11 transition economies and found that the positive association between the financial sector and growth was weaker in market economies compared to transition economies as well as in the long-run compared to the short-run.

Reform of justice systems

There is a large body of evidence, both at the macro- and micro-level, that considers the relationship between the rule of law and economic growth via mechanisms that protect property rights, facilitate incorporation and borrowing as well as ensure the enforcement of contracts. Overall, the studies agree on the existence of a positive correlation between the rule of law and entrepreneurial activity at the firm-level as well as growth and investment levels at the country-level. However, there is less evidence as to which legal institutions and what specific interventions are needed to create and support this environment.
At the micro-level, using firm-level data, while there are studies that support claims that property rights incentivise investment and increase productivity through enabling individuals to start a business, hire and fire workers as well as protecting investors by enforcing contracts, there are also studies that suggest such a link is dependent on the type of property and investment and the available markets for land, credit and other inputs. Surveying privately owned manufacturing firms across 5 Eastern European countries, Johnson et al. (2002) tested whether secure property rights are sufficient for investment by firm-owners. They found that firm-owners in the sample with the least property rights invested 32% of their profits, nearly 40% less than those with the most secure property rights who invested 56%, irrespective of access to bank finance. They concluded that secure property rights are sufficient for investment by firms in countries with low institutional development and that bank credit, although important, may matter more once property rights are secure. On the role of judicial efficiency, Lorenzani and Lucidi (2014) used data from the Council of Europe (e.g. number of judges and non-judge staff, court organisation, budget allocation to courts, use of ICT, etc.) over 2006 and 2010 covering EU and non-EU countries and showed that a 10% decrease in the courts to population ratio (10% reduction in litigation rates, i.e. incoming cases per 1000 inhabitants) is associated with a 0.51 percentage points (0.58 percentage points) increase in firms’ entry rate and a 0.05 percentage points (0.13 percentage points) increase in net FDI inflows as a share of GDP. Similar results were found in Latin America where, using a survey of CEOs and panel data from Latin America, Staats and Biglaiser (2012) found that judicial strength and rule of law are important determinants of FDI. In another study, looking at the relationship between rule of law and firm growth, Kumar et al. (2001) analysed data from 13 European countries and found that the positive association between judicial efficiency and firm size is stronger for firms in low capital-intensive industries, partly explained by the fact that a more sophisticated legal system is necessary to protect intangible assets such as reputation or client relationships. Other studies have documented this relationship at the country level: Laeven and Woodruf (2007) showed that there is a positive relationship between judicial efficiency and firm size in Mexico by reducing idiosyncratic risks faced by firm owners; a one-standard deviation improvement in the quality of the legal system was associated with a 0.15-0.30 standard deviation increase in firm size. Garcia-Posada and Mora-Snaguinetti (2013) obtained similar findings for Spain; Giacomelli and Menon (2012) also found evidence that the average size of manufacturing firms is lower in municipalities where judgements are slower and suggested that if the length of Italian civil proceedings decreased by half would lead to a 8-12% increase in average firm size, all else being equal.
[note] Countries include: Poland, Romania, Slovakia, Ukraine and Russia.
[note] The entry rate is a measure of entrepreneurial activity and is defined as the ratio of new firms to the total number of firms in a sector. Net FDI inflows measure new investment inflows from foreign investors (less disinvestment) in the reporting economy in a certain year.

At the macro-level, there is a widespread literature on the role of institutions in economic growth, especially the role of property rights in fostering investment and growth. Kaufman and Kraay (1997) used a combination of cross-country investor surveys and polls of experts and found that an increase on one point on their 6-point rule of law index was associated with between 2½ and 4-fold improvement in income per capita and a 15-25% increase in literacy. Acemoglu et al. (2001) found that variation in income levels across countries is closely associated with investor perceptions of the likelihood of expropriation of property. They showed that level of FDI is an important component of growth in developing countries, and that a crucial factor in attracting FDI is a stable, consistent, fair and transparent legal system. In line with the previous studies, Acemoglu and Johnson (2005) found that property rights have an effect on long-run economic growth, investment and financial development. Djankov et al. (2006) used data on business regulations in 135 countries and found that improving the quality of business regulations from a set of countries from the worst to the best quartile is correlated with a 2.3% in annual economic growth. However, Haggard and Tiede (2011) question whether researchers can adequately isolate the effects of property rights from other elements of institutions. Using data from 74 developing and transition economies they compared the relationship between four types of rule of law and economic growth. They found that violence and corruption, the basic law and order, is a stronger determinant of economic growth than the ‘rule of law’ indicators used.
[note] Countries with greater constraints on politicians and elites and more protection against expropriation by these powerful groups are substantially higher income per capita (i.e. higher long-run growth rates), greater investment rates, and more developed stock markets.
[note] They looked at business environment configurations across seven areas: starting a business, hiring and firing workers, registering property, getting bank credit, protecting equity investors, enforcing contracts in the courts and closing a business. Also, a quartile is a 25% interval – the fourth quartile consist the 25% countries with the worst quality of business regulation and the best quartile are the 25% with the highest quality of business regulation.

In conclusion, the literature highlights the importance of properly functioning judicial systems and related institutions for the whole economy but there is less evidence as to which aspects of the legal institutions and which interventions are most successful under different conditions.

Strengthening independent media
Media assistance is based on the principle that a country’s media should be ‘free, independent and pluralistic’. While most organisations agree that it is a precondition for democratic development, other rationales for activities in the field include media assistance as a means to economic development, combatting corruption, preventing conflict and promoting human rights or as a contributor to broader social and human development.

Empirical evidence is anecdotal; it is difficult to identify a direct relationship of cause and effect between media and democratisation as media can be viewed either as dependent and mirroring society or as a primary force in forming society (McQuail, 2005). Norris (2002) conducted a comparative statistical analysis of 135 nations and concluded that independence of media and public access are two clear indicators that can help us understand whether the media can positively impact democratic governance (cited in Arsenault and Powers, 2010). To ‘test’ the theory with data, Price et al. (2002) analysed country case studies of post-communist transition societies including BiH, Ukraine and Poland. Although they found a link between liberalised media and democratic society, and identified the structure of the media system and government regulation as important macro-level variables, they argued, in line with the wider literature, that it is difficult to determine causality. In examining the patters of media ownership in 97 countries, Djankov et al. (2003) found that state ownership of media is associated with lower levels of political rights, civil liberties, security of property, and quality of regulation and higher levels of corruption and risk of confiscation.

To further study the relationship between media freedom and democratisation, some researchers have focused on countries in transition in the CEE region. Voltmer and Schmitt Beck (2006, cited in Stetka et al. 2013) conducted a comparative study of four countries in transition (Hungary, Bulgaria, Uruguay and Chile) and found evidence of a relationship between media consumption and political knowledge, political participation, the evaluation of political parties and preferences for democratic political order. In line with research in the CEE region, studies from Latin American countries use examples of public scandals to conduct an empirical analysis. Porto (2008) showed that the greater professionalisation and development of critical reporting in in Brazil’s largest television network (TV Globo) following the fall of the authoritarian regime in 1985, forced the chief executives to adapt their communication strategies, with complex obligations for quality improvement.

The performance of media institutions however, is also closely dependent on external economic conditions. In a study based on content analysis, Pinto (2008) suggests that watchdog journalism in Argentina has ‘lost its bite since 2005’, possibly due to the economic crisis as well as the challenging organisational culture of the news media which favours corporate investments. A weakening trend of investigative journalism, which was not particularly strong to start with, has been observed in many CEE countries as well, especially since the beginning of the economic crisis in 2007/8 which put news media organisations under unprecedented pressure and resulted often in the trimming of investigative departments.

In one of the most rigorous studies to attempt an empirical analysis of press freedom and economic and social indicators, Guseva et al. (2008) concluded that “all findings confirm the importance of press freedom for development. A free press always has a positive influence, whether it be on poverty and its various aspects, on governance, on violence and conflict issues”.

In conclusion, case studies from around the world show that, over the long term, there is a positive and strong relationship between independent and free media and economic growth, largely due to the role that an independent and free media can have in fostering greater accountability and transparency in public institutions, critical factors for generating public and international confidence in governments and markets they oversee.

Literature Review References:
Acemoglu, D., Johnson, S. and Robinson, J., 2001. “The colonial origins of comparative development: an empirical investigation”, American Economic Review Vol. 91, pp. 1369-1401.
Acemoglu, D., and Johnson, S., 2005. “Unbundling Institutions”, Journal of Political Economy, 113(5), 949‐995.
Andreev, S., 2008. “Corruption, Legitimacy and the Quality of Democracy in Central and Eastern Europe and Latin America”, Review of Sociology Vol. 14, pp.91-115.
Arsenault, A., and Powers, S., 2010. “Review of the Literatur”, The Media Map Project: A resource on the impact of media development worldwide”, The Media Map Project.
Attila, J., 2008. “Corruption, Taxation and Economic Growth: Theory and Evidence.” CERDI-CNRS. Working paper.
Bekaert, G., Harvey, C.R., Lundblad, C.T., 2003. “Equity market liberalisation in emerging markets”, The Journal of Financial Research, Vol. XXVI (3), pp. 275-299.
Bernanke, B.S., 2006. “Energy and the Economy”, speech to the Economic Club of Chicago, June.
Bohi, D.R. and Toman, M.A., 1993. “Energy security: Externalities and policies”, Energy Policy, 21: 1093- 1109.
Bohi, D.R. and Toman, M.A., 1996. “The Economics of Energy Security”. Kluwer Academic Publishers, Boston.
Campos, N. and Coricelli, F., 2002. “Growth in Transition: What We Know, What We Don’t, and What We Should,” Journal of Economic Literature XL(3): 793-836.
Carstensen, K. and Toubal, F., 2004. ‘Foreign direct investment in Central and Eastern European countries: a dynamic panel analysis’, Journal of Comparative Economics 3, pp. 3-22.
Caporale G.M., Rault C., Sova R., Sova A., 2009. “Financial Development and Economic Growth: Evidence from Ten New EU Members”, DIW working paper no.940.
Cuervo-Cazurra, A., 2006. “Who Cares about Corruption?” Journal of International Business Studies Vol. 37, No. 6.
De Melo, M., Denizer, C., Gelb, A. and Tenev, S., 2001. “Circumstance and Choice: The Role of Initial Conditions and Policies in Transition Economies,” World Bank Economic Review, Vol. 15, No. 1, pp. 1-31.
Djankov, S., McLiesh, C., Nenova, T., and Andrei Shleifer, 2003. “Who Owns the Media?”, Journal of Law and Economics, 46, pp. 341-382.
Djankov, S. McLiesh, C. and Ramalho, R. M., 2006. “Regulation and growth”, Economics Letters, 92(3), 395‐401.
European Bank of Reconstruction and Development (EBRD), 2016. “Transition Report 2015-2016”.
Eschenbach, F., Francois, J.F. and Schuknecht, L., 2000. “Financial sector openness and economic growth”, in: S.Claessens and M. Jansen (ed.), The Internationalization of Financial Services. Issues and Lessons for Developing Countries, The Hague, Kluwer Law International, 103–115.
Fink G., Haiss P., Mantler H.C., 2005. “The Finance-Growth-Nexus: Market Economies vs. Transition Countries, EuropaInstitut Working Paper 64.
Fischer, S., Sahay, R. and Végh, C., 1998. “From Transition to Market: Evidence and Growth Prospects,” IMF Working Paper No. 98/52, Washington: IMF.
Freedom House, 2016. “Nations in Transit”.
Freedom House, 2016. “Freedom of Press”.
Fuest, C., Maffini, G. and Riedel, N., 2010. “How does corruption in developing countries affect investment and tax compliance?”, article in Critical issues in taxation and development, Cambridge, Mass: MIT Press.
Garcia Posada, M., and Mora-Sanguinetti, J., 2013. “Firm Size and Judicial Efficacy: Evidence for the New Civil Procedures in Spain”, Bank of Spain Working Paper No. 1303.
Gani, A. 2007. “Governance and Foreign Direct Investment Links: Evidence from Panel Data Estimations.” Applied Economics Letters. Volume 14, Issue 10.
Giacomelli, S. and Menon, C., 2012. “Firm Size and Judicial Efficiency in Italy: Evidence from the Neighbour's Tribunal”, SERC Discussion Papers 0108, Spatial Economics Research Centre, LSE.
GIZ Regional Office Western Balkans, 2014. “GIZ in Bosnia and Herzegovina”.
Goldsmith, R.W., 1969. “Financial Structure and Development”, Yale University Press, New Haven, CT.
Gross, R., Trevino, J.L., 2005, “New Institutional Economics and FDI Location in Central and Eastern Europe’’, MIR: Management International Review, Vol. 45, No. 2 (2005 2nd Quarter), pp. 123-145
Guseva, M., Nakaa, M., Novel, A.S., Pekkala, K., Souberou, B., and Stouli, S., 2008. “Press freedom and development: an analysis of correlations between freedom of the press and the different dimensions of development, poverty, governance and peace.” Paris: UNESCO, 2008, 131 p., ill., tab., abbr. p. 125, bibl. p. 127-130.
Gupta, S., Davoodi, H., and Alonso-Terme, R. 2002. “Does Corruption Affect Income Inequality and Poverty?”, Economics of Governance, 2002, vol. 3, issue 1, pages 23-45
Haggard, S., and Tiede, L., 2011. “The rule of law and economic growth: Where are we?”, World Development, 39(5), 673‐685.
Hagmayr B., Haiss P.R., Sumegi K., 2007. “Financial Sector Development and Economic Growth - Evidence for Southeastern Europe” EuropaInstitut Working Paper.
Havrylyshyn, O., Izvorski, I. and Rooden, R., 1998. “Recovery and Growth in Transition Economies 1990-97: A Stylized Regression Analysis,” IMF Working Paper No. 98/141, Washington: IMF.
Hamilton, J.D., 2003. “What is an oil shock?”, Journal of Econometrics, 113: 363-398.
Hamilton, J.D., 2005. “Oil and the macroeconomy”, The new Palgrave Dictionary of Economics, MacMillan.
Holmberg, S., and Rothstein, B., 2011. “Dying of corruption”, Health Economics, Policy and Law.
Johnson, S., McMillan, J. and Woodruff, C., 2002. “Property Rights and Finance,” American Economic Review, 92 (5), 1335.
Kaufman, Daniel, Kraay, A. and Zoido-Lobaton, P., 1999. “Governance matters”, World Bank Institute, Policy Research Working Paper 2196.
Kenourgios D., Samitas A. 2007. “Financial Development and Economic Growth in a Transition Economy: Evidence for Poland”, Journal of Financial Decision Making, 3, (1), 35-48.
Kumar, K., Rajan, R. and Zingales, L., 2001. “What Determines Firm Size?” Chicago Booth Working Paper.
Laeven, L., and Woodruff, C., 2007. "The Quality of the Legal System, Firm Ownership, and Firm Size", Review of Economics and Statistics, 89, 4, pp. 601-614.
Lambsdorff, J., 2003. “How Corruption Affects Productivity“, Kyklos LVI (4), 459-76.
Levine, R., Zervos, S., 1998. “Stock markets, banks, and economic growth”, American Economic Review 88, 537–558.
Lenz, N. and Prsa, V., (2015). “Growth potential of energy sector reforms: new evidence on EU and Southeast European countries by exploring impact on electricity generation”, in: Zbornik radova Ekonomskog fakulteta u Rijeci/Proceedings of Rijeka Faculty of Economics.
Levine, R., Loayza, N., Beck, T., 2000. “Financial intermediation and growth: Causality and causes”, Journal of Monetary Economics 46, 31–77.
Levine, R., 2005. “Finance and Growth: Theory and Evidence”, In Handbook of Economic Growth, ed. Philippe Aghion and Steven N. Durlauf, 865–934. Amsterdam: Elsevier.
Lorenzani, L. and Lucidi, F., 2014. "The Economic Impact of Civil Justice Reforms," European Economy - Economic Papers 530, Directorate General Economic and Financial Affairs (DG ECFIN), European Commission.
Lupusor, A., Fala, A. and Popa, A., 2016. “Transnistrian Economic Brief, February 2016 (#5)”, Expert-Grup.
OECD, 2013. “Anti-corruption Reforms in Eastern Europe and Central Asia: Progress and Challenges, 2009-2013”, OECD.
Markandya, A. and Hunt, A., 2004. “The externalities of energy insecurity”. ExternE-Pol research project for the European Commission.
McQuail, D., 2005. “McQuail’s Mass Communication Theory”. London, Thousand Oaks: Sage.
Norris, P., 2002. “Democratic Phoenix: Political Activism Worldwide”. Cambridge: Cambridge University Press
Pinto, J., 2008. “Muzzling the watchdog: The case of disappearing watchdog journalism from Argentine mainstream news”, Journalism, 0(6), 750-774.
Porto, M., 2008, “TV news and political change in Brazil: the impact of democratization on TV Globo’s journalism”, Journalism, Vol. 8, n. 4, 2007, pp. 381-402.
Price, Monroe E., Rozumilowicz, B. and Verhulst, S.G., 2002 “Media Reform”, London: Routledge.
Sanyal, R. and Samanta, S., 2008. “Effect of Perception of Corruption On Outward US Foreign Direct Investment, Global Business and Economics Review”, 10: 123-140.
Seligson, M., 2003. “The Impact of Corruption on Regime Legitimacy: A Comparative Study of Four Latin American Countries”, The Journal of Politics, Vol. 64(2), pp. 408-433.
Staats, J. L., and G. Biglaiser, 2012. "Foreign Direct Investment in Latin America: The Importance of Judicial Strength and Rule of Law", International Studies Quarterly, 56, pp. 193-202.
Stetka, V., Loveless, M. and Jebril, N. 2013. “Media and democratization: what is known about the role of mass media in transitions to democracy’, Reuters Institute for the Study of Journalism at the University of Oxford.
Tanzi, V., & Davoodi. H. R., 2000. “Corruption, Growth, and Public Finances”, Working Paper No 182, International Monetary Fund.
Transparency International, 2016. “Corruption Perception Index”.
Ugur M., and Dasgupta N., 2011. “Evidence on the economic growth impacts of corruption in low-income countries and beyond: a systematic review”, London: EPPI-Centre, Social Science Research Unit, Institute of Education, University of London.
Valkenburg, P. and Semetko, H.A., 1998. ‘The Impact of Attentiveness on Political Efficacy: Evidence from a Three-Year German Panel Study’, International Journal of Public Opinion Research, 10/3: 195–210.
Wei, S.-J., 2000. “How taxing is corruption on international investors?”, Review of Economics and Statistics, 1(11), pp. 1-11. World Economic Forum (WEF), 2015.
Word Bank/IFC, 2010. “Alternative Dispute Resolution Program (ADR) in the Western Balkans: Giving Mediation a Chance”.
World Bank, 2014. “Serbia Judicial Functional Review: Executive summary with recommendations”, Multi-Donor Trust Fund for Judicial Sector Support in Serbia.
World Bank, 2016. “Doing Business” survey.
Jong-Sung, Y., 2005. “Corruption and Inequality as Correlates of Social Trust: Fairness Matters More Than Similarity”, Harvard University, Working Paper No. 29.
Zhang, Y., Parker, D. and Kirkpatrick, C., 2002. “Electricity Sector Reform in Developing Countries: an Econometric Assessment of the Effects of Privatisation, competition and Regulation”, Working Paper no.31, the Centre on Regulation and Competition, University of Manchester: Manchester.
Zhang, Y.F., Parker, D. and Kirkpatrick, C., 2008. “Electricity Sector reform in developing Countries: An Econometric Assessment of the Effects of Privatization”, Competition and Regulation, Journal of Regulatory Economics, Vol. (33), pp.159‐178.
Zurawicki, and Habib, 2010. “Corruption and foreign direct investment: what have we learned?”, International Business and Economics Research Journal, 9(7), pp 1- 10.