ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	Building Resilience through Asset Creation and Enhancement (BRACE) II
Country or region targeted	South Sudan
Type of amendment	Cost and time extension
Original project budget	£20,000,000 (100% ICF)
Current project budget	£32,600,000 (100% ICF)
New project budget	Up to £39,600,000 (100% ICF) / (up to £7m additional)
Original project start and end dates	01/08/2015 – 31/03/2018
Current project end date	31/01/2021
New project end date (if applicable)	31/12/2021
Business Case Vault Document No.	5275355

INFORMATION
What is the project’s purpose?
Building Resilience through Asset Creation and Enhancement (BRACE II) is DFID South Sudan’s flagship resilience and international climate finance project. This extension maintains delivery of resilience building work during a period of uncertainty in South Sudan and bridges the transition to a multiyear humanitarian and resilience programme planned to start in 2021. / The programme is centred around four main objectives: / Address immediate food insecurity and basic needs (provision of conditional cash assistance) / Improve longer-term food security (support for agro-pastoral production) / Increase capacity to absorb, anticipate and adapt to climate variability and extremes (support climate change adaptation) / Improve community relationships and social cohesion / Improving food security is critical to reducing the need for humanitarian assistance. South Sudan’s food security crisis continues unchecked, with 6.35m (54%) of the population facing crisis or worse levels of food insecurity in August 2019. This crisis is not only caused by conflict and insecurity but also by the economic crisis that has eroded households’ purchasing power. It is further exacerbated by localised climate shocks as flooding, heavy rains or drought. / BRACE II uses a ‘Cash/Food for Assets’ approach in which vulnerable households receive food assistance under the condition that they work on the creation or rehabilitation of ‘assets’, such as anti-flooding dykes, clearing new farm land, water ponds, etc. This approach has double benefits: the food assistance immediately relieves food insecurity while the creation or rehabilitation of assets makes households less vulnerable to climate shocks and helps them produce their own food. Complementary activities are also implemented to improve agricultural practices, access inputs and increase skills and awareness on key areas. Furthermore, communities decide together which assets they would like to create and then work together to create or improve them, helping to build community cohesion. / BRACE II is key part of DFID South Sudan’s strategy of balancing our emergency humanitarian support with interventions that build self-reliance where access and security allows. This also reduces dependence on aid in the longer-term. A key objective of this programme is to increase resilience to climate extremes and funding for this programme is 100% International Climate Finance (ICF). / BRACE II currently comprises 3 components: / A first component delivered by the UN World Food Programme and UN Food and Agriculture Organisation in partnership in former Northern Bahr-el-Ghazal and Warrap. / A second component delivered by an NGO consortium led by World Vision Australia in former Northern Bahr el Ghazal, Warrap and Eastern Equatoria, started in early 2018. / A component for monitoring, evaluation and learning activities delivered by a third-party contractor. The contract with the previous provider expired in 2019 and so evaluation services will be procured in line with DFID procedures as part of this extension.
What is the objective of the amendment?
The objective of this extension is to continue the work of BRACE II and bridge the transition to a single humanitarian and resilience programme from 2021. The original business case was approved by Ministers for five years, with an initial tranche of £20m for the first two and half years of the programme, and an additional £12.6m for the following 2.5 years. An extension of funding will allow DFID South Sudan to: / Extend the NGO component by supporting an estimated additional 38,000 people for two years, including an additional location if stability allows. The original business case envisaged that the programme would continue operations from BRACE I in Western Bahr el Ghazal, Northern Bahr el Ghazal and Warrap and extend into two new states (Lakes State and Eastern Equatoria). Disruption to the procurement of the NGO led component by the July 2016 crisis and the need for a more flexible geographic remit has led to the current footprint in former Northern Bahr el Ghazal, Warrap, and Eastern Equatoria. This extension offers the opportunity for the NGO component to build on their track record, adapt their package based on learning so far and extend to a new location if stability allows. / Extend support to the UN component to complete the 2020 cycle of cash transfers for 18,875 households covered by the programme and strengthen climate adaptation and natural resource management activities across partners. A review of climate and resilience work across DfID South Sudan in 2019 recommended enhancing climate information services and community based natural resource management. Whilst BRACE II already has climate adaptation as a core objective, there is an opportunity to consolidate and scale effective practices to meet the ambition set out under the climate and natural resources shift of the strategic approach to Africa. For example, severe flooding in 2019 has demonstrated the need to further help communities anticipate weather related shocks, as well adapt to them. / Support and shape coordination of resilience activities under the Partnership for Recovery and Resilience (PfRR) in South Sudan by providing support for representation and coordination. Aweil is one of the lead candidate partnership areas under the PfRR, established in 2018 to help development stakeholders work together to reduce vulnerabilities and build resilient households. / Invest in a final evaluation of the BRACE II programme, building on the mid term evaluation at the end of 2018.
What is the additional and total support the UK will provide?
The UK will provide up to an additional £7m to deliver this programme, bringing the maximum total programme value to £39.6m. An indicative funding split is as follows: / Compo-nent Implementing partner / supplier Activity delivered Phase 1 budget Phase 2 budget Extension / indicative budget / 1 / (UN) WFP Food assistance / (Food/cash for Assets) £12,300,000 £12,600,000 3m / FAO Agricultural and Natural Resource Management training and farming inputs / 2 / (INGO) World Vision Australia Cash for assets and livelihoods assistance (training, inputs etc.) £7,000,000 / [not spent] £7,000,000 [rolled forward] £3.8mm / Independent monitoring and evaluation £700,000 £200,000 / TOTAL Budget: / £20,000,000 Budget: / £12,600,000 Budget: / £7,000,000
What are the expected results?
In this extension, BRACE II will aim to reach an additional 38,000 unique beneficiaries alongside extending support for existing households. By August 2021 BRACE II will have reached an estimated 226,700 beneficiaries, with the majority of support being transferred to beneficiaries as cash. / The original business case stated that BRACE II would provide assistance for up to 400,000 people over 2.5 years –representing a cost per beneficiary of £50. Those initial results assumed that each beneficiary would be supported for only one year. Building resilience, however, takes time and, based on the lessons learned from BRACE I, it was agreed that BRACE II would provide multi-year assistance to the same households. The phase 2 addendum to the business case envisaged a cost-per-beneficiary-per-year of £45, with beneficiaries under component one being reached for 3 years and component two for 2 years to enable a comparison of different support packages. The 2017 annual review calculated the cost per beneficiary per year as £53, which fell to an estimated £49 per beneficiary in 2018.
What is the approach to implementation?
Testing different delivery models/approaches to enhance adaptive programming / As originally intended in the Business Case, DFID have tested two approaches in order to compare and adapt our delivery model. Different support packages and approaches have been tested in the NGO led component since it started work in early 2018, for example on the promotion of savings groups. This process has also helped DFID to identify the added value and unique selling points of different types of implementing partners (WFP, FAO, INGOs, NNGOs). Further adaptation of the approach will be tested through this extension based on learning from the mid-term evaluation, for example by adapting the timing of conditional transfers and considering a wider set of rural livelihood opportunities. A final evaluation planned for late 2020 will allow the strengths and weaknesses of the operational models and interventions to be assessed, with learning fed into successor programming. / Cross-cutting issues / Climate-sensitivity: Climate adaptation is central to BRACE II, with the mid-term evaluation finding that an estimated 43% of BRACE II beneficiaries have improved climate resilience, and another 67% could be considered shock-proofed, (i.e. better able to manage a climate shock). Severe flooding in 2019 demonstrated the need to redouble efforts to help people anticipate, absorb and adapt to climate shocks. This will be strengthened through this extension, learning from the central BRACED programme which ended in 2018 as well as other partners. / Gender Equality: The original business case included a gender equality statement and BRACE II has made a deliberate effort to target women and adapt the programme to their needs, for example by starting activities later in the day so women are able to attend after household work, as well as promoting gender equality in programme structures. We will continue to look for ways to gender inform programme activities, conducting more disaggregated analysis of the results and reviewing how gender sensitivity can be incorporated within every aspect of the programme. / Conflict-sensitivity: BRACE II aims to promote social cohesion and reduce the likelihood of communal conflict through community-based planning and governance structures, shared work and management of natural resources and infrastructure. As defined in the business case, implementing partners will continue work to understand: i) the context; ii) the interactions between this programme and the context; and iii) how the programme can address causes of conflict and avoid negative impacts. WFP has an ongoing partnership with the Conflict Sensitivity Resource Facility (CSRF) to document existing good practice in conflict sensitivity, work on an action plan and produce assessment frameworks (e.g. for conflict sensitivity in development of feeder roads and other infrastructural development). Good practice related to BRACE II activities will be shared with other partners in this extension period. / Nutrition: In August 2019 all counties where BRACE II is being implemented were in a serious or critical situation on the IPC for Acute Malnutrition scale. The second phase of BRACE II increased its focus on nutrition based on the increasing amount of evidence linking malnutrition to chronic food security in South Sudan, and this will be continued in the extension. In practical terms this involves including nutrition messages within skills development activities, and ensuring that the project prioritises activities that more directly contribute to nutrition outcomes, for example vegetable production. / Terrorism Act: The risk of terrorism is assessed to be low in South Sudan, as is the risk of programme funds being diverted to fund terrorist activities.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The theory of change and logframe for the BRACE II programme has evolved since the original business case to reflect our increased understanding and the changing context and to reflect both intermediate and final outcomes. The midterm evaluation conducted in late 2018 demonstrated progress towards these outcomes as well as recommendations for adaptation which are being considered as part of this extension. / There are two changes to the original business case in the extension of this programme: / Geographic locations of the programme: The original business case pre-identified five former states in which BRACE II would be implemented. This decision was taken when the conflict was mainly concentrated in the three states of Greater Upper Nile. The situation has changed significantly since 2016 when conflict spread to different parts of the country. BRACE II is currently being implemented in three of the former states, with this extension providing the option to extend into a new location based on thorough analysis on need and stability in the short to medium term. / Support for the Partnership for Recovery and Resilience: The original business case envisaged a steering committee and technical committee to ensure that the project aligns with local plans, other programmes and includes learning and feedback. State level representation and regular meetings have been a challenge however, and so coordination has been focussed at the project level. The creation of the Partnership for Recovery and Resilience in 2018 has provided a platform for UN agencies, NGOs, donors, Government representatives and civil society to work together, supporting a shift away from humanitarian response to locally owned recovery and resilience building in key areas. The activities under BRACE II are well aligned to the pillars and principles of the PfRR, with the UN component providing a practical demonstration of partnership working. National and area-based coordination frameworks are being developed and this extension provides for existing BRACE II partners to be more actively involved in these structures. This is expected to deliver better coordination of programmes at local level, stronger monitoring and learning processes across all agencies and better alignment to local plans and household priorities.
[note] http://www.ipcinfo.org/fileadmin/user_upload/ipcinfo/docs/IPC_South%20Sudan_Key_Messages_August_2019.pdf
[note] The procurement for the second component was launched in late 2015 but received no suitable bids. The process was then put on-hold following the drawdown of the British Embassy in July 2016 and later terminated. It was relaunched in 2017 and the successful partner began activities in 2018.
[note] If the economic context/ market functionality deteriorates significantly, food may be provided instead of cash.
[note] http://www.ipcinfo.org/fileadmin/user_upload/ipcinfo/docs/IPC_South%20Sudan_Key_Messages_August_2019.pdf