## Logframe Summary
LOGICAL FRAMEWORK SUMMARY |  |  |  | h
NB: Data auto-populates from tabs
PROJECT TITLE | Central African Republic Humanitarian and Recovery Programme (CHURP)
Impact Weighting Total | 100%
Overall Risk Rating | Severe
IMPACT
| Impact Indicator 1 |  | Baseline | Milestone 1
Reduced suffering and improved resilience in CAR and among people displaced from CAR |  |  | Baseline |  |  | Target (PCR)
| Percentage of people targeted by the Humanitarian Response Plan who are reached by the programme | Planned (Total) | 83.33% |  |  | 89.32%
Achieved (Total)
Source
Project logframe and HRP
OUTCOME 1 | [7 empty] | Assumptions | TOTAL BENEFICIARIES M1 | TOTAL BENEFICIARIES M2 | TOTAL BENEFICIARIES M3
Address essential humanitarian needs in CAR and among people displaced from CAR | Outcome Indicator 1.1 |  | Baseline | Milestone 1 |  |  |  | Security situation permitting accessibility and movements in the targeted areas. Security situation allows for supply lines and staff movements. Adequate cooperation by implementing partners. Collaboration with key government and UN agencies in not reduced. Donor payments of funds are timely. MINUSCA forces are maintained on the field. IDPs and host communities support the programme. Double counting across agencies DFID proportion of ICRC beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known. % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known. | 945705.259 | 1099567.128 | 502970.8
| Number of people in CAR reached yearly with DFID humanitarian assistance. (includes double counting across agencies) |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
|  | Planned | 969734 | 589133.8333 | 622421.5 | 594303 | 1805858.3333
|  | Achieved |  | 886907.259 | 863394.757 | 284877.8 | 2035179.816
Source
Partner Reports (FAO, ICRC, CHF and Mentor Consortium and SI*Milestone 2 only*)
| Outcome Indicator 1.2 |  | Baseline | Milestone 1
| Number of displaced Central Africans reached yearly with DFID humanitarian assistance |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3/Target (PCR)
|  | Planned | 154236 | 197050 | 181796 | 243175
|  | Achieved |  | 58798 | 236172.371 | 218093
Source
Partner Reports (UNHCR and WFP)
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 26,000,000 (CAR) + 10,000,000 (CAR Refugees) | 0 | 0 | 36000000 | 100
INPUTS (HR) | DFID (FTEs)
2.75 FTEs: 1.5 A2 Humanitarian Advisers, 0.25 A2 programme manager, 1.0 B2 programme officer
OUTCOME 2 | [7 empty] | Assumptions
Better co-ordination and coherence of the humanitarian, development and UN system in CAR | Outcome Indicator 2.1 |  | Baseline | Milestone 1 |  |  |  | CAR Humanitarian Fund continues to have strong management and oversight CAR Humanitarian Fund has consistent staffing Donor policies allow funding for pooled funds
| The CAR Humanitarian Fund (CHF) continues to have a sustained donor base |  | Baseline | [added after AR 2017] | Milestone 2 (AR 2018) | Milestone 3/Target (PCR)
|  | Planned | 9 donors |  | 8 donors | 8 donors
|  | Achieved |  |  | 9 donors | 11 donors
Source
CHF Advisory Board
INPUTS (£) | DFID (£)
0
INPUTS (HR) | DFID (FTEs)
1.0 FTE Humanitarian Adviser
Central Africans in CAR (outputs 1-5)
OUTPUT 1 - FAO, ICRC, CHF, SI | Output Indicator 1.1 | [6 empty] | Assumptions
|  |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
The agro-pastoral production and food security in the targeted areas is improved and reinforced | Number of people in CAR reached through livelihood and food security assistance (includes double counting across agencies) | Planned | 15267 | 250373.5 | 107714.5 | 30935 | 389023 | - Security situation permitting accessibility and movements in the targeted areas. - Adequate cooperation by implementing partners. - Respect of the commitments of the Letter of Agreement - Appropriate transport, storage and related security of equipment delivered. - Goods and services required are delivered in the quantities needed, at a reasonable cost and within a time limit compatible with the work plans.
|  | Achieved |  | 280700.862 | 103341 | 39610 | 381984.886
Source
Partner Reports (FAO, ICRC, CHF, and SI *M2 only*)
Output Indicator 1.2
| Number of beneficiaries receiving assistance through market-based cash and vouchers* (includes double counting across agencies) |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
|  | Planned | 6582 | 25322.5 | 25206.25 | 4193 | 54721.75
|  | Achieved |  | 25420.096 | 42900 | 235.4 | 67785.4
DFID proportion of ICRC beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
| *SDP Humanitarian | Partner Reports (FAO, ICRC)
IMPACT WEIGHTING (%) | 25% | [6 empty] | Double counting across agencies
RISK RATING | Severe
OUTPUT 2 - ICRC, CHF, MI, SI | Output Indicator 2.1 | [6 empty] | Assumptions
|  |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3/Target (PCR) (Cumulative ICRC) |  | ¤ No loss of drugs through stealing and embezzlement. ¤ License to import pharmaceuticals is maintained for all partners. ¤ Transport means to carry drugs to the field sites remain available (flights, road). ¤ Vaccination remains part of the MoH plans. ¤ A sufficient cold chain is available. ¤ EPI service from MoH or other agency (WHO, etc.) provides required vaccines on time. ¤ No insecurity and/or climatic conditions render health facilities inaccessible for patients. ¤ No cultural barriers prevent beneficiaries from seeking access to health facilities services (for instance women not willing to be visited by a male health worker) ¤ Qualified staff is available at the supported facilities as scheduled. ¤ Counterfactual to prove satisfaction of beneficiaries is in place. Sample of surveys are big enough to be representative. ¤ A workshop is held within the Consortium to define services, supervision and training package, and all the members have agreed to implement. Authorities at all levels (national/regional/district) have agreed. ¤ The referral system is in place and tariff and criteria are well understood by each party. ¤ GBV survivors seek remedial services in the consortium's supported facilities
Affected population are reached by healthcare, water and sanitation and protection support | Number of beneficiaries reached in CAR by healthcare support (includes double counting across agencies) | Planned (Total) | 354782 | 261147.8333 | 454451 | 300995 | 304580
|  | Achieved (Total) |  | 194609.856 | 250129 | 305165.728 | 311090.584
Source
Partner Reports (Milestone 1 & 2: ICRC and Mentor; Milestone 3:ICRC, MENTOR and CHF)
Output Indicator 2.3
| Number of people with improved access to water and sanitation (hard activities only)* (includes double counting across agencies) |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
|  | Planned (MENTOR) | 51145 | 500 per water point | 85879.5 | 219362 | 281242
|  | Planned (ICRC+CHF) | 4050 | 31347.5
|  | Planned (Total) | 55195 | 31847.5
|  | Achieved (Total) |  | 65614.052 | 162982 | 450381.8 | 661136.852
Source
| *SDP WASH | Partner Reports (ICRC, CHF and Mentor)
IMPACT WEIGHTING (%) | 25%
RISK RATING | Severe | [6 empty] | DFID proportion of ICRC beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
OUTPUT 3 - FAO, CHF, MI | Output Indicator 3.1 | [6 empty] | Assumptions
| Number of new malnutrition cases from children under 5, adolescent girls (10-19) and women under 50 in CAR that gain access to treatment (includes SAM and MAM cases) * (includes double counting across agencies) |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
DFID helps improve children's, women's and girls' nutrition in CAR |  | Planned (Total) | 0 | 440 | 769 | 721 | 1930 | - Security situation permitting accessibility and movements in the targeted areas. - Adequate cooperation by implementing partners. Respect of the commitments of the Letter of Agreement
|  | Achieved (Total) |  | 529 | 1501 | 2200 | 4230
Source
Partner Reports (Cordaid and IMC within Mentor Consortium)
* SDP Nutrition High
| Output Indicator 3.2 | [6 empty] | ¤ UNICEF provides the necessary amount of nutrition therapeutic supplies in a timely manner. ¤ No security issues hinder people to reach areas where treatment and IEC on nutrition are held. ¤ IEC sessions contribute to improving U5 and women's capacity to prevent malnutrition
| Number of children under 5, adolescent girls (10-19) and women under 50 in CAR with improved capacity to prevent malnutrition** (includes double counting across agencies) |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Cumulative Target (PCR)
|  | Planned (Total) | 27817 | 31946 | 52780 | 19642 | 104368
|  | Achieved (Total) |  | 20835 | 17531 | 12871 | 51237
|  | Source | [5 empty] | Double counting across agencies
Partner Reports on soft activities (FAO and Mentor Consortium)
**SDP Nutrition Medium
Output Indicator 3.3
|  |  | Baseline | Milestone 1 (AR 2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Target (PCR)
| Cure rate among children treated for acute malnutrition | Planned (Total) | 77% | Above 75% | Above 75% | Above 75% | Above 75%
|  | Achieved (Total) |  | 86% | 86% | 89% | 87%
Source
Partner Reports (Mentor Consortium and CHF)
IMPACT WEIGHTING (%) | 15%
RISK RATING | Severe
OUTPUT 4 - CHF | Output Indicator 4.1 (revised) | [6 empty] | Assumptions
DFID empowers humanitarian coordination for rapid and effective decision-making in CAR | % of emergency reserve allocations dispersed to projects within 30 days |  | Baseline | [added after AR 2016] | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Target (PCR)
|  | Planned | 85% |  | 85% | 85% | 85% | Security situation does not deteriorate so agencies are able to continue operating and field visits are able to take place.
|  | Achieved |  |  | 29% | 100% | 100%
Source
Partner reports (CHF)
| Output Indicator 4.2 |  | Baseline | Milestone 1
|  |  | Baseline | Milestone 1 (2017) | Milestone 2 (AR 2018) | Milestone 3 (PCR) | Target (PCR)
| % of CAR HF projects monitored through field visits within their project duration | Planned | 0% | 40% of projects monitored in 2016 | 40% of projects monitored in 2017 | 40% of projects monitored in 2018 | 40% projects monitored
|  | Achieved |  | 43% | 69% | 40% of projects monitored in 2018 | 40% of projects monitored
Source
Partner Reports (CHF monitoring reports)
IMPACT WEIGHTING (%) | 15%
RISK RATING | Major
Displaced Central Africans (output 5)
OUTPUT 5 - WFP and UNHCR | Output Indicator 5.1 | [6 empty] | Assumptions
Displaced Central Africans see their basic needs met and communities in are supported in hosting them | Total number of people who have received basic food assistance* (single counting) |  | Baseline | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) / Target (PCR) |  | There is no escalation of conflict, lack of state authority and impeded deployment of security forces (United Nations) that could prevent implementation of activities in a large part of the project area in CAR. There is no security incident hampering food distributions in CAR and along the border with CAR in neighboring countries. Access to beneficiaries and areas of influx is possible. Complementary activities are provided by partner There is adequate funding to avoid pipeline breaks
|  | Planned | 0 | 136496 | 80300 | 124564
|  | Achieved |  | 164624 | 51008 | 198003
Source
| * SDP Humanitarian | Partner Reports (WFP)
Output Indicator 5.3
| Number of pregnant women and children under five who receive nutrition support aimed at preventing MAM (blanket feeding) *** |  | Baseline | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) / Target (PCR)
|  | Planned | 0 | 55510 | 40000 | 12800
|  | Achieved |  | 39217 | 11293 | 13618
Source
| *** SDP Nutrition Medium | Partner Reports (WFP)
Output Indicator 5.4
| Number of individuals (refugees and most vulnerable nationals) who benefit from livelihoods support activities |  | Baseline | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) / Target (PCR)
|  | Planned | 3168 | 3168 | 5280 | 5280
|  | Achieved |  | 3168 | 5526.771 | 5280
Partner Reports (UNHCR)
Output Indicator 5.5
| Number of persons of concern registered by biometric registration |  | Baseline | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) / Target (PCR)
|  | Planned | 30,554 | 30554 | 61496 | 48611
|  | Achieved |  | 30554 | 58759.371 | 12104
Source
Partner Reports (UNHCR)
Output Indicator 5.6
| Number of refugees who access primary healthcare services |  | Baseline | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) / Target (PCR)
|  | Planned | 5092 | 5092 | 5280 | 8102
|  | Achieved |  | 5092 | 90043.5974 | 8102
Source
Partner Reports (UNHCR)
IMPACT WEIGHTING (%) | 20%
RISK RATING | Major
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 10000000 | 0 | 0 | 10000000 | 100

## FAO
FAO |  | Male | Female | U5 | Children 5-17 | Adults 18-49 | Elderly 50+
|  | 0.5 | 0.5 | 0.14 | 0.26 | 0.53 | 0.07
OUTCOME 1 | [10 empty] | Estimated % of target group | % female (F) | % male (M)
Outcome Indicator 1.1 | [9 empty] | Infants & young children (0-59 months) | 0.14 | 0.07 | 0.07
Address essential humanitarian needs in CAR |  |  |  | Baseline (Dec 2016) | Milestone 1 (1 Jan- 31 May 2017) | Milestone 2 (1 June 2017 - 31 May 2018) | (1 June 2018 - end of project) | Target (1 Jan 2017 - 31 Mar 2019 ) |  | Children (5-17y) | 0.26 | 0.13 | 0.13
|  | Planned | Male Total |  | 137500 | 50000 | 0 | 187500 |  | Adults (18-49y) | 0.53 | 0.27 | 0.26
| Number of people in CAR reached yearly with DFID humanitarian assistance. |  | Female Total |  | 137500 | 50000 | 0 | 187500 |  | Elderly (≥ 50y) | 0.07 | 0.04 | 0.03
|  |  | Under 5 Total |  | 38500 | 14000 | 0 | 52500
|  |  | Children (5-17) Total |  | 71500 | 53000 | 0 | 0
|  |  | Adults (18-49) Total |  | 145750 | 7000 | 0 | 0
|  |  | Elderly (50+) Total |  | 19250 | 0 | 0 | 0
|  |  | Under 5 Male |  | 19250 | 7000 | 0 | 26250
|  |  | Under 5 Female |  | 19250 | 7000 | 0 | 26250
|  |  | Children (5-17) Male |  | 35750 | 13000 | 0 | 48750
|  |  | Children (5-17) Female |  | 35750 | 13000 | 0 | 48750
|  |  | Adults (18-49) Male |  | 71500 | 26000 | 0 | 97500
|  |  | Adults (18-49) Female |  | 74250 | 27000 | 0 | 101250
|  |  | Elderly (50+) Male |  | 8250 | 3000 | 0 | 11250
|  |  | Elderly (50+) Female |  | 11000 | 4000 | 0 | 15000
|  |  | TOTAL | 0 | 275000 | 100000 | 0 | 375000
|  | Achieved | Male Total |  | 108225
|  |  | Female Total |  | 108225
|  |  | Under 5 Total |  | 30303
|  |  | Children (5-17) Total |  | 56277
|  |  | Adults (18-49) Total |  | 114718.5
|  |  | Elderly (50+) Total |  | 15151.5
|  |  | Under 5 Male |  | 15151.5
|  |  | Under 5 Female |  | 15151.5
|  |  | Children (5-17) Male |  | 28138.5
|  |  | Children (5-17) Female |  | 28138.5
|  |  | Adults (18-49) Male |  | 56277
|  |  | Adults (18-49) Female |  | 58441.5
|  |  | Elderly (50+) Male |  | 6493.5
|  |  | Elderly (50+) Female |  | 8658
|  |  | TOTAL |  | 216450 | 117500 | 43700 | 377650
Source
Partner Reports (FAO impact indicator 1)
OUTPUT 1 | Output Indicator 1.1 | [7 empty] | Assumptions
|  |  |  | Baseline (Dec 2016) | Milestone 1 (1 Jan- 31 May 2017) | Milestone 2 (1 June 2017 - 31 May 2018) | (1 June 2018 - end of project) | Target (1 Jan 2017 - 31 Mar 2019 )
|  | Planned | Male Total |  | 117500 | 37500 | 0 | 155000 | - Security situation permitting accessibility and movements in the targeted areas. - Adequate cooperation by implementing partners. - Respect of the commitments of the Letter of Agreement - Appropriate transport, storage and related security of equipment delivered. - Goods and services required are delivered in the quantities needed, at a reasonable cost and within a time limit compatible with the work plans.
|  |  | Female Total |  | 117500 | 37500 | 0 | 155000
|  |  | Under 5 Total |  | 32900 | 10500 | 0 | 43400
|  |  | Children (5-17) Total |  | 61100 | 39750 | 0 | 0
|  |  | Adults (18-49) Total |  | 124550 | 5250 | 0 | 0
|  |  | Elderly (50+) Total |  | 16450 | 0 | 0 | 0
|  |  | Under 5 Male |  | 16450 | 5250 | 0 | 21700
|  |  | Under 5 Female |  | 16450 | 5250 | 0 | 21700
|  |  | Children (5-17) Male |  | 30550 | 9750 | 0 | 40300
|  |  | Children (5-17) Female |  | 30550 | 9750 | 0 | 40300
|  |  | Adults (18-49) Male |  | 61100 | 19500 | 0 | 80600
|  |  | Adults (18-49) Female |  | 63450 | 20250 | 0 | 83700
|  |  | Elderly (50+) Male |  | 7050 | 2250 | 0 | 9300
|  |  | Elderly (50+) Female |  | 9400 | 3000 | 0 | 12400
The agro-pastoral production and food security in the targeted areas is improved and reinforced | Number of people in CAR reached through livelihoods assistance |  | TOTAL | 0 | 235000 | 75000 | 0 | 310000
|  | Achieved | Male Total |  | 108225
|  |  | Female Total |  | 108225
|  |  | Under 5 Total |  | 30303
|  |  | Children (5-17) Total |  | 56277
|  |  | Adults (18-49) Total |  | 114718.5
|  |  | Elderly (50+) Total |  | 15151.5
|  |  | Under 5 Male |  | 15151.5
|  |  | Under 5 Female |  | 15151.5
|  |  | Children (5-17) Male |  | 28138.5
|  |  | Children (5-17) Female |  | 28138.5
|  |  | Adults (18-49) Male |  | 56277
|  |  | Adults (18-49) Female |  | 58441.5
|  |  | Elderly (50+) Male |  | 6493.5
|  |  | Elderly (50+) Female |  | 8658
|  |  | TOTAL |  | 216450 | 75000 | 9050 | 300500
Source
Partner Reports (FAO impact indicator 1)
Output Indicator 1.2
|  |  |  | Baseline (Dec 2016) | Milestone 1 (1 Jan- 31 May 2017) | Milestone 2 (1 June 2017 - 31 May 2018) | (1 June 2018 - end of project) | Target (March 2019)
| Number of beneficiaries receiving assistance through market-based cash and vouchers* | Planned | Male Total |  | 12500 | 12500 | 0 | 25000
|  |  | Female Total |  | 12500 | 3500 | 0 | 7000
|  |  | Under 5 Total |  | 3500 | 6500 | 0 | 13000
|  |  | Children (5-17) Total |  | 6500 | 13250 | 0 | 26500
|  |  | Adults (18-49) Total |  | 13250 | 1750 | 0 | 0
|  |  | Elderly (50+) Total |  | 1750 | 0 | 0 | 0
|  |  | Under 5 Male |  | 1750 | 1750 | 0 | 3500
|  |  | Under 5 Female |  | 1750 | 1750 | 0 | 3500
|  |  | Children (5-17) Male |  | 3250 | 3250 | 0 | 6500
|  |  | Children (5-17) Female |  | 3250 | 3250 | 0 | 6500
|  |  | Adults (18-49) Male |  | 6500 | 6500 | 0 | 13000
|  |  | Adults (18-49) Female |  | 6750 | 6750 | 0 | 13500
|  |  | Elderly (50+) Male |  | 750 | 750 | 0 | 1500
|  |  | Elderly (50+) Female |  | 1000 | 1000 | 0 | 2000
|  |  | TOTAL | 0 | 25000 | 25000 | 0 | 50000
|  | Achieved | Male Total |  | 12500
|  |  | Female Total |  | 12500
|  |  | Under 5 Total |  | 3500
|  |  | Children (5-17) Total |  | 6500
|  |  | Adults (18-49) Total |  | 13250
|  |  | Elderly (50+) Total |  | 1750
|  |  | Under 5 Male |  | 3250
|  |  | Under 5 Female |  | 3250
|  |  | Children (5-17) Male |  | 6500
|  |  | Children (5-17) Female |  | 6750
|  |  | Adults (18-49) Male |  | 6500
|  |  | Adults (18-49) Female |  | 6750
|  |  | Elderly (50+) Male |  | 750
|  |  | Elderly (50+) Female |  | 750
|  |  | TOTAL |  | 25000 | 42500 |  | 67150
|  | Source | [6 empty] | RISK RATING
| *SDP Humanitarian Food | Partner Reports (FAO output 2, indicator 2.1) | [6 empty] | Severe
OUTPUT 3 | Output Indicator 3.2 | [7 empty] | Assumptions
| Number of children under 5 and women under 50 in CAR with improved capacity to prevent malnutrition** |  |  | Baseline (Dec 2016) | Milestone 1 (1 Jan- 31 May 2017) | Milestone 2 (1 June 2017 - 31 May 2018) | (1 June 2018 - end of project) | Target (1 Jan 2017 - 31 Mar 2019 ) | - Security situation permitting accessibility and movements in the targeted areas. - Adequate cooperation by implementing partners. Respect of the commitments of the Letter of Agreement
|  | Planned | Male Total |  | 3750 | 3750 | 0 | 7500
|  |  | Female Total |  | 3750 | 3750 | 0 | 7500
|  |  | Under 5 Total |  | 1050 | 1050 | 0 | 2100
|  |  | Children (5-17) Total |  | 1950 | 1950 | 0 | 3900
|  |  | Adults (18-49) Total |  | 3975 | 3975 | 0 | 7950
|  |  | Elderly (50+) Total |  | 525 | 525 | 0 | 1050
|  |  | Under 5 Male |  | 525 | 525 | 0 | 1050
|  |  | Under 5 Female |  | 525 | 525 | 0 | 1050
|  |  | Children (5-17) Male |  | 975 | 975 | 0 | 1950
|  |  | Children (5-17) Female |  | 1950 | 2025 | 0 | 4050
|  |  | Adults (18-49) Male |  | 1950 | 1950 | 0 | 3900
|  |  | Adults (18-49) Female |  | 2025 | 2025 | 0 | 4050
|  |  | Elderly (50+) Male |  | 225 | 225 | 0 | 450
|  |  | Elderly (50+) Female |  | 300 | 300 | 0 | 600
DFID helps improve children's, women's and girls' nutrition in CAR |  |  | TOTAL | 0 | 7500 | 7500 | 0 | 15000
|  | Achieved | Male Total |  | 0
|  |  | Female Total |  | 0
|  |  | Under 5 Total |  | 0
|  |  | Children (5-17) Total |  | 0
|  |  | Adults (18-49) Total |  | 0
|  |  | Elderly (50+) Total |  | 0
|  |  | Under 5 Male |  | 0
|  |  | Under 5 Female |  | 0
|  |  | Children (5-17) Male |  | 0
|  |  | Children (5-17) Female |  | 0
|  |  | Adults (18-49) Male |  | 0
|  |  | Adults (18-49) Female |  | 0
|  |  | Elderly (50+) Male |  | 0
|  |  | Elderly (50+) Female |  | 0
|  |  | TOTAL |  | 0 (activity not yet started) | 10000 |  | 10000
|  | Source | [6 empty] | RISK RATING
| **SDP Nutrition Medium | Partner Reports on soft activities (FAO output 3, indicator 3.1) | [6 empty] | Severe

## ICRC
ICRC
Baseline (if applicable) | 2015 Appeal - see CAR 2015 204852 |  |  | PLANNED |  |  | ACHIEVED
Milestone 1 | 2016 Appeal. Assessed in AR June 2017 |  |  | 2016 DFID % of Appeal: | 4.3% | £1.5m of £34.8m (43.4m Swiss F) | 2016 DFID % of Spend: | 4.8% | £1.5m of £31.1m (38.8m Swiss F)
Milestone 2 | 2017 Appeal. Assessed inAR June 2018 |  |  | 2017 DFID % of Appeal: | 2.75% | £1m of £36.4m (45.4m Swiss F) | 2017 DFID % of Spend: | 3.1% | £1m of £31.8m (43.2m Swiss F)
Milestone 3 | 2018 Appeal. Assessed in PCR March 2019 |  |  | 2018 DFID % of Appeal: | 8.45% | £3m of £35.5m (47.0m Swiss F) | 2018 DFID % of Spend: | 8.8% | £3m of £34.12m (45.2m Swiss F)
Target | 2016, 2017, 2018 Appeals. Assessed in PCR March 2019 | [6 empty] | TBC
OUTCOME 1
Outcome Indicator 1.1 | [7 empty] | Assumptions
Address essential humanitarian needs in CAR |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | (2018 Appeal) | Cumulative Target (PCR) | Security situation does not deteriorate and agencies are able to continue operating. Total beneficiary number estimated using the figure from the indicator with the highest number of beneficiaries
| Number of people in CAR reached yearly with DFID humanitarian assistance. | Planned | 63045 | 37821 | 19332.5 | 42250 | 99403.5
|  | Achieved |  | 46493.76 | 30951 | 58748.8 | 136193.56
|  | Source | [5 empty] | RISK RATING
|  | Partner Reports (ICRC) | [5 empty] | Severe
OUTPUT 1 | Output Indicator 1.1 | [6 empty] | Assumptions
The agro-pastoral production and food security in the targeted areas is improved and reinforced |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | (2018 Appeal) | Cumulative Target (PCR) | DFID proportion of ICRC beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
| Number of people in CAR reached through livelihoods assistance | Planned | 6582 | 2773.5 | 3437.5 | 4225 | 10436
|  | Achieved |  | 4826.784 | 4365 | 7832 | 17023.784
Source
Partner Reports (ICRC - productive inputs)
Output Indicator 1.2
| Number of beneficiaries receiving assistance through market-based cash and vouchers* |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | (2018 Appeal) | Cumulative Target (PCR)
|  | Planned | Not defined | 322.5 | 206.25 | 4193 | 4721.75
|  | Achieved |  | 420.096 | 400 | 235.4 | 635.4
|  | Source | [5 empty] | RISK RATING
| *SDP Humanitarian Food/Cash/Vouchers | Partner Reports (ICRC - food rations/commodities; cash) | [5 empty] | Severe
OUTPUT 2 | Output Indicator 2.1 | [6 empty] | Assumptions
|  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | (2018 Appeal) | Cumulative Target (PCR) | DFID proportion of ICRC beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
Affected population are reached by healthcare, water and sanitation, and protection support | Number of beneficiaries reached in CAR by heathcare support | Planned | 4670 | 1935 | 1650 | 7183 | 10768
|  | Achieved |  | 3425.856 | 2499 | 6591.728 | 12516.584
Source
Partner Reports (ICRC - 2016: number of consultations, 2017: number of people supported across 4 PHC centres, 2018: number of people supported across 6 health structures)
Output Indicator 2.3
| Number of people with improved access to water and sanitation (hard activities only)* |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | (2018 Appeal) | Cumulative Target (PCR)
|  | Planned | 0 | 25047.5 | 19332.5 | 42250 | 86630
|  | Achieved |  | 37821.024 | 30951 | 58748.8 | 127520.824
|  | Source | [5 empty] | RISK RATING
| *SDP WASH | Partner Reports (ICRC - number of rural/semi-urban and urban residents access to sustainable sources of water) | [5 empty] | Severe
Note on E2: Gemma MacArthur: Al individua;l figures are the same as previous log frame
Note on E11: Hannah Gough: Figure used in CAR 2015 PCR was the indicator with the highest beneficiaries
Note on G18: Hannah Gough: no people in farming households
Note on H18: Hannah Gough: no people in farming households
Note on I18: Hannah Gough: 50,000 = no people in farming households
Note on I24: Hannah Gough: economic securityKatie Wambui: ICRC confirmed cash and cash for work for different people. SDP team confirmed cash for work can be counted. Page 5 appeal, cash for work: enable some 5,900 heads of household (supporting up to 29,625 people) to participate in cash-for-work activities Cash: page 4 appeal: distribute food or cash coupons to up to 12,500 people (2,500 households), and to children being treated for malnourishment in Kaga Bandoro, hospital patients in Bangui, and their families/caretakers (up to 7,500 people/1,500 hICRC confirmed cash and cash for work for different people. SDP team confirmed cash for work can be counted. Page 5 appeal, cash for work: enable some 5,900 heads of household (supporting up to 29,625 people) to participate in cash-for-work activities Cash: page 4 appeal: distribute food or cash coupons to up to 12,500 people (2,500 households), and to children being treated for malnourishment in Kaga Bandoro, hospital patients in Bangui, and their families/caretakers (up to 7,500 people/1,500 households in all)ouseholds in all)
Note on I37: Hannah Gough: 100,000+400,000 = 500,000 people to have access to water

## CHF
CHF |  |  |  | 0.44 | Male
Baseline | CAR 2015 204852 unless stated |  |  | 0.56 | Female | PLANNED |  |  | ACHIEVED
Milestone 1 | 2016 Appeal. Assessed in AR June 2017 |  |  | 0.5 | Children 0-17 | 2016 DFID % of Appeal: | 0.9% | 0.9% (£4m of £427.9m (531.5m USD)) | 2016 DFID % of Spend | 26.7% | £4m of £14.96m (19.35m USD)
Milestone 2 | 2017 Appeal. Assessed in AR June 2018 |  |  | 0.46 | Adults 18-59 | 2017 DFID % of Appeal: | 1.6% | £5.5m of £337.1m (497.3m USD) | 2017 DFID % of Spend | 33.7% | £5.5m of £16.3m (22.1m USD)
Milestone 3 | 2018 Appeal. Assessed in PCR March 2019 |  |  | 0.04 | Elderly 60+ | 2018 DFID % of Appeal: | 0.5% | £2m of £390.5m (515.6m USD) | 2018 DFID % of Spend | 29% | £6.3m of £21.8m (28.4m USD)
Target | 2016, 2017, 2018 Appeals. Assessed in PCR March 2019 |  |  |  |  | Total DFID % of Appeal: | TBC | £8.5m of TBC | Total DFID % of Spend | TBC
OUTCOME 1
Outcome Indicator 1.1 | [8 empty] | Assumptions
Address essential humanitarian needs in CAR |  |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Cumulative Target (PCR) | % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
| Number of people in CAR reached yearly with DFID humanitarian assistance. | Planned | Total | 435922 | 17100 | 28800 | 376527 | 422427
|  |  | Male | 191805.68 | 7524 | 12672 | 165671.88 | 185867.88
|  |  | Female | 244116.32 | 9576 | 16128 | 210855.12 | 236559.12
|  |  | Children 0-17 | 217961 | 8550 | 14400 | 188263.5 | 211213.5
|  |  | Adults 18-59 | 200524.12 | 7866 | 13248 | 173202.42 | 194316.42
|  |  | Elderly 60+ | 17436.88 | 684 | 1152 | 15061.08 | 16897.08
|  | Achieved | Total |  | 432779.499 | 446073.757
|  |  | Male |  | 190422.9796
|  |  | Female |  | 106636.8686
|  |  | Children 0-17 |  | 53318.4343
|  |  | Adults 18-59 |  | 24526.4798
|  |  | Elderly 60+ |  | 17311.18
|  | Source | [6 empty] | RISK RATING
|  | Partner Reports (CHF - # personnes ciblees) | [6 empty] | Severe
OUTPUT 1 | Output Indicator 1.1 | [7 empty] | Assumptions
|  |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Cumulative Target (PCR) | DFID proportion of CHF beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
The agro-pastoral production and food security in the targeted areas is improved and reinforced | Number of people in CAR reached through livelihoods assistance | Planned | Total | 8115 | 12600 | 22308 | 26710 | 61618
|  |  | Male | 3570.6 | 5544 | 9815.52 | 11752.4 | 27111.92
|  |  | Female | 4544.4 | 7056 | 12492.48 | 14957.6 | 34506.08
|  |  | Children 0-17 | 4057.5 | 6300 | 11154 | 13355 | 30809
|  |  | Adults 18-59 | 3732.9 | 5796 | 10261.68 | 12286.6 | 28344.28
|  |  | Elderly 60+ | 324.6 | 504 | 892.32 | 1068.4 | 2464.72
|  | Achieved | Total |  | 17757.102 | 18638 | 22728 | 59123.102
|  |  | Male |  | 7813.1249
|  |  | Female |  | 9943.9771
|  |  | Children 0-17 |  | 8878.551
|  |  | Adults 18-59 |  | 8168.2669
|  |  | Elderly 60+ |  | 710.2841
|  | Source | [6 empty] | RISK RATING
|  | Partner Reports (CHF 2016 - Sante obj 2: appuie OS 2 # de menages ayant recu une assistances pour la sauvegarde our la restauration de leurs moyens d'existence - multiplied by number of people; CHF 2017 - Sécurité Alimentaire Objectif 3: Restaurer l’accès et la disponibilité d’une alimentation de qualité par la sauvegarde des moyens de subsistance + Sécurité Alimentaire Objectif 1: Sauver des vies et contribuer à l’autonomie économique de la population; CHF 2018 - Sécurité Alimentaire Objectif 3: Restaurer l’accès et la disponibilité d’une alimentation de qualité par la sauvegarde des moyens de subsistance + MSSC Objectif 1 : Soutenir la reconstitution des moyens de subsistance en faveur des populations affectées et à risque + MSSC Objectif 2 B+C : Renforcer l’autonomisation socio-économique des populations affectées et à risque) NB: for all, 5 person per household | [6 empty] | Severe
Output 2 | Output Indicator 2.1 | [7 empty] | Assumptions
Affected population are reached by healthcare, water and sanitation, and protection support | Number of beneficiaries reached in CAR by healthcare support (includes double counting across agencies) |  |  | Baseline | [added after AR 2017] | Milestone 2 (2017 Appeal) | Milestone 3 (2018 appeal) / Target (PCR) |  | DFID proportion of CHF beneficiaries for milestones and target calculated using % of DFID funds of appeal target total. Proportion may change for achieved figures when actual % is known after the appeal total reached is known.
|  | Planned | Total | 110690 |  | n/a | 118286
|  |  | Male | 48703.6 |  |  | 52045.84
|  |  | Female | 61986.4 |  |  | 66240.16
|  |  | Children 0-17 | 55345 |  |  | 59143
|  |  | Adults 18-59 | 50917.4 |  |  | 54411.56
|  |  | Elderly 60+ | 4427.6 |  |  | 4731.44
|  | Achieved | Total |  |  | n/a | 116145
Male
Female
Children 0-17
Adults 18-59
Elderly 60+
Source
Partner Reports (CHF 2017 - ?; CHF 2018: # de consultations curatives réalisées dans les zones affectées par un choc humanitaire + )
Output Indicator 2.3
| Number of people with improved access to water and sanitation (hard activities only)* |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Cumulative Target (PCR)
|  | Planned | Total | 4050 | 6300 | 11200 | 121765 | 139265
|  |  | Male | 1782 | 2772 | 4928 | 53576.6 | 61276.6
|  |  | Female | 2268 | 3528 | 6272 | 68188.4 | 77988.4
|  |  | Children 0-17 | 2025 | 3150 | 5600 | 60882.5 | 69632.5
|  |  | Adults 18-59 | 1863 | 2898 | 5152 | 56011.9 | 64061.9
|  |  | Elderly 60+ | 162 | 252 | 448 | 4870.6 | 5570.6
|  | Achieved | Total |  | 23198.028 | 118785 | 88304 | 230287.028
Male
Female
Children 0-17
Adults 18-59
Elderly 60+
|  | Source | [6 empty] | RISK RATING
| *SDP WASH | Partner Reports (CHF 2016 & 2017: # personnes beneficiant de l'approvisionnement en eau potable d'urgence; CHF 2018: # de personnes affectées (désagrégé par sexe et âge) ayant bénéficié durablement de l’eau potable pour répondre à leur(s) vulnérabilité(s)*) | [6 empty] | Severe
Output Indicator 3.3 | [8 empty] | Assumptions
|  |  |  | Baseline | [added after AR 2016] | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Target (PCR)
DFID helps improve children's, women's and girls' nutrition in CAR | Cure rate among children treated for acute malnutrition | Planned |  | 77% |  | Above 75% | Above 75% | Above 75%
|  | Achieved |  |  |  | Above 75%
Source
Partner Reports (CHF)
Output 4 | Output Indicator 4.1 (revised) | [7 empty] | Assumptions
|  |  |  | Baseline | [added after AR 2016] | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Target (PCR) | Security situation does not deteriorate so agencies are able to continue operating and field visits are able to take place.
DFID empowers humanitarian coordination for rapid and effective decision-making in CAR | % of emergency reserve allocations dispersed to projects within 30 days | Planned |  | 85% |  | 85% | 85% | 85%
|  | Achieved |  |  |  | 29%
Source
Partner reports (CHF)
Output Indicator 4.2
|  |  |  | Baseline | Milestone 1 (2016 appeal) | Milestone 2 (2017 appeal) | Milestone 3 (2018 appeal) | Target (PCR)
| % of projects monitored through field visits within their project duration | Planned |  | 39% | 40% of projects monitored in 2016 | 40% of projects monitored in 2017 | 40% of projects monitored in 2018 | 40% of projects monitored
|  | Achieved |  |  | 43% | 69% | 40% of projects monitored in 2018 | 40% of projects monitored
|  | Source | [6 empty] | RISK RATING
|  | Partner Reports (CHF monitoring reports) | [6 empty] | Major

## MENTOR
MENTOR
OUTCOME 1
Outcome Indicator 1.1 | [8 empty] | Assumptions
Address essential humanitarian needs in CAR |  |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) | Total Target (PCR) | ¤ Collaboration with key government and UN agencies in not reduced. ¤ Donor payments of funds are timely. ¤ MINUSCA forces are maintained on the field. ¤ IDPs and host communities support the program. ¤ Security situation allows for supply lines and staff movements.
|  | Planned | Male
Female
Under 5
Over 5
| Number of people in CAR reached yearly with DFID humanitarian assistance. |  | TOTAL | 290567 | 259212.8333 | 452801 | 175526 | 175526
|  | Achieved | Male
Female
Under 5
Over 5
|  |  | TOTAL |  | 191184 | 247630 | 182429 | 182429
|  | Source | [6 empty] | RISK RATING
|  | Partner Reports (MENTOR Consortium: MENTOR Initiative, IMC, Cordaid and Oxfam) | [6 empty] | Severe
OUTPUT 2 | Output Indicator 2.1 | [7 empty] | Assumptions
|  |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) |  | ¤ No loss of drugs through stealing and embezzlement. ¤ License to import pharmaceuticals is maintained for all partners. ¤ Transport means to carry drugs to the field sites remain available (flights, road). ¤ Vaccination remains part of the MoH plans. ¤ A sufficient cold chain is available. ¤ EPI service from MoH or other agency (WHO, etc.) provides required vaccines on time. ¤ No insecurity and/or climatic conditions render health facilities inaccessible for patients. ¤ No cultural barriers prevent beneficiaries from seeking access to health facilities services (for instance women not willing to be visited by a male health worker) ¤ Qualified staff is available at the supported facilities as scheduled. ¤ Counterfactual to prove satisfaction of beneficiaries is in place. Sample of surveys are big enough to be representative. ¤ A workshop is held within the Consortium to define services, supervision and training package, and all the members have agreed to implement. Authorities at all levels (national/regional/district) have agreed. ¤ The referral system is in place and tariff and criteria are well understood by each party. ¤ GBV survivors seek remedial services in the consortium's supported facilities
|  | Planned | Male
Female
Affected population are reached by healthcare, water and sanitation, and protection support |  |  | Under 5
Over 5
| Number of beneficiaries reached in CAR by healthcare support |  | TOTAL | 239422 | 259212.8333 | 452801 | 175526
|  | Achieved | Male
Female
Under 5
Over 5
|  |  | TOTAL |  | 191184 | 247630 | 182429
Source
Partner Reports (MENTOR Consortium: MENTOR Initiative, IMC, Cordaid and Oxfam) [Consortium Logframe Ref: O1]
Output Indicator 2.3
| Number of people with improved access to water and sanitation (hard activities only)* |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) | Total Target (PCR)
|  | Planned | Male
Female
Under 5
Over 5
|  |  | TOTAL | 51145 | 500 per water point | 55347 | 55347 | 55347
|  | Achieved | Male
Female
Under 5
Over 5
|  |  | TOTAL |  | 4595 | 13246 | 303329 | 303329
Source
| *SDP WASH | Partner Reports (MENTOR Consortium: MENTOR Initiative, IMC, Cordaid and Oxfam) Consortium Logframe Ref: I1,22 and I1,23
OUTPUT 3 | Output Indicator 3.1 | [7 empty] | Assumptions
| Number of new malnutrition cases from children under 5, adolescent girls (10-19) and women under 50 in CAR that gain access to treatment (includes SAM and MAM cases) * |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) | Total Target (PCR) | ¤ UNICEF provides the necessary amount of nutrition therapeutic supplies in a timely manner. ¤ No security issues hinder people to reach areas where treatment and IEC on nutrition are held. ¤ IEC sessions contribute to improving U5 and women's capacity to prevent malnutrition
|  | Planned | Male
Female
Under 5
Over 5
DFID helps improve children's, women's and girls' nutrition in CAR |  |  | TOTAL | 0 | 440 | 769 | 721 | 1535
|  | Achieved | Male
Female
|  |  | Under 5 |  | 525 | 1431
|  |  | Over 5 |  | 4 | 70
|  |  | TOTAL |  | 529 | 1501 | 2200 | 4230
Source
| * SDP Nutrition High; | Partner Reports (Cordaid and IMC) Consortium Logframe Ref: 3.1
Output Indicator 3.2
| Number of children under 5, adolescent girls (10-19) and women under 50 in CAR with improved capacity to prevent malnutrition** |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) | Total Target (PCR)
|  | Planned | Male
Female
Under 5
Over 5
|  |  | TOTAL | 27817 | 24446 | 45280 | 19642 | 89368
|  | Achieved | Male
Female
Under 5
Over 5
|  |  | TOTAL |  | 20835 | 7531 | 12871 | 41237
Source
| **SDP Nutrition Medium | Partner Reports on soft activities [Consortium Logframe Ref: I1.13]
Output Indicator 3.3
|  |  |  | Baseline (October 2016) | Milestone 1 (1 Oct 2016 - 30 April 2017) | Milestone 2 (1 May 2017 - 30 April 2018) | Milestone 3 (1 May 2018 - 31 March 2019) | Total Target (PCR)
| Cure rate among chlidren treated for acute malnutrition | Planned |  | 77% | Above 75% | Above 75% | Above 75% | Above 75%
|  | Achieved |  |  | 86% | 86% | 89% | 87%
|  | Source | [6 empty] | RISK RATING
|  | Partner Reports (MENTOR Consortium: MENTOR Initiative, IMC, Cordaid and Oxfam) [Consortium Logframe Ref: I1.13] | [6 empty] | Severe
Note on B4: Hannah Gough: Disaggregation for this outcome indicator uses overall statistics in consortium consolidated logframe/data spreadhseet from cell C368 on the graphs tab
Note on G10: Mentor: Calculated as the follows: (pop2016 438106/12months*3) +(pop2017449059/12months*4)
Note on G15: Mentor: Calculated as the sum of consultations + SAM + immunization + assisted deliveries + ANC + TPI + rape survivors + pediatric hospitilizations + obstetric emergencies handled + CHW malaria cases handled + CHW diarhea cases handled between Oct 1 2016 - April 30 2017. Double counting is likely, as say, for example, a woman benefits from an ANC cycle and then gives birth assisted in a supported facility. She would be counted twice. Unless we would put in a place a system of tracking individual names across services, double counting is inevitable.
Note on G25: Mentor: Target is at least one contact per person per year with healthcare support; see G10 for calculation method
Note on G30: Mentor: Calculated as the sum of consultations + SAM + immunization + assisted deliveries + ANC + TPI + rape survivors + pediatric hospitilizations + obstetric emergencies handled + CHW malaria cases handled + CHW diarhea cases handled between Oct 1 2016 - April 30 2017. Double counting is likely, as say, for example, a woman benefits from an ANC cycle and then gives birth assisted in a supported facility. She would be counted twice. Unless we would put in a place a system of tracking individual names across services, double counting is inevitable.
Note on G44: Mentor: Cordaid repaired the water point at Nzelete Health Facility in Alindao in October 2016. There was no "enquete de taux de frequentation" done to know how many people the water point serves so this is the sum of the number of consultations, cases of SAM treated, children vaccinated, women who received CPN, and number of assisted births that have taken place in the Health Facility Oct 1, 2016 - April 30, 2017.
Note on G54: Mentor: Calculated as the sum of the targets for SAM for IMC and Cordaid between October 1 2016 - April 30 2017 based on 3.04% prevalence rate.
Note on G59: Mentor: IMC = 155 Cordaid = 374
Note on G68: Mentor: There is no international or national accepted target for number of people reached through IEC nutrition messages; the Consortium sets targets for IEC based on all IEC topics together, not topic specific. However, the Consortium has agreed that 10% of people reached through IEC should be reached with messages related to nutrition. During the first 7 months of the project, the Consortium reached 8.5% of total people reached through IEC with messages related to nutrition.
Note on G73: Mentor: MENTOR = 4,638 Cordaid = 14,957 IMC = 1,240
Note on G79: Mentor: Cordaid = 77% IMC = 98%
Note on H10: Mentor: Calculated as the follows: (pop2017449059/12*8) + (pop2018460285/12*4)
Note on H25: Mentor: Target is at least one contact per person per year with healthcare support; see H10 for calculation method
Note on H30: Mentor: Calculated as the sum of consultations + SAM + immunization + assisted deliveries + ANC + TPI + rape survivors + pediatric hospitilizations + obstetric emergencies handled + CHW IPTs between May 1 2017 - April 30 2018.
Note on H39: Mentor:90,970 =SUM(4578+4620+7111+4620+8959+9091+6412+4479+5477+35623) The Consortium plans to construct 3 new water points (2 in Paoua/Markounda and 1 in Batangafo) and to rehabilitate/repair 6 water points (5 in Paoua/Markounda and 1 in Batangafo) during Phase 2. The water points are to serve the Health Facility meaning the target population is the same as the Health Facility. The catchment area for the 9 Health Facilities concerned totals 55,347 people. In addition, the Consortium will contribute to the construction of a gravity-fed water system serving 35,623 IDPs in PK3 site in Bria city. The total target is set at 90,970. The Consortium is no longer working with Oxfam as from January 31 2017, so WASH activities are to be implemented by other partners. This transition period is expected to have an impact on the timeframe of activity implementation.
Note on H44: Mentor: Cordaid repaired the water point at Nzelete Health Facility in Alindao in October 2016. There was no "enquete de taux de frequentation" done to know how many people the water point serves so this is the sum of the number of consultations, cases of SAM treated, children vaccinated, women who received CPN, and number of assisted births that have taken place in the Health Facility between May 1, 2017 - April 30, 2018 = 12,754 beneficiaries. Oxfam rehabilitated the waterpoint at Kadjama Health Facility in Markounda in December 2017. As in Alindao, there was no "enquete de taux de frequentation" done to know how many people the water point serves. The sum of consultations, children vaccinated, women who received CPN, and number of assisted births that have taken place in the HF since December 2017 = 492
Note on H54: Mentor: Calculated as the sum of the targets for SAM for IMC and Cordaid between May 1 2017 - April 30 2018 based on 3.04% prevalence rate.
Note on H59: Mentor: Cordaid = 1,116 IMC = 385
Note on H68: Mentor: Based on the weighting of IEC activities focusing on nutrition between October 1 2016 and April 30 2017 (=8,5%) at Health Facility and CHW level. Partners agreed to increase the target to be 10% of total people reached through IEC sessions to be reached by messages related to nutrition. Calculated as the sum of total targets for IEC sessions between May 1 2017 and April 30 2018 (452,801*.10) = 45,280
Note on H73: Mentor: MENTOR= 3,370 IMC= 1,957 Cordaid= 2,204
Note on H79: Mentor: Cordaid = 89% IMC = 83%
Note on I30: Katie Wambui: Number of total consultations May 2018-31 Mar 2019
Note on J10: Mentor: Calculated as the follows: (pop2018 284,343/12*5) + H10 + G10 Target population has been reduced as from May 2018, namely for MENTOR's CHWs. (Cumulative calculation done according to DFID's request).
Note on J54: Mentor: Calculated as the sum of the targets for SAM for IMC and Cordaid between May 1 2018 - September 30 2018 based on 3.04% prevalence rate + H83 + G83 (Cumulative calculation done according to DFID's request).

## WFP and UNHCR
CAR REFUGEES - WFP and UNHCR |  |  |  | NB: WFP figures are for DFID's contribution only.
Milestone 1 in AR 2017 | 2016 appeal
Revised Milestone 1 | 2016 appeal corrected
Milestone 2 | 2017 appeal assessed in AR June 2018
Milestone 3 | 2018 appeal assessed in PCR June 2019
OUTCOME 1
Outcome Indicator 1.2
|  |  |  | Baseline (July & August 2016) | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned WFP | Male | 74033.28 | 79918.08 |  | 79918.08 |  | 57744 |  | 74686
|  |  | Female | 80202.72 | 86577.92 |  | 86577.92 |  | 62556 |  | 80673
|  |  | Under 5 | 44728.44 | 48283.84 |  | 48283.84 |  | 34887 |  | 50624
|  |  | Over 5 | 109507.56 | 118212.16 |  | 118212.16 |  | 85413 |  | 114254
|  |  | Elderly | n/a | n/a |  | 6493.344 |  | 4691.7 |  | 8751
|  |  | Disabled | n/a | n/a |  | n/a |  | 12030 |  | 13646
Address essential humanitarian needs among people displaced from CAR | Number of displaced people from CAR reached yearly with DFID humanitarian assistance. |  | Total | 154236 | 166496 |  | 166496 |  | 120300 |  | 194564
|  | Planned UNHCR | Male
Female
Under 5
Over 5
Elderly
|  |  | Total | 0 | 38814 |  | 30554 |  | 61496 |  | 48611
|  | PLANNED TOTAL |  | 154236 | 205310 |  | 197050 |  | 181796 |  | 243175
|  | Achieved WFP | Male |  | 13557.12 |  | 13557.12 |  | 85159
|  |  | Female |  | 14686.88 |  | 14686.88 |  | 92254
|  |  | Under 5 |  | 8190.76 |  | 8190.76 |  | 35483
|  |  | Over 5 |  | 20053.24 |  | 20053.24 |  | 141930
|  |  | Elderly |  | n/a |  | 1101.516 |  | 6919.107
|  |  | Disabled |  | n/a |  | n/a |  | 166768.22
|  |  | Total |  | 28244 |  | 28244 |  | 177413 |  | 205989
|  | Achieved UNHCR | Male
Female
Under 5
Over 5
Elderly
|  |  | Total |  | 33588 |  | 30554 |  | 58759.371 |  | 12104
|  | ACHIEVED TOTAL |  |  | 61832 |  | 58798 |  | 236172.371 |  | 218093
Source
Partner Reports (UNHCR and WFP)
Outcome Indicator 1.1
| % of beneficiaries with reduced or stabilised Coping Strategy Index (CSI) |  |  | Baseline | [added after AR 2017] |  | Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned |  |  |  |  | 60% |  | 70% |  | 70%
|  | Achieved |  |  |  |  | 64.09% |  | 63.65% |  | 60.1%
Source
Partner Reports (WFP)
OUTPUT 5 | Output Indicator 5.1 | [11 empty] | Assumptions
Displaced Central Africans see their basic needs met and communities in are supported in hosting them | Number of people who have received basic food assistance* (single counting) |  | Baseline (July 2016) |  | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR) |  | There is no escalation of conflict, lack of state authority and impeded deployment of security forces (United Nations) that could prevent implementation of activities in a large part of the project area in CAR. There is no security incident hampering food distributions in CAR and along the border with CAR in neighboring countries. Access to beneficiaries and areas of influx is possible. Complementary activities are provided by partner There is adequate funding to avoid pipeline breaks
|  | Planned (by type of assistance) | 0 |  | General food distribution | 119016 | General food distribution | 119016 | General food distribution | 40000 | General food distribution | 60000
[5 empty] | Cash transfers | 17480 | Cash transfers | 17480 | Cash transfers | 28000 | Cash transfers | 74564
[5 empty] | Food assistance for assets | N/A | Food assistance for assets | N/A | Food assistance for assets | 8000 | Food assistance for assets | 3000
[5 empty] | Cash for assets | N/A | Cash for assets | N/A | Cash for assets | 4300 | Cash for assets | 0
[5 empty] | Total | 136496 | Total | 136496 | Total | 80300 | Total | 124564
|  | Achieved (by type of assistance) |  |  | General food distribution | 164624 | General food distribution | 164624 | General food distribution | 36886 | General food distribution | 63531
[5 empty] | Cash transfers | 38571 | Cash transfers | 22250 | Cash transfers | 10811 | Cash transfers | 108857
[5 empty] | Food assistance for assets | N/A | Food assistance for assets | N/A | Food assistance for assets | 3311 | Food assistance for assets | 25615
[5 empty] | Cash for assets | N/A | Cash for assets | N/A | Cash for assets | N/A | Cash for assets | N/A
[5 empty] | Total | 203195 | Total | 164624 | Total | 51008 | Total | 198003
|  | Planned (by age and gender) | Male | 0 | 65518 |  | 65518 |  | 38544 |  | 12286
|  |  | Female |  | 70978 |  | 70978 |  | 41756 |  | 13073
|  |  | Under 5 |  | 39584 |  | 39584 |  | 26499 |  | 12924
|  |  | Over 5 |  | 96912 |  | 96912 |  | 53801 |  | 21954
|  |  | Elderly |  | n/a |  | 5323.344 |  | 3131.7 |  | 3681
|  |  | Disabled |  | n/a |  | n/a |  | 8030 |  | 646
|  | Achieved (by age and gender) | Male |  | 97533.6 |  | 79019.52 |  | 24483.84
|  |  | Female |  | 105661.4 |  | 85604.48 |  | 26524.16
| * SDP Humanitarian Food/Cash/Vouchers |  | Under 5 |  | 58926.55 |  | 47740.96 |  | 16832.64
|  |  | Over 5 |  | 144268.45 |  | 116883.04 |  | 34175.36
|  |  | Elderly |  | n/a |  | 6420.336 |  | 1989.312
|  |  | Disabled |  | n/a |  | n/a |  | 47947.52
Source
Partner Reports (WFP)
Output Indicator 5.3
| Number of pregnant or lactating women and children under five who receive nutrition support aimed at preventing MAM (blanket feeding) * |  |  | Baseline (July 2016) | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned | Women |  | 0 |  | 0 |  | 0 |  | 0
|  |  | Under 5 |  | 55510 |  | 55510 |  | 40000 |  | 12800
|  |  | Total | 0 | 55510 |  | 55510 |  | 40000 |  | 12800
|  | Achieved | Women |  | 0 |  | 0 |  | 0
|  |  | Under 5 |  | 39217 |  | 39217 |  | 11293
|  |  | Total |  | 39217 |  | 39217 |  | 11293 |  | 13618
Source
| *SDP Nutrition Medium | Partner Reports (WFP)
Output Indicator 5.4
| Number of individuals (refugees and most vulnerable nationals) who benefit from livelihoods support activities |  |  | Baseline (Aug 2016) | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned | Male |  |  |  | 1485 |  | 2475 |  | 2475
|  |  | Female |  |  |  | 1683 |  | 2805 |  | 2805
|  |  | Under 5 |  |  |  | 0 |  | 0 |  | 0
|  |  | Over 5 |  |  |  | 3168 |  | 5280 |  | 5280
Elderly
|  |  | Total | 3168 | 373.824 |  | 3168 |  | 5280 |  | 5280
|  | Achieved | Male |  |  |  | 1485
|  |  | Female |  |  |  | 1683
|  |  | Under 5 |  |  |  | 0
|  |  | Over 5 |  |  |  | 3168
Elderly
|  |  | Total |  | 1037.22 |  | 3168 |  | 5526.771 |  | 5280
Source
Partner Reports (UNHCR)
Output Indicator 5.5
| Number of persons of concern registered by biometric registration |  | Baseline (August 2016) | Baseline (Aug 2016) | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned | Male |  |  |  | 16231 |  | 28839 |  | 22788
|  |  | Female |  |  |  | 14323 |  | 32679 |  | 25823
|  |  | Under 5 |  |  |  | 3570 |  | 7189 |  | 5681
|  |  | Over 5 |  |  |  | 26984 |  | 54329 |  | 42930
Elderly
|  |  | Total | 30,554 | 9135.646 |  | 30554 |  | 61496 |  | 48611
|  | Achieved | Male |  |  |  | 16231
|  |  | Female |  |  |  | 14323
|  |  | Under 5 |  |  |  | 3570
|  |  | Over 5 |  |  |  | 26984
Elderly
|  |  | Total |  | 33588.464 |  | 30554 |  | 58759.371 |  | 12104
Source
Partner Reports (UNHCR)
Output Indicator 5.6
| Number of refugees who access primary healthcare services |  | Baseline (August 2016) | Baseline (Aug 2016) | Milestone 1 in AR 2017 |  | Revised Milestone 1 (2016) |  | Milestone 2 (2017) |  | Milestone 3 (2018) / Target (PCR)
|  | Planned | Male |  |  |  | 2387 |  | 2475 |  | 3798
|  |  | Female |  |  |  | 2705 |  | 2805 |  | 4304
|  |  | Under 5 |  |  |  | 595 |  | 617 |  | 947
|  |  | Over 5 |  |  |  | 4497 |  | 4663 |  | 7155
Elderly
|  |  | Total | 5092 | 81.472 |  | 5092 |  | 5280 |  | 8102
|  | Achieved | Male |  |  |  | 2387
|  |  | Female |  |  |  | 2705
|  |  | Under 5 |  |  |  | 595
|  |  | Over 5 |  |  |  | 4497
Elderly
|  |  | Total |  | 1031.504 |  | 5092 |  | 90043.5974 |  | 8102
|  | Source | [10 empty] | RISK RATING
|  | Partner Reports (UNHCR) | [10 empty] | Major
Note on J59: Hannah Gough: Some cash transfer beneficiaries also received GFD therefore the total is only for GFD to avoid double counting
Note on K31: Gemma MacArthur: formula is k25+k26?
Note on M43: Gemma MacArthur: in wfp report this target is 60%?
Note on M44: Gemma MacArthur: For wfp cameroon report this is listed as household (60.1%) not beenficiaries? For Chad report this is beneficiaries and it is at 50%

## SI
Solidarités
OUTCOME 1
Outcome Indicator 1.1
Address essential humanitarian needs in CAR | Number of people in CAR reached yearly with DFID humanitarian assistance. |  |  | Baseline (TBC) | Target | Assumptions | Target from proposal
|  | Planned | Male Total | 88298 | 10529.12 |  | 13036.5
|  |  | Female Total | 91902 | 10958.88 |  | 9491.5
|  |  | Children Under 5 Total | - | 5801.76
|  |  | Children (6-18)Total | - | 7091.04
|  |  | Adults (19-59)Total | - | 7950.56
|  |  | Elderly (60+)Total | - | 644.64
|  |  | Under 5 Male | - | 2842.8624 |  | 48
|  |  | Under 5 Female | - | 2958.8976
|  |  | Children (5-18) Male | - | 3474.6096 |  | 22480
|  |  | Children (6-18) Female | - | 3616.4304
|  |  | Adults (19-59) Male | - | 3895.7744
|  |  | Adults (19-59) Female | - | 4054.7856
|  |  | Elderly (60+) Male | - | 270.7488
|  |  | Elderly (60+) Female | - | 373.8912 |  | -
|  |  | TOTAL | 180200 | 21488 |  | 22528
|  | Achieved | Male Total |  | 10444
|  |  | Female Total |  | 10796
|  |  | Children Under 5 Total |  | 572
|  |  | Children (6-18)Total |  | 6068
|  |  | Adults (19-59)Total |  | 11627
|  |  | Elderly (60+)Total |  | 973
|  |  | Under 5 Male |  | 1274
|  |  | Under 5 Female |  | 1298
|  |  | Children (6-18) Male |  | 3021
|  |  | Children (6-18) Female |  | 3047
|  |  | Adults (19-59) Male |  | 5933
|  |  | Adults (19-59) Female |  | 5694
|  |  | Elderly (60+) Male |  | 216
|  |  | Elderly (60+) Female |  | 757
|  |  | TOTAL |  | 21240
|  | Source |  |  |  | RISK RATING
|  | Partner Reports (Solidarités Consortium) |  |  |  | Severe
OUTPUT 1 | Output Indicator 1.1
|  |  |  | Baseline (TBC) | Target | Assumptions | Target from proposal
The agro-pastoral production and food security in the targeted areas is improved and reinforced | Number of people in CAR reached through livelihoods assistance | Planned | Male Total | 279.3 | 3414.81 |  | 3410
|  |  | Female Total | 290.7 | 3554.19 |  | 3549
|  |  | Children Under 5 Total | - | 1879
|  |  | Children (6-18)Total | - | 2297
|  |  | Adults (19-59)Total | - | 2584
|  |  | Elderly (60+)Total | - | 209
|  |  | Under 5 Male | - | 920.71
|  |  | Under 5 Female | - | 958.29
|  |  | Children (6-18) Male | - | 1125.53
|  |  | Children (6-18) Female | - | 1171.47
|  |  | Adults (19-59) Male | - | 1262
|  |  | Adults (19-59) Female | - | 1322
|  |  | Elderly (60+) Male | - | 87.78 |  | 0
|  |  | Elderly (60+) Female | - | 121.22 |  | -
|  |  | TOTAL | 570 | 6969 |  | 6959
|  | Achieved | Male Total |  | 2650
|  |  | Female Total |  | 2688
|  |  | Children Under 5 Total |  | 1494
|  |  | Children (6-18)Total |  | 1673
|  |  | Adults (19-59)Total |  | 1962
|  |  | Elderly (60+)Total |  | 208
|  |  | Under 5 Male |  | 723
|  |  | Under 5 Female |  | 771
|  |  | Children (6-18) Male |  | 841
|  |  | Children (6-18) Female |  | 832
|  |  | Adults (19-59) Male |  | 983
|  |  | Adults (19-59) Female |  | 979
|  |  | Elderly (60+) Male |  | 102
|  |  | Elderly (60+) Female |  | 106
|  |  | TOTAL |  | 5338
|  | Source |  |  |  | RISK RATING
|  | Partner Reports (Solidarités Consortium) |  |  |  | Severe
Note on G20: Hannah Gough: Without double counting the figure is 21,488. With double counting the figure is 22,688
Note on G35: Hannah Gough: Without double counting the figure is 21,240. With double counting, the figure is 23,228