Annual Review – post April 2018

Title: Programme for Strengthening State Capabilities in India
Programme Value £ (full life): 4,995,000		Review Date: 27/02/2020
Programme Code: 300738	Start Date: 27/02/2019	End Date: 01/11/2023

Summary of Programme Performance
Year	2020
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Vault id 53314488
DevTracker Link to Log frame:	Vault id 53312732

A. Summary and Overview (1-2 pages)

Description of programme

The Programme for Strengthening State Capabilities (PSSC) is a £4.99 m programme, including a £495,000 cost extension agreed in January 2020. The £ 4.5 m Business Case was approved by the DFID India Head of Office (HoO) in October 2018, spanning an implementation period of 5 years (2018 -2023).

The programme aims to strengthen capacity and capabilities of state and sectoral institutions and support the Government of India (GoI) in its crucial reforms to bring in greater transparency, accountability and improve delivery of public services commensurate with that of a rising power.

The programme is expected to deliver the following two outputs:

Output 1: Strategic engagements with states leading to stronger partnerships
Output 2: Capability building mechanisms to influence key reforms in select states and sectors

The overall outcome envisaged is strengthened capacity of institutions in select states and sectors to develop and implement good policies and practices. The expected impact of the programme is strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth in the selected states and sectors.

India-UK/DFID Partnership on civil service modernisation (CSM)

In January 2020, the HoO approved a cost extension (£495,000) to enable the UK to partner with GoI (through the World Bank) in its ambitious Civil Service Modernisation (CSM) Plan, a PM Modi priority, and includes the cost of secondment of a senior DFID staff into the World Bank.

Aligned with the framework of PSSC, collaboration on India’s Civil Service Modernisation (CSM) work has advanced at a rapid pace in the last six months - Department of Personnel and Training (DoPT), Government of India, through the DFID-World Bank state capability partnership. We (DFID working as one HMG) have collaborated on PM Modi’s flagship ‘first of its kind’ civil service ‘common’ foundation course for new civil service entrants (with a global component), brought senior UK speakers & cross-government teams to engage with senior Indian counterparts through a peer-to-peer approach and highlighted several good practices on CSM from the UK. The uptake of this work is strong, and we will fold the CSM strand into the programme (with possibly a new output).

UK Government engagement on this will help build high-level connections and institutional relationships between Britain and India that will have wider enduring value in the years ahead.
Summary supporting narrative for the overall score in this review

This is the first annual review of the PSSC programme. The review concludes the programme has delivered against its outputs and scored an A.

Till date, the programme, has partnered with two key multilateral organisations – i) the World Bank (through two Externally Financed Outputs (EFOs) – in low income states and across key sectors and ii) the International Monetary Fund (IMF), through an MoU, to provide high quality public finance technical assistance and training support to low income states and its officials. Through these two partnerships, the programme has committed to spend £2.47 m over a period of two years (2019-2021).

Apart from setting up partnerships with the WB and IMF, the first year of implementation was utilised to set up and operationalise strong governance arrangements and to track programme activities - that included joint periodic reviews throughout the year.

With the World Bank, we have set up two EFOs, that will support select low income states in taking an evidence-led approach to driving cross government and sectoral reforms to improve service delivery and achieve better development outcomes.

EFO 1- Focuses on ‘Strategic State Engagement for Policy Reforms and Strengthening Capabilities' in the states of Punjab and Odisha. These two states were chosen based on the geographic and sectoral priorities of DFID India as well as the development needs of the states - in consultation with the World Bank.

EFO 2 – Focuses on ‘State Partnership for Enhancing Commercialisation of the Power Sector’. This aims to deepen DFID India’s engagement in the power sector, by undertaking innovative pilots and providing analytical and advisory support to bolster institutional strengthening in the sector that complement the engagement in the power sector of DFID’s Power Sector Reform programme and the Prosperity Fund’s energy sector programme.

With the IMF’s South Asia Regional Training and Technical Assistance Centre (SARTTAC), we have signed a MoU that is helping strengthen sub-national capacity for public financial management in Odisha. The second partnership state is to be agreed with IMF by September 2020.

The programme also successfully piloted a collaborative workshop with the Lal Bahadur Shastri National Academy of Administration (LBSNAA) – Government of India’s apex institution for training its top administrative officials – on aspects of gender mainstreaming and gender sensitivity in crucial aspects of public service delivery.

During this period, we have received a proposal on building state capability from a consortium of India-based premier Think Tanks - to provide high quality advisory and policy analysis support related to private sector, regulation and building markets. We have analysed the proposal and we are at the final stages of discussion with the partners.

Recommendations for the year ahead

We will develop a Strategic Framework for engagement with GoI’s CSM modernisation agenda in order to be able to respond to both opportunities and challenges as they emerge, to maximise development opportunities and manage risks. The Strategic Framework, which will include the secondment of a senior DFID staff to the World Bank will enable us to advance the State Capability and CSM agenda together, through this programme - working with Government of India, the World Bank, LBSNAA and other Think Tanks. The Strategic Framework should be developed and agreed by the DFID India Programme Team by September 2020.

New partnerships such as the one we are developing with Think Tanks will help us provide a stronger independent research and evidence base to inform our state capability work (with private sector, market and regulation focus) with the World Bank and the IMF and with Government of India partners. The partnership with Think Tanks should be agreed by the DFID Programme Team by June 2020.

The programme will develop a targeted partnership with India’s premier civil service training institute, the LBSNAA to support capacity building of Indian civil servants on key India-UK priorities such as; private sector development, urban and city management, climate and gender. This is to be agreed by the DFID Programme Team by September 2020.

We will look to agree the second partnership state with IMF by June 2020. We will establish how SARTTAC uses the IMF’s Results Based Monitoring (RBM) System and independent evaluations to measure how its capacity development work is translating into improvements in policy-making and government administration (i.e. to credibly demonstrate where and how DFID India support has contributed to strengthening state capabilities), particularly in the two state governments which DFID India identified to focus on. The DFID Programme Team should complete this by September 2020.

We have reviewed the current Theory of Change (ToC), and the log frame, and we have noted that the programme does not capture the focus needed on climate and environment issues. Following the annual review, we shall ensure that these priorities are reflected in both the ToC and the log frame. The new log frame should be finalised by the DFID Programme Team no later than end of July 2020.

The learning for the first year of implementation is to have a more effective governance mechanism in the form of rigorous joint periodic reviews with the Multilaterals; especially the World Bank to ensure better visibility for DFID and greater technical collaboration. This will be monitored by the DFID Programme Team on a quarterly basis.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Strategic engagements with states leading to stronger partnerships
Output number per LF		1	Output Score	A
Impact weighting (%):		60	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of pilots supported with a pro-poor impact	Agreements signed with World Bank to implement innovative pilots in partner states	Milestone Achieved
1.2 % of engagements involving senior government officials	Progress reports reflect the level and extent of government engagement	Milestone Achieved

Provide supporting narrative for the score

The programme developed a partnership with the World Bank to support strategic state engagement for facilitating implementation of policy reforms, strengthening public institutions, building state capabilities and facilitating knowledge sharing across states to scale up good practices and innovative solutions. The partnership was forged in keeping with the World Bank’s new Country Partnership Framework in India that has a state partnership approach rather than the usual standalone project implementation approach. The World Bank has acknowledged that the partnership with DFID has been instrumental in allowing them to lift the dialogue at the highest level of the state government(s) and has led to initiation of strategic policy engagements.

The following activities were progressed under the World Bank partnership during the year:

  1. In Odisha, a rapid diagnostic assessment on the key drivers of growth for the state was completed by the World Bank team and subsequently presented to the government (principally the Chief Minister, Chief Secretary and a Committee of Principal Secretaries). This included ten policy notes across various development issues for the state and helped highlight the macro-fiscal situation and areas where the state would need support, including strengthening the state’s capacity to plan, budget and implement programs for social protection and thematic areas like energy, water, urban and agriculture. The diagnostic has helped define a set of mid-term priorities and subsequent policy recommendations and articulated the state partnership along the following three pillars:

1. expediting economic transformation;
2. strengthening state capability;
3. forging a sustainable and resilient future.

The diagnostic also helped classify the development priorities of the state as immediate and mid-term.

In Punjab, extensive policy dialogue with the state government particularly with the offices of the Chief Minister and Chief Secretary were initiated for supporting the state in revitalising growth and ensuring sustainable development. This work highlighted that putting Punjab back on a fast and sustainable growth path will require a multi-sectoral and systematic approach to reform, focused around upgrading the financial and operational bandwidth of the state to steer development, promoting a shift away from the current agricultural model that is unsustainable and ensuring that cities are equipped to become new engines of growth.

The World Bank team along with technical experts and consultants engaged in extensive policy dialogue and agreed priority areas of engagement. Where appropriate DFID teams were also involved in these discussions. The Government of Punjab (GoP) has requested support in the following three priority areas:

1. strengthening transversal systems and capabilities for managing public finances
2. improving resources efficiency in the agriculture-groundwater-energy-agriculture nexus;
3. strengthening urban finances and planning frameworks.

As part of the ongoing support, analytical and diagnostic studies have been initiated and technical assistance is being provided in response in a range of areas. These include public financial management (PFM), planning and public investment management functions, data systems (to support the creation of a single interface between government and citizens to continuously monitor performance and improve service delivery and socio-economic outcomes), agriculture (focusing on the agriculture-groundwater-energy nexus), strengthening district capabilities, stakeholder communication and institutional and e-governance structures (to strengthen governance and urban finances in two specific cities, Ludhiana and Amritsar).

  1. Under the World Bank partnership, all policy dialogues were held with the partner state governments at the highest level of government and bureaucracy (particularly with the offices of the Chief Minister, Chief Secretary and Principal Secretaries of key departments) to ensure optimum buy-in. In addition, under the ‘Lighthouse India’ initiative, a workshop was delivered by the World Bank in partnership with the NITI Aayog on ‘Energy-Water-Agriculture Nexus: Grow Solar, Save Water, Double the Farm Income’ in December 2019 in New Delhi. The workshop was designed to promote knowledge sharing among officials from across Indian states and the exploration of opportunities to leverage solar for increasing climate – resilient farm income. The event brought together 90 high level government officials from states, policy and technical experts, farmer representatives, and private sector to share their experiences of managing the energy-water-agriculture nexus.

Lessons identified this year, and recommendations for the year ahead linked to this output

Right at the outset, the DFID programme team ensured a strong governance structure for its partnership with the World Bank. This included setting up of a two-tiered governance structure. Since the EFOs were signed, two quarterly coordination meetings were held in May 2019 and November 2019 to discuss progress updates and new activities planned under the EFO. A one HMG Steering Committee meeting was also held in August 2019 between the Head of DFID India, the FCO Economic Counsellor and the Head of World Bank India, that discussed overall progress and collaboration as well as development priorities and new opportunities for the World Bank - UK collaboration. In addition, the Bank and DFID teams have been regularly interacting on specific state and sectoral areas of engagement, including participation of DFID team in some high-level client meetings and missions. The team understands the need for continuing to strengthen the governance and partnership arrangements with World Bank and ensure greater technical collaboration with and visibility for UK/DFID.

Output 1: The indicators and milestones should be reviewed and updated particularly to ensure that they are defined with greater specificity. This work should be actioned by the DFID Programme Team no later than end of July 2020.

Output Title	Capability building mechanisms to influence key reforms in select states and sectors
Output number per LF		2	Output Score	A
Impact weighting (%):		40	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Demand led evaluation of government pilot intervention (WB)	At least 1 evaluation started	Milestone Achieved
2.2 Number of knowledge products/exchange programmes facilitated to inform policies - knowledge products, visits, policies informed	At least one contract is in place to deliver on knowledge products to inform policy	Milestone Achieved
2.3 Number of capacity development training availed by national and state government (particularly low-income states) on governance, decentralization, participation, responsiveness, transparency and accountability	Implementing partners have drawn up a training plan with partner governments	Milestone Exceeded / IMF SARTTAC have shared the Workplan for the period from May 2019 – April 2020. / LBSNAA organised 3 trainings for Indian civil servants from across cadre and states on issues of gender mainstreaming and violence against women and girls.

Briefly describe the output and provide supporting narrative for the score

In addition to forging strategic partnerships with states and providing cross sectoral technical advice, the programme has also taken a multi-pronged approach to develop capacity of the state and sectoral institutions for better public service delivery. This includes supporting evaluation of innovative pilots to inform the scaling up of reform initiatives, developing knowledge products and delivering exchange programmes to inform policies, setting up a strategic partnership with the International Monetary Fund’s South Asia Regional Training and Technical Assistance Centre (SARTTAC) to strengthen PFM capacity at the sub-national level and developing capacity to implement gender mainstreaming across ranks of bureaucracy. The programme also piloted a partnership with GoI’s premier training institute for civil servants – the Lal Bahadur Shastri National Academy of Administration (LBSNAA) to provide bespoke training on issues around gender and violence against women and girls – to induce a sensitised approach to public service delivery.

  1. Supporting evaluation of innovative pilots of the World Bank in partner state (Output 2.1): under the state partnership in Punjab, the programme is supporting the evaluation of an innovative pilot where the World Bank is providing implementation assistance to the Government of Punjab in the delivery of 253 (Phase 1 - 3 pilots and Phase 2 - 250) electricity feeders pilots. The pilot incentivises farmers in the more efficient use of electricity and water by monetising electricity savings they achieve and transferring them directly into their bank accounts. Through the independent impact evaluation, DFID is helping to assess the direct and indirect benefits of the pilot to farms and households. World Bank has appointed International Water Management Institute for the evaluation. The evaluation methodology uses a mixed method assessment including both quantitative and qualitative analysis, focus group discussions and engagements with key stakeholders. Two Focus Group Discussions (FGD) were held in 2019 with early and late adopters of the scheme. The consultants were also tasked with undertaking qualitative assessments of gender impacts.

  1. Develop Knowledge products and facilitate exchange programmes to inform policies (Output 2.2): under its sectoral partnership with the World Bank for the energy sector, DFID is supporting the World Bank to define the scope of work for the preparation of a Digitalisation Roadmap for Utility Sustainability for the state Electricity Distribution Company in West Bengal. In December 2019, a Preliminary draft Digital readiness report for the distribution company (Electricity Distribution Companies - Discoms) and a preliminary draft guidance documents on few key digital initiatives had been prepared by the consultants. These are being reviewed by the World Bank.

As part of the partnership, DFID and the World Bank engaged with NITI Aayog for the development of State Energy Index. So far, the work has focused on the developing the data collection methodology and defining appropriate indicators. DFID India has been intrinsically involved in these dialogues but there has not been much progress on the development of State Energy Index.

  1. Provide training to sub-national government officials (Output 2.3): the IMF SARTTAC delivered 28 training courses during the period under review. In line with expectations two were implemented for officials working in the Union government and three for recipients working in State governments. Of particular note is the acceleration of the centre’s work at the state level. DFID India identified Odisha as one of two state governments that it wanted SARTTACC to focus its technical assistance work. As part of this process SARTTAC established that there was strong political commitment and a strong counterpart team in place. Work has focused on strategic top-down budgeting (including the budget calendar), macro-fiscal forecasting and developing expenditure ceilings. Odisha is currently working on developing a fiscal strategy report and a debt information statement to complement existing budget documents. In consultation with DFID, SARTTAC will identify at least one other state to focus its support to during the next year.

Under a pilot partnership between DFID India and LBSNAA under this programme, the National Gender Centre at LBSNAA, organised 3 workshops in December 2019 and January 2020 to bring together key stakeholders from across fields of administration, law enforcement and judiciary who have been engaged in investigation and prosecution of cases of Violence against Women and Children. The purpose of these courses was to not only to identify the critical gaps in the parallel processes but also to arrive at possible solutions and best practices in order to minimize these gaps and strengthen the system to enable prevention of violence against women and children. Final report is expected to be shared with DFID in March 2020.

Lessons identified this year, and recommendations for the year ahead linked to this output

Output 2.3: The DFID Programme Team will:
1. continue to build the partnership with SARTTAC and consider whether there is a role that the DFID Asia Regional Tax Adviser could play in this process.
2. coordinate with other DFID programmes which are funding IMF capacity development activities, including the Public Finance and Tax Department’s programme supporting the IMF, to ensure there is alignment of strategic objectives and better information sharing,
3. agree the ‘second’ state government where it would like SARTTAC to target its technical assistance work and ensure this is reflected in its future workplan.
4. review and update the indicators and milestones particularly to ensure that they are defined with greater specificity so that they are more closely aligned with the objective of the support and therefore a more meaningful basis for assessing and monitoring progress. This work should be actioned by no later than end of June 2020.
5. ensure that SARTTAC applies, as it did in Odisha, the approach of systematically scoping (recording and tackling) political risks in its capacity development work in the ‘second’ state government (in line with other RTACs which DFID supports)
6. establish how SARTTAC uses the IMF’s Results Based Monitoring (RBM) System and independent evaluations to measure how its capacity development work is translating into improvements in policy-making and government administration (i.e. to credibly demonstrate where and how DFID India support has contributed to strengthening state capabilities), particularly in the two state governments which DFID India identified it to focus on.

The programme will finalise and start implementing the partnership with consortium of think-tanks - to provide high quality advisory and policy analysis support in partnership with top national and international institutions and to potentially explore a secretariat role in bringing together all strands of work under PSSC.

The programme will coordinate with other DFID/ HMG supported programmes to leverage synergies and learning e.g. – DFID supported Power Sector Reform programme, FCO’s energy technical assistance programme

State Energy Index: DFID will need to be informed of a more strategic decision on whether and how to take this forward by the World Bank. If the World Bank and NITI Aayog decides to go ahead with it, then they should develop a timetable for finalising the arrangements for data collection and the publication of annual indicators and agree this with DFID India.

The programme will consider developing a targeted partnership with a small amount of funding with LBSNAA to support hands-on capacity building of Indian civil servants on key priorities of UK-India partnership such as; private sector development, urban and city management and climate gender.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

We have reviewed the current Theory of Change (ToC), and the log frame, and we have noted that the programme does not capture the focus needed on climate and environment issues. Following the annual review, we shall ensure that these priorities are reflected in both the ToC and the log frame.

As this is the first year of the implementation, there was no major change to the theory of change except that the budget has been increased from initial £4.5m to £4.99m.

Input	Interventions	Output	Outcome	Impact
Up to £4.99m TA / DFID Resource: / SRO / Sr. Advisers / Programme Manager	Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness (meetings, diagnostic analysis, research, seminars)	Strategic engagement with states leading to stronger partnerships	Strengthened institutional systems and capabilities (planning, management, policy making, implementation capacity) in select states and sectors	Strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth
		Identify key areas of governance, institutional and policy strengthening in states and across sectors
		Evidence driven and informed pipeline development for DFID India
	Commission demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening	Enhance DFID's ability to respond to demand driven governance, institutional and policy reforms to influence and enhance state capability / Enhance DFID's ability to influence key reforms
	Provide capacity development trainings and associated activities to states and sector institutions	Enhance capacity of state administration based on gaps identified from the diagnostics and research

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

It is too early to comment on the contribution to expected outcomes and impact. Initial trends are positive and in the right direction.

The DFID programme will revise the programme logframe by June 2020 and milestones will be set for outputs, outcomes and impact appropriately. The team will continuously monitor the progress and take actions for course correction when appropriate.

Impact	Indicator-1
Enhanced state capability for service delivery in partner states and ministries leading to better performance towards the SDGs	Ranking of SDG performance of the partner states

Outcome-1	Indicator-1.1
Improved policies and systems to strengthen government capabilities	Number of Policies/ programs/systems adapting /adopting based on the recommendations provided

	Indicator-1.2
	Level of changes made in the policies and systems in the government machinery

Explain major changes to the logframe in the past year (1/2 page)

None

Describe any planned changes to the logframe as a result of this review (1/2 page)

Indicators will be reviewed based on new partnerships planned in the second year i.e. contribution to the World Bank Trust Fund and Secondment of a senior DFID staff.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The programme is currently in its first year of implementation. The progress has been satisfactory from VfM perspective. The programme needs to continue to achieve the intended objectives as set in the business case. However, it is too early to comment on most of the indicators at this stage of the programme.

Team signed 3 agreements with the Multilateral Organisations which have clear objectives, deliverables with timelines. Payments are made in arrears and as per the deliverables.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

In its first year of implementation, the programme has achieved sufficient economy. The main cost drivers are related to shaping the programme, mapping out potential partners and forging partnerships. The programme brought on-board influential partners namely, the World Bank and the IMF and has a commitment to spend £2.47 through them. In addition, there is ongoing work to develop a Trust Fund with the World Bank which it intended to take the partnership with World Bank beyond the EFOs.

In terms of contracting type and associated fiduciary risks, two Externally Financed Output (EFO) agreements has been signed with the World Bank and an MoU with IMF with clearly defined outputs (linked to the programme logframe), tranche payments and a robust governance framework.

Being the first year of implementation it is too early for the programme to show progress on the ‘Effectiveness’ and ‘Equity’ parameters of VfM.

As explained above, the programme is on track on counts of Economy and Efficiency parameters of Value for Money. It should continue on its own merits. Going forward the programme should sharpen its logframe to capture its leveraging power across the partnerships. It should also further continue to be diligent on ensuring its partners are delivering the outputs and outcomes competitively.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall Risk Rating – Moderate.

A risk register of the programme has been developed using the latest risk management guidelines of DFID. Mitigation strategies for each of these risks have been designed and the task team has agreed to review the overall risk rating of the programme biannually. The risk register is available on AMP.

The key risks and mitigation measures during the first year are provided below and there are no changes except for a new reputational risk have been added.

Risk Description	Risk Category	Mitigation Strategy	Residual Risk
There is a risk that in the partnership with the multilaterals DFID is not engaged with as an equal partner, adversely impacting the goals for outcome and impact	Reputational	DFID has set up a firm governance structure for engagement with the World Bank. Working collaboratively across the spread of the partnership is non-negotiable	Major
There is a risk that the programme supports small scale/ad-hoc initiatives that are not subsequently scaled up	Delivery	The programme has been carefully screening activities funded through it and is only supporting ones that are crucial to GoI and UK's priorities and are strategic. Payments are linked with agreed milestones	Moderate
Programme interventions do not lead to envisaged impact	Delivery	By carefully screening sub-projects and through the governance arrangements, DFID will systematically follow up with government counterparts and implementing partners on progress and uptake of interventions and recommendations	Minor

Based on the year one learning, a new risk will be added to the existing risks –

Risk Description	Risk Category	Mitigation Strategy	Residual Risk
With multiple partners delivering on programme objectives, safeguarding risks are overlooked exposing DFID to reputational risk	Reputational	SRO to ensure partners have appropriate safeguarding mechanism in place, in line with DFID requirements, and have periodic discussions. Delivery chain mapping undertaken along with risk mapping where appropriate.	Minor

Update on partnership principles (1/2 page)

DFID India’s 2015 Partnership Principles state that DFID India’s partnership is based on a shared commitment to:
- Helping India reduce poverty and leave no one behind as well as the delivery of other SDGs.
- Respecting human rights and other international obligations.
- Strengthening financial management and accountability and reducing the risk of misused funds through weak administration or corruption.
- Strengthening domestic accountability.

In accordance with these, PSSC complies with DFID India’s partnership principles and when funding is channelled through partner organisations this is done in accordance with these principles. Compliance is ensured through due diligence, financial audits and reviews.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Two EFOs with the World Bank and one MoU with the IMF SARTTAC were initiated in the programme in the reporting period. Constant engagement by the programme team, with the implementing partners, has led to high quality outputs and deliverables. With some assignments especially World Bank, this has meant repeated and consistent messaging and working very closely with them to ensure a high-quality output. The partnership with the IMF is at the early stage.

Spend is closely monitored and forecasts are regularly reviewed and uploaded on DFID’s programme and financial management systems (ARIES/AMP). Payments were made in the ongoing projects only after outputs undergo the mandatory quality assurance process by the SRO. The total project spend as on 31st January 2020 is £2.23m. Forecast for the financial year 2020-21 is £1.5m.

Date of last narrative financial report(s)	NA
Date of last audited annual statement (s)	NA

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The agreement arrangements are closely managed by the SRO and the task team. From a commercial perspective, financials are managed by the Programme Officer who ensures timely financial management and monitoring. All existing partnerships are working well. Regular progress of the partnership is managed through reports and informal meetings. The monitoring of the programme in the review period was undertaken through the following:

Regular meetings including formal and informal discussions with the World Bank and IMF carried out in their respective projects to review progress and payment-based deliverables.

This is a desk based Annual Review. The Annual Review was conducted by Narender Singh Kheparh, Programme Officer (and an interim SRO) and Sanjukta Roy, Governance Adviser with support from Adritha Subbiah, Energy and Green Growth Analyst. Monica Khanna, Programme Manager, Jaydeep Biswas, Senior Governance Adviser and Gaurav Kapoor, Team Leader reviewed the report and provided their inputs. Rajesh Kishan, Governance Adviser, DFID London has also reviewed the report and provided his inputs independently.

Evidence (1/2 page)

No formal evaluation was planned for the last reporting period.

As the programme develops further during its second year, it will be important to ensure that beneficiary monitoring arrangements are established and implemented effectively for each component. One option which the Programme Team could explore is whether in the absence of direct engagement with the state government stakeholders, whether the British Deputy High Commissioner network could be used more effectively to create an independent and more objective feedback mechanism and to forge direct relationships with state governments. In addition, the Programme Team should also consider whether and how beneficiary perspectives can be reflected in the governance arrangements.

Learning (1/2 page)

The learning for the first year of implementation is to have a better governance mechanism with the Multilaterals especially the World Bank to ensure better visibility for DFID and greater technical collaboration.

Progress on recommendations from previous reviews (1/2 page)
Not Applicable.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided