Annual Review - Summary Sheet
Title: Improving the Quality of General Education in Ethiopia
Programme Value: £130 million		Review Date: Updated in February 2016 / Review Period: April 2015 – Feb 2016
Programme Code: 203396	Start Date: 18 October 2013	End Date: July 2018

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	Moderate	Moderate

Main Acronyms Used
CEICT	MoE Centre for Education and ICT
EMIS	Education Management Information System
ECCE	Early Childhood Care and Education
ESDP	Education Sector Development Programme
GEQIP	General Education Quality Improvement Programme
GoE	Government of Ethiopia
JISM	GEQIP Joint Implementation Support Mission
MDTF	Multi Donor Trust Fund
MoE	Ministry of Education
MoFEC	Ministry of Finance and Economic Cooperation
QESSP	Quality Education Strategic Support Programme
PTAs	Parent Teacher Associations
SIP	School Improvement Programme

The Ethiopian General Education Quality Improvement Programme Phase II (GEQIP II) was approved by DFID in October 2013 to support the Government of Ethiopia’s (GoE’s) general education sector. It is a four-year (January 2014 - July 2017), £130 million programme with two components:
Component 1: £120 million to the GoE through a World Bank Multi-Donor Trust Fund (MDTF) to support the GoE’s GEQIP II. It is being implemented by the Federal Ministry of Education (MoE) across the country, working in 11 regions, 1000 districts, 20 universities, 36 Colleges of Teachers Education and 40,000 schools.

Component 2: £10 million to GoE’s Quality Education Strategic Support Programme Phase II (QESSP II), through the DFID-contracted fund manager (the British Council). QESSP is designed to maximise the impact of GEQIP II by providing support for research and evidence building, capacity building and technical assistance to the MoE.
GEQIP II is expected to contribute to improved learning conditions, institutional capacity for enhanced learning outcomes, student retention and learning achievements for more than 22 million children, of which half will be girls. By using a mix of instruments and working closely with Government of Ethiopia (GoE) and partners, the programme is expected to produce improved learning outcomes for students at grades 4, 8, 10 and 12 - scoring above the basic level in the National Learning Assessment, particularly for language and mathematics.
The total project cost for component 1 is about £377 million, of which £120 million is DFID’s contribution (about 32% of the total project costs). Other development partners contributing to the MDTF are Finland, Italy, USAID, and Norway. About £89 million is allocated by the World Bank and a further £69 million by the Global Partnership for Education (GPE).
Summary of progress and lessons learnt since last review
- Phase two of the GEQIP supports improvements in teaching and learning of more than 22 million children in more than 34,000 schools. Whilst teacher supply remains a constraint, GEQIP II is on track to keep more children in school and improve their learning achievements.
- GEQIP II grants are supporting School Improvement Programmes (SIPs) in all schools, focusing on improved teaching and learning, with special support for inclusive education and emerging regions.
- GEQIP II has now supplied 63 million textbooks, most of which are expected by MOE (in the February 2016 MoE Semi-Annual Report) to now be in schools, at a unit cost of only £0.40.
- 40% of schools have been inspected and ranked by the new inspectorate supported by GEQIP II
- GEQIP II has enabled more than 100,000 primary teachers to upgrade from Certificate to Diploma.
- Phase II of the Quality Education Strategic Support Programme (QESSP II) has provided technical support to the Ministry of Education (MoE) including for the launch of the fifth phase of Ethiopia’s Education Sector Development Programme (ESDP V) and for Capacity Assessments.
- Although the 2015 National Learning Assessment results have been delayed (as explained below), available data from last year’s grade 10 examinations shows 30,510 additional children sat exams (62% girls) and 118,990 additional students (57% girls) passed. We expect similar improvements to be reflected across the age groups.
Lessons Learnt
- Effectiveness of school-grant-supported SIPs in strengthening school-based management, teaching approaches and Parent Teacher Associations (PTAs), and support for inclusive education.
- Large-scale international competitive bidding takes time - up to 18 months - but with big savings.
- Importance of an effective inspectorate for sector monitoring.
- Capacity constraints in developing and implementing work plans and in procurement. This has been a problem since GEQIP I and is an area that QESSP is seeking to tackle.
Action on key recommendations from last annual review
- Procedure for issuing school grants has been revised and schools are now receiving grants on time.
- Preparations are in hand for QESSP II consultancy support to Education Management Information System (EMIS).
Summary of Recommendations for the next year
- Use the Inspection rating of schools as an indicator of education quality.
- Improve the extent to which reports identify ways of overcoming bottlenecks, and are then acted on.
- Encourage and monitor the effective use of textbooks.
- In the Mid Term Review, focus on teacher training, data and monitoring, and possibilities for extending support to Early Childhood Care and Education (ECCE).
- Work with DFID economists and other donors to begin discussions on a future handover to government of funding for the school grants and broader GoE financing in the education sector.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/

Outline of the programme
The Government of Ethiopia (GoE) launched the General Education Quality Improvement Programme (GEQIP) in 2009. GEQIP is an eight-year programme to help implement the fourth Education Sector Development Programme (ESDP IV). GEQIP provides resources to improve the quality of primary and secondary education. (‘General Education’ in Ethiopia also includes Early Childhood Education and Adult Education but these are not currently covered by GEQIP.) The UK contributed £95 million to the first phase GEQIP I (2009 – 2013) through a World Bank Multi Donor Trust Fund (MDTF).
GEQIP I resources, along with government and other donor’s contributions, focused on:
- Introducing school grants to support school-based development;
- Supplying 88 million high quality textbooks and teachers’ guides alongside a revised curriculum;
- A pre-service and in-service Teacher Development Programme (TDP); and
- Capacity building for Management and Planning (MAP) at all levels of the sector.
The second phase (GEQIP II) has introduced, alongside the above, support to the creation of a Schools Inspectorate and support to Information and Communications Technology (ICT) to improve the quality of education. DFID is providing £120 million to GEQIP II through the MDTF.
In addition, DFID provides technical support through a Quality Education Strategic Support Project (QESSP). The first phase (QESSP I) funded the secondment of a DFID Senior Education Adviser to MoE, consultancy and a research fund to support MoE in the design of GEQIP II. In the second phase of QESSP (QESSP II), DFID is providing £10 million, through a Fund Manager (British Council) engaged by DFID, to improve evidence-based programming and support capacity building. Focal areas for QESSP II include sector strategic planning, communications and monitoring and evaluation.
The business case assumes that this programme will contribute to the overall operational plan and DFID’s international development objectives (more children in primary school because of UK assistance) by quality improvements encouraging students to continue in school. As the EMIS annual statistics report for 2014/15 has yet to issue, there is insufficient evidence to assess this. However, the November 2015 Results Based Aid Independent Verification Report showed a significant increase the proportion of students sitting the secondary education certificate examination over the last year (i.e. staying in school long enough to sit the exam) and a significant improvement in their performance. Other aspects of the operational plan such us supporting a government-led programme continue to apply.
There was related, parallel support to districts through the DFID-supported ‘Promoting Basic Service Project’ (PBS). DFID support was withdrawn from this programme in December 2015. PBS provided flexible block grants for expanding and improving the quality of basic services in several sectors, including in education. PBS also provided capacity building, especially in financial management and citizen engagement. However, PBS does not form part of the programme being evaluated in this review.
The context has changed since the last review to the extent that ESDP IV has been replaced by ESDP V. The policy base remains the same, but ESDP V involves a more concentrated focus on a few, select important policy priorities, for example: capacity development for improved management; improving teacher quality; school improvement planning and quality assurance; developing core foundation skills including an expansion and quality improvement of Early Childhood Care and Education (ECCE); and reducing high primary drop-out and repetition rates. Apart from ECCE, these are all areas supported by GEQIP. We recommend that the GEQIP Mid Term Review examine the case for expanding GEQIP II into the ECCE subsector.
The second Growth and Transformation Plan (GTP II – 2015/16 -2019/20) has been finalised. For General Education, this emphasises: government capacity building for good governance and community participation; more support for adult education and expanding education in the emerging regions, including local teacher development; expansion of postgraduate training for teachers. Apart from adult education, which is beyond the scope and resources of GEQIP II, these are key features of GEQIP II and QESSP II. QESSP II will also help GoE to develop the 10 year Education Roadmap to achieve of the GTP goals.
The GoE is committed to the provision of high quality education for all, which is demonstrated by its high rate of investment in education (education spending accounts for about 25% of the federal budget) as well as the ambitious targets in the GTP II. All activities initiated by this project are in complete alignment with the ESDP IV and ESDP V and with the existing mandate of the various implementing agencies. This has insured the technical sustainability of the project.
Based on financing and results trends in the sector, it is anticipated that Ethiopia will near universal primary education, the rate of expansion will slow and the demand for additional teachers will reduce by the end of the GEQIP II period. This will free-up the GoE’s own resources for no-salary related expenditure such as instructional materials and school running costs.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome of GEQIP II is ‘Improved learning conditions and institutional capacity for enhanced learning outcomes’. This is currently measured by:
% of teachers showing student-centred teaching approaches.
There is no April 2016 milestone. The World Bank Project Appraisal Document (PAD) measures this indicator in terms of whether teachers ask questions in class. The December 2015 GEQIP II Joint Implementation Support Mission (JISM) agreed that this is not an appropriate measure of student-centred teaching, is not easy to measure and is not being measured.
The JISM recommended instead defining student-centred teaching as: (i) Teaching is well planned with appropriate resources; (ii) teachers having adequate knowledge of the subjects that they teach; (iii) teachers using appropriate and modern teaching methods to increase student participation; and (iv) teachers conducting appropriate assessment of student learning and giving appropriate feedback to students. These are being measured internally by schools and by the inspectorate. The JISM recommended defining and using an index for improvement in these four areas, which would then be used within the DFID logframe.
Visits to a sample of schools as part of this review showed teachers using student-centred teaching approaches effectively. But the inspectorate reports indicate that 91% of schools are, overall, below the expected standard. The measures put in place by GEQIP II, including ongoing support to the inspectorate, should lead to improvement in subsequent years. But this also depends on having a stable and motivated teaching force and this does not seem to be the case for most schools.
% of schools using at least half of their school grants allocation for the SIP teaching and learning domain (April 2016 milestone 50%)
This milestone has been greatly exceeded: schools have been clearly instructed, visits showed full adherence, and there is no evidence that any schools have deviated from this.
% of Parent Teacher Associations (PTAs) positively involved in the management of school grants (April 2016 milestone 80%)
Evidence to date suggests that all PTAs are involved as per the guidelines and training provided to schools. Schools were instructed in this and our visits confirmed PTA involvement including minutes.
% of pilot secondary schools using Information Communication Technology (ICT) for learning (April milestone e-content developed).
Work has recently started on e-content with the Korean International Cooperation Agency (KOICA) and QESSP II support.

Overall output score and description
A: Outputs meet expectation

Key lessons
- Discretionary school grants linked to SIPs are effective in strengthening school-based management and PTA involvement. They also contribute to improved teaching and learning.
- Large-scale international competitive bidding takes time but is worthwhile when it yields big savings. .
- The new inspectorate is efficient in acquiring information and identifying failing schools, and in providing feedback to support teacher development, school development and quality control.
- Inefficiencies in the Education Management Information System (EMIS) lead to problems in planning.
- Delays caused by capacity weaknesses in developing and using GEQIP II work plans, especially within universities; also by procurement constraints, especially within the Information Communication Technology component.

Key actions
- Provide urgent QESSP II support for EMIS.
- In preparing for the Mid Term Review, pay particular attention to: (a) the efficiency of the Teacher Development Programme (TDP); (b) monitoring in terms of information flow and indicators, especially the potential of the Inspection rating of schools as an indicator of education quality; and (c) to consideration of including ECCE in the final stages of GEQIP II.
- Ensure key evaluative studies are built on, notably via the Mid Term Review. This includes the TDP impact study and the study of teacher supply and demand.

Has the logframe been updated since the last review?
- The March 2015 Annual Review recommended replacing one of the indicators for textbook printing and distribution with: ‘the % of schools inspected each year’. However, on further reflection, both textbook indicators were felt to be useful. The new framework has, therefore, added the inspection indicator but also retained both textbook indicators.
- The previous Output 3 indicator on SIP guidelines has already been achieved and doesn’t need monitoring. It has, therefore, been replaced by the following: ‘% of schools receiving training on linking SIP with improved student learning’.
- For strengthening education and management, the following additional indicator has been added: ‘number of researches conducted/innovations and relevant interventions identified, designed and implemented by the Regional Education Bureaus (RBEs) and MoE’. This is a key aspect of QESSP II that needs monitoring.
- The indicators of the Information Communication Technology (ICT) component relating to ICT policy and infrastructure have been replaced by the following indicator that is being monitored by MoE: ‘Universities using ICT competency based framework for teachers and to support teachers’ professional development’. This is more relevant than the previous indicator to raising the quality of education.
A ‘quality of reporting’ criterion has been added to the milestones for inputs to the GEQIP II annual planning exercise, as this is the essential aspect of these inputs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved curriculum, textbooks and inspection
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Ratio of number of students to number of subject books distributed to students	1:0.8	MoE annual report to June 2015 shows the ratio of 1:0.9; no later figures are available. The Regional Education Bureaus (RBEs) and schools visited in Addis Ababa, Amhara and Oromia estimated an overall book ratio of at least 1:1 for at least the main school subjects. The main book procurement had not yet reached schools in Afar. / (Indicator Score: A)
Number of textbooks and teacher's guides (based on new curriculum) distributed to schools (cumulative)	30 million	More than 63 million textbooks of different subjects and grades (more than 90% of the project plan) have been successfully procured, and according to the MoE report 12,368,738 have reached schools to date. / (Indicator Score: B)
% of schools inspected each year	40%	Overall 44% of schools were inspected, and all districts achieved at least 20% of schools inspected. / (Indicator Score: A)

Key Points
- Support to the creation of an inspection system has been a major achievement of GEQIP II. There is now a strong, trained inspectorate that by 2016 will have visited and rated schools on a 4-point scale. Only 2 schools attained the top category 4, whilst 91% were in categories 1 and 2 – i.e. less than satisfactory. Category 1 schools (26% this year) undertake a retest. Schools also undertake self-assessments against the same criteria. Some regions have the inspectors based in autonomous agencies reporting directly to the Regional Council. This enhances transparency and has led to follow-up by the Regional Council. The rating provides an excellent education quality indicator and the reports are a valuable source of other data, and enable triangulation of EMIS data.
- On the negative side, the International Competitive Bidding (ICB) procurement process for textbooks took around 18 months. (This is not unusual globally for such procurements and the World Bank Project Appraisal Document assumed 15 months). On the positive side, this ICB procurement made a £17 million saving: the average price for 63 million textbooks was £0.40 compared with more than £0.75 for GEQIP I. The issue now is ensuring effective use of the textbooks.
- Bids have been launched for Braille books and supplementary readers.
- GEQIP II is supporting National Learning Achievement (NLA) tests, including the creation of 5,700 test-bank items (i.e. a bank of questions that can accessed randomly to help the reliability of the tests). The 2011 and 2015 test results, and the comparison between them, are currently being analysed and are likely to pose useful guidance on efforts to raise the quality of education.
Summary of responses to issues raised in previous annual reviews
The March 2015 Annual Review recommended the cancellation of one of the indicators for textbook printing and distribution and replacing with the following: ‘% of schools inspected each year’. However, on further reflection both textbook indicators were felt to be useful. The new framework has therefore added the inspection indicator but also retained both textbook indicators.
Recommendations
Use the Inspection rating of schools as an indicator of education quality.
- Use an index based on the inspection reports to measure student-centred teaching.
- Encourage and monitor the efficient distribution and effective use of textbooks or reconsider a more realistic milestone at the next Annual Review.
- The impact rating should be raised to 20%, as the inspectorate is likely to have much more impact than previously envisaged.

Output Title	Strengthened teacher training programme
Output number per LF		2	Output Score	C
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Number of teacher trainees completing programmes with updated curricula (% female) / Number of Alternative Basic Education (ABE) Facilitators upgraded each year	28,000 / (35% female) / 1,200	100,000+ primary teachers are taking diploma-upgrading courses. No gender figures exist for colleges but for universities 33% of the intake is female. Not all courses have updated curricula. Review due in 2016. / GEQIP II is not currently funding upgrading courses for facilitators. There have been consultations on minimum standards. / (Indicator score: C)
No. of teachers licensed (cumulative)	40,000 / (50% female)	76,000 (57% female) primary teachers and 15,000 (15%) of secondary have taken the written test. Initial results show fewer than half met the standard. However, no teachers have been licensed because of delays in the teacher performance assessment tools. / (Indicator score: C)

Key Points
- Despite the high number of teachers taking diploma-upgrading courses, the first output indicator scored ‘C’. This is because the updated curriculum was not used by all the colleges of teacher education. Similarly, under the second indicator, no teachers in the system have been licensed or received a licensing certificate as the MoE is still struggling to put in place the performance assessment tools.
- This component is over-budget, yet capacity constraints in planning and implementing GEQIP work plans have led to serious delays in many key areas. These include: updating teacher education curricula; Alternative Basic Education (ABE) facilitator training; implementing a structured system for continuous professional development; clarifying the role of English Language Improvement Centres; an action plan for science and mathematics; identifying a centre of excellence; and finalising teacher licensing. Some of the universities involved have a very low fund disbursement rate.
- The Teacher Development Programme impact study reported as in preparation in the last annual review has not gone ahead, again due to constraints in planning capacity. It is to be reconsidered during the Mid Term Review.
- To help with some of these problems, QESSP II will provide analytical and capacity-building technical support to the MoE TDP Department.
- The teacher-licensing programme should eventually be very important in restricting the teaching profession to those competent to teach. But that will require the process to be compulsory even for existing teachers; at present it is voluntary. The need to measure performance – the reason for the current delay - is crucial, but should not be taking so long to develop. The fact that half the first group of teachers examined were below standard shows the importance of this subcomponent.
- The licensing directorate lacks the technical expertise that is required to develop the performance assessment tools or implement them. Since there are no licensed assessors locally, it is not clear who should undertake performance assessment. While a large number of prospective teacher trainees were being identified, tested and provided admission into a college or university, the drop-out rate at each stage, even after being admitted into an institution, was extremely high. Such a high attrition rate not only has an impact on the cost of teacher selection but on the ability of the MoE to effectively match teacher supply with demand. It also limits the ability of teacher education colleges and universities to efficiently plan.
- The main problem is the low status of the teaching profession, linked to low pay, and the consequent low level of applicants and high turnover. QESSP is examining this through a study of “Analysis of Teacher Demand and Supply Gap in Ethiopia: Magnitude, Determinant Factors and Possible Remedies”. GEQIP II includes a study of cost-effectiveness of the selection process.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Due to capacity and communication constraints, no action has been taken on tracking and reporting to Development Partners the percentage of teacher training delivered through the new curriculum.
- The budget implication of the new universities providing secondary teacher training programme were taken into account, but not all are making full use of the budget.
- The QESSP II study of teacher supply and demand should enable MoE to re-think its teachers selection strategy to encourage applicants as well as increase female participation.
Recommendations
- Ensure thorough Teacher Development Programme (TDP) impact study is undertaken and feeds in to future TDP strategy.
- There should be closer monitoring of universities and a full analysis of this component in the GEQIP II Mid Term Review to improve the approach to teacher development in the second half of GEQIP II.
- The MOE needs to decide who should do the performance assessment and QESSP needs to support this if there is a capacity gap in making this to a reality.
- Drop the second indicator for the next Annual Review if GEQIP II is not funding the upgrading courses for ABE facilitators. This indicator should be replaced with an indicator that measures teachers’ performance.

Output Title	Improved school improvement programme including provision of school grant
Output number per LF		3	Output Score	A++
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% of schools receiving school grants in October every year.	40%	This milestone has been greatly exceeded. There has been a major improvement in the provision of the grants with 70% of schools receiving them before the end of October. / (Indicator Score: A++)
% of schools receiving training on linking SIP with improved student learning	50%	All schools have received training and have ensured that at least 50% of the grant is linked to improving student learning. / (Indicator score: A++)

Key Points
- There were major delays in previous years in the timely disbursement of the school grant. There were cases where schools only received the grant by the end of the academic year, which made spending by the end of the year very challenging. This contributed to the low fund utilisation of the programme in the previous years as the school grant took the lion’s share of the project budget.
- There has been a dramatic improvement in the timeliness of disbursement of this third school grant under GEQIP II from federal to the regional levels and to schools. This has been achieved by delinking calculations from the annual work plan of other GEQIP II components, as recommended in the March 2015 Annual Review. There has also been a major emphasis by Regional Education Bureaus (REBs) on ensuring adherence to guidelines, a concern raised in the Ministry of Finance and Economic Cooperation (MoFEC) audit of the previous, 2014-15, school grant.
- This component is now efficiently supporting school-based management through the preparation and funding of school-based strategic and annual improvement plans in all schools. These plan focus on teaching and learning, developed with the PTA and are monitored through school self-assessments (with the PTA) and by supervisors and inspectors. Those interviewed saw the grants as the key contribution of GEQIP II. Many countries have found effective school-based management, linked to continuous professional development of teachers, to be key to improving the quality of education. A school-based approach is particularly important in the present context of high staff turnover.
- The focus in GEQIP II is on using school grants for improving learning achievement through additional learning materials such as textbooks, supplementary readers, and charts, laboratory equipment, teachers’ reference books, educational media etc.
- 1% of the grant is reserved for inclusive education measures such as provision for those with impaired vision or hearing and physical disabilities. Anecdotal evidence from visits suggests that this may not be sufficient to cover these needs, though data on student needs is very weak.
- MoE report that water, sanitation and hygiene (WASH) issues form a major use of the funds not allocated to teaching and learning.
- The major concern over this component is that, whilst it is now built into Ethiopia’s system for managing schools, there is no direct government funding for these grants. It will be disastrous if funding ceases at the end of GEQIP II. Given that this was also a key part of GEQIP I, preparations should now be underway to move at least gradually to GoE funding of the grants.
- Addis Ababa Education Bureau notes that their region is disadvantaged in the funding formula as the population growth rate is much higher than for other regions. On the other hand, there may be more opportunity in this region for parental support and possibly lower costs in using the grant.
- The SIP Directorate conducted a number of Training of Trainers (ToT) activities for participants selected by regions, including on SIP framework, on revised school grant guidelines and on decision- making during SIP preparation. Cascading the training in the regions is ongoing. So far 36,095 school principals were trained.
- Simplified SIP frameworks for Alternative Basic Education Centres (ABEs), the School Based Management manual, and Reading Clubs’ guidelines to encourage reading activities in schools were approved by the MoE and are ready to be disseminated to regions.
- The World Bank is ready to disburse a second school grant tranche under GEQIP II to drought –affected schools but only when the MoE and MoFEC confirms the effective utilisation of the grant disbursed in the first tranche.
- Joint activities by SIP and inspection directorates include joint monitoring and evaluation visits, as well as collection and dissemination of the best SIP and inspection practices.
Summary of responses to issues raised in previous annual reviews (where relevant)
- As noted above, school grant calculations have been delinked from the annual work plan of other GEQIP II components, as recommended in the March 2015 Annual Review.
- Standard MoE templates and a revised guide for preparing School Improvement Plans are in use in schools as recommended in the September 2014 and March 2015 annual reviews. Associated training has been given to all schools.
Recommendations
- Work with DFID economists and other donors to begin discussions on a future handover to government of funding for the school grants and broader GoE financing in the education sector.
- Develop data on inclusive education needs and consider whether more funding is needed.
- Consider, on equity grounds, whether to amend the funding formula to take account of variations in population growth rates.
- Consider in Mid Term Review whether to extend grants to ECCE (Early Childhood Care & Education).
- The milestones for both the indicators greatly exceeded expectations this year. The indicators / milestones should be revised for the next annual review. Indicators linked to the SIP activity in improving school performance in coordination with the inspection directorate could useful.

Output Title	Strengthened education management and administration
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
No. of supervisors and directors exposed to quality and relevant short term leadership training annually (%female)	1000 (females 20%)	22,000 trained. (Female proportion unknown). / (Indicator Score A+)
No. of capacity building proposals supported by QESSP II	6	9 areas of capacity building work have received or are receiving consultancy support from QESSP II, plus an overseas visit to the World Economic Forum support to ESDP V and preparations for the 10 year roadmap / (Indicator score: A+)
No of researches conducted/innovations and relevant interventions identified, designed and implemented by the REBs and MoE (cumulative)	5	An Organisational Capacity Assessment was undertaken and 6 country studies are underway / (Indicator score: B)

Key Points
- The reason for the very large number of supervisors and school directors trained is a major initiative undertaken by Amhara REB. Other regions do not have clear plans for leadership training. A clear framework is needed.
- QESSP II started later than intended – in March 2015 – but has already provided a key Organisational Capacity Assessment, supported the development, translation and communication of ESDPV, and has undertaken preparatory work for the 10-year road map.
- One crucial piece of QESSP-supported research will be the study of teacher supply and demand.
- QESSP is acting as secretariat to the Education Technical Working Group (ETWG)
- There has been a more rapid take-up of capacity building and research than anticipated: the number of capacity-building proposals has exceeded the anticipated 6.
- The 2014/15 Education Statistics Annual Abstract has still not been released. It is being held back because of suspected inflated numbers for Somali Region. (There are systems in place nationally to verify data visits by district and regional statisticians, supervisors and inspectors but extra support and a survey were needed for the Somali Region). This is a one-off delay.
- The Regional Education Bureaus (REBs) visited reported that the Education Management Information System (EMIS) software is no longer compatible with some of their information needs.
- DFID, the World Bank, Finland and UNICEF are working together to give comprehensive support to the EMIS directorate. A terms of reference has been drafted and approved to mobilise a national consultant to the EMIS directorate.
Summary of responses to issues raised in previous annual reviews (where relevant)
Despite some significant training, there is still no 2014/15 EMIS annual report. The need remains to identify and respond to the remaining EMIS capacity constraints and enable timely reporting of education data. The scope of QESSP II support to this area has been agreed.
Recommendation
- MoE should consider QESSP II support for the development of a strategic approach to planning for leadership training and management capacity building at regional, district and school levels.
- MoE should consider releasing the EMIS annual reports on time even when the data is suspect (with a note to this effect against the suspect data).
- Add, as an additional logframe indicator, the following GEQIP II Results matrix indicator: ‘Timeliness of disseminating education statistics annual abstract’. The target date should be October.
- Examine how the information transmission and verification process can be made more efficient, including an assessment of the software currently being employed.
- The impact rating should be increased to 20% given the increased strategic importance of QESSP II.
- The review recommends amending the milestones for indictor 1 and 2 for the next annual review.

Output Title	Improved use of Information Communication Technology (ICT) to enhance the quality of education
Output number per LF		5	Output Score	B
Risk:		Severe	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Universities using ICT competency based framework for teachers and to support teachers’ professional development	Development of a competency based framework for the teachers and the eLearning materials for the students	The MoE Information Communication Technology Department (CEICT) is arranging workshops for universities, teacher colleges and others in partnership with the Teacher Development Department / (Indicator score B)

Key Points
- This component has been slow to start and has developed less strategically than originally envisaged. Part of this has been a problem with arranging the necessary procurement for technical support, training and equipment; also general capacity constraints in regard to developing the necessary work plans. It is questionable how much this component will contribute to improved quality in schools by the end of GEQIP II compared with the inspectorate, textbook supply and improvements in management and leadership. It is therefore recommended that the logframe impact weightings be amended accordingly.
- The teacher professional development component of this output is just starting.
- The current emphasis is on collecting and developing eLearning materials for schools. Korean International Cooperation Agency (KOICA) has supplied a technical adviser.
- A situational analysis of ICT in schools will be undertaken in April. This should be helpful in supporting future policy and showing the present role of ICT in improving the quality of education.
- The equipment contract has also been signed for the ICT pilot in 300 secondary schools throughout the country. The schools have been chosen to ensure they have electricity and internet access, rooms for computer labs, etc. and in proportion to the secondary schools in each region.
- An ICT policy adviser is currently being recruited who will also advise on future institutional arrangements for ICT in schools.
- The Ministry of Communication and Information Technology have supplied the basic software for the mobile phone/tablet pilot in 6 schools in emerging regions, for which e-content is now being developed with the help of the KOICA adviser.

Summary of responses to issues raised in previous annual reviews (where relevant)
- CEICT now has international technical support in place through KOICA.
- The need still exists for the MoE to identify lessons learnt and good practice (and failures) from other African countries and factor these into the ICT policy and implementation strategy. The policy adviser needs to be guided and monitored in this regard.
- The situational analysis to be undertaken in April includes an assessment of maintenance in terms of both the availability of technical expertise and budget.

Recommendations
- Ensure the ICT situational analysis feeds in to the policy development in a way that enhances the role of ICT in improving teaching and learning in schools.
- As this component is relatively new, there is a good reason to give more time to demonstrate the transformative effect it could have despite the slow start. It will be important to review this component as part of the mid-term evaluation and reconsidered at the next Annual Review.
- Given that the ICT programme is developing more slowly and less strategically than envisaged in the business case, the impact weighting should be reduced to 5%.

Output Title	Improved co-ordination, monitoring and evaluation
Output number per LF		6	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% Implementing Agencies providing timely inputs to GEQIP annual planning exercise and GEQIP six monthly reports	60% with good quality	There was 100% involvement from implementing agencies in the annual planning process. The annual progress report was reasonably complete in reporting on all activities, though in some cases with insufficient clear analysis of progress made on the delivery of planned activities. Also there was relatively little analysis of the problems encountered and especially of how they would be tackled. / (Indicator score: A)
Evidence base on impact of reforms aimed at improving the quality of education	There is no 2016 milestone, (only the 2016 Mid Term Review to be reported on in the next Annual Report)	The recently produced NLA results will provide some evidence on impact

Key Points
- The GEQIP II and QESSP II core contracted staff are now all in place.
- The GEQIP II coordination office is following up with communications and visits to try to ensure arrival and proper utilisation of funds as well as implementation of work plans. Joint Implementation Support Missions are carried out every 6 months. QESSP II is also helping MoE in regard to coordination and communications.
- Nevertheless, as noted in the last annual report, monitoring and evaluation is proving a challenge, in particular in access to accurate data, and in identifying and dealing with bottlenecks.
- The World Bank and Amhara region carried out a 3-day consultative meeting with wide participation to review performance for the Teacher Development component and set the basis for the next annual plan.
- Some key studies have either been completed or are in preparation that help in the evaluation of the programme and should be built on for future planning. These include: the QESSP II study of teacher supply and demand; the QESSP II organisational capacity assessment and plans for a GEQIP II Comprehensive Evaluation.

Summary of responses to issues raised in previous annual reviews (where relevant)
The milestone of the first indicator has been amended to focus on quality rather than just quantity and timeliness of information. The quality of reporting has improved, but more analysis is needed on how bottlenecks are to be tackled.

Recommendations
- Improve the extent to which reviews, visits and reports identify bottlenecks, identify ways of overcoming them, and ensure these are acted on.
- Ensure that key evaluative studies are built on, notably through the 2016 Mid Term Review.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Performance on the key cost drivers for GEQIP II is as follows:
Cost Driver	% of / budget	Change in 2014/15	Action
Cost of school grants	45%	No change	None
Teaching/learning materials	19%	Lower unit cost – around £17m saved	Saving used for more books
Pre-service teacher training	3.6%	More teacher updating, increased cost	Prepare for cost over-run
In-service training	5.4%	No change	None
ICT infrastructure	5.2%	Slow procurement, may be savings	None as yet

The school grants are flexible in that schools can use them as they see fit within overall guidelines. Thus it is not possible to determine the expenditures beforehand and then seek ways of reducing the cost. Instead, guidelines are used to ensure the grants are used appropriately, focusing on teaching and learning, and with a negative list of prohibited purchases. It may be possible in a later review to explore ways of combining purchases for a number of schools to reduce costs.
The budget for teaching and learning materials is below that needed for an ideal quantity and range of teaching and learning materials. The large reduction in cost obtained this year through International Competitive Bid (ICB) helps by allowing more materials for the same budget - increasing cost effectiveness.
There is no change as yet in the cost of in-service training. The pre-service teacher-training budget is likely to increase, partly as a result of increasing the amount of teacher updating. The main Information Communication Technology (ICT) procurement has only just been agreed and it is not clear as yet whether there will be savings.

VfM performance compared to the original VfM proposition in the business case

The business case assumed that the overall impact of GEQIP II alongside other developments would effectively add the equivalent of 1.5 years to a student’s primary and secondary school career. That is to say, there would be an increase in learning per student of, on average, 15% per year over a 10-year period which is the period for which inputs such as textbooks could be expected to last. Given the absence of up-to-date education statistics, it is not possible to say whether this assumption remains realistic. .
However, the following Economy, Cost-Effectiveness and Efficiency VfM indicators show an overall significant improvement in value for money though there are still problems with regard to efficiency of procurement. These indicators were proposed in the September 2014 annual review and are based on the DFID Human Development Programmes VfM framework.
1. Average cost per textbook (a measure of Economy): The latest ICB procurement of printing and distribution of 63 million textbooks had a unit cost of only £0.40, well below the unit cost of £0.70 for GEQIP I and for most sub-Saharan African countries (Tanzania £1.5, Kenya £2.43)
2. Total cost per primary teacher trained (a measure of Economy): The WB Education Sector Financing Review gives the annual per full-time student cost at a College of Teacher Education (CTE) in 2012 of £354 which is well below the £475 assumed in the business case.
3. Average price of computer labs installed and operational in secondary schools (a measure of Economy): Specific data for this is not yet available. The contract for installing 2 labs each in 300 schools, plus national infrastructure for supporting this, was expected in the PAD to cost £18.8 million. This could be considered as a cost per lab of £31,300. However, given the likely high cost of national infrastructure overheads, the threshold cost of an additional laboratory would be far less.
4. Cost per primary pupil educated (a measure of Cost-Effectiveness): The WB Education Sector Financing Review shows a unit cost of £13 in 2012/13. This is below the £20 assumed in the business case for primary pupils and that in similar African states, e.g. £42 in Tanzania.
5. Procurement processes completed on time (a measure of Efficiency): The 18 months taken for the main ICB textbook procurement was a major cause of the project underspend in 2014/15, albeit in keeping with international norms for such contracts. ICT procurement is well behind schedule.
6. Receipt of school grants - speed of delivery by system (a measure of Efficiency): There has been a very significant improvement, with most schools receiving the grants early in the school year.
Assessment of whether the programme continues to represent value for money

GEQIP II is central to delivering Ethiopia’s Education Sector Development Programme as it addressed the key challenge of the sector (deteriorating educational quality in Ethiopia) by investing on textbooks, teachers training, school grant, etc. The Theory of Change remains valid and it continues to represent value for money as revealed by the cost per textbook purchased, cost per teacher trained, cost per pupil educated and performance over other cost-effectiveness indicators of the programme.

As it has been clearly indicated in the Business Case, GEQIP is using the government system to deliver results. This in turn strengthens the GoE systems including the procurement, financial systems. QESSP II mobilised national and international consultants, which will help the technical people at MoE to learn and share best national and international experiences to strengthen the system and deliver more.

Quality of financial management

The December 2015 Joint Implementation Support Mission (JISM) concluded that the borrower and the implementing agencies maintain financial management system that are adequate to support project implementation and provide accurate and timely information regarding project activities. However, certain areas were found to need improvements, actions, and follow up, and the risk remained unchanged as ‘substantial’.

This annual review also takes on board the recommendations of the 2015 DFID Internal Audit, the 2015 GEQIP II Audit of School Grants by Ministry of Finance and Economic Cooperation (MoFEC) and the World Bank’s response to this, plus the 2015 National Audit Office (NAO) of DFID.
In regard to the DFID Internal Audit:
- DFID has managed Fiduciary Risk by monitoring the implementation and effectiveness of the World Bank safeguards and risk mitigation measures. All narrative and reporting requirements have all been adhered to.
- The March 2016 MoFEC Interim Financial Report (IFR) showed that GEQIP II had, by January 9 2016, disbursed 36% of its available resources: US$196 million of the total commitment of $550 million. The project had utilised and documented 84% of this (US$164 million), with an 88% disbursement rate for regions, 70% for MoE and 71% for universities. The 2015 year ending balance was half that at the end of 2014.
  - Improved utilisation, especially by regions, has mainly been a result of improved release of school grants, with 70% of the 2015/16 grants arriving in October as intended, and others soon after.
  - The lower disbursement rate for MoE is mainly due to ‘late’ completion of textbook procurement. The funds were scheduled for expenditure in 2014/15 in order to have the budget in place for the International Competitive Bid (ICB) process to begin. But the process took more than a year (which the World Bank sees as normal globally) so the expenditure is actually taking place in 2015/16.
  - Low utilisation of funds by the universities remains a problem. 3 of these universities have a rate below 40%. These are universities new to GEQIP II. The report states that ‘MoE with other stakeholders should continuously and persistently monitor and control these universities’. DFID will liaise with the World Bank and MoE on this and ensure that significant funds not utilised by some of the universities are returned for use elsewhere on the programme. There is also space to discuss this issues during the Mid- Term Review of GEQIP II, which will be carried out by end of June 2016.
  - Problems have been caused by EMIS delays, which need avoiding in future – school grants had to be based on previous data increased by the national average increase in the school age group.
The project has an original financing gap of £51m. This financing gap has now increased to £80 m due to two factors: (i) reduction in financing commitment of some development partners; and (ii) significant expansion of the teacher upgrading programs. MoE is seeking additional resources, especially from the Global Partnership for Education, and is committed to covering any residual shortfall in later years of GEQIP II. There has been no evident impact of the closure of DFID support to PBS III.

In regard to the NAO Audit, distribution of textbooks to schools appears to be proceeding satisfactorily. Also, schools have now received, and are working to, guidelines for the school grants.

The MoFEC Audit Report on the 2014-2015 school grants highlighted several issues such as use of incorrectly formatted cashbooks, some schools not having a separate bank account for the GEQIP grants, some schools not collecting grants at the time available, problems with financial reporting and asset registers and inadequate visits to schools by district Finance and Economic Cooperation staff. The World Bank response included a request to MoFEC for a detailed follow-up action plan. Discussions with Regional Education Bureaus and schools indicated that much more attention has been paid to training for and implementation of guidelines for the latest, 2015-2016, school grants.

The total project cost, including contingencies, is $550 million. GEQIP II funds constitute pooled financing from various sources, including the development partners (DFID, Finland, Italy, USAID), International Development Association (IDA), and the Global Partnership for Education (GPE).

Since the project started in January 2014, DFID made two disbursements twice totalling £76 million. The table below summarises the expenditure apportionment until the quarter ending January 9, 2016.
Expenditure Apportionment
Amount transferred to the Designated Account (USD)	Total amount Documented (USD)	Balance to be documented (USD)
$195,663,486.16	$166,519,247.79	$29,134,273.38

Date of last narrative financial report	GEQIP II Interim Financial Report (IFR) for second Quarter ended January 09,2016 submitted to the WB on March 24/2016
Date of last audited annual statement	January 2016.

## E: RISK
Overall risk rating: Moderate

Overview of programme risk

All risk matrix controls/mitigation actions are in place (including, for example, the World Bank checking social safeguards) and there are no new risks.

The first delivery risk is slow utilisation of funds. As noted in the previous section, the two main causes of slow utilisation - delay in the major textbook procurement and in the 2014 release of school grants – have now been resolved and the spending should be more in track next year. The December 2015 Joint Implementation Support Mission (JISM) recommended that, from Jan 2016 onward, monthly reports should be compiled of immediately available funds, or cash at hand, by all implementing agencies to be submitted to MoFEC, MoE and World Bank to enable the delays/ bottleneck in disbursement to be addressed. A good number of regions are now reporting monthly to MoEFC.

There is an increased funding gap (delivery risk 1.3). The project has an original financing gap of £51 million. This financing gap has now increased to £80 million due to significant expansion of the teacher upgrading programs but expectations that it will be significantly reduced using Global Partnership for Education funding. There is also a sustainability risk from the fact that there is no government funding for the school grants and this should be considered in the Mid Term Review.

Severe drought has not yet led to a diversion of GEQIP II resources (delivery risk 1.4). However, 50% of the schools in Afar opened late because of the drought and around 1.2 million children needed food assistance, which is likely to impact on student achievement. The World Bank has asked MoE if the school grant should be increased for affected schools but MoE have not yet requested this.
December 2015 Joint Implementation Support Mission (JISM) included a social development report and recommendations for taking forward a social action plan.

The December 2015 JISM concluded that the borrower and the implementing agencies maintain financial management system that are adequate to support project implementation and provide accurate and timely information regarding project activities. However, certain areas were found to need improvements, actions, and follow up, and the risk remained unchanged as ‘Medium. There appear to be no reputational risks.
Outstanding actions from risk assessment
Given that the bulk of the textbooks have now been delivered, the risk for Output 1 has now been reduced to Moderate.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe

Neither the GEQIP II Business Case nor PAD provides a timescale other than the start and end dates of the project, and, apart from end date, the schedule for QESSP II is indicative. No major components of the project (i.e. ones likely to have a significant impact on outcomes) are off track to the extent that they are unlikely to be completed by the end of the project. However, a number of minor components (with low impact on outcomes) may not be completed (e.g. assessment of new curriculum and strengthening English Language Improvement Centres). The Mid Term Review will examine this issue and whether some of these minor components should now be dropped from the project.
Performance of partnership (s)
Formal partnerships and contacts have been enhanced through the QESSP II Steering Committee, chaired by the Minister, and from QESSP II support for ESDP V and planned support to the roadmap.
Contributions by financing partners have been good. DFID, the Embassy of Finland, Italy the World Bank and Global Partnership for Education (GPE) have maintained their commitments though there has been a reduction in funding from the USAID and the Italian Development Cooperation. Norway has joined the MDTF with €6 million.
The flexible nature of QESSP II is enabling us to be more responsive in regard to supporting evidence-based policy-making and planning, and capacity building.
Reference was made to the Promoting Basic Services Project in relation to the low teacher absenteeism (12%) but low ‘time on task’ in the classroom; also the overlaps with WASH and potentially health sectors, especially for ECCE. There is scope for strengthening interaction between DFID-supported interventions in education and in other sectors, notably the health sector, especially in emerging regions.
Asset monitoring and control
All GEQIP II assets are governed by the Ethiopia’s public finical management systems. The QESSP II Fund manager has a well-organised assets register system. All assets from the project so far have been captured by the assets register system and DFID conducts asset spot checks bi-annually, including surprise checks, and the outcome of the check will be acted upon and documented.

G: CONDITIONALITY

Update on partnership principles (if relevant)

DFID’s Programme Partnership Arrangement (PPA) judged that there is no new or additional information since the country level PPA was conducted and judged that the Government has shown strong commitment to improving education services and there was sufficient evidence of their commitment to the partnership principles to allow DFID’s 2015 disbursement to the Multi Donor Trust Fund.

Another programme level PPA will be completed before the next disbursement in June 2016, which will consider any change in context in Ethiopia which may impact upon our partnership.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evidence acquired from reports, visits, studies and other sources indicate that the Theory of Change and its assumptions are still relevant. However, as highlighted in the new ESDP V, there is increased realisation within GoE and DPs of the importance of ECCE in equitably improving the quality of education in Ethiopia.
Data from the education inspectorate, created with the support of GEQIP II, will contribute to a wider evidence base. The QESSP II study will also contribute, especially on teacher supply and demand and assessments of children with disabilities in applying the 1% of school grants allocated to inclusive education.
A format has been developed, with training in its use, for financial and physical reporting by GEQIP II focal persons of all implementing agencies and by Regional Operation Officers. A monthly procurement process checklist has been developed for monthly, timely procurement to identify and deal with bottlenecks.

MoE provided an Annual Progress Report in August 2015 and Semi-Annual Report in February 2016. But there is still insufficient gender disaggregation of data in MoE reports. The World Bank is giving technical support to improve the quality of planning and reporting for the MoE staff.
DFID took part with GoE and other GEQIP II partners in two Joint Implementation Support Missions - one in June 2015 and the second in December 2015, including field visits in Amhara and Southern Nation and Nationalities People regional states. The two missions reviewed GEQIP II progress by component and provided support to resolve key technical issues; including timely disbursement of school grant, school inspection and sound budget utilisation; and carried out a procurement and financial management review. Both missions discussed and agreed with the government essential actions and milestones that need to be delivered to achieve the expected results from the project.
Based on the action points, an international consultant has been contracted to investigate the implementation of the school inspections in some regions and to gain an updated picture of the progress made by MoE in managing the inspection system across the country.
DFID will take part with MoE and other GEQIP II partners in the upcoming Mid Term Review, which will take place starting from end of June 2016. It is expected that the Mid Term Review will look closely at how GEQIP II has progressed in the last two years and will identify areas that need further support. It is expected that there is a possibility of supporting the government in the area of ECCD to make the support from GEQIP II more comprehensive.

Monitoring progress throughout the review period

The annual review team comprised Rahel Yergashewa (DFID-E Education Adviser), Moltotal Mekuria (Programme Manager) and Education Development Trust Consultant Digby Swift. Besides examining all relevant documentation and reports, the review team carried out interviews with MoE, MoFED, World Bank and the Embassy of Finland in Addis Ababa, and visits to Addis Ababa, Amhara, Oromia and Afar Regional Education Bureaus and schools. The team also consulted with the DFID Head of Office, DFID Ethiopia Human Development team members and economists.
This review has been quality assured by DFID E’s Operational Excellence Team and Robert Stansfield (DFID – E Acting Human Development Team Leader and Senior Responsible Owner (SRO) for the programme).
Their comments have been incorporated.

A number of key documents were also consulted as part of this review including:

1. GEQIP BC and Logframe
2. Ethiopia GEQIP II World Bank first and second Implementation Support Missions – Aide Memoires – July 2015 and December 2015 respectively
3. DFID Internal and External Audit reports
4. Government January 2016 Audit report and School Grant Audits reports
5. MoE GEQIP II annual and bi annual reports