Annual Review – post April 2018

Title: Women for health: Empowered Female Health Workers in Northern Nigeria
Programme Value £ (full life): £35.7m		Review Date: February 2020
Programme Code: 202694	Start Date: Nov 2012	End Date: Oct 2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A+	A	A	A	A+	A
Risk Rating	Medium	High	High	Moderate	Moderate	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717189.odt
DevTracker Link to Log frame:	45548110

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

Women for Health (W4H) is an 8 year, £35.7m programme implemented in 6 Northern Nigerian States (Kano, Katsina, Jigawa, Zamfara, Yobe and Borno). It started in November 2012 with a goal to increase women and children’s access to health services in areas of high unmet need. Its impact measures of success include improved routine immunisation rates; improved attendance to antenatal care services; and increased proportion of deliveries by skilled birth attendants. Its main purpose is to increase the number of female health workers in training to serve in rural health facilities in Northern Nigeria.
[note] This programme was approved prior to DFID Nigeria’s Geographical Footprint approach, which focuses DFID effort on 3 partner States (Kano, Kaduna, Jigawa) and 3 Nigerian regions (Northeast, Southwest and Southeast/South/south)

To achieve this, the project was designed to improve health training and education for 6,007 rural girls and women; to support the recruitment and retention of 250 female midwives and to assess the need for a new cadre of community health worker. However evidence from the first year of implementation revealed the need to act on multiple parts of the system to address all key bottlenecks, hence the number of project outputs was expanded to include: increased training capacity of health training institutions in programme states; improved management and financing of health training institutions; improved quality of education provided by health training institutions; increased government and community support for female health workers for rural areas; and strengthened community based service delivery for women and children’s health.
[note] The original business case target was 6,750 students trained or in training. In 2015, as student information systems were improved through W4H support a more accurate baseline figure was obtained. As a result of the revised methodology and revised baseline data, the outcome level target was revised downwards slightly to 6,007.

The W4H programme worked in the following areas in its initial 5 states (Kano, Katsina, Jigawa, Zamfara, Yobe):

- Improved physical, management and teaching capacity of 20 health training institutions (HTIs), including rehabilitation of facilities and equipment supply, increasing the number of female tutors, securing accreditation from regulatory councils thereby increasing the number of approved student places (index places), introducing the concept of student voice and feedback, and supporting a more female friendly environment.
- Improved the quality of teaching by supporting the institutions to transit to a student-centred learning approach, it also introduced e-learning and twinning (skills and knowledge exchange) between UK and Northern Nigerian midwifery tutors.
- A Foundation Year Programme (FYP) was developed for rural women who did not have an adequate standard of secondary education to be able to enrol in the HTIs. This Foundation Year is aimed to improve science skills and build the confidence of the young women who wish to become nurses, midwives or community health extension workers (CHEWs). Upon graduation these young women are employed and posted to serve their home communities, thereby addressing the acute shortage of health workers in rural health facilities and improving the likelihood of retention.
- Community engagement in 912 underserved communities in the five programme states has encouraged communities to think more positively about sending their daughters to tertiary education and to sponsor young women to attend the FYP and eventually HTI courses.
- The programme engaged with government to ensure commitment, legislation and budgeted funding to sustain the HTI and FYP activities into the future.

W4H was originally due to end in October 2017. The programme received a no-cost extension to March 2018 and a further 2.5 year £8m cost-extension to October 2020 to start a second phase, which expanded the programme to Borno State, adapting the approach for the conflict affected context in Yobe and Borno; to institutionalise learning and scale up at State and Federal levels; and maximise the impact of previous investment in Kano, Katsina, Jigawa and Zamfara, to ensure sustainability of successful initiatives while transitioning from direct support.

During the extension phase, the programme scaled down from direct support in Kano, Katsina, Jigawa and Zamfara; continued implementation in Yobe; and expanded to Borno State. In the four scale-down states the programme no longer funds direct interventions such as infrastructure upgrades for HTIs or the FYP. Support is limited to facilitating advocacy for continued domestic financing of HTIs as well as the recruitment and deployment of graduate health-workers; support for planning and budgeting of human resources for health (HRH) interventions; data collection to monitor progress; support for accountability systems between communities and government; and maintaining twinning relationships between training institutions and UK based tutors. This “post-intervention” phase also provides an opportunity to learn about the key barriers to sustainability and troubleshoot them.

The programme is also enhancing sustainability and nationwide scaling up of its interventions during the extension phase through establishing a permanent Human Resources for Health Learning Hub at the Bayero University Kano, as well as a strategic partnership with the Nursing and Midwifery Council of Nigeria (NMCN). However, the poor maintenance culture of health training institutions remains a risk to the sustainability of W4H’s infrastructure investments, and will need to be followed up through the Lafiya programme and continued DFID engagement.

Context

At the beginning of the W4H programme in 2012, Northern Nigeria had a critical health workforce shortage. There were inadequate numbers of health workers and also a poor distribution of workers to rural areas, where the majority of the population live and mortality rates are highest. In Jigawa there were 5 nurses per 100,000 population, 7 per 100,000 in Zamfara and 10 per 100,000 in Kano; compared with the south-east (Enugu 59) the south-west (Lagos 58) and south-south zones (Akwa Ibom 56; Bayelsa 53). There was chronic under-investment by state governments in health training institutions – most were dilapidated, with only one of the 16 schools in the five target states fully accredited by regulators, accepting only 893 students a year.
[note] Nigeria Health Workforce Profile 2009 (2010) Federal Republic of Nigeria, Federal Ministry of Health.

The inadequate number of health-workers was compounded by severe gender imbalances. In northern Nigeria, up to 65% of females had no formal education. In the Jigawa state, only 2 out of 35 (6%) employed physicians were women and 78% of the entire health workforce was male. According to the 2008 Nigeria Demographic Health Survey, 39% of women in the north west zone had serious problems accessing care due to a lack of female providers and only 31% of women received ante-natal care from a skilled provider - suggesting that female health workers are particularly important where social norms may prohibit women from receiving care from male health workers.

What has changed in the context?

While Northern Nigeria still has a serious health workforce shortage, the supported states have invested substantially more of their resources in the training and recruitment of health-workers, particularly targeting females. Seven new training institutions have been established, and almost all now have full accreditation, with the training pipeline (admission places) more than doubled in throughput from 893 to 2067, and a new community midwifery cadre established. Teaching quality has dramatically improved, with exam pass rates increasing from 62% to 82% and institutions in supported states now seen as models for others nationwide. All initially supported States now fully finance and implement foundation year programmes which target poor, rural young women to be trained to become health-workers. More than 600 additional midwives have been recruited and deployed, mostly to rural areas, with average retention rates for midwives rising from 71% to 89%. According to the Nigeria Demographic and Health Survey, the proportion of women in the north-west zone receiving ante-natal care from a skilled provider rose to 53.9% by 2018. At the national level, new leadership at the Nursing and Midwifery Council is driving forward initiatives to improve the quality of teaching and expand the training of new cadres of health-workers (community midwives).

Programme management

The W4H project is in its 7th year and has had strong performance over the course of the year. Reports are submitted with accurate information and milestone deliverables have been largely achieved on schedule. The project has remained flexible and continues to adapt activities and budgetary allocations to changes in context and other factors. However, with an average variance of -13.5%, financial performance was sub-optimal over the past year, driven by various factors. In the April - June quarter, project activities were affected by election challenges in some states, these challenges led to the reconstitution of some state cabinets and resulted in the need to reschedule activities with government officials. In the April – June and July – September quarters there were delays in procurement of equipment due to unavailability of stock from international vendors. The programme generally complied with DFID terms and conditions and other requirements, however appropriate use of UKAid branding was noted to be inconsistent over the past year.

DFID Nigeria’s management of W4H is led by an Abuja A2 adviser/SRO as well as a Kano-based B2 programme officer. Over the past year a Kano-based A2L regional coordinator (with significant health management experience) joined the team, making available some of her time to provide additional technical oversight. The DFID team maintained regular engagement with the programme through regular quarterly meetings, field visits and annual reviews. The team also maintains regular engagement with relevant Nigerian federal and state governments, supporting the programme’s sustainability objectives by raising human resources for health issues in key meetings. Given that W4H is based in Kano and works primarily in Northern Nigeria, having key members of the DFID team Kano-based has helped in maintaining regular oversight of the project.

Summary supporting narrative for the overall score in this review (1/2 page)

The Women for Health W4H programme is making progress towards achieving its log frame indicators and even exceeding targets in some areas. During the year under review, the programme achieved the following:

1. The Borno College of Nursing and Midwifery (BCONM) will shortly become, for the first time in its 40-year existence, fully accredited by the Nursing and Midwifery Council of Nigeria (NMCN). This will mean a doubling of the number of students it can train each year. The W4H programme provided extensive infrastructural upgrades (administration block, library, creche, science and ICT lab) to the College to raise its standard from provisional to full accreditation. The programme also partnered with the DFID programme Solar Nigeria, which provided a reliable off-grid 135KVA solar power system to the College. W4H also tasked other partners like WHO and UNICEF to support the college with laboratory equipment and class desks/chairs.
2. Across the 4 exiting (Kano, Jigawa, Katsina and Zamfara) states, the sum of NGN 48,955,780 (GBP108,790.6) was released by state/local governments for the implementation of the Foundation Year Programme, reflecting their commitment to sustain the FYP beyond the W4H programme. Multisectoral steering committees in host ministries with dedicated desk officers and community structures have been established to ensure a bottom up process of implementing the FYP programme. These structures are necessary for enrolment, retention and maintenance of FYP students in the school, and for post-graduation when they return to serve their communities as nurses or midwives.
3. The programme trained 100 female community volunteers on trauma identification and management. These, in turn, sensitized 1,249 women in internally displaced persons IDP camps and 558 women in host communities to provide trauma healing and counselling for young women selected for the FYP and other identified victims. This complemented the training of academic staff on the new humanitarian curriculum to improve the knowledge, skills and competencies of students to provide quality services in conflict and humanitarian settings. The programme also supported the development and implementation of enhanced safeguarding principles across all the training institutions in Borno and Yobe.
4. The Human Resources for Health Learning Hub supported 3 non-W4H states (Kaduna, Niger and Sokoto) to study the innovative FYP strategy for replication with costed strategic plans. Kaduna and Sokoto states have successfully commenced implementation. The centre is proposed to provide mandatory continuous professional development programmes (MCPDP) for nurses and midwives to generate revenue to run the hub after W4H exit while also serving as a learning and development resource for the NMCN.
5. The W4H programme held state level learning events where success stories were disseminated to all stake holders with demonstration of commitment by state Governors, traditional institutions and all stakeholders to support and champion the FYP programme for sustainability. Strategies and success stories have been documented for future lesson learning and adaptation in the Learning Hub physical and virtual library.
6. W4H supported the NMCN to improve the quality of clinical teaching in health training facilities by adopting the preceptorship method. A detailed training manual has been developed and used to train 30 master trainers across six geopolitical zones of the country as a strategy to enhance the quality of clinical teaching and learning during clinical trainings in hospitals.
7. The programme developed a functional web application portal as an online monitoring tool for the NMCN. This will be used for periodic assessment of accredited institutions to ensure they are up to date on their accreditation status, a means of monitoring and maintaining standards in between accreditation visits and enable electronic feedback reporting to the institutions. The NMCN is also collaborating with the Nigerian Information Technology Development Agency (NITDA) to incorporate the e-learning system into the national IT policy.

Overall output score and description: A – Outputs met expectation

Output	Weighting (%)	Score
Output 1: Increased, appropriate and better-quality training for nurses and midwives in conflict affected areas in Yobe and Borno	45%	A
Output 2: Dissemination of the W4H approach to facilitate learning for sustainability and scale up	10%	A+
Output 3: Federal capacity, policy and systems strengthened for better and more gender equal HRH planning, production, recruitment, deployment and retention.	20%	B
Output 4: State governments and HTIs in 4 states (Jigawa, Kano, Katsina and Zamfara) have capacity, policy and systems strengthened for sustainability	25%	A

Recommendations for the year ahead (1/2 page). Unless otherwise stated, all recommendations should be implemented by the close of the programme in October 2020.

1. DFID should use its strategic engagement with the Borno State government to raise and monitor sustainability, continued maintenance of health training infrastructure, and provide continued technical support and capacity building through the new Lafiya programme. W4H should continue to engage with training institutions to encourage and provide training in preventative maintenance culture and good practice.
2. W4H should continue to support Borno state to learn from the experience of Yobe state.
3. DFID and W4H should ensure a smooth transition to the new Lafiya programme during its inception phase, including support for the Nursing and Midwifery Council, trauma management and safeguarding within its scope of interventions.
4. W4H should engage with government and other donor programmes who work with IDPs to consider whether the women’s community group approach should be scaled up and incentives provided to these groups.
5. W4H should work with the Learning Hub to support interested States to establish advocacy groups to drive political engagement and financing.
6. W4H should work with the Learning Hub to arrange at least one lesson learning workshop with all the states before the programme closes.
7. W4H should ensure that all its knowledge management products and resources are easily available on the Learning Hub website – by March 2020.
8. W4H should collaborate with DFID and other donor livelihoods programmes to provide empowerment opportunities to FYP graduates who do not progress into health training, and transition out of providing skills training to these beneficiaries itself.
9. W4H should ensure that, except for infrastructure works in Borno and Yobe states, UKAid branding is visible on construction and renovation works. The UKAid logo should apply on all W4H products, documentation, equipment and procurement in applicable locations – by May 2020.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increased, appropriate and better-quality training for nurses and midwives in conflict affected areas in Yobe and Borno
Output number per LF		1	Output Score	A
Impact weighting (%):		45%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of student places in the Schools of Nursing and Midwifery in Borno and Yobe approved by regulatory bodies (Cumulative performance)	School of nursing 150 / School of midwifery 120 / Community midwifery 70	SON 150 / SOM 120 / CM 70
Number of Health Training Institutions (HTIs) meeting the required tutor to indexed students’ ratio in Yobe and Borno	4	4 / (SoN and SoM Damaturu) / (SoHT Damaturu and SoHT Maiduguri)
Number of tutors in Yobe and Borno trained with an integrated humanitarian intervention curriculum for both in-service and pre-service education	50	93
Cumulative Number of Foundation Year Programme students admitted into professional training in HTIs in Yobe and Borno	300	317
Cumulative Number of women enrolled into FYP in Yobe and Borno	1208	1130

Provide supporting narrative for the score
This output is designed to improve the number of women entering and completing training, as well as the quality of training for health-workers in Yobe and Borno States. In Yobe, this follows on from significant progress during the first phase of the programme, while in Borno this effort only started in 2018. There is an emphasis on conflict sensitivity, doing no harm, and safeguarding. The output is on track to achieve the desired results for the year under review.

W4H provided extensive support to improve the infrastructure and capacity of the school to raise its accreditation standard and secure additional index spaces for admitting female students into midwifery training. The programme provided an administration block, library, creche, science and ICT lab to the College, and partnered with the DFID programme Solar Nigeria, which provided a reliable off-grid 135KVA solar power system. To meet tutor requirements, 20 (BNSc) tutors are undergoing training in the Post Graduate Diploma in Education (PGDE) programme to qualify as tutors.

W4H also tasked other partners like WHO and UNICEF to support the college with laboratory equipment and desks/chairs for the classes. The Presidential Committee on North East initiatives (PCNI) was engaged to support the College of Nursing and midwifery Damaturu and donated seven vehicles (worth over £330,000) to serve for transporting students during clinical placements. The Nursing and Midwifery Council has visited the school, has given provisional approval to increase index slots to admit 100 community midwives and were very happy to confirm that full accreditation will be awarded in the following weeks.

W4H developed a humanitarian curriculum for health workers in training or service to meet the needs of traumatized conflict affected communities. W4H is working along with the International Committee of Red Cross, the International Rescue Committee and the Nursing and Midwifery Council of Nigeria, to harmonize the humanitarian curriculum with other relevant isolated manuals for future scale up at national level.

The Foundation Year Programme (FYP) is being implemented in Borno and Yobe, with 120 young women enrolled during the review period, with a cumulative 240 in Borno State and Yobe currently in the process of recruiting 178 young women. The FYP in Borno is still being funded by W4H but strategies are being worked out with the government to transfer funding to the state Government. FYP students from the Internally Displaced Persons (IDP) camps serve as role models/mentors for other young rural women in the camps, and they promote active participation in health activities.

The W4H learning event and graduation ceremony also yielded results, with the Yobe State government making commitments to improve infrastructure, increase students’ allowances and ensure recruitment of all FYP graduates. So far, student allowances have been increased by 100%, all FYP graduates were given permanent and pensionable appointment and construction of new classroom blocks and staff offices is ongoing.

All FYP students in Borno have undergone trauma healing training where a lot of issues were identified and 68% of trauma related problems were addressed through counselling and community engagement on trauma. Women’s groups in Internally Displaced Persons (IDPs) camps and settlement communities were trained on trauma healing techniques for cascading to other women. So far 200 Women were trained on trauma healing and identification, it was very innovative and participatory for easy learning and action.

Psychological distress/ trauma management and referral systems were strengthened in line with the World Health Organisation (WHO) recommendations. W4H has facilitated the recognition of the College of Nursing and Midwifery as a community for trauma referral purpose. Data is being collected and analysed by the institution’s counsellors to help make informed safeguarding decisions.

Lessons identified this year, and recommendations for the year ahead linked to this output

Given the limited time W4H has had to operate in Borno relative to the other States, and the short time left to the end of the programme, achieving a similar level of sustainability is unlikely to be realistic. While the State Governor has made some commitments, for example to fund the FYP and to release funds for accreditation of health institutions, experience indicates more sustained engagement and capacity building from DFID will be required. DFID should use its strategic engagement with the Borno State government to raise and monitor sustainability and provide continued technical support and capacity building through the new Lafiya programme.

Bringing Yobe and Borno states Health training institutions and legislators together to share experiences helped to speed up activity and political engagement in Borno state. W4H should continue to support Borno state to learn from the experience of Yobe state.

Trauma is such an important but underestimated issue. W4H, the Health Training Institution management and the engaged consultants were surprised with the scale of the issue and the pervasive impact it was having on the students. Efforts by W4H and processes established so far to address this issue will need to be sustained. Trauma management and safeguarding should be integrated into the scope of activities to be continued by the Lafiya programme.

The enthusiasm of women’s community groups under the W4H community engagement approach was a pleasant surprise to the programme. There have been discussions on how (and whether) to compensate the groups for their work cascading the trauma healing training to other women in IDPs and settlement communities. W4H should engage with government and other donor programmes who work with IDPs to consider whether this approach should be scaled up and incentives provided to these groups.

Life skills and empowerment training held for FYP students helped them to be more active and negotiate for their rights and accountability to their communities. W4H should engage with state governments and NGOs to consider scaling up this approach.

Output Title	Dissemination of the W4H approach to facilitate learning for sustainability and scale up
Output number per LF		2	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of states not supported by W4H engaging with the learning hub to learn from the W4H approach and other good practice	2	5
Cumulative Number of reporting and learning products (including data from current W4H states) produced and shared	16	16
Number of Health Training Institutions aware of and using the new CHEW curriculum (incorporating task shifting for safe delivery and family planning)	4	8

Briefly describe the output and provide supporting narrative for the score
This output aims to widen the impact and improve the sustainability of W4H’s efforts by expanding the dissemination and use of lessons learned from the programme through long-term institutions.

The programme has continued to partner with the Centre for Gender Studies, Bayero University Kano to promote the W4H initiatives for possible scale up in non W4H states. The Centre accommodates the Human Resources for Health Learning Hub, established and equipped to serve as a learning space with a physical library and training room with dedicated staff and equipment. The Hub has been visited by both the W4H and non W4H states as well as stakeholders from Kano state. The University has deployed two IT personnel and constructed additional facilities at the Hub at their own expense, demonstrating commitment to the centre.

In 2018, three states (Niger, Kaduna and Bauchi) engaged with the Learning Hub. In 2019, five states (Kebbi, Sokoto, Nassarawa, Adamawa and Gombe) engaged with the Hub, training institutions held series of meetings with the hub representatives with the aim of learning from the W4H initiatives. Cross River State have also indicated interest in some interventions particularly the foundation year programme FYP, the tutor twinning programme TTP and the student-centred learning SCL. Sokoto and Kebbi states have started the implementation of FYP, while Niger and Kaduna states have commenced start up activities towards establishing FYP in their states. Kaduna, Sokoto and Kebbi states have provided funding and an institutional home to host the FYP programme in the three states.

Advocacy and sensitization visits have commenced by the visiting teams (of Adamawa, Niger and Gombe) to their respective State Ministries of Health (SMoH), local government and the traditional institutions to promote political ownership, implementation and funding of the FYP programme. All states (Sokoto, Kaduna, Kebbi and Niger) have been supported to develop FYP strategies and costed operational plans for the implementation of the strategy. Sokoto state has successfully used the document in advocating to the state governor for increased funding for the FYP.

The School of Nursing and Midwifery Calabar, Cross Rivers state is working with the College of Nursing Sciences Sokoto state on the twinning initiative using the Student-Centred Learning (SCL) approach, mentored by one of the first set of individual twins from the School of Midwifery Dambatta, Kano. The twinning is being facilitated by the Nursing and Midwifery Council (NMCN), using still pictures and videos of classroom demonstration sessions shared on a WhatsApp platform.

In 2018, the programme produced a total of 10 knowledge management (KM) products. 2019 has a cumulative target of 16 KM products by the end of the year, which has been achieved in the second quarter by adding 6 more products. The 6 additional KM materials produced are listed below:

1. Student-centred learning: A practice guide for teachers
2. W4H policy brief: Increasing tutor numbers in Health Training Institutions in Northern Nigeria
3. A success story on Borno FYP titled – “Building Back Better in Borno: Adapting the Foundation Year Programme for conflict affected Borno state”
4. Helping a dream to come true: Becoming a female health worker in Northern Nigeria
5. A 2nd edition of the programme “the journey so far” document (A comprehensive report on the programme journey)
6. An updated programme overview.

While there has been limited distribution of copies of these materials by W4H and the learning hub through a number of events and the W4H website, they (and indeed no learning materials whatsoever) are currently (at the time of writing) not available on the learning hub website www.learninghub4hrh.org. This is a missed opportunity to broaden the effective reach of W4H’s knowledge materials to those institutions and individuals who are unable to physically access W4H or learning hub offices or events.

The programme supported the colleges of health sciences and technology in 5 W4H states to promote the new Community Health Extension Worker (CHEW) task shifting curriculum. Currently all eight Colleges of Health Sciences and Technology are implementing the new revised curriculum, exceeding the overall programme target for the indicator 2.3. In 2019, the programme, in collaboration with the Community Health Practitioners Registration Board (CHPRB), with the participation of all the Colleges of Health Sciences and Technology in W4H exiting states including Yobe and Borno, developed a lesson observation checklist for use by Health Training Institutions managers to assess teaching standards and methodology in their colleges, helping improve quality assurance in implementing the new task shifting curriculum.

Lessons identified this year, and recommendations for the year ahead linked to this output

Governments in all the non W4H states engaged were interested in implementing the FYP but did not have funds readily available for the start-up implementation activities. Where funds were provided, they tended to be insufficient and released late. However, they were all willing to give whatever support needed for the implementation, such as arranging meetings and reaching out to other key stakeholders who would be involved in the implementation.
W4H should work with the Learning Hub to support interested States to establish advocacy groups to drive political engagement and financing.

Advocacy visits to State Council of Chiefs Chairs facilitated messaging to district heads, who readily accepted the FYP and helped source for the right candidates. This emphasises the role of the traditional institutions in supporting demand side activities and their continuous commitment to the sustainability of the FYP. The Emir of Dutse in Jigawa has affirmed he will continue to support the cause through influencing government and all stakeholders, while proffering suggestions on ways of improvement where needed. Across the northern states the traditional institution is the gateway to acceptance of any community initiative.

Bringing the states together during the Capacity Building Workshop made it easier to pass the same message to all the non W4H states and secure more commitment from them. It also made it easier to monitor the progress of each state based on the implementation work plans developed. This also provided an opportunity for states which have started implementation, such as Kaduna, Sokoto and Kebbi, to share their experiences and lessons learned. W4H should work with the Learning Hub to arrange at least one lesson learning workshop with all the states before the programme closes.

Support to states to produce strategy and costed plan documents helped make them make a stronger case for the implementation of the FYP. For example, in Sokoto state the HRH committee used the document in securing funding for increasing the numbers of FYP students to be enrolled.

W4H should ensure that all its knowledge management products and resources are easily available on the Learning Hub website – by March 2020.

Output Title	Federal capacity, policy and systems strengthened for better and more gender equal HRH planning, production, recruitment, deployment and retention
Output number per LF		3	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of schools benefiting from supportive supervisory visits by regulatory bodies to improve efficiency	16	16
Number of academic staff supported to participate in regulatory bodies organized Mandatory Continuing Professional Development (MCPDs)	300	225
Number of joint initiatives pursued with the aim of building Human Resources for Health (HRH)	3	3
Number of states supported to develop HRH Profile to improve national HRH data	Cumulative 10 (5 this year)	Cumulative 10 (4 this year)

Provide supporting narrative for the score
This output focuses on intervening at national level to enable better regulation and oversight of health training institutions and health workers by building capacity of the regulatory bodies. It also aims to expand the impact and sustainability of health training innovations and successes introduced by W4H beyond its supported states through national adoption by regulatory bodies. This is a new output for W4H and activities started in 2018. Much was achieved this year on this output, well beyond the areas reflected by the indicators, although under-achievement of indicator 3.2 (for reasons beyond the control of the programme) results in a score of B for this output.

During the year W4H continued to provide systems strengthening and capacity building support to the Nursing and Midwifery Council of Nigeria (NMCN) to improve its regulatory effectiveness. The Council developed a 5-year strategic plan along with M and E and accountability frameworks to operationalize the strategic plan. An advocacy plan was developed for engaging government and strategic partners for increased support and synergy. The council also developed a sustainability plan with a transition roadmap which takes account of W4H exit in 2020. However, the Council identified a number of interventions which are still at early stage, and is requesting continued DFID support through the new Lafiya programme.

W4H also supported the institutionalisation of supportive supervision (SS) which has been approved by the NMCN governing board and is already being implemented. W4H also provided equipment, including digital tablets to improve data collection and analysis during the accreditation visits. An online accreditation module is being developed which will complement the periodic accreditation visit to the institutions. In 2019, the NMCN conducted supportive supervision visits to 16 Health Training Institutions in eight states, thereby meeting the milestone target. NMCN has undertaken to visit all institutions with full accreditation at least twice within the five-year accreditation period.

W4H’s Student Centred Learning (SCL) methodology and Mandatory Continuing Professional Development Programme (MCPDP) curriculum has been approved by the NMCN for use in all HTIs. 30 National Master Trainers were trained, and 180 persons trained at a zonal level. The States have adopted the use of SCL for all forms of MCPDP nationwide. It was launched at national level in early December 2019 and another set of training was conducted in mid-December 2019. Training institutions are reporting improved learning quality and academic participation by both students and tutors as well as increased graduation rates as positive outcomes. The late launch of the training by NMCN meant the programme could not meet the milestone of 300 trainees by the time of this review, however at the current rate it is well on track to meet or exceed the end of programme target.

The programme also supported the NMCN to develop a preceptorship curriculum/manual to compliment the SCL. The manual was launched nationally by the NMCN on 3rd of December 2019 and it was used to train 36 master trainers across 6 geopolitical zones of the country. All preceptors (experienced nurses and midwives who provide practical training to students in a clinical setting) will now be required to be trained and certified by the Council. NMCN will start piloting the manual in January 2020 across selected facilities.

W4H has also supported reforms within NMCN to increase private participation in nursing and midwifery training. Within the last two years, two private nursing and midwifery schools have been established in two W4H States (Kano and Katsina).

W4H is also targeting more interventions for nationwide scale-up. These include safeguarding guidelines for nursing and midwifery training institutions (NMTIs), and (working with the International Rescue Committee IRC, Red Cross ICRC and the NMCN) a national curriculum for the training of health workers in conflict affected settings. W4H’s Student Information Management system, SIMS, is now operational in 73 schools across the country with a targeted country wide coverage by the end of 2020.

National and state level capacity for workforce planning, management, and budgeting remains weak, and the national human resources for health information system is poorly developed. To help address this W4H has worked with the Federal Ministry of Health (FMoH) to undertake human resource assessments in 10 states, meeting the programme target. Six states were supported in 2018 and four in 2019. The programme also supported the harmonization and dissemination of HRH training manuals by the FMoH.

Lessons identified this year, and recommendations for the year ahead linked to this output

The NMCN recently restructured its Department of Planning, Research and Statistics into three new sections (planning, research and statistics). This helped improve the coordinated implementation and monitoring of the NMCN strategic plan.

Improvements in W4H forward planning with NMCN to ensure activities are scheduled at least one month in advance, helped reduce conflict with NMCN’s other core activities.

W4H should engage with the new DFID Lafiya programme to ensure ongoing support to NMCN is effectively transitioned to the new programme.

Output Title	State governments and HTIs in 4 states (Jigawa, Kano, Katsina and Zamfara) have capacity, policy and systems strengthened for sustainability
Output number per LF		4	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Cumulative Number of rural young women enrolled into FYP and funded by states in Jigawa, Kano, Katsina and Zamfara	1699	1738
Cumulative Number of FYP graduates who enter professional training in Jigawa, Kano, Katsina and Zamfara	665	769
% of students who pass national exams in Jigawa, Katsina and Zamfara	80%	82%

Provide supporting narrative for the score
This output focuses on monitoring and ensuring the sustainability of W4H’s impact, particularly the FYP and improved quality of teaching, in states where the programme no longer provides direct support (exiting states).

All the states continue to demonstrate significant government interest and ownership of the Foundation Year (FYP) programme through funding and legislation. All ministries hosting the FYP in W4H exiting states have budget lines with adequate and timely fund release. More students continue to be enrolled on the FYP, fully funded by state governments, exceeding the programme targets. State Foundation Year Programme Working Groups (SFYPWG) manage an accountability mechanism between FYP implementing agencies, communities and government.

Advocacy and Demand Creation Groups (A&DCGs) across exiting states also serve as a sustainability mechanism for accountability and ownership. Their role includes the selection, mentoring, support and follow up of FYP beneficiaries in training. Roles and responsibilities of the groups have now been clearly stated, with 39 A&DCGs across the five states registered with LGAs and states that enable them source for funds and other resources to effectively monitor FYP implementation.

680 FYP beneficiaries secured admission into HTIs, exceeding the milestone targets for the year. Those who failed to gain admission are taught livelihood skills to support themselves and their families. This also serves as motivation to other families to enrol their girls into school as there is much to be gained from formal education.

Student performance at the national qualifying examination has improved to 82% from the 77% recorded in the previous year. This achievement is attributed to the utilization of e-learning resources and the Student Centred Learning (SCL) teaching methodology in supported institutions. These pass rates have encouraged the nationwide adoption of these methodologies by the NMCN and schools in other states.

W4H continued to build the capacity of staff at training institutions to monitor the implementation of SCL in schools and troubleshoot e-learning challenges. A medium for experience sharing and mutual support among participating institutions has also been institutionalised. All the exiting states (plus Yobe) have now fully taken over activities which support institutions to achieve and maintain their accreditation status.

Lessons identified this year, and recommendations for the year ahead linked to this output

Training the FYP graduates who failed to secure admission into health training institutions in other livelihood skills is likely to encourage girl child education and contribute to the gender empowerment objectives of the W4H programme. There are a number of donor and government livelihood and empowerment programmes that target women and could benefit such young women. W4H should collaborate with government and donor skills programmes such as ENGINE, FITILA and others to provide skills opportunities to FYP graduates who do not progress into health training.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The overarching theory on which the intervention rests is that increasing the numbers of female health workers in rural areas in Northern Nigeria will lead more women to utilise health services such as immunisation, antenatal care and skilled birth attendants (SBAs). This is expected to happen because being treated by a female health worker is seen as more culturally acceptable by women, their families and their communities. Moreover, increasing the numbers and profile of women health workers in rural areas and improving their terms and status may have a positive effect on the status of women, making it more likely that women will seek educational and income opportunities and in particular will train to become health workers.

During the first phase between 2012 and 2018, the programme worked on the following main areas –
1. Working with state governments to improve their funding and support for HTIs, the FYP for rural young women, and recruitment, deployment and retention of health workers.
2. Working with HTIs to improve their standards of training quality as well as their ability to meet the needs of female trainees.
3. Working with young women from rural communities to train and become health workers, and role models for women’s empowerment in their communities.
4. Working with communities to actively support young women to receive training and take up their services when they return as health workers through the Foundation Year Programme (FYP).

The theory, interventions and assumptions remain valid, the programme continued to push and ensure the sustainability of all initiatives as well as the scale up in some non W4H states through the Learning Hub. Our work continues to focus on:
1. Working with federal institutions to improve their regulation and oversight of health worker training and institutionalise successful innovations through nationwide adoption.
2. Working with a Learning Hub hosted by Bayero University Kano to ensure institutionalisation of W4H HRH initiatives.
3. Working with training institutions and other partners to address the peculiar needs of conflict affected students and communities.

The diagram below details the theory of change for the second phase of the programme, as updated over the past year.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The table below summarises progress on the expected outcomes and impact.

S/N	Indicators	Milestone	Progress	Remark
Impact indicator 1	Proportion of women attending antenatal care (ANC)	70%	67%
Impact indicator 2	Proportion of births attended by skilled birth personnel	55%	43%

Outcome indicator 1	Number of female students enrolled in training as health workers in (i) Yobe and Borno, (ii) Kano, Jigawa, Katsina and Zamfara (Cumulative)	Borno/Yobe 1241 / Other States / 8175	Borno/Yobe / 1232 / Other States / 7560
Outcome indicator 2	Proportion of FYP nursing, midwifery and CHEW graduates employed and deployed in rural areas (Cumulative)	50%	Proportion deployed to rural areas / 72.1% (305/423) / Nursing: 53% (46/86) / Midwifery: 87% (153/169) / Community Midwifery: 82% (81/97) / CHEW/JCHEWs: 48% 31/60 / 11 others from other courses in SoHT also graduated	Of the 423 FYP trainees who have graduated as health workers as at November 2019, 311 (73.5%) have been employed and 305 (72.1%) deployed to rural areas.
Outcome indicator 3	Percentage of female graduates absorbed by state and deployed to rural areas	35%	Total 45% (422/937) / Nurses: 18% (116/616) / Midwives: 95% (261/275) / Community Midwives: 98% (45/46)

As indicated in the last review, the W4H’s ability to directly influence the impact indicators is very limited – W4H works in six out of 36 states (the indicators are national), and human resources is only one out of several constraints to increasing coverage of ante-natal care and skilled birth attendance. W4H is expected to contribute to improvements over the long term, and is currently undertaking a research study which will attempt to estimate its impact.

Progress on the three outcome indicators has been good, with milestones met or exceeded.

Explain major changes to the logframe in the past year (1/2 page)

The major changes to the logframe are on indicator 1.1 on the Number of student places in the SoN&M in Borno and Yobe approved by regulatory bodies (i) indexed places SHT, SON, SOM. The target for additional indexed places in Borno has been moved to the last year of the programme, as work on infrastructure and tutor training is still ongoing.

Indicator 3.1 on the Number of schools benefiting from supportive supervisory visits by regulatory bodies to improve efficiency was revised from 20 to 16 following the decision of the NMCN’s governing board to provide supportive supervision visits only to institutions with full accreditation.

These changes were agreed by the SRO in July 2019.

Describe any planned changes to the logframe as a result of this review (1/2 page)

No changes are planned for the next reporting year.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The programme continues to track the performance of the indicators in the programme VfM strategy. The indicators cut across the 4Es of economy, efficiency, effectiveness and equity according to the DFID VFM framework. The programme prepared a new VFM strategy in 2018, which included new indicators across the 4Es. For this reason, trend information is not available before 2018 in many cases.

 A Cost effectiveness analysis (CEA) was conducted for phase 1 of the programme in January 2019 which focused on outcome 1, linking the cost of investment from DFID to the number of female students enrolled in training as health workers. No further CEA analysis was carried out during this reporting period. The phase 1 CEA findings can be used to benchmark cost effectiveness for Phase 2 for Borno and Yobe across W4H interventions supporting student enrolment and results directly attributable to the Foundation Year Programme.

The major cost drivers for this programme are personnel fees and the company’s mark up on overheads. DFID have successfully managed this through the programme achieving VfM in both economy and efficiency savings. The programme has retained high quality staff and sufficient numbers of community level field workers to continue delivering significant results across the States. The programme has achieved VfM gains through government employment of all trained FYP graduates and successful leveraging of other donors support to the HTIs.

Economy
Programme resources are maximized and savings were recorded across key activity areas through tracking of international, national and overall average fee rate.

Efficiency
The programme scale up to Borno and Yobe and slower phase out in four other states has minimized the risk of losing sustainability and maximized the gains by having a large scale (geographically) increased number of health workers in training and recruitment. The scale up of the FYP program and other supported interventions to non W4H states as well as the anticipated transitioning of some initiative the new Lafiya programme is also likely to contribute to the overall efficiency of the programme.

Effectiveness
There is enough evidence about the programme outputs producing the outcome (improved quality and quantity of female health workers). However, the evidence of impact on health coverage measures such as skilled birth attendance and ante-natal coverage as well as gender empowerment will be much more difficult to establish. The programme has undertaken a study which will attempt to assess this qualitatively and quantitatively, and it may be important to continue to monitor this well beyond the programme lifetime.

Equity
The programme is directly targeting poor young women who would not ordinarily have the opportunity to train as health workers or indeed secure access to reasonable employment, from deprived rural communities who have very limited or no access to health workers able to meet their needs.

An assessment of progress is provided below.

Indicator	2019 performance	Benchmark/Trend & Analysis
Economy
Unit cost of construction in health training institutions per sq. metre	£172.093 for the construction work in Borno	This compares with £216.24/ sq.m obtained by W4H in 2018.
Average fee rate for staff and consultants	The overall average daily fee rate is £194.52 during 2019	This compares with £250.5 in 2018, and £183 for the MNCH2 programme since inception.
Average cost of training per participant day	An average cost of N12,215 (£27) in 2019	This compares with N41,048 (£88) obtained in 2018.
Efficiency
Programme management costs as proportion of total expenditure	16.22%	This compares with 18.6% obtained in 2018, and 18% for the MNCH2 programme in 2017/18.
Effectiveness
Graduation rate in national exams	82%	There has been an increase from 77% last year. This performance can be attributed to the utilization of SCL and e-learning that are now fully functional in all the HTIs.
Cost Effectiveness
Cost (to W4H) per female student enrolled in health-worker training since inception	£4,401	This compares with £3,700 anticipated in the business case. However, the business case was written 7 years ago. At UK average inflation rate during the period (2.18%) this should be around £4,497 today.
Cost (to W4H) per female student newly enrolled in health-worker training (does not include students already enrolled at the start of the programme)	£5,464	This is a new indicator, and there are no national or international benchmarks available. W4H investment is mainly to increase the training pipeline capacity, which is expected to endure over time. By 2028, this figure is expected to reduce to £1,376 per newly enrolled student.
Equity
Proportion of female health workers employed who are posted to a rural area	92%. Of the 455 female nurses, midwives and community midwives recruited by supported States in 2019, 422 were posted to a rural area.	This compares with 84% in 2018.
Sustainability
Government contributions as % of W4H expenditure	A total of £805,674 was expended by supported state governments for W4H promoted HRH activities. This includes the statutory monthly contribution from Zamfara and Yobe. Some of the support were both for FYP and infrastructure investment in health training institutions in 2019. This is 22% of W4H’s forecasted expenditure in 2019/20	This compares well with £731,727 leveraged from state governments in 2018, and the MNCH2 programme, where government contributions were 7% of programme expenditure in 2017/18.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

From an economy and efficiency perspective, the W4H programme appears to compare well with available benchmarks. From a cost-effectiveness perspective, though there are no widely accepted benchmarks to compare with, the £5,464 cost per female student newly enrolled in health-worker training over the course of the programme might appear high. However, the programme’s emphasis on sustainability (as demonstrated by progress on its sustainability indicator) means that it is more appropriate to assess its cost-effectiveness using benefits obtained over a considerable period even after the programme has closed. An estimate of the programme’s long-term cost-effectiveness indicates that by 2028, the cost per female student newly enrolled in health-worker training is expected to have fallen to £1,376, a 75% reduction. The programme has also undertaken to do a further cost-effectiveness analysis at impact level using measures such as the cost per Disability Adjusted Life Year (DALY) averted using estimates of programme impact on health intervention coverage. This study is ongoing and results are expected in the coming months.

The cost-effectiveness measures however do not take account of

The considerable improvement in quality of health-worker training (demonstrated by the significant improvement in pass rates), which mean that a much greater proportion of students pass national exams and become health-workers. Improvements in quality (all things being equal) should also translate to better health outcomes delivered by each health worker while they are in service.

Benefits from wider adoption of programme interventions beyond the supported states, which is beginning to happen through adoption by the Nursing and Midwifery Council and the learning hub.

Wider impacts on female empowerment, particularly in rural areas in Northern Nigeria. This is critical to development in Nigeria and an important focus of the W4H programme. The ongoing research study (see section G below) will attempt to estimate this as well.

Given the analysis above, from a VFM perspective, the programme should continue to its end date in October 2020.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating:
The overall risk rating is Major.

The programme risk rating increased from moderate to major between phase 1 and phase 2 because of additional risks associated with programme implementation in Borno state.

Context and Operational Risk
Security concerns in Borno, Yobe, Zamfara and Katsina states, including kidnappings in Katsina and Zamfara, restricted W4H engagement to state capitals and limited access to communities where FYP students come from. This had implications for the FYP recruitment, bonding and feedback process. Significantly reduced access to many areas in Borno over the last year had a limited effect on W4H, as the programme only works within the relatively secure city of Maiduguri. In Borno, the community engagement approach was modified to cover IDP camps and resettlement communities, and FYP bonding agreed with camp leadership. There have been difficulties in accessing and recruiting young women trapped in hard to reach LGAs. To mitigate, W4H has collaborated with local NGOs and LGAs officials in those affected LGAs to recruit suitable young women, with screening and other measures in place to protect against abuse of the recruitment process.

The 2019 general election presented a major risk to the delivery and sustainability of W4H interventions. At least three (who have completed their maximum 3 terms) out of six state governors and their officials as well as many legislators were replaced. The programme developed an election risk mitigation strategy which included bringing forward key activities that require government commitment and funding, ensuring W4H issues are included in hand over notes, and immediate engagement with incoming administrations. In some cases, such as in Borno, W4H postponed infrastructure investments until new administrations had been established in order to maximise leverage opportunities.

Safeguarding and Reputational Risk
Some of the young women recruited in the FYP in Borno, particularly those living in IDP camps stand the risk of being sexually abused and exploited within and outside the school. This risk is illustrated by the results of the psycho-social study conducted by the programme. W4H is mitigating by putting necessary safeguarding measures in place.. The programme has engaged with IDP community leaders, camp management and the government to ensure reporting protocols are clear and students are provided with the necessary information and support. The programme has integrated its safeguarding approach with a broader Safeguarding, Mental Health and Psychosocial approach. The programme has engaged with IDP community leaders, camp management and the government to ensure reporting protocols are clear and students are provided with the necessary information and support. In addition, training institutions were supported to establish trauma counselling teams which are connected to the state trauma referral system. W4H has supported training institutions to develop safeguarding policies and gender sensitivity plans, including actions to protect young women such as adequate lighting, guards, matrons etc. Confidential counselling mechanisms are established to enable young women to report any areas of concern. The risk of beneficiaries being attacked by terrorists after being posted to insecure areas on completion of their training is being mitigated through guarantees from the state government that no graduates will be posted to an insecure community at the end of their training.

Despite a range of mitigating measures taken by the programme, the vulnerable nature of the programme’s beneficiaries particularly in Borno, and the indirect nature of its interventions (the programme interfaces with beneficiaries through training institutions and state governments) results in a residual safeguarding risk assessed at medium. This is above DFID’s current safeguarding risk appetite (minor), so is being escalated to the DFID Nigeria portfolio for additional mitigating measures, such as through a proposed DFID Nigeria review of safeguarding risk.

Delivery Risk
The poor maintenance culture of health training institutions remains a risk to the sustainability of W4H’s infrastructure investments. Future deterioration of infrastructure upgraded by W4H due to a lack of timely and effective maintenance, leading to potential downgrading of accreditation status and reduction in indexed student places available, is a risk. To mitigate, W4H will continue to engage with HTIs to encourage and provide training in preventative maintenance culture and good practice, monitoring of their performance in this area as well as dissemination of best practice guidelines and manuals.

Fiduciary Risk
Fiduciary risks continue to be managed well through implementing policies and guidelines for the management of grants, with adherence checked through both internal (annually) and independent financial audit. Detailed specifications are developed for each construction project, with inspection by W4H prior to final payment to contractor. Independent financial audits check the quality of construction work.

Outstanding action from 2018 risk assessment
None

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Date of last narrative financial report(s)	19 November 2019
Date of last audited annual statement (s)	18 June 2019

Commercial issues

DAI Global Health (formerly Health Partners International) has contractual responsibility to DFID for the W4H programme. Key sub-contractors for programme delivery are DAI Nigeria (formerly GRID Consulting) and Save the Children. DAI Global Health provides overall coordination, oversight, strategic planning and international expertise. DAI Nigeria provides technical leadership in public financial management as well as operational oversight of in-country financial and human resource management. Save the Children provides technical leadership in the areas of quality of teaching, humanitarian and advocacy. Along with DAI Global Health, representatives of DAI Nigeria and Save the Children sit on the Programme Review Board which has a technical, advisory and oversight function.

The W4H project is in its 7th year and has had strong performance over the course of the year. Reports are submitted with accurate information and milestone deliverables have been largely achieved on schedule. The project has remained flexible and continues to adapt activities and budgetary allocations to changes in context and other factors.

The project successfully leveraged funds from state governments to support W4H gains in each state (funds committed to W4H initiatives by state governments in 2019 currently stand at £805,674). The project continues to comply with DFID’s terms and conditions and other requirements. However, during this review, the team observed that UKAid branding was not consistently displayed on programme supported interventions. W4H should ensure that, except for infrastructure works in Borno and Yobe states, UKAid branding is visible on construction and renovation works. The UKAid logo should apply on all W4H products, documentation, equipment and procurement in applicable locations – by May 2020.

Financial performance

To date the programme has spent £31m out of its total £33.7m lifetime budget. In the current financial year, as at the end of October 2019 it had spent £2m out of a forecast of £3.7m. To date, two sets of quarterly milestone deliverables have been submitted as per the agreed schedule, including narrative progress reports, with 100% approval rate. A third milestone deliverable report for Oct – Dec 2019 is currently being processed.

The average variance over the course of the year has been -13.5%, this has been driven by various factors. In the April - June quarter, project activities were affected by election challenges in some states, these challenges led to the reconstitution of some state cabinets and resulted in the need to reschedule activities with government officials. In the April – June and July – September quarters there were delays in procurement of equipment due to unavailability of stock from international vendors. The project attempted to mitigate this by adjusting the forecast and reallocating spend to other months.

W4H has adopted an approach which uses investments by the project to leverage commitment by the states to support the training institutions (as indicated above, in 2019, the states committed £805,674). Another significant cause of the variance was delays in construction in Borno state. Construction originally scheduled to take place in August and September was delayed because the Borno State Government had not fulfilled its pledges to support the institution resolve critical gaps in resources. This has been resolved, additional efforts were taken to engage with the state government, and procurement processes began in November 2019.

Financial management

Invoicing, budget monitoring and reporting are managed by DAI Global Health. W4H has a national head office in Kano and one state office in Borno. Each office produces monthly accounts that are checked and compiled at the national head office before submission to DAI Global Health for processing. The annual workplan runs from April-March in alignment with DFID’s financial year. Annual work planning and budgeting takes place in the first quarter of each calendar year, with a mid-year review in September/October to review progress and revise plans and budgets for the remainder of the programme year.

Following the annual planning and budgeting exercise at the start of each programme year, expenditure against both commitments and agreed budgets is monitored monthly for all programme locations. Internal quarterly financial reports are submitted to the Programme Review Board to ensure that they have close oversight of the programme’s financial position and are alerted to key issues arising. Financial reports are also submitted to DFID on a quarterly basis.

DFID has commissioned an independent audit exercise covering the period October 2018 to September 2019, which is currently being tendered. The W4H programme had been audited independently by DFID three times since inception, and has earned an unqualified audit opinion each time. The last audit which covered the period up to September 2018 confirmed that the recommendations of the previous audit covering the period from January 2016 to 30 June 2017 were largely implemented.

Asset monitoring

W4H has established processes for the management of programme assets. Detailed asset registers are maintained in all programme offices, with a consolidated master register kept in the Kano head office. The National Logistics and Security Manager, and Borno State Logistics and Admin Officer conduct periodic spot checks to ensure that all the items represented on the asset registers are physically present. The Finance and Administration Manager has overall responsibility for the maintenance of W4H assets registers and carries out physical verification of the existence of all registered assets at least twice a year; this was last done in February 2019 in all programme offices, a second verification exercise is currently ongoing (December 2019) Assets verification exercises were conducted as part of DFID commissioned audits to document physical existence, conditions and locations of assets. Recommendations from the assets’ verification exercises have been implemented while updates to the assets register are being reported to DFID on quarterly basis through the PMC meetings.

The programme recently concluded a disposal of unneeded assets from the four exiting States. Some of the assets were transferred to other HMG programmes and programme beneficiary partners, while others were sold through an external auction. Auction proceeds have been returned to DFID.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The W4H programme is implementing its M&E activities in line with the Monitoring, Evaluation, Accountability and Learning (MEAL) plan developed for the extension phase of the programme. Progress is monitored through the submission of quarterly progress reports and quarterly programme management meetings between DFID and W4H.

Over the past year DFID has conducted monitoring visits to project sites in Borno, Yobe and Jigawa. During these visits, meetings and discussions were held with the project, government and other partners, beneficiaries (students) and communities. Project infrastructure work was also inspected and spot-checks carried out in project offices. DFID also had discussions with federal institutions, such as the Nigerian Nursing and Midwifery Council.

This annual review report was prepared by DFID, drawing upon observations of the programme delivery in targeted states through monitoring visits, evidence presented in W4H quarterly and annual reports as well as the W4H annual review self-assessment.

Evidence (1/2 page)

No evidence has emerged to seriously challenge programme design or rationale since approval of the business case. Evidence from project implementation suggests that the theory of change and underlying assumptions hold true.

The W4H research study is ongoing with the research protocol finalised, tools developed and pilot tested, and research assistants/data collectors also identified. The design is intended to collect both quantitative and qualitative data. While the programme is targeting four communities in each state for the qualitative component, the quantitative component is targeting all graduates from 2014 in one training institution per state.

Overall, the purpose of the expected research study is to enable donors and other stakeholders to learn from the W4H approach so that it can be applied and adapted more widely in Nigeria and across the region.

The study has two main objectives:

- To demonstrate the results and value of DFID’s investment in this programme across Phase I and Phase II. This will include a measure of effectiveness, cost effectiveness and impact.
- To generate lessons and learning to assist national and international stakeholders in replicating, adapting and scaling up the successes of this approach in the original five states of Phase 1. This will include an assessment of efficiency, sustainability and equity.

Learning (1/2 page)

Learning continues to be an integral part of the W4H project, with output 2 of the programme dedicated to learning with support from a Monitoring, Evaluation and Learning Advisor. The learning component of the programme has been integrated into the programme MEAL plan. A number of learning activities have taken place during the reporting period, including active participation and thought leaderships in events including the Nursing Leaders Conference, Forum of Heads of Health of Training Institutions Conference and a host of others.

The programme also organised state level learning and graduation events where programme knowledge were disseminated, and FYP beneficiaries were presented to the Government and stakeholders.

The Programme HRH Learning Hub at the Bayero University’s Centre for Gender Studies is working to ensure scale-up of W4H HRH initiatives with its engagement with non W4H states. This effort has resulted in some states adopting some W4H initiatives and NMCN promoting the new SCL and e-learning initiatives to all its schools. Also, as part of the learning, Kaduna and Sokoto states have fully adopted the FYP programme and are currently implementing in their states.

Progress on recommendations from previous reviews (1/2 page)
Most recommendations from the 2019 annual review have been largely or fully addressed. Specifically

W4H and DFID will need to work with the Borno State government and a broader range of partners in Borno to highlight the issue of abuse, violence and psycho-social trauma in order to tackle it more comprehensively
Progress: Trauma assessment conducted among all the FYP students in Borno, trauma healing trainings and sessions conducted. Four psychiatric nurses and twelve tutors were trained on trauma identification and management. State Strategic Framework for MHPSS and operational guidelines was also developed in Borno.

W4H and DFID should further mitigate the political risks caused by the upcoming elections by engaging early with Governors-elect and their new governments as soon as possible following the election by August 2019 –
Progress: W4H engaged with the new Permanent Secretary and Head of Service from Kano; engaged with Zamfara, Kano and Katsina legislators and other stakeholders. Through the FYP graduation ceremonies, W4H effectively engaged with Katsina, Jigawa and Yobe Governors and key emirs of the states. Chief of Staff and some members of Zamfara executives were also engaged with. DFID State Coordinators supported by raising W4H related issues during engagements with state governments.

The learning hub will need to work very closely with other relevant parts of the University to ensure it remains well connected to wider health systems learning and research.
Progress: The Learning Hub at the CGS, Bayero University, Kano is currently collaborating closely with the Faculties of Nursing and Community Medicine in the College of Health Sciences, Centre for Infectious Diseases Research and the African Centre of Excellence, Population Health and Policy (ACEPHAP) Bayero University, Kano to conduct a research study on “Factors Influencing Acceptance and Utilization of Health Care Services in the Rural Areas: The Role of Community Engagement in Kano State” to examine the role played by communities in addressing the acute shortage of female health workers. This is aimed at enhancing effective utilization and acceptance of healthcare facilities in the rural areas of Kano State.

W4H and the Centre for Gender Studies will also need to invest substantially in increasing the visibility of the learning hub through participation in conferences and other national and international events:
Progress: W4H and Learning Hub including Steering Committee Members actively participated and provided thought leadership on the concept of preceptorship at the nursing leaders conference. They also conducted a sensitization meeting for the University community and the W4H intervention states, and conducted a symposium on team work approach for health workers in Kano. We actively participated and led thought discussions on SCL at the forum of head of nursing institutions in Nigeria.

W4H needs to find innovative ways to develop stronger strategic engagement with other critical federal institutions, possibly through working with other partners (such as the World Health Organisation) by October 2019
Progress: The programme is engaging with the National Information Technology Development Agency (NITDA) on the scale-up of e-learning, with the WHO on the Human Resource for Health registry, with ICRC on trauma response in Borno and with the Federal Ministry of Health on all national interventions.

W4H should ensure that the requirement for certification of clinical tutors (preceptors) is piloted first, and lessons learnt, before it is implemented more widely – by October 2019.
Progress: The preceptorship curriculum has been approved by the NMCN governing board. Final approved version has been published and launched by NMCN. NMCN was supported to train 30 National Master Trainers. All initial discussions and arrangement finalised and will pilot preceptorship training in 30 health facilities with NMCN guidance.

DFID should consider what interventions currently supported by the W4H programme should be taken up through its next generation of health programming (which is expected to start by the end of 2019), particularly in Borno – by May 2019.
Progress: DFID identified the W4H interventions which should be taken up by the new Lafiya programme. These were incorporated into the terms of reference for the Lafiya contract, which will start shortly. A process for transitioning these interventions will be agreed and implemented during Lafiya’s inception phase.

Post intervention work in some W4H States has helped maximise sustainability and learning. W4H should prepare a short paper and presentation illustrated with case studies and lessons learned around the post-intervention approach, sustainability, and leveraging domestic financing - and present to DFID – by June 2019. DFID should consider replicating this approach in other programmes by building in post intervention phases for sustainability and learning.
Progress: W4H has drafted a paper on its sustainability approach, and hopes to present it to DFID as part of the National level learning event. DFID is also planning a workshop on sustainability and leveraging domestic financing in health, where lessons from W4H will be shared with SUNMAP2 (which also has a short post-intervention phase) and the new Lafiya programme.

In addition to the research study, W4H should prepare case studies demonstrating the impact of Foundation Year Programme graduates when they return back to their communities – by August 2019.
Progress: Two case studies have been finalised; one on Borno FYP building back better and the second, on impact of FYP graduates on family planning uptake.

W4H should conduct a tracer study to determine and demonstrate the progression of students from FYP through health-worker training and on to employment – by June 2019.
Progress: DFID and W4H agreed to incorporate the tracer study into the ongoing W4H research study.

DFID and W4H should amend the logframe to ensure milestone expectations are aligned with the annual review dates – by May 2019.
Progress: The logframe has been amended accordingly.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided