## Sheet1
PROJECT NAME | ST HELENA Short Term TC 2014/15 (ARIES 203507)
IMPACT | Impact Indicator 1 |  | Baseline (Dec 2013) | Milestone 1 | Milestone 2 | Target (March 2015)
Improved technical capacity to meet reasonable assistance needs and accelerate sustainable social and economic development in St Helena | Local revenue as a percentage of the recurrent budget | Planned |  |  |  | at least 50%
|  | Achieved | 50% |  |  | 55% (operational plan formula/ratio)
Source
SHG Finance Directorate end year information
| Impact Indicator 2 |  | Baseline (Dec 2013) | Milestone 1 | Milestone 2 | Target (March 2015)
| Population level maintained or increased | Planned |  |  |  | at least 4,158
|  | Achieved | 4158 |  |  | Average (4,087) (SHG state it was 4,046 in 2012/13)
Source
SHG Finance Directorate end year information
OUTCOME | Outcome Indicator 1 |  | Baseline (March 2014) | Milestone 1 | Milestone 2 | Target (March 2015) | Assumptions
Improved effectiveness of public service provision (measured against SHG’s Sustainable Development Plan targets). | Number of SDP targets achieving “green status" | Planned |  |  |  | 75% rated green, Reds are not above 19% | SHG prioritise TC inputs that support the top eight key result areas of SDP2
|  | Achieved | 67% rated green, 14% amber and 19% red |  |  | New SDP: 39% Green, 22% Amber, 17% Red, 3% Amber-Red. For 19% benchmarks not established yet.
Source
DAPM Tracker, SDP performance reports.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £2m |  | 0 | 0 | £2m | 100%
INPUTS (HR) | DFID (FTEs)
Programme Manager (0.3) SD/Health/Education/ Governance/Economist Advisers 0.4 (collectively)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2013/14) | Milestone 1 |  | Target (March 2015) | Assumption
Improved effectiveness of public service provision (measured against STTC outputs and a selection of prioritised SHG sector targets). SHG SHOULD REVIEW AND SUGGEST PRIORITISED TARGETS IF DIFFERENT | Effective use made of the STTC budget provision measured by percentage of TC outputs/reports delivered on time and to standard. | Planned | a) % of officers completing against total posts: 22% b)% of officers delivering to required standard on time against total completing |  |  | a) % of officers completing against total posts (28%) b) % of officers delivering to required standards on time against total completing (100%) | SHG recruit the range of technical cooperation officers envisaged in an economic and effective and manner SHG manage technical cooperation offers effectively and efficiently to support achievement of the desired outcomes
|  | Achieved | N/A - not previously measured. |  |  | a) % of officers completing against total posts (29%) b) % of officers delivering to required standards on time against total completing (58%)
Source
DFID records; SHG STTC monitoring reports and minutes of SHG/DFID monitoring meetings.
| Output Indicator 1.2 |  | Baseline (2012/13) | Milestone 1 |  | Target (March 2015)
| Percentage of prioritised capital programme delivered | Planned |  |  |  | 100% prioritised capital programme delivered.
|  | Achieved | 10% |  |  | 30% (input from DFID OTD Infrastructure Advisor)
Source
SHG Finance and Human Resource Department reports
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 | Milestone 2 (2013/14) | Target (March 2015)
50% | Completion of the child safeguarding action plan and delivery of 2014/15 objectives. | Planned |  |  |  | Completion of the child safeguarding action plan and delivery of 2014/15 objectives
|  | Achieved | N/A |  |  | The Action Plan is a live document and will be updated continually. In terms of the original plan, drafted in early 2014, around 85% is complete or in hand. (SHG input)
|  | Source |  |  |  |  | SHG recruit the range of technical cooperation officers envisaged in an economic and effective and manner
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See cell B19
INPUTS (HR) | DFID (FTEs)
See cell B21
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2013) | Milestone 1 (May 2014) | Milestone 2 (October 2014) | Target (March 2015) | Assumptions
Improved human resource capacity available in SHG and in accordance with the DFID TC protocol | Percentage of critical STTC posts agreed between SHG and DFID filled, and accompanied by agreed ToRs and contracts. | Planned |  | DFID and SHG agree a final prioritised STTC listing | DFID and SHG agree a revised TC Protocol. | 95% posts successfully recruited. | Both SHG and DFID have effective and efficient approval procedures that minimise TC recruitment timescales.
|  | Achieved | 2012/13: 100%, 2013/14: 86% |  |  | 71% of posts successfully recruited.
Source
SHG STTC monitoring reports and minutes of SHG/DFID monitoring meetings.
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (2010) | Milestone 1 ( July 14) | Milestone 2 (31/03/14) | Target (December 2014)
50% | Streamlined recruitment and induction processes for Technical Cooperation. | Planned |  | Review current recruitment and induction processes with improvement action plan created |  | Action Plan implemented
|  | Achieved | Limited advertising utilised and slow processes |  |  | Recruitment Process was agreed at BDG in October 2014
Source
|  | Human Resource Department reports |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See cell B19
INPUTS (HR) | DFID (FTEs)
See cell B21