Annual Review - Summary Sheet

Title: Democratic Governance Support Programme / DIÁLOGO – Diálogo Local para a Boa Governação
Programme Value: £7,987,196.71		Review Date: March 2016
Programme Code: 201958-102	Start Date: 1 year Inception from 15 Feb 2012, Implementation from March 2013	End Date: 28 Feb 2017

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

DIÁLOGO aims to contribute to improved governance, accountability and responsiveness at the municipal level through working with civil society, media and municipal institutions. It is a DFID programme led by DAI.

This annual review assesses the programme’s progress during its fourth year, March 2015 to February 2016. It draws heavily on an extensive Mid Term Review (MTR) carried out in 2015 by IDS. The MTR provides strong evidence that the programme is performing well and that the basic theory of change is effective. That is, when civil society, media and municipalities engage in an integrated way (i.e. when DIALOGO’s three sub-outcome areas are effective) municipal governance improves. The MTR notes that it is this combination that is the programmes’ strength: “Most key stakeholders agree that Diálogo is performing strongly. It is a pioneering programme, not because it focuses on municipal governance per se but because it is investing at scale in a unique combination of municipal, civic and media engagement strategies in five of Mozambique’s most politically and economically significant cities.”

As with previous annual reviews, Dialogo has met or exceeded all its output indicators on citizen participation in municipal governance; media coverage and public debate; and municipal institutions engagement with citizens. These processes have resulted in various concrete results (further details of these examples can be found in Annex 2):
- in Maputo this has included the improvement of solid waste collection, urban sanitation, lighting and security (including joint community-police patrolling);
- in Beira, citizens’ demands for more access to water, energy and market services and more consistently priced urban transport have been met;
- in Quelimane civic groups are better able to engage with non-municipal institutions around issues that are not local problems but municipal problems including water provision, hygiene of toilets in hospitals, access to electricity;
- in Tete civic groups’ lobbying, working with the business association CTA, contributing to the reduction in toll prices; and
- in Nampula, all Municipal Assembly sessions now have a specific session for citizens to discuss their demands with all assembly members.

Beyond these immediate results, the programme aims to sow the seeds for longer term change. The MTR provides an assessment of outcome level change demonstrating the emergence of a more informed citizenry who value the media as a source of information. The examples above support this assessment, highlighting a civil society that is more empowered (able to articulate demands); more politically informed (able to approach the relevant government institution); and more collaborative (able to work across groups including the private sector and media). However the MTR found that citizens were more skeptical about the value of CSOs and were less confident that the authorities would deliver on promises, despite some clear examples of municipal institutions responding to citizens’ needs.

The MTR highlighted several areas where the programme needed to focus on to be more effective. This Review highlights the key ones that DFID assesses as most important and provides more details one what DFID would like to see implemented. These include:
- the need to close the citizen observer element of the programme based on lack of value for money;
- the need to support the resolution of issues not entirely within the municipalities’ remit but that are important to citizens (e.g. sexual violence, livelihoods);
- the importance of balancing programme investment short term results (e.g. the resolution of practical local issues such as building a bridge) with more long term structural change (which should continue and increase – see recommendations);
- getting to a more strategic place on inclusion so that the programme considers issues not number of women/youth and assesses the layers of exclusions within these groups;
- an increased focus on learning in order to influence decentralisation policy, other decentralisation programmes in Mozambique and other programmes internationally; and
- the challenges related to sustainability particularly around collaboration between partners.

Summary of recommendations for the next year

Below is a summary of the main and more strategic recommendations of this annual review. More detailed and further recommendations can be found in the relevant sections.
N	Recommendation	Timeframe	Responsible
1	Generate and measure the sustainable impact of civic groups. This will mean a) assessing their impact beyond the direct membership; b) supporting them reach out and involve a wider range of citizens in their work (e.g. through closer collaboration with media); and c) identifying and then consolidating their key capabilities.	3 months to set out plan for each municipality	PMU
2	Tackle the harder issues that are most important to citizens e.g. sexual violence and livelihoods. This will: / a) support coalitions that bring together media, women’s groups, municipal authorities and the police to discuss prevention of sexual violence. / b) link up with supply-side and private-sector development programmes to broker dialogue between youth groups, municipal authorities and the private sector to discuss job-creation.	3 months to set out plan for each municipality	PMU
3	Balance the shorter terms results with an increased focus on long term structural/strategic changes based on a more coherent approach. This will involve: / increased municipal level co-ordination (rather than via PMU) to clarify roles and enhance joint working. / More analyse of and action to influence the key blocks to participatory governance in each municipality to address the structural causes.	3 months to set out plan for each municipality	PMU
4	Gender and inclusion: Responding to the detailed findings of the MTR set out an inclusion strategy that covers all strands of the programme. Steps will include: / recruitment of a gender/inclusion expert with international experience; / Identifying the priorities for women and youth in municipalities; / Identifying what prevents women and youth from participating meaningfully in governance issues at municipal level including economic, social and cultural barriers; / Within these groups (‘women’ and ‘youth’), identifying who are the most vulnerable and excluded ; / Analysing how the programme can address these issues directly and by working with others; / Link with BBC media	Recruitment by 3 months. Strategy by 6 months	PMU / DFID
5	Build sustainability into the media element by supporting media partners build links with other media organisations and sources of funding.	3 months	PMU
6	Support stability more explicitly e.g. can programme provide TA to municipalities on how they respond to civil unrest to ensure an appropriate response that calms rather than fuels violence? Links to recommendation 2.	immediate	PMU
7	Strengthen the work on learning and influencing. This should consist on a strategy that would include: / Influencing other municipalities and central government: / Passing learning to and influencing other programmes in Mozambique. / Internationally: going beyond Mozambique to share Dialogo's innovative approach?	3 months	PMU
8	Keep building the link with supply side programmes, particularly Prodem.	Throughout	PMU / with support from DFID
9	Value for Money: Set out a simple VfM strategy to drive the choice of indicators, assessment approaches, data collection and documentation. This should include: / Addressing the recommendations in the MTR; / Shifting the focus from economy and efficiency to effectiveness, including equity and sustainability. / DFID to consider how to use and share lessons learnt from VFM analysis and findings of the MTR.	3 months	PMU and DFID
10	Financial management: PMU to suggest how to complement grant making with other approaches to funding activities if feasible at this stage in the programme.	6 months	PMU
11	Contract management: DFID with PMU to consider if IDS should be contracted directly rather than through DAI.	Next year	DFID
12	Logframe: a) add outcome and output indicators on learning and influencing; b) disaggregating output 2; c) reduce outcome indicators while keeping the balance between perception and fact.

Annexes
Annex 1: DIALOGO Logframe
Annex 2: Dialogo change stories 2015
Annex 3: MTR
Annex 4: Value for Money matrix
Annex 5: Risk matrix
Annex 6: Progress against last year’s Annual Review

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201958/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201958/

DIALOGO aims to contribute to improved governance, accountability and responsiveness at the municipal level in Mozambique. DIALOGO works in five large urban municipalities (Maputo, Beira, Nampula, Quelimane and Tete) in a context dominated by significant political tension, which, together with the history of centralization in Mozambique, results in a lack of openness for dialogue and negotiation around municipal governance issues as well as a lack of attention on the same issues on the part of civil society and the media. DIALOGO therefore brings together citizens and municipal governments to improve governance and strengthen democracy at the local level facilitate consistent interaction and collaboration to result in positive changes in local governance.

Context
At the municipal level, democratic governance remains a work in progress. Municipal institutions were first elected in 1998, with elections taking place every five years and represent the only level of decentralised government in Mozambique. Municipal Councils can make autonomous spending decisions using their budget (80% from central transfer; and 20% from municipal taxes). However, what they can spend it on is limited as many of the services most vital to citizens (e.g. health, education, water, electricity) are still controlled by the Province (who have deconcentrated power only and administer central decisions).

The DIALOGO baseline study (from 2012) confirmed that citizens and municipal governments are not effectively communicating or partnering to solve local issues, resulting in little accountability for the policies and programmes funded or executed by municipal governments. It also confirmed that different municipalities present different challenges – both politically and in terms of the capacity of stakeholders. For example, the capacity of civil society is higher in Nampula than in Tete; while the municipal institutions in Quelimane are more responsive than in Maputo.

Local elections in November 2013 were competitive and resulted in some Frelimo mayors (the ruling party) voted out. Indeed, in the five Dialogo municipalities, three now have opposition Mozambique Democratic Movement (MDM) mayors and MDM led assemblies (Beira, Nampula and Quelimane). Of the two where Frelimo retained power, Maputo and Tete, Frelimo’s share of the seats in the assemblies significantly decreased.

The General elections followed in October 2014 with Frelimo retaining the Presidency and majority in the National Assembly, albeit with a reduced number of seats. The resulting new Government has not set out a clear stance on decentralisation despite the opposition Renamo’s demand for control of provinces where they won the most votes. This, along with other unresolved issues, has led to an increase in violent confrontations between the armed forces and Renamo during 2015 and early 2016. As a result, over 11,000 citizens have fled to Malawi and there are an unknown number of internally displaced people. The violence continues in the absence of any meaningful dialogue between the two sides.

Alongside the political fragility, the macro-economic context has become increasingly difficult. In 2015, vulnerability to external shocks led to a slowdown in growth, a reduction in foreign exchange reserves and rising inflation and food prices. The high levels of public indebtedness, for example from EMATUM, have proved difficult to manage. Life for citizens has been made even harder with drought in the south and the floods in the north. Recent initial results from a national poverty survey suggest some improvement in living standards but rising inequality.

The change in context, particularly the politicisation of the decentralisation debate, has impacted on the programme. The spill over from tensions in the broader political environment has meant the programme has at times been perceived to be against the ruling party of the municipality (e.g. pro-Renamo in Tete; but pro-Frelimo in Beira). Positively, in some municipalities, with the election cycle over, a more constructive relationship has been building between MDM Municipalities and Frelimo Provinces (for example in Quelimane) allowing Dialogo’s work on issues of joint interest (e.g. Health, education, security) to be more effective. And the dynamism of the urban governance environment underpinned by the competitive politics, supports both increased engagement from citizens and municipal uptake of participatory governance approaches.

Outline of the programme

The strategic vision of the programme is that regular, constructive interactions between citizens and local governments will improve governance and strengthen democracy at local level. Simultaneously, increased awareness of these interactions through media coverage and independent evidence should impact on national policy. As the different municipalities provide different challenges, DIALOGO has developed tailored theories of change for each of the municipalities to ensure the most adequate approach in each.

At the impact level citizens’ priorities will begin to be a part of the municipal agenda. In the target municipalities, the project will see an increase in the quality of citizen participation in municipal governance and citizens will report an increase in the accessibility and importance of municipal assemblies and councils.
At the outcome level there will be an increase of citizens who say that information accessed about Municipal Council business (e.g.: solid waste collection) is easy to both find and understand; an increase of citizens who say that help in addressing problems affecting the neighbourhood is always forthcoming from civil society organisations (CSOs); and an increase of citizens who feel their opinion is taken into account in community meetings.
At the output level, the programme will increase (i) the number of CSOs engaging with municipal institutions on priority issues; (ii) the number of civic groups supported on engagement practices; (iii) the number of media programmes on municipal governance and electoral processes; (iv) the number of communication initiatives to disseminate municipal information; and (v) will support municipality action plans.

DIALOGO is managed by a consortium led by Development Alternatives Incorporated (DAI) Europe, in partnership with COWI, and managed by a programme management unit (PMU) in Maputo. Further sub-contracted partners of this consortium include the Institute for Development Studies (IDS) in charge of the monitoring and evaluation component, CESC (Centro de Aprendizagem e Capacitação da Sociedade Civil) working mainly with civil society organisations and providing the key community facilitators, and IREX with a focus on media partners.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The Mid Term Review 2015 (attached at Annex 3) allows an assessment of progress at the outcome level since the baseline study of 2012 – not possible in previous annual reviews. The MTR analysis shows that: “in general citizens are more aware of the importance of municipal government and more included to raise their voice, but less satisfied with the level of government responsiveness in 2012.”

The table below provides details and shows a mixed picture. The indicators around citizen engagement with municipalities have been partly met; those around the media promoting public debate have been fully met; and those around the municipal institutions engaging differently have not been met.
Outcome Statement: Several actors interact effectively around municipal governance issues
Indicator	Baseline	Milestone / 2016		Achieved		Comment
Sub-Outcome 1: Organised citizens engage with municipal institutions around specific issues Indicator
1.1: % of respondents that say that they have municipal information (MTR)	Know about plan: 8.5 / Received information 16.5 / Easy to find: 12.5 / Easy to understand: 14	10.4 / 18.5 / 14.5 / 16		10.3 / 18.8 / 15.4 / 16.1		Met
1.2: % of respondents who consider that help in addressing problems affecting the neighbourhood is always or usually forthcoming from CSOs. (MTR)	0.61	4.6		1.8		Not met but three times higher than baseline.
1.3: % of respondents who feel that their opinion is fully, very or often taken into account in community meetings. (MTR)	Overall: 51.6 / Men: 56.3 / Women: 47.9 / Youth: 52.0	55.6 / 58.4 / 49.7 / 53.9		44.9 / 51.7 / 41.1 / 43.1		Not met: Lower than baseline. Significant risk area. (NB – milestones figures quoted by PMU are different to those in the MTR – IDS and PMU to resolve).
1.4: Level of CSO engagement capacity on municipal governance (Outcome Mapping – score out of 5)	1.9/5	3/5		3.4/5		Met
Sub-Outcome 2: Media promote public debate around municipal governance issues
2.1: % of survey respondents who agree fully or partially with the statement ‘The media provides valuable information about local issues that concern my community” (MTR)	56.8	61.8		66.1		Met
2.2: # of people that participate in media space for citizen voice on municipal governance (project reports)	Total: 0 / Maputo:0 / Beira: 0 / Tete:0 / Quelimane:0 / Nampula: 0	9,800 / 800 / 600 / 600 / 4000 / 3800		17,099 / 3348 / 971 / 1911 / 7369 / 3500		Exceeded
2.3: # of media outlets that use ICT to support citizen participation in media debates (project reports)	Total: 4 / Maputo: 1 / Beira: 1 / Tete: 0 / Quelimane: 1 / Nampula: 1	8 / 2 / 1 / 1 / 2 / 2		10 / 2 / 2 / 2 / 2 / 2		Met
2.4: Level of Media capacity to promote public debate around municipal governance issues and to work together with municipal institutions and CSOs (Outcome Mapping)	1.5/5	2.5/5		3.2/5		Met:
Sub-Outcome 3: Municipal institutions engage different stakeholders into municipal governance
3.1: # of participatory events organized by municipal institutions (project reports)	Total: / Maputo: / Beira: / Tete: / Quelimane: / Nampula:		60 / 5 / 4 / 1 / 20 / 30		38 / 18 / 3 / 1 / 5 / 11	Not met largely due to suspension of participatory budgeting in Quelimane; participatory planning in Nampula; and the MoU by the municipality of Beira. Output 3 has details.
3.2: % of survey respondents who feel that decisions taken in these meetings are acted on always or mostly (MTR)	Overall: 21.6 / Men: 20.4 / Women: 22.5% / Youth: 21.9%		25.6 / 22.3 / 24.6 / 23.9		11.0 / 10.1 / 11.5 / 10.0	Not met and less than baseline – area of risk
3.3: Level of Municipal Institutions capacity engagement with several municipal actors on municipal governance (outcome mapping)	24.5/5		4/5		3.6/5.	Not met – but on a positive trajectory

The awareness of municipal plans (outcome 1.1), increasing propensity to consider CSOs as allies in solving community problems (outcome 1.2), and perception of media as a useful source of information on local issues (outcome 2.1) suggest a more informed and critical citizenry emerging in Dialogo municipalities. But outcome indicator 1.2 and 1.3 show that citizens in every municipality except Tete are less rather than more willing to attend community meetings and are more sceptical that their voices will be heard in those meetings and that decisions taken will be acted on. There may be wider reasons behind this (e.g. lack of perceived response due to slow dispersal of funds to municipal level government) but the MTR notes it would have “expected to see a much stronger trend towards increased perception of the value of CSO as partners for local problem solving… it is questionable whether the civic group strategy will generate sustainable change”.

It is worth noting that the outcome indicators are largely based on the MTR’s survey asking 1, 200 citizens across the 5 municipalities their views on municipal governance. This type of survey measures the ripple effect in terms of change in the views’ of citizens the programme is not working with. So the MTR did not find evidence of significantly increased value of CSOs for local problem solving or that citizens’ felt their opinion would be taken into account of those it surveyed (i.e. largely not direct beneficiaries). But the MTR also noted that the workshop sessions with the direct beneficiaries provided anecdotal evidence of an incipient ripple effect with individual citizens and other neighbourhood groups seeking our Dialog-supported civic groups for help and advice in engaging with municipal authorities.

Recommendation: Capture the ripple effect: As the MTR states, the programme will need to work to capture this ripple effect through further participatory analysis with local stakeholders. One option would to do this during the Final Evaluation by IDS. But as a one-off study, this approach risks not capturing any change. Rather, the MTR suggests the PMU use a series of “what has worked and hasn’t worked” studies to capture mid-range impacts that go beyond the civic group members. It could also involve asking the civic groups themselves to analyse why citizens have become more sceptical about CSOs. Such a task, while difficult, would be in line with the Secretary of State’s challenge to the programme to innovatively capture its outcomes. Output 1 has recommendations for how to better generate the ripple effect.

The indicators for the media have all been met or exceeded. This is a significant area of strength for the programme although needs remain around sustainability and gender (see output 2 for details).

Outcome 3.2 shows that municipalities are overall seen as significantly less responsive than in 2012 (by almost 50%), particularly in Quelimane. In some cases this perception may be more linked to raising expectations than the actual behaviour of the government and indeed the MTR found that levels of trust amongst citizens in government are in decline across Mozambique. But the perception of less responsive municipal governments than in 2012 remains a significant concern. The programme will want to support Quelimane in particular not only be more responsive but be perceived as being more responsive. Output 3 has further details.

The other method for capturing impact level change is by assessing change upwards rather than sideways e.g. how the direct beneficiaries have used the programme. The outcome mapping captures this through a process of peer-reviewed self-assessments. This has more positive evidence that the programme is generating change in terms of increased engagement capacity on municipal governance issues by CSOs, the media and the municipalities (outcomes 1.4; 2.4; and 3.3 respectively). Indeed the MTR found “observable growth in systemic engagement capacity for multi-stakeholder dialogue on municipal governance issues acquired at the level of the municipal governance system as a whole”.

Recommendation: Update logframe. There should be a way to streamline the outcome indicators (some reflect output level activity) but one will need to be added to bring in the influencing of the others beyond the five municipalities the programme is doing, and should do more (see output 3 for detailed recommendations on this).

Overall output score and description

The full logframe is at Annex 1. Overall output score for the programme is A+ as outputs have exceeded expectations.

Key lessons and actions

The MTR highlighted several areas where the programme needed to focus on to be more effective. This Review highlights the key ones that DFID assesses as most important and provides more details one what DFID would like to see implemented. These include:
- the need to close the citizen observer element of the programme based on lack of value for money;
- the need to support the resolution of issues not entirely within the municipalities’ remit but that are important to citizens (e.g. sexual violence, livelihoods);
- the importance of balancing the consolidation of short term results (e.g. the resolution of practical local issues such as building a bridge) with more long term structural change (which should continue and increase – see recommendations);
- getting to a more strategic place on inclusion so that the programme considers issues not number of women/youth and assesses the layers of exclusions within these groups;
- an increased focus on learning in order to influence decentralisation policy, other decentralisation programmes in Mozambique and other programmes internationally; and
- the challenges related to sustainability particularly around collaboration between partners

Has the logframe been updated since the last review?

Yes. Some baseline figures have changed as the MTR process identified some discrepancies. Some changes were also made following last year’s annual review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civic Engagement: Mobilising, sensitising and supporting citizens to engage on municipal governance.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1. # of civic groups and individuals assisted on engagement practices	98 civic groups and 1, 706 individuals assisted on engagement practices: / Maputo: 12 groups and 187 individuals / Beira: 13 groups and 392 individuals / Tete: 15 groups and 211 individuals / Queli: 29 groups and 287 individuals / Nampula: 29 groups and 629 individuals	Milestone exceeded / 140 civic groups and 2, 395 individuals assisted on engagement practices: / Maputo: 18 groups and 621 individuals / Beira: 35 groups and 451 individuals / Tete: 19 groups and 312 individuals / Queli: 35 groups and 372 individuals / Nampula: 33 groups and 639 individuals
1.2. # of coalition/ synergies between municipal actors working around priority issues	61 coalition/ synergies between municipal actors working around priority issues / Maputo: 19 / Beira: 10 / Tete: 9 / Quelimane: 12 / Nampula: 11	Milestone exceeded / 80 coalition/ synergies between municipal actors working around priority issues[1] / Maputo: 21 / Beira: 12 / Tete: 12 / Quelimane: 23 / Nampula: 12
1.3. # of municipal actors that engage with municipal institutions on current priority issues (disaggregated by type of organization - youth and gender focused)	138 municipal actors that engage with municipal institutions on current priority issues (31 of which are gender and youth focused) / Maputo: 15 (6 gender and youth) / Beira: 17 (2 gender and youth) / Tete: 16 (5 gender and youth) / Quelimane: 42 (11 gender and youth) / Nampula: 48 (7 gender and youth)	Milestone exceeded / 196 municipal actors that engage with municipal institutions on current priority issues (33 of which are gender and youth focused) / Maputo: 28 (3 gender & youth) / Beira: 22 (5 gender & youth) / Tete: 47 (5 gender & youth) / Quelimane: 51 (13 gender & youth) / Nampula: 73 (6 gender & youth)

Key Points

This output has been exceeded across all indicators. The Theory of Change (ToC) expects to see “organised citizens engage with municipal institutions around specific issues”. The review team saw that the ToC was clearly holding true with civic groups engaged and coalitions of change being built between Dialogo partners. Concerns about the prioritisation of issues and the need to tackle more structural ones are highlighted below.

Details

1.1: Exceeded in all municipalities. This assesses the extent of programme support on engagement practices/social accountability tools. Civic groups, with support from the CESC municipal facilitator, and some local NGOs use tools such as community score cards (CSCs) and community action plans (CAPs) to identity local needs and monitor progress. This approach supports an “issue-based approach” which leads to strong community engagement and ownership and recognises the need to build local capacity.

In Quelimane the review team met with some impressively motivated civic groups. With support from the Dialogo/CESC facilitator, these groups had carried out three CAPs (in 2013) which identified the need for safe drinking water, latrines and better roads. Following meetings with the municipal institutions some of these priorities were now being addressed. Disappointingly however, the public toilets that the review team visited, built as a result of the CAPs, were not functional (no water); and the “casa de bairro” (community centre) had not been built in the bairro that requested it, but a neighbouring one. The PMU is aware of these issues and is following up. But it suggests a need for longer-term monitoring by civic groups (in order to follow up with the water institution, FIPAG); and better planning by the municipality (to only build toilets once there is agreement from FIPAG to provide water).

In Beira, the first CRC on municipal public services is being carried out which given the generally closed nature of the municipality is a considerable step forward. In Maputo the CSC on solid waste, which identified the need for better management of local providers, supported the municipal decision to use citizen feedback, sent through an app on mobile phones, to manage their contracts with service providers. While this model used apps on mobile phones for citizens to report which will not be appropriate everywhere, the principle of citizen feedback to manage contracts is one that could be applied in other municipalities.

1.2 Exceeded in all municipalities. This indicator assesses the extent to which Dialogo partners are working together. The clearest examples are of coalitions between the media and civic groups which are often mutually beneficial. I Quelimane, the review team heard how the community radio stations received information and the civic group benefited from greater reach and exposure.

A further example taken from 2015’s Change Stories (Annex 2) is set out below. It notes Dialogo’s potential to prevent civil unrest. Participation as a means of preventing instability is an important lesson for Mozambique’s governments at all levels and integral to the argument the programme is making at the central level for more open decentralised government.

New transport tariffs for Beira, but no popular unrest / The last time that municipal council of Beira tried to increase the tariffs for public transport within the city of Beira, it ended up in popular unrest that forced the municipal council to freeze the decision. It was in 2012 and since then there has not been an increase in prices, even with constant complaints from the service provider associations. The service providers have been struggling to maintain their operations at the old prices, so they decided unilaterally to shorten the routes, which means that the users were paying the double of the price to do the same route. Over the past few years, the municipal council have been trying to tackle down the routes shortening, with no success. / Being a key local issue, DIÁLOGO partners suggested a new approach to the municipal council to address the issue, which calls for a broader consultation and new awareness raising actions prior to a decision about a potential price increase. / How did DIÁLOGO contribute to the solution? / A survey was conducted to get user perceptions about the increase of tariffs and the quality of services. / Focal group discussions were conducted in the most sensitive neighbourhoods involving the municipal council, service providers, users and DIÁLOGO local partners in order to share the findings of the survey and to look for consensual solutions around the new price. / Awareness campaigns involving local authorities, community’s leaders, civic groups and local media were conducted. / What was been achieved to date? / A new tariff went into force without any major incidents. / More municipal police on the streets providing oversight of service provider activities to tackle routes shortening. / A new hotline was activated to allow for better interaction between citizens about the quality of services provided. / The way forward? / What should be emphasised in this process is not the result itself, but the adopted strategy to achieve the goal. Based on this successful experience, DIÁLOGO’s partners in Beira are using the same approach to solve other critical issues.

The least successful example is probably around CSOs working together. As the Review Team witnessed (during discussions between CSOs on a Municipal Platform in Quelimane), mistrust was high preventing effective collaboration. The Annual Report states that in Tete, a similar problem was overcome with the support of MASC to build trust and joint working. The PMU may want to use this model again in Quelimane - and other municipalities given that this is likely to be an issue across the board.

1.3 Exceeded in all municipalities. This indicator measures “engagement” as all formal or informal contacts[2] between municipal actors to influence behaviours, attitudes or decisions of municipal institutions. This indicator includes the participatory budgeting (PB) work the programme has been doing in Nampula, Quelimane and Maputo with support from the World Bank. The municipalities have set aside a proportion of their budget (around 10% in most) to be allocated on the basis of the results from the PB framework. The review team saw this had given the programme a real framework for engaging with municipal institutions (further details on PB are in output 3.3).
[2] DIALOGO is a complex programme operating in a challenging environment and therefore needs to work formally with partner institutions while also networking informally to be able to gather knowledge and promote the concept of the programme.

An different example is from Maputo where Dialogo’s support the CSO, RuTH to bring together academia, private sector and public providers to suggest short and long term solutions to the transport crises. This contributed to the Council acting to ensure better public transport for example through establishing the exclusive track for buses.

The gender and youth targets have also been met. Indeed, the MTR notes that implementing the programme though women’s and youth groups has allowed those involved to access an arena from which they have been traditionally excluded. But it also notes that: the strategy adopted was to work directly with women and youth groups, with little reflection about what promotion of gender equality and social inclusion should look like in the context of a programme that aims to foster dialogue between citizens and municipal institutions.”

Challenges and recommendations

Recommendation 1: Generating sustainable impact of civic groups
As noted in the outcome section, the PMU will need to take steps to measure the “ripple effect” to demonstrate the programme’s sustainable impact. It will also need to look at how to generate this ripple effect through for example encouraging the civic groups to work more openly (limits on resources incentivises them to stay small); mentor others in their community; and report back on what they do. Using the media to reach a wider audience on rights and responsibilities would be a key part of this (e.g. broadcasting the theatre groups’ performances).

The other element of generating sustainable impact is around building the capacity of civic groups and establishing mechanisms that allow them to continue to hold the government to account even when the programme closes – and they are no longer being paid. CESC with Dialogo will have some ideas already but needs to consider what capacity they want to focus on “leaving behind” in each municipality (the ability to do CAPs? Or CRCs? Or both?) and then formalise a long term municipal commitment to responding to these (e.g. to using CAPs in municipal plans). This will also involve leaving effective CSO platforms were possible and using MASC to support this where necessary.

Recommendation 2: Target the more difficult issues that really matter to citizens
The MTR found there were some areas of good fit on what the programme was working on resolving and on what citizens cared about (particularly around the rehabilitation of infrastructure, improved drainage, and better street lighting). However it also noted a discrepancy between the programme investment and local priorities, particularly around employment, education, crime/security and social behaviour and relationships. Indeed, all the civic groups the review team with quoted employment as their biggest concern. This suggests the programme is not always aligning its support to citizens’ most pressing needs.

This discrepancy is in large part because the MTR assessed the priorities of a different set of citizens using a different methodology (survey and focus group discussions) that did not restrict citizens to prioritising within municipal competences as the programme does. The programme’s more narrow approach was positive in that it allowed them to build coalitions around the less difficult issues (e.g. waste collection) and as requested by DFID, deliver results in terms of municipal governments acting to address citizen’s needs. But at this stage in the programme, with the ToC established and the credibility of the approach in place, the programme should, on the basis of clear criteria, start to tackle the more difficult issues that really matter to citizens. While DFID needs to be realistic in terms of can be achieved in the limited time left, the programme needs to start getting beyond its comfort zone and focusing on the areas that matter most to citizens, even if only partly within the municipal remit.

MTR: For example, Diálogo could support coalitions that bring together media, women’s groups, municipal authorities and the police to discuss prevention of sexual violence. The programme could also link up with supply-side and private-sector development programmes to broker dialogue between youth groups, municipal authorities and the private sector to discuss job-creation.

Recommendation 3: Balance addressing individual issues with a more coherent, strategic approach at each municipality
Collaborative working between its partners is integral to the Dialogo approach and one which the PMU strives to promote. The initial idea was that CESC would lead the work with civic groups to identify issues of concern; the Dialogo partner NGO would seek to influence the municipal institutions; and the media would underpin both. But as was clear during the review team visit, partners were not always clear on the role or added value of others. Establishing municipal level co-ordination mechanisms, led by either the lead NGO or the CESC facilitator would certainly support a more coherent municipal approach and free up time for the PMU to focus on central policy influencing. This has been raised in previous Annual Reviews as it is simply not possible for the Programme Management Unit (PMU) to do everything.

As part of this more coherent approach, the NGO or CESC facilitator in each municipality could move to assessing the structural issues that underlie and are common to the practical issues. These structural issues are not only based on sectors (e.g. sanitation, security, land management); but also about the ways of working (e.g. is it that the municipality is not allocating resources transparently; are procurement processes weak resulting in low quality contractors; is there a lack of co-ordination with provincial government on water and electricity etc). The NGO can then lead on influencing the municipality on these structural issues working with other donor programmes. This would allow the programme to have increased and more sustainable impact rather than being restricted to resolving specific issues.

However, this would require the local NGO to have significant analysis capacity and to understand the way municipal governance works, including budgeting. It will be the case that for some Dialogo partners it will be more effective use of the last year to consolidate what they know (e.g. embedding participatory practices) rather than to attempt a more strategic approach now. But if the programme is extended, and certainly in Nampula, the focus can shift.

Recommendation 4: A strategic approach to youth and gender; and assess the degrees of exclusion
The MTR highlights that working with women and youth groups is not enough, there needs to be an assessment of the need/issue the programme is seeking to overcome; the answer to which might not be working with women or youth groups. The need for a more strategic approach to gender was raised in previous Annual Reviews but the MTR notes ”overall DFID has not provide clear guidance to PMU on what it wants to see”. While absolutely correct that DFID did not provide a prescriptive definition of what the programme should do this does not appear an adequate reason for a lack of strategy.

There are three layers of intervention for Dialogo to impact of gender inequality and exclusion:
- Ensuring municipalities deliver services that meet the needs of women and youth;
- Enabling women and youth to be a part of dialogue with municipalities in order to ensure accountability and responsiveness;
- Using the process of bringing women and youth into the conversation to challenge perceptions about the most excluded groups, their capacity and capabilities to be leaders and change agents within their communities.

Key areas for urgent action under a revised gender strategy are:
- recruitment of a gender/inclusion expert with international experience to help the programme analyse gender dynamics and identify relevant aspects of social exclusion to inform its programming
- What are the priorities for women and youth in municipalities where Dialogo is working. ongoing disaggregation of survey and consultation results, analysis of needs and priorities by gender and sex to ensure gender/youth sensitive service delivery
- what is it that prevents women and youth from participating meaningfully in governance issues at municipal level? This analysis should look at economic (i.e. lack of money for transport), social (i.e. time poverty) and cultural (i.e. perceptions of women/youth, discrimination, lack of self esteem/belief to speak up) barriers.
- Within these groups (‘women’ and ‘youth’) who are the most vulnerable and excluded? How can the programme address these issues?
- How can it work with others to address these issues?

As the MTR highlights there is a: “risk that more marginal voices will be neglected”. The new strategy should therefore go beyond gender and youth to consider social difference and degrees of exclusion and vulnerability.

.

Output Title	Strengthen and Engage Media
Output number per LF		2	Output Score	A +
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1. # of interactive media transmissions and articles (radio, television, newspaper) on municipal governance	Total:354 / Maputo: 70 / Beira: 40 / Tete: 30 / Quelimane: 70 / Nampula: 144	Exceeded / Total: 419 / Maputo: 91 / Beira: 40 / Tete: 43 / Quelimane: 85 / Nampula: 160
2.2. # of trained journalist on several issues	65	Exceeded / 92
2.3 # of media programs and articles about electoral process from media grantees	n/a (the target for this year is 0 as this indicator was targeted for the run-up to the local elections which happened during year 1 of implementation).	n/a
2.4. # of investigative journalism pieces on priority issues reported by independent media	0	Exceeded / 5 (1 in each municipality)
2.5. # of media outlets where ICT were set-up	0	Exceeded / 2 (Beira and Tete)

Key Points

All indicators exceeded. Under Output 2, strengthening media engagement, DIALOGO’s theory of change expects to see that “media promotes public debate around municipal governance issues”. The MTR notes that “media are increasingly valued as a source of information, but not yet seen as partners for efforts to resolve local problems”. The media partners that the review team met with, confirmed that DIALOGO support (often very practical in terms of the buying of equipment and providing training) had allowed them to both involve citizens more and focus on municipal governance issues. Gender remains a work in progress and sustainability is a concern.

Details

2.1 Exceeded all municipalities. The target number of interactive media-transmissions and articles on municipal governance issues was exceeded. This relates largely to the work of community radio stations that use Dialogo-provided equipment to interview citizens in public spaces to report on their views. The review team met two local radio stations in Quelimane (one led by nuns and the other by a youth group) both impressively committed to supporting citizens’ voice and working in their spare time for small subsidies. Both confirmed that the equipment provided by Dialogo allowed them to include more citizen’s voices and opinions in their broadcasts.

2.2 Exceeded. 65 journalists received training on radio editing; radio journalism; governance; social media and digital tools; and business plan creation and management for financial sustainability. The journalists benefiting from the training are from all media partners in the 5 target municipalities.

2.3 Exceeded. Five investigative pieces were carried out. These were scheduled to have taken place in 2014 but were delayed to 2015 given the difficulty of doing them in the pre-general election environment in 2014. These pieces were selected through a challenge fund launched in October 2014 and published during 2015. They covered:
- Tete: the impact of the boom due to the investment in the extractive industry on real estate speculation, urban planning and the use of natural resources.
- Nampula: decision-making behind how the public water system is being expanded.
- Maputo: how the municipal rubbish collection is being used.
- Quelimane: the results of the 2011-2014 round of PERPU (urban equivalent of 7 milhoes) assessed for effectiveness.
- Beira: the political and administrative conflicts between the state and municipal governments and the impact this has on the provision of services to citizens.

The radio partners interviewed the authors and held debates on the topics.

2.5 Exceeded. Information and communication technology (ICT) was set up in two media outlets during the past year of implementation – one in each in Beira and Tete. These were new media partners to the programme.

Challenges and recommendations

Recommendation 5: Generating sustainable change
The community radios appear committed to both raising municipal governance issues and interacting with citizens – as such this is a sustainable change. But what other sustainable changes will the programme support, particularly in terms of capacity? More links could be established with other Dialogo media organisations in a mentoring scheme as a means of both building individual capacity and learning lessons across the programme.

Recommendation 6: Gender
The MTR notes that media is the weakest component in the programme on gender/inclusion. Despite
media partners ensuring half of their interviewees are women and youth, and positive examples of the programme supporting organised women’s groups in engaging with the media, there are a number of issues affecting women’s participation in media activities. These include language barriers and gendered access to and control over mobile phones. These issues have been raised previously and reinforce the need for a highly competent gender/inclusion expert to make a comprehensive assessment of the programme. This needs to include shifting focus so that women/youth are the producers of news, not just the audience of the news. A first step would be to disaggregate indicator 2.2. DFID to explore link with BBC World Action.

Output Title	Engagement of Municipal Institutions
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1.# of communication initiatives to disseminate municipal institution’s information	Total: 14 / Maputo: 4 / Beira: 2 / Tete: 0 / Quelimane: 4 / Nampula: 4	Exceeded / Total / Maputo: 14 / Beira: 1 / Tete: 3 / Quelimane: 9 / Nampula: 3
3.2. # of DIALOGO Municipal Technical Support Plans designed and agreed	Total: 5 / Maputo: 1 / Beira: 1 / Tete: 1 / Quelimane: 1 / Nampula: 1	Met / Total:5 / Maputo: 1 / Beira: 1 / Tete: 1 / Quelimane: 1 / Nampula: 1
3.3 % of implementation of Municipal Technical Support Plans (% annual activities)	Maputo: 80% / Beira: 20% / Tete: 0% / Quelimane: 90% / Nampula: 95%	Met / Maputo: 80% / Beira: 80% / Tete: 33% / Quelimane: 60% / Nampula: 73%
3.4 # of dissemination/advocacy activities on lessons learned /best practices/ municipal studies beyond target municipalities	5	Exceeded / 10

Key Points

Indicators have been met or exceeded. For Output 3, municipal engagement, DIALOGO’s theory of change expects to see “municipal institutions engage with different stakeholders on municipal governance”. Based on feedback from the municipal representatives from the councils and the assemblies in the focus municipalities and the DIALOGO annual report, DIALOGO has allowed them to improve their understanding about different approaches to municipal governance, particularly the added value of participatory governance (planning and budgeting) as well as regular interaction with local stakeholders and communities.

Details
3.1 Exceeded. Activities under this indicator included, among others reproduction and dissemination of the municipal activity plans, budgets and key legislation. DIALOGO helps them disseminate this information through the production of a municipal newsletter, website, and a hot line.

3.2 and 3.3 Met overall. The targeted number of Municipal Technical support Plans designed and agreed was met for the past year (1 in each municipality[3]), but the implementation of the annual activities of these plans was not fully met in Quelimane and Nampula. These plans included actions such as support to improve the respective municipality’s communication capacity and their ability to deliver services based on need, including using participatory budgeting. This is largely done through technical assistance.
[3] The plan for Tete was designed but not yet formally agreed. However activities have started.

The failure to meet the implementation target in Quelimane stems from the municipal council decision to suspend the participatory budgeting process on the basis of a lack of resources and the need to repair damage done by flooding. This was damaging to the credibility of all involved (Dialogo partners and the Council). The programme Annual Report states that in response to this, the programme is now supporting the Council with a campaign to raise more taxes (although the Council did not mention this to the Review Team). However a more appropriate response would be to support the Council’s budgeting processes as the issue appears to be more a lack of planning rather than a lack of resources. In Nampula the target was missed due to the Council’s decision to focus on the participatory budgeting process and temporarily suspend its other communities meetings.

The targets for Tete (0%) and Beira (20%) were very unambitious and both exceed their targets. In Tete progress has been made by focusing on the Municipal Assembly rather than the Council the programme The Programme also extended its civic engagement network through the creation of a civil society platform for municipal governance and by revising the projects of the local NGO partners, for example creating community development committees to work with municipal institutions. The addition of media in Tete has also increased the coverage of municipal governance issues and increased local debate.

In Beira, the programme has faced particular difficulties. The Council suspended the MoU with the programme believing it to have supported Frelimo civic groups. The PMU acted swiftly to resolve the issue and the MoU was reinstated. The Council has since become more open to collaboration with DIALOGO partners, which has opened the door for DIALOGO to support the first CRC in Beria and provide training to municipal assembly members.

The issue of double administration continues to cause difficulties. This is true in the three DIALOGO focus municipalities (Beira, Nampula and Quelimane) where the municipality is led by the opposition party MDM while the district and provinces are led by the ruling part Frelimo. One risk under this current set-up is that the two levels of government work around each other and therefore duplicate many processes and efforts. The PMU must continue to closely monitor the political and administrative situation and work with the Ministry of State Administration (MAE), the National Association of Municipalities (ANNAM) and other key actors to improve municipal management and avoid duplication of administration. DIALOGO should also continue to play an active role by bring together municipal, district and provincial government actors within the focus municipalities to clarify roles and responsibilities and facilitate cooperation.

3.4 Exceeded. This indicator captures DIALOGO activities that aim to disseminate lessons learned, best practice studies, or to promote exchange among target and non-target municipalities. Activities include workshops, meetings, publications, newsletters, and websites with resources for municipalities. During 2015 this included supporting the ANNAM conference in Pemba, exchanges of lessons learned between Quelimane and Mocuba, exchanges in Maputo on transportation and urban dynamics around safety, the National Urban Forum (a Cities Alliance initiative), and international exchanges in Zimbabwe and Angola (Urban Challenges workshop) with other DFID governance programmes.

Challenges and Recommendations
Recommendation 7: Develop a learning and central policy influencing strategy
In order to generate sustainable change that is both lasting and goes wider than the five target municipalities, the programme must take what it has learnt and use it to influence others, particularly government. This is clearly in the ToRs between DFID and DAI.
This is not though adequately reflected in the logframe (output 3.4 is very narrow) which has caused the misunderstanding that this is not valuable to DFID. However, leaning/influencing element is integral to the success of the programme and a comprehensive strategy is required that can then be used to provide output indicators.

This strategy should include.
Influencing other municipalities and central government: On what: The strategy should pick out the key issues that Dialogo wants to influence others around based on its experience and what it assesses as a key block to more effective municipal functioning. This might include citizen engagement (including participatory budgeting); and double administration. How: through increased exchanges with other municipalities and the PMU becoming more actively involved in central policy debates on decentralisation in Maputo. This will involve working with MAE and ANNAM but also other programmes.
Passing learning to and influencing other programmes in Mozambique:  This is starting but the systemic gathering of lessons learnt and the sharing of them is key to more lasting sustainable impact.
Internationally: almost every civil society programme in Africa has been influenced by SAVI.  So how will Dialogo go beyond Mozambique to share its innovative approach?

The MTR itself has useful data and lessons relevant to those outside of Dialogo, particularly other municipal programmes. The Strategy should include how the MTR will be used to influence others.

Recommendation 8: Keep building the links with supply side programmes
The MTR notes that “Dialogo has developed considerable convening power, which the programme uses effectively to strengthen interactions among different organisations in favourable contexts. In less favourable contexts…the programme’s approach will need to be complemented by additional tailored engagement strategies...to build on existing links with supply-side initiatives to seek systematic co-ordination”. The PMU have been working hard on this and are in regular communication with other programmes. For example, helping set the agenda for the Cities Alliance National Urban Forums and ensuring they include debate on participatory governance. But this would benefit by being more formalised through MoUs that set out how the programmes will work together, particularly with Prodem.

Recommendation 9: Build the link to stability
The UK Aid Strategy has a greater focus on stability and it is an area of increasing concern to DFID Mozambique. Risks of instability in Mozambique are increasing not only due to the lack of resolution between Frelimo and Renamo (see context section) but also due to the negative trends in the economy which could lead to an increase in civil unrest, particularly in urban areas (see risk matrix at Annex 5).

The programme has already supported the resolution of conflict through open discussion and dialogue (see the Beira example in output 1). Could it do more to demonstrate and measure this impact as well as to more explicitly support it. For example, provide TA/sharing of lessons to municipalities on how they respond to civil unrest to ensure an appropriate response that calms rather than fuels violence? Links to recommendation 2 on targeting the more difficult issues that are not entirely within the Municipalities remit.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers of the programme have not changed from previous years and include:
- Travel costs
- Municipal workshops
- Direct and indirect staff
- Administrative overheads
- Grants

The cost drivers are tracked as part of the value for money (VfM) monitoring (annex 4) and the programme has historically performed well regarding the key cost driver metrics. After the first year of implementation, the project has normalised costs, expenditures and activity management, thus allowing it to have better control in order to meet its VfM targets consistently.

VfM performance compared to the original VfM proposition in the business case

The MTR states that ‘The economic appraisal and value for money analysis in the original business case do not provide an ideal framework to assess Diálogo’s VFM in monetary or quantitative terms now or at final evaluation. However, they offer a useful backdrop for qualitative analysis of some of the programme’s key VFM assumptions’. Some assumptions in the original analysis in the BC still prove valid and relevant namely: the rational for DFID’s investment in municipalities, the value the programme was expected to deliver and the programme’s management model and grant making approach.

One of the key findings of the MTR is that ‘DIALOGO benefits from the PMU’s strong intuitive VFM analysis and efforts to drive better VFM, but it lacks an explicit VFM strategy’. This has reduced the value of its VFM matrix as the indicators are assessed to be better suited for reporting rather than learning or supporting VfM judgements. Despite the lack of an explicit strategy, DIALOGO has ‘demonstrated that VfM thinking plays a significant role in management decision-making, including programme adaptation’. The MTR evidence suggests that the indicators have been critical not only for DFID’s monitoring of DIALOGO’s VfM but have also enabled and triggered the programme’s VfM thinking.

The report also provides useful insights and recommendations on how to make pragmatic adjustments to the indicators for the remainder of the programme in order to make the VfM framework more effective and useful.

Assessment of whether the programme continues to represent value for money

The MTR found it difficult to reach an absolute judgement on whether DIALOGO is achieving VfM. This was because of: the difficulty in assessing VfM in complex governance programmes; the nature of DIALOGO’s contract; data availability; indicators and the complicated nature of the contribution analysis.

The MTR assessed the programme to be performing reasonably well in the areas of economy and efficiency. It assessed the indicators as reasonable, useful for learning and demonstrating the programme is delivering VfM.

In terms of effectiveness, the MTR found variances across municipalities (to be expected given the varying contexts). It also highlighted concerns over the relevance of efficiency indicators, particularly how these are collected and assessed; and that although difficult to control, effectiveness can be optimised through financial and human resources allocations by using learning from monitoring and review processes. The MTR recommends that now that the programme is consolidated and showing positive VfM trends in economy and efficiency, the focus should shift to effectiveness, including equity and sustainability. The report states that ‘…providing issues of equity and sustainability are addressed, it could be argued that by the end of the programme, DIALOGO should have achieved reasonable value for money within the context of far more realistic ambitions than those included in the original business case’.

The MTR provides a full analysis of the utility of current VfM indicators and recommendations for refining them for the remainder of the programme. This should be used to inform the discussions between the PMU/DFID on how to improve the VfM matrix, collection of evidence and analysis going forward.

Below is a discussion of the performance against the current VfM indicators, along with findings from the MTR. The complete VfM Matrix can be found in Annex 4.

Economy

Cost per major cost driver: 1) domestic RT airfare (per trip); 2) municipal learning workshops (per workshop); 3) PMU staff costs (as % of overall spending for period); 4) external consultant costs (total per day of consultancy); and 5) Maputo office administrative costs (as % of overall spending for period).

Indicators relating to the average cost rates of items associated with key cost drivers suggest that most are in line with targets.

% of grants awarded on a competitive basis

This VFM metric is not used as it was decided to remove the Challenge Funds grants from the grant portfolio due to a lack of viable options of grantees.

MTR findings:

The PMU encourages economy in its own procurement, the procurement it undertakes on behalf of the municipal councils and also in the negotiation of grants.

Grant budget negotiations are informed by cost driver and VFM consciousness, but in some instances too great a focus on economy could undermine effectiveness and value for money.

DIALOGO shares office space and resources with other programmes. This has allowed the programme to save more money and created the potential to maximise the achievement of outputs with the budget committed.

Efficiency

Cost per civic group supported, and per person participating in media space for citizen voice on municipal governance issues during the reporting period

The cost per civic group supported was under target for Y1 (£3,560 with target at £15,000), over target for Y2 (£8,527 with target at £5,000) and under target for Y3 (£8,471 with target at £10,000). This cost will tend to decrease as the number of civic groups the programme works with increases.

Similarly, the cost per person participating in media space for citizen voice on
Municipal governance issues, has remained well below the target of £15 per person since Year 2, as the programme added more media partners and worked smarter to obtain better VFM.

# of days to process a grant (from announcement to first fund transfer, for Challenge Fund grants; from presentation of initial proposal to first fund transfer, for non-competitive grants)

The number of days to process a grant has fluctuated throughout the life of the project, while the targets went from 45 days in Year 1 to 30 days in Years 2 and 3. Using lessons learned and improvement in internal processes the most recent grants in Year 3 took 28 days to process..

% of DIALOGO budget spent on direct programmatic support versus administration and other overhead costs

For the life of the project DIALOGO has averaged spending 67% of its budget on direct programme support versus 33% on administration and other overhead costs. This indicator allows DFID to track if the spend is happening according to the commercial proposal and therefore provides some level of control given the nature of DIALOGO’s contract. The MTR highlights that DIALOGO’s management model appears to be expensive particularly when benchmarked with other similar programmes. This is something that will be looked at in more detail at final evaluation.

Cost per beneficiary per major objective included in annual municipal engagement action plans

This VfM calculation began in Year 2 once the municipal action plans were created and there was enough data on beneficiaries to make reasonably useful calculations. The target for Years 2 and 3 was £12.50 per citizen benefitting from improved interaction and communication. This amount has averaged £4.91 per citizen for the life of the project. The target for Years 2 and 3 is £35 per citizen benefitting directly from improved practices of accountability and consultation. This amount has averaged £24.48 per citizen for the life of the project.

MTR findings:
The media component appears to be relatively efficient, especially in Nampula and Quelimane.

The PMU has succeeded in making economies in the project support budget that could increase efficiency; however it needs to be careful this does not unintentionally undermine effectiveness and overall VFM.

IDS, COWI and the PMU agree that the overall MEL system is not delivering optimal VFM, mainly due to lack of integration between the two tools.

Effectiveness

# of activities developed in collaboration with complementary programmes / implementers

Historically the project has developed 80% of its activities in collaboration with complementary programmes/implementers. During Year 3 the programme collaborated with many other organisations including the World Bank, ANNAM, GIZ, the National Urban Forum with Cities Alliance and the Governance Informal Group. Approximately 82% of activities were created in collaboration with complementary programmes/implementers, thus surpassing target of 40% by a healthy margin. DIALOGO is collaborating with other actors strategically in ways that should increase the programme’s potential effectiveness, although narrative reports have not always documented this well.

.% of grant-funded projects implemented successfully

DIALOGO has not yet achieved its target for the project implementation success rate indicator which is an average score of 8. In Year 2, based on 18 grants, the project scored 6.6 out of 10 which the PMU believes reflected the challenges the programme had in working with new partners with limited programmatic, administrative and financial competencies. In Year 3, 14 completed grants were evaluated, with an average score of 6.8, showing a marginal increase in performance.

MTR findings:
There is evidence that DIALOGO’s support to media and municipalities increases citizens’ access to information and there are examples of DIALOGO contributing to the kind of value anticipated in the business case. However, political factors mean progress is uneven across the municipalities.

Equity

DIALOGO has yet to fully incorporate equity into its grant making and value for money strategy. Therefore, it may not currently be delivering value for money according to the perceptions of certain groups of citizens.

Equity considerations need to go further than looking at women and youth and also consider how class, political affiliations and patronage relationships influence voice and the choice of priority projects and distribution of benefits.

Recommendations:

PMU/DFID to agree on the steps to take in relation to the VfM analysis, findings and recommendations on how to refine the current indicators provided by the MTR. A simple VfM strategy should be developed, to drive the choice of indicators, assessment approaches, data collection and documentation. This process needs to be pragmatic and within the PMU’s capacity. DFID should share responsibility for contributing to actions that will be expected to generate sustainability.

PMU to shift focus from economy and efficiency to effectiveness, including equity and sustainability. PMU to use knowledge generated by the MTR to consider making human and financial allocations decisions to enhance VfM.

DFID to consider how to use and share lessons learnt from VFM analysis and findings of the MTR.

PMU to use lessons from MTR to inform VfM thinking going forward and might want to consider a few suggested options from the MTR:
- Replication: Consolidating learning in order to influence other programmes to allocate funds to replicate successful DIALOGO initiatives, such as the media approach.
- Sustainability: Consolidating learning in order to influence other programmes or sponsors to provide funding to sustain ongoing media activities, and/or to fill gaps that influence the government’s capacity for responsiveness (e.g. local tax collection); ensuring skills developed within the PMU can be at least be partially transferred to other institutions and programmes operating in the municipal governance field.
- Equity: Finding optimal means to ensure that the interests of the most marginalized are represented directly or indirectly in participatory planning and budgeting activities.
- Effectiveness: Seeking to increase effectiveness in Tete and Maputo through additional tailored engagement and aligned incentive strategies, e.g. more systematic coordination with PRODEM and the World Bank Cities and Climate Change programme.
- Efficiency: Decentralisation and simplification of reporting lines for CESC facilitators so that the PMU is able to quickly respond to issues identified by civic groups.
- Efficiency/effectiveness: Determining and sharing key lessons about optimal civic group incentive strategies.
Ensure any efforts to increase economy and efficiency (e.g. ‘saving’ on technical assistance) do not unintentionally jeopardise effectiveness.

Quality of financial management

DFID’s contract with DAI Europe is structured as a fixed-price contract around programmatic deliverables and outputs. DAI is responsible for the overall financial management of the programme and its financial regulations ensure proper and efficient use of resources and effective internal control. DFID settles the payments as per the contract on a quarterly basis. The PMU developed a separate Performance Payment Plan, which lists the deliverable and output indicators to which quarterly payments are linked. The PMU indicates on its list of Key Performance Indicators which correspond to deliverable and output payments, with output payments linked directly to log frame outputs.

The PMU maintains strong internal systems for procurement, expenditure recording, and inventory management. The recommendations from previous audits have all been implemented.

Ernst & Young has been contracted to conduct the programme’s audits for the 5 year implementation period. The audit is due end of July 2016 and for the first time, the audit will not just cover the PMU, but also look at the systems of some programme partners.

The contract value with DAI Europe is £7,987,196.71. During financial year 2015/16 DIALOGO spent £1,688,171.35 against a forecasted £1,789,146.84. To date the programme has spent £6,471,887.49 and is on track.

The MTR assessed DIALOGO’s grant making systems to determine if they are fit for purpose and conducive to good partnerships. MTR findings:
The grant making and funding support model takes a tailored approach to funding different types of organisations.

Spend varies across municipalities, reflecting the extent of suitable grantees identified in the original mapping as well as the municipal government’s willingness to engage.

Apart from a few complaints that are likely due to the tailored nature of the grant making model and DIALOGO’s efforts to reduce financial risks, partners interviewed seemed happy with the approach and appreciative of funding for their individual projects.

The PMU believes that the grant making model prevents the programme from being as responsive as it might be if it used an alternative funding approach.

Incentive and grant levels that were highlighted as a concern in the 2014 AR still appear to be an issue, and a review of different approaches taken by the programme is needed to ensure that economy concerns do not undermine effectiveness.

The nature of the portfolio, partner capacity and DFID’s demands for data have resulted in high transaction costs for programme staff and reduced resources available to support programme learning and sharing that could enhance the overall impact and VFM of the programme.

Approaches to reducing the risk of financial impropriety appear appropriate for the nature of the programme

The grant management information system is not as effective as it might be.

Recommendations

- The PMU should consider the possibility of adopting an approach to funding activities that overcomes some of the current inflexibility of the grant making model, with a shift towards activity-based support with a larger TA component. Although difficult at this stage in the programme.
- They should purchase or design a grant management database programme with easy and effective analysis and reporting functionality.

Date of last narrative financial report	24 March 2016
Date of last audited annual statement	31 July 2015

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The programme is established and broadly delivering it’s outputs. There are a number of medium to high level risks associated with the programme. The most significant risk affecting DIALOGO, and beyond its control, are the difficulties involved in different parties (FRELIMO, RENAMO and MDM) working together, the fact that different parties in different layers of government can potentially restrict access to resources for each other, influence and that in many DIALOGO municipalities you have at least 2, or even all 3 of these political parties directly interacting. At the municipal level this tension has resulted in an increase in political polarisation and intolerance, thus reducing the space for dialogue. This risk is particularly high in the municipalities located in areas of RENAMO influence, such as Nampula, Quelimane, Beira and Tete.

From the beginning of the programme, the DIALOGO team has incorporated political risk assessment into the design of activities and other decision-making processes. The PMU conducts municipal learning workshops and Theory of Change workshop attended by all DIÁLOGO partners annually in order to review programme implementation, and to assess contextual changes and risks.

The complete risk matrix can be found at annex 5.

Outstanding actions from risk assessment

No outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on track and progressing according to schedule. The timeframe remains in line with the agreed timeline of February 2012 to February 2017 approved in the Business Case. DFID is considering if it represent VfM to extend the contract for a short period of time.

Performance of partnership (s)

DFID chairs a quarterly management meeting. Work plans, objectives, budgets and review processes have been shared openly and collaboratively with DFID. DIALOGO and DFID are committed to learning and being open when programmes are facing challenges, and being prepared to adjust as necessary.

An informal group has been established between MASC, CEP, DIALOGO aimed at sharing information on monitoring and practices with the aim to improve programme results. However, during 2015 little progress was made. One of the reasons was that MASC has been focused on the transition to a foundation, and also the fact that DIALOGO and CEP are working in different geographic and thematic spaces, which makes collaboration difficult. In spite of that, DIALOGO is strengthening its collaboration with other supply side programmes such as GIZ’s PRODIA II and the Cities Alliance country project, as well as with the WB decentralization programme. Several meetings were also held with PRODEM to look for areas for mutual collaboration, which have led to some tangible results.

Asset monitoring and control
The PMU submits asset registers as part of their regular reporting and assets spot checks are done annually by DFID Mozambique. The next spot check is due by 30 April 2016.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The UK Partnership Principles are not used as a specific tool in the direct management of this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The programme contains a subcontract with IDS specifically responsible for the external monitoring and evaluation of the programme. IDS conducted the baseline survey in 2012 and the MTR in 2015.

The MTR was of high-quality, well-evidenced and based on comprehensive discussions with the PMU and DFID. It demonstrated that the programme was well positioned in relation to the policy context and performing well. It also raised some important areas to work on, many of which have been raised previously in Annual reviews and in quarterly meetings (e.g. around gender, less centralised programme management, the need to link up with supply side programmes etc.).

But the MTR will only be as useful as the programme response to it. This should include using both it and this Annual Review to structure its work going forward. The PMU will need to set out both its strategic response to the issues raised and then how it will deliver it.

The planned end evaluation by IDS is planned for August 2016. This however falls only a year after the MTR and so would not be a useful exercise as little change would be discernible. DFID should consider if and how to push this back. Currently, DAI contract IDS to do this evaluation. However DFID, in discussion with DAI could take on the contract from DAI to ensure no conflict of interests.

Monitoring progress throughout the review period

PMU reports progress on the programme every quarter and provides comprehensive annual progress reports. These reports are reviewed and discussed jointly in quarterly meetings chaired by DFID. These quarterly meetings also provided an opportunity for partners to discuss specific issues related to the programme and its response to contextual changes. The DFID Mozambique adviser responsible for this programme also held monthly meetings with the DIALOGO PMU Director to discuss the programme.

As part of this annual review, the DFID review team conducted (i) a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and reviewing key activities and communication outputs; (ii) a series of interviews with the DIALOGO consortium and key DIALOGO partners in Quelimane; (iii) a presentation of the Annual Report and progress over the review period by the PMU; and iv) detailed review of the MTR.

This annual review was conducted during April 2016, by a core team of three DFID staff including two Governance Advisers and a DFID Mozambique Programme Officer from DFID Mozambique.