Annual Review – Summary Sheet

Title: Building Resilience through Asset Creation and Enhancement - Phase Two (BRACE II)
Programme Value £ (full life): £39.6m		Review Date: March 2020
Programme Code: 204888	Start Date:04/09/2015	End Date: 31/12/2021

Summary of Programme Performance
Year	2016	2017	2018	2019
Programme Score	B	A	A	A
Risk Rating	Severe	Severe	Major	Major

DevTracker Link to Business Case:	Business case and addendum
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Building Resilience through Asset Creation and Enhancement (BRACE) II is DFID South Sudan’s flagship resilience and international climate finance project, aiming to increase the capacity of vulnerable households to cope with shocks, improve their food security and build better community relationships. BRACE II has two delivery components and an independent monitoring and evaluation component. Component I began in 2015 and is delivered by the World Food Programme (WFP) and the Food and Agriculture Organization (FAO) in partnership. Component II began in 2018 and is delivered by an NGO consortium led by World Vision (WV). BRACE II builds on a successful three-year pilot project, BRACE I, and was set up with these two delivery modalities to enable DFID South Sudan to compare approaches.

BRACE II provides a multi-year package of support, firmly grounded in community participation. Vulnerable households are provided with regular cash transfers[1] to meet their immediate needs on the condition that they work on household and community assets[2] like roads or flood dykes to improve productivity and resilience to shocks. Alongside this, they receive agricultural inputs together with training on good nutrition, conflict management, and climate sensitive agriculture to help them increase food production and build resilience in the longer term. Improving food security is critical to reducing the need for humanitarian assistance, and BRACE II is a key part of DFID South Sudan’s strategy to balance emergency humanitarian support with interventions that build self-reliance where possible.
[1] $40.5 x 6 transfers in 2019 (WFP), $44.50 x 3 transfers (cohort A) or 6 transfers (cohort B). If cash no longer remains a viable option, the programme will switch to vouchers or food as appropriate.
[2] ‘Assets’ include creation or rehabilitation of roads, anti-flooding dykes, clearing new farm land, water ponds, creating vegetable gardens, etc.

The programme has four main objectives:

1. Address immediate food insecurity and basic needs (provision of conditional cash assistance).
2. Improve longer-term food security (support for agro-pastoral production).
3. Increase capacity to absorb, anticipate and adapt to climate variability and extremes (support climate change adaptation).
4. Improve community relationships and social cohesion.

BRACE II was designed to target areas of South Sudan that are highly food insecure but more stable than other parts of the country. This allows the programme to provide longer term support to help people develop their self-reliance and reduce their need for emergency assistance. This has focused on former Northern Bahr el Ghazal and Warrap States, with work in Eastern Equatoria having started in 2018 to test expansion of the approach.[3] In late 2019, a cost and time extension was approved to maintain delivery of resilience building work during a period of uncertainty in South Sudan and bridge the transition to a multiyear humanitarian and resilience programme planned to start in 2021.
[3] This review refers to the original ten states of South Sudan. The Greater Bahr-el-Ghazal region covers the North-West part of the country and includes the three states of Western Bahr-el-Ghazal, Northern Bahr-el-Ghazal and Warrap.

Figure 1: Map showing all BRACE II Locations.

Context update

South Sudan’s food security crisis continues unchecked, with 6.35 million (54%) of the population facing crisis or worse levels of acute food insecurity in August 2019.[4] This was a small 5% reduction in the total number of people facing crisis or worse food insecurity compared to the same point in 2018, attributed to greater stability after the signing of the Revitalized Agreement on the Resolution of the Conflict in South Sudan (R-ARCSS) in September 2018, leading to better access to livelihoods and markets. The crisis is not only caused by conflict and insecurity but also by the economic crisis that has eroded households’ purchasing power. This is exacerbated by climate shocks such as flooding, which has been a major issue for the 2019 growing season and is anticipated to contribute to a considerably worse food insecurity picture in 2020.
[4] http://www.ipcinfo.org/fileadmin/user_upload/ipcinfo/docs/IPC_South%20Sudan_Key_Messages_August_2019.pdf.

The food security situation for the population at large has continued to deteriorate, including in the areas that BRACE II is implemented. In August 2019, four of the eight project areas were classified in emergency food insecurity (Phase 4: Aweil North, Aweil East, Aweil West, Aweil South), compared to two at the same time last year (Aweil East, Gogrial West). Projections were that all project areas except Magwi were likely to be in crisis levels of food insecurity (Phase 3) in the 2019 harvest period (September to December), with the situation worsening to emergency levels (Phase 4) by Q1 2020 in Aweil South. These projections were made before the impact of increased seasonal flooding was felt. Project areas have remained relatively stable over 2019, however, displacement and incidences of conflict have occurred, including in Northern Bahr el Ghazal where fighting that broke out in August led to a temporary suspension of movement across Aweil East, North and West and a one-day interruption to project activities.

Summary supporting narrative for the overall score in this review

The overall score in this annual review is A; ‘outputs met expectation’. This review covers the period between 1 November 2018 and October 31, 2019.

In this review period the UK spent a total of £11,693,089 through BRACE II, supporting over 28,135 vulnerable households with cash, agricultural supplies and training to improve their food security and resilience to shocks.  Households received over $6.5m of this support as cash to meet their immediate food needs on the condition that they invest time improving household and community assets such as farms and roads. Despite heavy flooding and a very difficult food security picture across the country, the diets of households in BRACE II are improving and the majority of assets are reported to still be in use after 12 months.

A progress assessment undertaken this year found that the programme continues to represent value for money. A mid-term evaluation was completed and partners under both components reached output milestones. Cash continues to be an efficient way of providing support, with the costs of transferring cash almost a tenth of the cost of transferring the equivalent value of food.

	Output indicators	Weighting	Score
1	Food insecure targeted households have access to labour-based safety nets (cash/food-based transfer)	35%	A
	This year BRACE II provided 188,700 vulnerable people (31,450 households) with a total of over $6.5m of conditional cash-based transfers, with over 96% of cash disbursed within the review period.
2	Community assets that enhance resilience to food insecurity and climate variability and extremes are improved or created	30%	A
	In 2019, 28,135 vulnerable households were able to access agricultural inputs under BRACE II. The project also reached its targets for the number of assets constructed, with more than expected still maintained or used 12 months+ after completion despite heavy rains.
3	Skills and knowledge for resilience are improved	25%	A
	Targets for the number of people trained on climate smart agriculture and nutrition practices were met or exceeded this year, showing an improvement on 2018. In addition, 1,299 people in project committees were trained in conflict mitigation.
4	BRACE II management is adaptive and informed by M&E and feedback mechanisms	10%	A
	The target for community feedback mechanisms being established was reached, however the proportion of people who know where to provide feedback was lower than expected. The M&E component completed the mid-term evaluation as well as several other products before it closed in July.

Output Scoring Calculator

A++	138% and above	Outputs substantially exceeded expectation
A+	113% - 137%	Outputs moderately exceeded expectation
A	88% - 112%	Outputs met expectation
B	63% - 87%	Outputs moderately did not meet expectations
C	Under 62%	Outputs substantially did not meet expectations

Summary of key recommendations for the next year

WFP and DFID will work with World Vision and other development partners to improve the value for money of cash transfers in South Sudan by aligning values and approaches where possible. Opportunities to maximise value through the use of a parallel or negotiated rate will be explored, and the development of a roadmap towards a social protection system will be supported.

DFID will review existing VFM matrices with all partners, aiming to agree the definitions and presentation of a streamlined core set of indicators.

DFID will contract further M&E services (third party monitoring and a final evaluation), in discussion with partners.

DFID will work with partners to update and refine the draft BRACE II theory of change.

Figure 2: Flood affected farm during the planting period
(Component I, Aweil South).[5]
[5] Photo: JAM.

## B: DETAILED OUTPUT SCORING

Output Title	Food insecure targeted households access to labour based safety nets (cash/food-based transfer)
Output number per LF		1	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/ FAO	Milestone for this review: WVI	Progress: WVI	Indicator Score / (equally weighted)
Number of women, men, boys and girls receiving cash/food transfers, disaggregated by sex and types of transfer [Accepted variance of 10%]	113,250 / (accepted variance 101,925)	113,250 / (100%)	75,900 / (accepted variance 68,310)	75,450 / (99.4%)	A / (99.7%)
Total amount of cash transferred to targeted beneficiaries (USD) [Accepted variance of 10%]	$4,586,625 / (accepted variance $4,127,962.50)	$4,586,625 / (100%)	$2,156,025 / (accepted variance $1,940,422.50)	$2,000,275 / (92.8%)	A / (96.4%)
Partner Score	WFP/FAO Score (equally weighted)	A / (100%)	WVI Score (equally weighted)	A / (96.1%)	A / (98.05%)

Supporting narrative for the score

This year, BRACE II reached a total of 188,700 people (31,450 households) with conditional cash-based transfers, of which 52.5% are female (54% in component 1 and 50.2% in component 2).

Partners under BRACE II plan to disburse cash between April and October to provide households with a regular income during the lean season when they need it most. In 2019, there was an improvement in timeliness across both components, with over 90% of cash disbursed within the review period. As with 2018, transfers had to be grouped under component I three times (Warrap in June and October, Northern Bahr el Ghazal in September) due to delays in verifying whether assets had been created by project participants. The final transfer was delayed in Northern Bahr el Ghazal as fingerprint and SCOPE registration issues have led to the process being continued offline for some participants.

This year has been an important one for roll out of the biometric SCOPE system under component I, with registration taking place in all project locations and cards printed and delivered. The project visit in December highlighted that some participants were not successfully registered first time, with plans to revert to a paper based system until re-registration could be completed.

The timing of asset creation and cash transfers remains an area for the programme to keep under review. The lean season is likely to hit households even earlier in 2020 as flooding this year has reduced harvests and household food stocks. This means it will be important for partners under both components to consider whether early and/ or combined transfers are possible so that households can purchase food before market prices peak.

In 2019, WFP maintained its cash transfer value of $40.50 per month ($2.70 per day of work) for six months. WFP re-tendered for a financial service provider in early 2019, with their negotiated rate decreasing from 25% to 21% above the official $/SSP exchange rate (197 SSP/$1 at its maximum) indicating a potential decline in value for money as the gap between the two rates widened. World Vision was unable to renegotiate terms with their financial service provider and continued to exchange dollars at the official exchange rate (c.158 SSP/$1). As a result of last year’s annual review, the decision was taken to increase the cash transfer value under component II to $44.50 in 2019 to try and align the amount that households receive in South Sudanese Pounds. Communities served by different partners under BRACE II can be located close to each other and so it is important to try and ensure they receive equivalent packages of support to avoid any tension between communities served by different partners. To allow for proper planning, this decision had to be taken before the renegotiated WFP rate was known, and so despite increasing the transfer from $40.50 to $44.50 per month, households under component II still received fewer South Sudanese Pounds than those served under component I. In 2020, a World Bank safety net programme is anticipated to implement cash for work activities in adjoining areas, and so alignment of cash transfer values across the partners continues to be a priority.

Recommendations

Basic financial literacy training and village savings and loans associations were included in both component I and II for 2019 to increase the benefits of the cash transfers. Partners should submit an update on the implementation of these (number, locations, lessons learnt) in the Q3 report 2020.

Partners will discuss options for alignment of cash transfer values in 2020 in coordination with other stakeholders (cash working group coordinator, World Bank safety nets lead) by March 2020.

Partners will review plans for the timing of transfers in 2020 based on expected household needs and purchasing power.

Figure 3: BRACE II Participants receive their cash entitlement
(Wungiir, Component I).[6]
[6] Photo: CWW/Rogers Otuta

Output Title	Community and household assets that enhance resilience to food insecurity and climate variability and extremes are improved or created.
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review: / WFP/FAO	Progress: / WFP/FAO	Milestone(s) for this review: / WVI	Progress: / WVI	Indicator Score / (equally weighted)
2.1 % of achievement in assets built, restored and maintained [Accepted variance of 10%]	100% / (accepted variance 90%)	94%	100% / (accepted variance 90%)	108%	A / (101%)
2.2 % of asset that are still used and/or maintained +12 months after their construction, disaggregated by types of assets	80%	80% / (100%)	80%	97% / (121%)	A / (110.5%)
2.3 # of households having access to improved seeds, tools, equipment [Accepted variance of 10%][7]	15,485 / (accepted variance 13,937)	15,485 / 100%	12,650 / (accepted variance 11,385)	12,650 / 100%	A / 100%
Partner Score	WFP/FAO Score (equally weighted)	98%	WVI Score (equally weighted)	109%	A / (103.5%)
[7] An estimate of six beneficiaries per household is used across by both delivery components.

Supporting narrative for the score

Progress under this output has improved from 2018 across both components. In 2019, abnormally heavy rainfall, flooding and water logging prevented some communities from reaching their goals on asset creation within the expected timeframe. Payments were made to communities despite this so that households would not be penalised for factors outside of their control, with agreement that work would continue as water recedes. Despite this, solid progress has been made, with crop and vegetable farms cultivated, flood dykes created, roads rehabilitated, and schools constructed. In addition, third party monitoring confirmed that seed delivery under component II improved in 2019, with positive feedback on the timing and quality of seeds provided.

Communities reported that some flood dykes created through BRACE II helped reduce the impact of flooding this year, however in other locations they were overtopped, demonstrating the ongoing need for support during planning phases to ensure assets are well located and constructed. Some partners in BRACE II locations are testing options for mechanisation to accelerate communities work on small scale infrastructure, as assets like multi-purpose ponds may take several years to construct using hand tools. Partnerships with other projects, businesses or organisations which can provide access to machinery without a large increase of costs may increase the effectiveness of assets, however the process will need careful management to ensure communities are empowered and labour is productive.

This year WFP conducted a rapid gender assessment of their Food for Assets Programme in South Sudan. This was positive about several measures taken to increase the gender sensitivity of asset creation, including general acceptance of the guideline that pregnant and breastfeeding women should not work on the assets. Adjustments to increase inclusivity were also recommended, for example by improving childcare systems for families while parents are taking part in asset creation, and differentiating work norms according to needs and abilities (e.g. for the chronically ill).

In response to last year’s annual review, indicator 2.2 now measures the use or maintenance of an asset 12 months after their expected completion to give a better picture of its relevance to the community and avoid monitoring errors due to the change in season (e.g. if a field is not being cultivated in the dry season). This indicator has been reported on by component I for the first time this year, estimated from a sample of assets visited in December 2019. The overall FFA baseline found even more positive results, with 93% of assets found to still exist and 89% of households still getting use from them.

Challenges remain under this output which partners are addressing:
- Block farms. Block farms are set up under BRACE II so that several households cultivate an area of land designated by the community side by side. Despite measures put in place to agree land allocation with the community and its governance structures, issues have arisen this year which have been managed by partners through dialogue and movement of activities. As defined in the 2019/20 proposal, it is important that block farms are located close to communities, are not too large and are appropriately sited (e.g. have access to water).
- Delayed inputs. In BRACE II areas FAO is promoting seed fairs to encourage local input markets and provide beneficiaries with choice over their seeds. This includes enrolling successful BRACE II participants as seed vendors to the programme. Unfortunately, agreements between FAO and their downstream partners were signed late in all areas which led to delays in participants being able to access seeds. These agreements have been negotiated to run until September 2020 which means that delays should not be replicated for the 2020 main season.
- Ensuring community planning processes are inclusive and representative. Through BRACE II, communities create plans which underpin the asset creation process. The planning process includes male and female community members, chiefs, partner staff, government representatives and other local leaders, however more could be done to ensure that plans are representative and owned by communities. For example, the rapid gender assessment commissioned by WFP this year found that women were often unable to attend the full three-day community-based planning process due to their caring and livelihood responsibilities. Focus groups also reported that people felt they had not meaningfully contributed to the selection and prioritisation of assets. Public meetings to communicate the planning process, invite views and validate outcomes would help communities to own the planning process and prioritise their needs, alongside measures to reduce barriers for women’s participation. WFP has revised its planning protocols for 2020.

The approach to asset creation also provides an opportunity to link the network of assets to wider development plans. Community asset plans could be linked into local area development plans and help prioritise support from other channels with the right coordination structures in place. In 2019, Aweil was selected as a priority candidate partnership area under the Partnership for Recovery and Resilience (PfRR) in South Sudan. This sets the stage for community owned area-based planning that is coordinated with the full range of support available from the humanitarian and development community.

Recommendations

Where possible, partners should test partnerships which can provide access to machinery to support asset creation without large increase of costs to the project. Lessons should be provided to DFID and shared with other programme partners.

BRACE II partners will coordinate their work with others in Aweil and provide examples of successes or challenges to the annual PfRR learning event due in late 2020.

- DFID governance adviser(s) should
  - review governance structures under BRACE II to identify any opportunities to strengthen dispute resolution/ peacebuilding mechanisms and link community planning processes to local governance structures and development plans.
  - approach the CSRF and other UK-funded research programmes to identify whether support is available on land-related issues, including reviewing existing studies on the legal framework for HLP and current efforts to address these issues.

Partners will continue to look for options to promote fruit trees in a way that they are likely to be maintained. This could include local procurement of appropriate seedlings by partners, communications on their importance and care or a focused effort on promoting them at appropriate sites such as nutrition gardens or institutions with access to water.

Output Title	Skills and knowledge for resilience are improved
Output number per LF		3	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review: WFP/FAO	Progress: WFP/ FAO	Milestone for this review: WVI	Progress: WVI	Indicator Score / (equally weighted)
# of people trained on improved and climate-sensitive agricultural practices [Accepted variance of 10%]	15,485 / (accepted variance 13,937)	15,485 / 100%	12,650 / (accepted variance / 11,385)	12,650 / 100%	A / (100%)
# of people trained for improved nutrition practices (disaggregated by sex) [Accepted variance of 10%]	18,875 / (accepted variance 16,988)	20,208 / (107%)	6,325 / (accepted variance 5,693)	7,092 / (112%)	A / (109.5%)
# of people trained on conflict mitigation in targeted communities [Accepted variance of 10%]	1,050 / (accepted variance / 945)	1,050 / 100%	249 / (accepted variance / 224)	249 / (100%)	A / (100%)
Number of dispute resolution / resource management structures set up (or improved)	105	105 / (100%)	9	9 / (100%)	A / (100%)
Partner Score	WFP/FAO Score (equally weighted)	A / (101.8%)	WVI Score (equally weighted)	A / (103%)	A / (102.4%)

Supporting narrative for the score

Improving skills and knowledge is a critical part of building resilience to shocks, and good progress has been made in reaching the targets set for 2019. The number of people receiving training on improved nutrition practices has improved dramatically between 2018 and 2019 following a concerted effort from partners under both components. Topics covered include breastfeeding, food preparation, diverse diets, hygiene and sanitation. In 2019, FAO had hoped to trial the introduction of orange flesh sweet potato to combat vitamin A deficiency. The logistical challenges of transporting and storing live vines meant this was not possible, and so local sourcing will be explored under both components for 2020.

WFP’s rapid gender assessment found that WFP has introduced gender responsive measures to the FFA programme design. This included guidance, tools and training to engage women in the community planning process and requiring equal representation of women and men in project committees to try to ensure a balance in decision making. There was evidence of support provided on the use of cash transfers, and opportunities identified to provide further messages on household decision making, more equal division of responsibilities and issues such as gender-based violence. There is a growing evidence base on improving nutrition outcomes by engaging men, and this could also be an area for the programme to explore.

The target for the number of people trained on improved and climate smart agriculture was higher this year for both components and has been achieved, however work is still needed to improve the approaches being promoted and address gaps in uptake, as even basic practices being promoted (mulching, manuring, spacing) are reported to have a low adoption rate. The target for the number of people trained on conflict mitigation reduced this year as this reflects the number of targeted Bomas rather than the number of participants.

A critical gap for all BRACE II participants is knowledge of likely upcoming weather-related shocks. Whilst communities are used to floods and droughts and have ways to adapt to these events, there are no systems in place to help them anticipate when the rains may arrive in a given season, how heavy they will be or when they may end. A reliable weather forecast that reaches farmers and is used to plan is a long way off in South Sudan, however, Aweil is one of the few locations that has a functioning and maintained weather station. Connecting delivery partners to forecasts provided by international organisations, creating feedback loops and helping them to communicate basic information to farmers would be a big step forward.

Recommendations

Any extension of activities should include an updated training plan which sets out the skills/ messages that programme participants should be provided with and how uptake is being promoted, learning from adoption rates so far.

Between February and May 2020, all partners should map available weather/climate information sources and test a simple mechanism to communicate forecasts to downstream partners and BRACE II communities.

Figure 4: BRACE II participant demonstrating their 2019 harvest (Component II).
Before entering the programme, this woman had not cultivated groundnuts before, however after training and support she harvested 8 bags in 2018 and 16 bags in 2019, enabling her to pay school fees for three children and invest in four goats.

Output Title	BRACE II management is adaptive and informed by M&E and feedback mechanisms
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/ FAO	Milestone for this review: WVI	Progress: WVI	Indicator Score / (equally weighted)
Partners' community feedback mechanisms established at the distribution sites [Accepted variance of 10%]	100% / (Accepted variance 90%)	100%	100% / (accepted variance 90%)	100%	A / 100%
Proportion of people who know where to complain/provide feedback [Accepted variance of 10%]	15% increase / =94.3% / (2017/18=82% achieved)	73% / (77.4%)	95%	81% / (85.2%)	B / (81.3%)
# of Monitoring & Evaluation & Learning products produced by the M&E component	2017/18 Milestone / 17	2017/18 / Progress / 15	2018/19 Milestone / 12 / (Cumulative 29)	2018/19 Progress / 15 / (Cumulative 30)	A[8] / (103%) / Cumulative
Partner Score	WFP/FAO (equally weighted)	A / (88.7%)	WVI (equally weighted)	A / (92.5%)	A / (94.8%)
[8] No milestone was reported on in 2018 due to ongoing contractual negotiations. Progress is therefore reported here, with the scoring based on cumulative achievements due to the review period covering the end of contract.

Supporting narrative for the score
2019 has been an important year for the M&E component of BRACE II, as set out further in section G. A performance improvement plan was put in place, with the provider completing the process, producing a number of learning products and ending the contract as planned in July 2019.

Feedback mechanisms in BRACE II include:
- Community feedback committees that collect and refer issues to project management committees.
- Feedback desks at distribution points that receive complaints from participants and non-participants, which are shared with project management committee members and/ or partner.
- A WFP toll free hotline to receive feedback.
- Community monthly and quarterly meetings.
- Feedback through field staff.

The proportion of households who know where to provide feedback has fallen from 2018 under component I, however this may be because the majority of people surveyed were new to the programme. The proportion has risen slightly in component II however is still lower than expected. The annual monitoring report from component II found the most used channels were community help desks (42%), field staff (25.2%), community monthly and quarterly meetings (15%). The most preferred feedback channel under component I was through project management committees and traditional leaders. There is a significant difference between the percentage of people who feel they have received a satisfactory response to a submission under the two components; 91% under component I and 68.4% of people under component II (down from 84.7% last year).

Recommendations

All partners should identify any barriers to feedback being provided through existing mechanisms and redouble efforts to communicate ways for people to provide feedback during the start of transfers in 2020.

In any extension partners will demonstrate how they have made adaptations to programme plans based on learning and feedback mechanisms.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The BRACE II theory of change has evolved since the business case and over the life of the programme. The latest draft pictorial representation is shown below. The mid-term evaluation recommended revising this based on clear measurable interpretations of terms such as resilience, climate risk, vulnerability and food insecurity. Clear shared definitions of these terms between partners in South Sudan are not agreed. The mid-term evaluation also suggested a descriptive theory of change; however, this did not provide a strong enough framing of the role of cash/food transfers to be agreed by all partners. In 2019, WFP drafted a theory of change for its resilience activities (including FFA), and World Vision developed a resilience framework for their work in South Sudan. A revision of the theory of change with input from the planned WFP Food for Assets evaluation, mid-term evaluation and experience of partners will be pursued ahead of a final evaluation planned for late 2020.

Figure 5: BRACE II theory of change draft for revision in 2020.

Describe where the programme is on track to contribute to the expected outcomes and impact.

The 2018 annual review provided a comprehensive update on the project’s progress towards intermediate and final outcomes based on the results of the mid-term evaluation. Partners do not routinely collect data towards all outcome level indicators and so the next full update on progress will be provided by a planned final evaluation late in 2020. Nevertheless, findings from partner surveys do provide information against select indicators below. BRACE II was designed to support people to cope with shocks like the flooding experienced this year, and anecdotal reports suggest that the cash and assets accumulated through the project have helped communities to absorb the impacts of this extreme event. Nevertheless, it will take time to assess whether the project has been successful in helping them to adapt to and anticipate future events.

	Resilience Index Measurement and Analysis
	2017	2018	2019*
Aweil Centre	26.23	31.48	23.39
Aweil East	34.68	37.19	29.02
Aweil North	32.82	42.96	31.10
Aweil South	23.42	29.61	30.47
Aweil West	31.83	31.90	42.05
Twic	30.31	33.21	38.66
Magwi		32.01	29.04
Gogrial West		33.21	40.51

FAO has been able to provide impact level information from the Resilience Index Measurement and Analysis (II) this year, showing an improvement in resilience indicators in areas that BRACE II is implemented between 2017 and 2018. The analysis for 2019 is not comparable to previous years due to a change in the method used, however the survey questions will be standardised in future.

Figure 6: Resilience Index Measurement and Analysis (higher number=more resilient).
* 2019 figures are not comparable to previous years due to a change in method.

Intermediate Outcomes (IO)
IO6: Increase in incomes at household level
The FFA 2019 baseline found that 37% of households earned enough money from vegetable gardens to cover 4-6 months of their food needs. Vegetable gardens are primarily promoted for household consumption and so being able to earn a relatively significant income from them indicates a large productivity gain for some participants.
IO7: Increase in cereal production at household level, disaggregated by increase in production and cultivated area [Metric Tonnes (MT)][9]
[9] The figures given calculate the value of crop production.
	Avg Production per HH (metric tonnes)
Aweil Center	1.38
Aweil East	0.64
Aweil North	0.43
Aweil South	0.24
Aweil West	0.36
Twic	0.48

Data presented by the mid-term evaluation and FAO indicates an increase in cereal production for BRACE II households this year, from a mean of 424 kg per household in 2018 to an estimated 603 kg per household in 2019. There is a high variation in the average production by location however, as shown in Figure 6.

The 2019 FFA baseline found that that 67% of households who graduated from FFA could sustain themselves through their own production without the need for external assistance. It also found that 58% of male headed and 55% of female headed households reported a change in the amount harvested since participating in FFA, with a 15% change reported for year 1 households, and a 71% change for graduated households.[10]
Figure 7: Mean production per BRACE II household, component I 2019
[10] *These results are perception based across FFA implementation areas and therefore are not BRACE II specific.

Final Outcome (FO): Improved food security and better community relationships
FO1: Prevalence of poor and borderline food consumption, disaggregated by sex of household head (Food Consumption Group)
Both WFP and World Vision conducted surveys in 2019 that provided information against outcome indicator 1. Under both components there was a decrease in the proportion of beneficiaries with a poor or borderline Food Consumption Score (low of 32.6% in December 2019 under component I and 27.6% under component II). WFP also found that graduated beneficiaries had better food security outcomes than first year beneficiaries. The majority (53%) of graduated beneficiaries had acceptable Food Consumption Scores compared to 35% of those in the first year of support.

Figure 8: Food Consumption Score, WFP FFA Outcome Survey 2019
FO2: Diet diversity score of targeted households, disaggregated by sex of household head (HDDS)
The dietary diversity of households has continued to increase under component I, from a baseline of 2.51 to 4.84 this year. There is more work to do however, as the 2019 WFP FFA survey found that roughly 25% of households have women of reproductive age who meet minimum dietary diversity standards.
FO3: Proportion of targeted households implementing crisis and emergency strategies, disaggregated by sex of household head (Livelihoods Coping Strategy Index)
The WFP annual survey found that 69.8% of households applied crisis/emergency strategies in 2019. This has risen significantly since last year (33%), though it still represents a slight reduction on the baseline of 71%. The extreme floods in 2019, coupled with the number of first year households registered may explain the increase in the use of emergency coping strategies from last year. This indicator would need to be combined with careful analysis to consider whether the programme has contributed to a larger buffer for people to rely on. For example, while this indicator tells us that people may have needed to sell assets this year to cope with the impacts of flooding, the headline result doesn’t tell us if the total number of assets they had access to increased.
Explain major changes to the logframe in the past year

No major changes have been made to the logframe over the last year, however two indicators have been updated to reflect recommendations from the mid-term evaluation and discussions with partners:

- Output indicator 2.2 measures the % of assets that are used and/ or maintained after their expected completion, as a measure of their sustainability and relevance to the community. The time lag for measuring their use was increased from 6 months to 12+ months to avoid seasonal affects distorting the results (e.g. farm land not being used in the dry season).
- Outcome indicator 7 aims to capture the increase in agricultural production resulting from participation in the programme. The mid-term evaluation recommended changing this from an indicator that measured increases in cereal production (volume and area cultivated) to a measure of increased value of production, to expand the indicator beyond cereals and to capture the outcomes from higher value crops. Partners felt this change may not capture a change in the volume of production which is so important for household food security, and so a dual indicator is proposed as follows ‘increase in agricultural production at household level, disaggregated by increase in production (MT), cultivated area (ha) and total value of production. This should help provide information on land productivity as well as the potential contribution to incomes.

Describe any planned changes to the logframe as a result of this review

No major changes are proposed. In 2020 we will consider how the results framework and/ or evaluation can further align to the pillars and measurement framework of the Partnership for Recovery and Resilience in South Sudan, beyond the use of RIMA II as an impact indicator.

Figure 9: A completed community access road
(Component I: Aweil West[11])
[11] Photo: © Concern World Wide/Joseph Aguer.

## D: VALUE FOR MONEY
In this review period the UK spent a total of £11,693,089 through BRACE II, supporting over 28,135 vulnerable households with cash, agricultural supplies and training to improve their food security and resilience to shocks.  Households received over $6.5m of this support as cash to meet their immediate food needs on the condition that they invest time improving household and community assets such as farms and roads. Despite heavy flooding and a very difficult food security picture across the country, the diets of households in BRACE II are improving and the majority of assets are reported to still be in use after 12 months.

BRACE II was used to pilot a new cross office VFM progress assessment in 2019. This found that the programme continues to represent VFM by delivering positive results in a difficult context while controlling costs and monitoring efficiency and effectiveness of the funds spent.

Assess VFM compared to the proposition in the Business Case, based on the past year

The BRACE II business case said that value for money would be tracked by looking at key unit costs such as the cost of delivering cash transfers, including a comparison between the two delivery mechanisms (UN-led and NGO led). Following the development of World Vision’s value for money indicators this year, all partners have developed a matrix of indicators to monitor value for money and a tracker to monitor cash transfers and asset creation. The VfM matrices are intended to be updated and submitted to DFID twice a year, however, no updates were received from FAO in 2019.

There are some areas that the business case did not envisage, however, including high annual inflation rates, an increasing spread/difference between the official and parallel exchange rate in South Sudan and a loss of value of GBP sterling against the US dollar. UK funds are paid in instalments to BRACE II partners in GBP, who then exchange these funds into USD to pay for some programme inputs, staff and equipment. A further exchange from USD to South Sudanese Pounds is then made for cash transfers and programme costs. Analysis undertaken for this review estimates that the UN partners have had significantly less budget available to them in USD than would have been assumed at the outset of the programme due to the decline in value of GBP against the USD since the programme was approved. This could explain the slight increase in the cost per beneficiary per year estimate under component I from the business case (£50) and/or may indicate that efficiencies have been found.

	Estimated Expected Budget ($)	Estimated Actual Budget ($)	Difference ($)	Difference (%)
WFP (Dec 2015- Dec 2019)	22,613,562	20,223,647	2,389,915	11%
FAO (Feb 2016- Dec 2019)	8,262,099	7,071,201	1,190,898	14%
WVI (Mar 2018- Dec 2019)	8,280,225	7,997,507	282,717	3%

Figure 10: Table showing the amount of USD expected by partners at the outset of the programme based on the GBP budget, and the likely amount available to them in USD based on the timing of payments.

Figure 11: Graph showing the widening of the gap between the parallel and official exchange rates 2017- 2020

Key costs
The cost-per-beneficiary-per-year estimates have risen very slightly to an average of £51.90 across the programme this year.[12] Component I is expected to cost more per beneficiary than the model under component II as it provides a larger package of support (18 months of cash over three years vs. 9 months of cash over two years). Tracking the estimated cost per beneficiary per year is a useful way of monitoring how costs are changing, however is not a measure of value for money unless compared with the costs of alternative packages or evidence on the results delivered.
[12] These calculations are basic estimates based on disbursed funds (October 2018 to October 2019 (WFP/FAO), January 2019 to January 2020 (WV)) and the number of people reached, with an assumed six-person household.

Cost per beneficiary per year estimates	Component I	Component II	Programme estimate
2017 Annual Review	£53		£53
2018 Annual Review	£53	£46	£49
2019 Annual Review	£58	£43	£52

Figure 12: Cost per beneficiary per year estimates by year and partner

The highest costs under BRACE II are cash transfers and staff, reflecting a programme model focussed on cash transfers and skills building. Under component II, 71% of the total budget was due to be transferred directly to households as cash, seeds and tools in 2019, with 16% of costs on staff and the remaining used for transport, logistics and equipment. This compares well to projects with similar goals under the Humanitarian assistance and Resilience in South Sudan (HARISS) programme. Under component I in 2019, 64% of funds transferred to WFP went to participants as cash and 54.5% of FAO’s budget was identified for input procurement and contracts with downstream NGOs, far less than the amount allocated to these lines under HARISS (over 70%). This is likely to be a result of the efficiencies of scale achieved by FAO’s multi donor Emergency Livelihoods Response Programme that DFID contributes to under HARISS, and the increased costs associated with providing longer term agricultural support that requires greater technical input.

As with last year, the main risks for 2020 are exchange rate fluctuations (GBP/USD and SSD official and parallel rates), and the availability of other donor funding to WFP/ FAO to provide economies of scale.

Economy: Finding savings

A key cost for WFP and FAO has been the cost of negotiating agreements with their delivery partners each year. In 2019, multi-year agreements were signed by WFP and FAO with their partners with the aim of reducing transaction costs, start up delays and staff turnover. While it is still too early to be able to quantify any efficiency savings, there are indications that this has led to reduced staff turnover and positive feedback has been received from tier two partners.

Efficiency: How much of a UK taxpayer’s £1 gets in recipients’ hands

In 2019 under component I, WFP received £5,568,698 from DFID and disbursed $4,586,565 (64%) directly to households as cash. 64p in every £1 reaching households as cash is broadly in line with previous years (68p in every £1 in 2018, 71p in 2017, 64p in 2016). As a comparison, in 2019 GiveDirectly reported that 79% of their organisation wide funds went to recipients as cash. GiveDirectly provides large unconditional transfers at scale in much more stable countries, providing a good indication of BRACE II’s value for money given the conditional and complementary approaches that are provided alongside the cash transfers and the higher costs associated with smaller, regular payments.

Value for money comparisons between the two components are difficult due to the different ways that figures are presented. Component II spent £3,859,973 between October 2018 and September 2019, of which 62% (£2,387,790) went on cash transfers and finance costs. The percentage of the total component I budget (WFP and FAO) for 2019 going directly to households as cash is estimated at 48%, rising to 55% when procurements of inputs (e.g. tools) is included, and 71% when contracts with delivery NGOs (e.g. training) is included. The percentage of the component II budget (19/20) due to be spent on cash, seeds and tools in 2019 was 71%, rising to 85% when direct staff costs are included. Across the programme, it is estimated that 74% of budgeted funds were allocated to cash, agricultural inputs and direct staff time (as a proxy for training) in 2019.
A comparison of costs to transfer food and cash demonstrates the efficiency of cash as a delivery modality. In 2019, WFP reports that it would cost $16m to transfer $5.5m (290%) worth of food to people due to the high costs of moving food in South Sudan. To transfer the same value in cash costs $1.83m (33%), demonstrates the continued efficiency of cash where markets are functioning. The reported costs to transfer cash have risen from 21% in 2018 to 33% in 2019 due to a recalculation of the costs involved (including partner costs, fees to financial service providers, and WFP operational costs).

Effectiveness: Is the project reaching its goals?

Partners and third party monitoring have confirmed that the project continues to provide the target number of vulnerable households with cash transfers, agriculture support and training, and that this is continuing to support progress towards outcomes.

One indicator of effectiveness is the timeliness of cash transfers and agricultural inputs, as they need to reach households ahead of planting and the lean season if they are to be effective in meeting immediate needs and reducing food insecurity. Partner reporting from 2019 shows that both components made their first payments in May at a critical point before the biggest market price increases. These payments are likely to have been effective in meeting the immediate needs of households, though payments under component II were more closely aligned to their original plans. The lean season may start earlier than previous years in 2020 due to the impact of floods reducing household food stocks, and so making a double payment early in the cash cycle could support households to purchase food before market prices peak.
Figure 13: Graph showing sorghum price trends in Aweil

The timeliness of inputs under component II improved in 2019, with positive feedback received through third party monitoring. Unfortunately, delays signing agreements with tier 2 partners meant that inputs were delayed under component I, reducing the likelihood that they were effective.
Project area	Month of Work	Month of Planned Payment	Actual Payment / Component I	Actual Payment Component II	Month of planned input dist’n/ fair	Actual month input dist’n/ fair- Comp I	Actual month input dist’n/ fair- Comp II
Northern Bahr el Ghazal	March	April (I only)	May		March		March and April
	April	May	June	May	April	June	April and May
	May	June	July	June	May	July
	June	July	September	July	June		June
	July	August	September	August
	August	September	November	September
	September	October (II)		October
Warrap	March	April (I only)	May		March		March / April
	April	May	June	May	April	June	April and May
	May	June	June	June	May	June
	June	July	August	July	June		May/ June
	July	August	October	August
	August	September	October	September
	September	October (II)		October
Magwi	April	May		May	March		March / April
	May	June		June	June		May / June
	June	July		July
	July	August		August
	August	September		September
	September	October		October

Figure 15: Table showing the timelines of cash transfers and agricultural inputs in 2019 under both components.
Equity: are the results equitably distributed?

BRACE II targets households that are vulnerable but able to participate in a labour-based programme. This relies on an assumption that those who are unable to participate are supported through other organisations. BRACE II supports between 4-12% of the estimated population in each project location, however the number of people who meet the vulnerability criteria far outweighs the number who can be supported. This means there will always be room to consider whether the programme could be more equitable in its approach. BRACE II partners work with communities to define the determinants of vulnerability and validate the selection of those that participate. Common criteria are poor or very poor female-headed households, those with chronically ill or disabled family members or households who do not own productive assets/ livestock and rely on casual daily labour for income. Third party monitoring, partner reporting and other learning sources continue to show that BRACE II is reaching the people it is meant to on this basis, but there is still a risk that targeting criteria excludes those who could benefit.

A key way to increase the number of people reached with a package of support is to reduce the length of time people participate in the programme whilst maintaining outcomes. Under component I households are provided 18 months of cash transfers and support over three years, whereas under component II households are provided 9 months of support over 18 months. The mid-term evaluation found that the biggest gains for households were likely to be made between years 1 and 2 of the programme, indicating that there may be scope to pursue a shorter model of support with the aim of reaching more people over time. The full-term evaluation should consider this carefully, as there may be a trade off in outcomes.

The four-country thematic evaluation of DFID multi-year humanitarian financing published in 2019 demonstrated the scale of the challenge in building resilience[13]. The study calculated the investment needed to help populations in different contexts reach the international poverty line (IPL), and the amount needed for them to considered economically resilient (e.g. unlikely to fall back below the IPL). One of the areas considered was the West Hararghe Zone of Ethiopia, which has a population of around two million, the same number of people estimated to live in Northern Bahr el Ghazal and the parts of Warrap that BRACE II is implemented in. Even using optimistic assumptions, their calculations found that investment of over $600 million would be needed to help everyone reach the IPL, and over $7 billion of highly profitable investment to reach some form of economic resilience. This figure is greater than DFID’s annual global programme spending. Whilst conditions between West Hararghe and Greater Bahr el Ghazal are different, this is a reminder that supporting people out of poverty is a generational effort.
[13] https://www.odi.org/sites/odi.org.uk/files/resource-documents/12809.pdf

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

BRACE II is key part of DFID South Sudan’s strategy of balancing emergency humanitarian support with interventions that build self-reliance where access and security allows. South Sudan does not produce enough food or seed to meet the demand of its population, and it is only through increasing agricultural production, trade and markets that the country will be able to reduce its extremely high levels of food insecurity. Giving people cash costs a lot less than providing the equivalent value of food, with WFP reporting that costs associated with distributing food reaching up to 300% of its value. Providing regular and predictable transfers allows households to plan and invest in household needs that are essential for resilience such as health and education when possible.

Recommendations

DFID economist to work with partners across the DFID portfolio to support an approach to tracking equity and benchmarking costs.

Partners should plan for a timely first cash payment in 2020 and consider making a combined cash transfer to households early in the cycle to help them purchase food before market prices peak.

E: RISK

Overall risk rating: Major (the risk rating has not changed since the last annual review).

Overview of programme risk

The overall programme risk rating for BRACE II remains unchanged from the last annual review, reflecting continued delivery in a challenging operating environment. The signing of the revitalised peace agreement R-ARCSS in September 2018 has led to a reduction in politically driven conflict, however, intercommunal violence and insecurity has continued and economic indicators have worsened. In addition this year, climate risks materialised in the form of extreme seasonal flooding that has impacted food production and disrupted livelihoods.

Significant risks include:

1. Economic volatility and exchange rate losses: Throughout 2019, the South Sudanese Pound lost 21% of its value against US Dollar, while the Bank of South Sudan (BSS) depreciated its indicative (official) rate by only 4% (from SSP154 to SSP160), meaning the gap between the two rates widened from 65% to 100%.
2. Conflict and insecurity: Since the signing of the Revitalized Pease Agreement R-ARCSS in September 2018, there has been a general improvement in incidences of violent conflict across the country. Instability and localised violence has continued, however, and uncertainty surrounded the November deadline for the formation of a transitional Government, now extended to February 2020. Whilst BRACE II operates in areas of relative stability, fighting in Northern Bahr el Ghazal and reported ambushes in Magwi led to a temporary suspension of access by BRACE II partners, with fear of attack and intercommunal violence leading to activities being shifted in Twic county.
3. Climatic shocks: In 2019, unusually heavy rainfall across East Africa has led to increased seasonal flooding in large parts of South Sudan, including BRACE II areas. This has had a significant impact on project activities as roads became impassable, assets were destroyed and crops lost. Climate adaptation measures such as flood dykes have helped to prevent some damage, and BRACE II participants report that the cash and assets they have been supported with through the programme have helped them manage the impact of the shock, demonstrating a level of resilience. As the majority of BRACE II participants rely on rainfed agriculture, the likelihood of variation in rainfall affecting food production remains high.
4. Migration and returnees: The period of relative stability in South Sudan and the proximity of BRACE II locations to borders with Sudan and Uganda mean that returnees to project areas remain likely. Identifying ways to support people looking to integrate into communities is an ongoing challenge for long-term programming like BRACE II, in addition to the risks presented by supporting cultivation on land that may be contested by different communities. In quarter 1 of 2019 there was an influx of 500 IDPs into a boma in Magwi where BRACE II is being implemented as a result of armed conflict. These were supported by alternative organisations and funding in this instance.
5. Safeguarding: DFID has completed satisfactory enhanced due diligence assessments on safeguarding for WFP, FAO and WV, and partners have reported on recommendations as part of quarterly reports. Partner discussions during the year included a focus on ways to safeguard children against hazardous work.

Recommendations

WFP should work with other agencies, the cash working group and the international community to identify whether and how a strategy can be defined to close the gap between the official and parallel exchange rates or support a shift to use of the parallel rate for cash transfers.

WFP and FAO should work with OCHA to identify opportunities to improve early warning systems for weather-related shocks in South Sudan.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

BRACE II project partners have delivered sustained results across all the three components over the review period, leading to a cost and time extension being approved at the end of 2019.

BRACE II Quarterly Report Timelines [45 days from end of quarter]
		FAO/WFP	WVA
	Expected	Received
Quarter 4 [2018]	15/02/2019	11/02/2019	15/02/2019
Quarter 1 [2019]	15/05/2019	14/5/2019	15/05/2019
Quarter 2 [2019]	15/08/2019	20/08/2019	15/08/2019
Quarter 3 [2019]	15/11/2019	11/11/2019	11/11/2019

Component I: UN partnership delivered by WFP and FAO

FAO and WFP have made progress in the joint implementation and reporting of the project, however, further efforts to collaborate are still needed. BRACE II was designed with two phases under component I to provide the opportunity for the programme to adapt in the second phase. Whilst WFP, FAO and their implementing partners work together on programme delivery and reporting, reaching an agreement on how the phase II budget would be split between the two UN agencies proved to be a significant challenge at the end of 2018. The goal was for the available budget to be split between the two agencies so they could reach the same households with their respective packages of support. This could not be achieved within the time available, however, an agreement was reached that WFP and FAO would jointly reach 15,485 households. A further 3,390 households would be supported by DFID funds up to the third WFP transfer in 2020, and with other donor funding through FAO for 2019 and 2020. Whilst this does not change the package of support provided to project participants, it does demonstrate the challenges and work required for a productive partnership.

DFID made four payments to WFP over the review period totalling £6,870,457.19. Due to agreements between DFID and WFP at headquarters level, WFP does not provide project specific financial reports, however, the cash disbursed alone demonstrates significant delivery and disbursal in 2019. Following the delayed budget agreement described above, FAO requested funds for phase II in December 2018 without a signed agreement or notification of forecast being submitted. FAO, with input from the representative, worked pragmatically with DFID to resolve this. In the review period, DFID made 2 payments to FAO totalling £2,292,659.70, with FAO having spent $2,627,227 as of October 2019. FAO’s performance based on the disbursement and use of budget against forecast and the accuracy of forecasting has shown improvement as a result of concerted engagement.

In 2019, a review was undertaken of the effectiveness of the ‘results compacts’ agreed with all UN HARISS partners under DFID South Sudan’s humanitarian programme (HARISS), including WFP and FAO. This approach to results-based financing was discontinued due to the high transaction costs involved.

Component II: NGO consortium led by World Vision

In the review period, DFID has disbursed £3,515,336.00 to World Vision Australia, with £2,718,656 (77.3%) spent by the end of quarter 3. This is a 9.33% improvement on the disbursement level during the same period in 2018. Improvements have been made on financial forecasting, and the quality of the partnership with SAADO and SPEDP has been maintained through the year.

Component III: Monitoring and Evaluation led by IMC Worldwide

Following unsuccessful attempts to negotiate a contract amendment in 2018, DFID set out a Performance Improvement Plan (PIP) for the M&E service provider to re-direct efforts toward ensuring delivery. The PIP ran from 7 December 2018 to 1 March 2019, and tracked progress against an agreed set of milestones alongside regular meetings and long-term technical support provided by the DFID Evaluation Quality Assurance Service (EQUALS). The quality and management of M&E services improved through the process to allow IMC to exit the PIP and continue the contract to completion in July 2019. Nine quarterly narrative and financial reports were submitted between inception and the PCR to document their main activities and progress on deliverables.

The M&E service provider spent a total of £559,391.7 (86%) over the life of the contract of a maximum £649,958. This has resulted in savings of £90,566 which will be used to contract a final evaluation.

Annual Audited Accounts

The WFP annual audited accounts for the period ending 31 December 2018 gave an unqualified opinion on WFP financial statements. This is a WFP global corporate audit rather than a BRACE II specific report. Though the audit covering the current review period 2019 will not be available for this review, one priority 1 recommendation on cash-based transfers remained relevant. It required WFP to continue rolling out the SCOPE beneficiary tracking system, with the goal of covering, by the end of 2019, 85% of cash-based transfers through SCOPE globally (by value). There was a 100% target for SCOPE registration in BRACE II locations in 2019, with some delays in the delivery of the of mobile Point of Sale (mPOS) machines in some project locations and registration issues in Northern Bahr el Ghazal delaying final cash transfers.

Similarly, FAO annual audited accounts for the period ending 31 December 2018 were returned with an unmodified audit opinion on the organisation’s financial statements as a whole. FAO posted a surplus of $173.8 million and total equity of $343 million indicating a solid solvent financial position. The audit report flagged delays in disbursement of funds to FAO by major contributors and the need to align its forecasts and donor's expenditure patterns to avoid the risk of FAO failing to implement projects and meeting its obligations. Therefore, the audit report made two recommendations with fundamental priority rating on finances with timeline for implementation in 2019. This has been implemented during this review period, which saw the BRACE II contribution arrangement No. 1.2018 being amended to align project proposed activity timelines with a quarterly payment schedule. This has ensured that FAO is able to pay for procurement and project activities promptly with less payment deficit in its financial statements. This has overall, improved FAO’s forecasting and expenditure in line with approved budget.

Asset Management

World Vision is the only BRACE II implementing partner that maintains and shares an asset register with DFID. The World Vision asset register indicates that all programme assets are located in Aweil North and Magwi respectively. Magwi has not been visited by DFID staff at the time of the review, and a December 2019 monitoring visit to Aweil could not include Aweil North due to access and time constraints. A monitoring visit to a component II site is therefore a priority for 2020. IMC worldwide do not have any assets to record whilst DFID agreed centrally that WFP and FAO should manage assets themselves in line with their UN policies.

Recommendations

An asset spot check will be conducted as part of any DFID field trip to a component II site in 2020

WFP will report on the proportion of SCOPE use and any implementation issues by January 2021

Date of last narrative financial report(s)	FAO: 11/11/2019, WFP: None provided as per DFID-WFP HQ agreement, WV: 15/11/2019 IMC: 18/9/2019
Date of last audited annual statement (s)	WFP received 09/01/2020 covering the period 01/01/2018 – 31/12/2018 (Vault No.: 53203171) / FAO received 14/01/2020 covering the period 01/01/2018 – 31/12/2018 (vault No.: 53331368) / World Vision Australia: AAA Not available at the time of reporting.

G: MONITORING, EVIDENCE & LEARNING

This annual review was undertaken by DFID South Sudan’s livelihoods advisor (SRO), programme manager and programme officer between December 2018 and February 2019 with input from the senior economist. A four-day project monitoring visit was conducted as part of the review process, and the draft was discussed with delivery partners and shared with cross-cutting advisers in the DFID office.

Progress of BRACE II has been monitored closely over the review period through:

- Third Party Monitoring conducted in November 2018 (Gogrial West and Magwi, WVA) and June/July 2019 (Aweil South and Aweil North, WFP/FAO) under component III.
- Project site visits by DFID staff carried out in December 2019 (WFP/FAO- Aweil Centre and South).
- WFP, FAO and World Vision officers regularly visiting project sites to monitor implementation by partners and seek beneficiary feedback (staff from Juba and field offices).
- Quarterly narrative and financial reports submitted by partners to DFID.
- Regular meetings with implementing partners.
- Field based staff providing monthly reports to WFP, FAO and World Vision and communicating regularly on operations and risks.
- Field work for the mid-term evaluation conducted in October/ November 2018.

M&E Component

Component III of BRACE II provides for independent monitoring and evaluation services to the programme. A contract in place from January 2017 to July 2019 undertook four principle M&E activities:

- Third Party Monitoring (TPM) monitored implementation and identified emerging outcomes or impact. Thirteen distinct TPM visits (each one produced a factsheet) were conducted over five TPM rounds at key programmatic time periods, inclusive of all co-operating partners and locations for both Components I and II.
- Thematic Learning used findings from TPMs and the Mid-Term Evaluation (MTE) once complete, to support and inform learning for DFID and the implementing partners.
- Evaluation measured progress against outcomes and impact and generated evidence to answer programmatic questions through the MTE.
- Value for Money (VfM): The M&E component supported the generation of two sets of programme-level VfM studies (VfM matrices at Implementing Partner-level and a VfM assessment paper analysing some of the MTE results).
M&E Component Products

By the end of the contract, a total of 30 M&E products were delivered by the M&E service provider as follows.
  - 1 Inception Report: finalised in July 2017
  - 1 FAO rapid review report: delivered and accepted in January 2018
  - 1 theory of change workshop in June 2017
  - Thematic Learning Mission 1 on skills development learning brief: accepted January 2018
  - Thematic Learning Mission 1 detailed report: delivered and accepted January 2018
  - 13 third party monitoring factsheets, 8 up to October 2018: TPM1 factsheets (1-4) were submitted on 31 January 2019; TPM 2 factsheets (5-6) were submitted on 27 July 2019; TPM 3 factsheets (7 – 8) were submitted on 20 September 2018 and 05 October2018. TPM 4 factsheets (9 – 11) were submitted on 04 February 2019 and 25 February2019, and TPM 5 factsheets (12-13) were submitted on 31 July 2019.
  - 4 learning and action workshops: October 2017, 1 donor meeting (held in March 2019) and 2 partner events (held in March 2019 and July 2019)
  - 1 overarching BRACE II logframe: delivered and agreed in April 2018
  - 1 M&E framework document: submitted on 20 February2019 and accepted in April 2019
  - 1 final MTE Terms of Reference (ToR), submitted on 08 February 2019
  - 1 MTE report: final version was submitted on 24 June 2019 and accepted in July 2019
  - 1 VFM assessment paper was submitted on 19 July 2019
  - 1 final learning paper on labour and opportunity costs submitted on 31 July 2019 in lieu of a TLM 2 detailed report
  - 1 Project Completion Report (PCR) submitted on 18 September2019
  - 1 briefing note on International Climate Fund (ICF) KPI 4 was submitted on 12 April 2019.

As noted earlier in this review, the M&E component faced several challenges and a performance improvement plan was initiated at the end of 2018. Significant DFID staff resource and long term technical assistance from the Evaluation Quality Assurance Service (EQUALS) were dedicated to improving the management and delivery of M&E products, with final version of the mid-term evaluation rated ‘good’. The findings of the mid- term evaluation have provided a solid basis for discussions between partners and other donors and are being considered as part of a programme extension. For example, understanding that households spend their cash transfers on a range of needs including health and education demonstrates that unrestricted cash is providing additional value as a modality than the equivalent value of food would. Findings that labour may be the binding constraint on agricultural production challenges assumptions about the need for participants to clear more land, and points partners to promote labour saving and higher yielding farm techniques. The mid term evaluation highlighted that some participants increase their agricultural production to a level where they are seeking out new markets, whereas others do not, suggesting the programme could look for a differentiated approach tailored to people’s needs and aspirations.

Unfortunately, some other outputs delivered under this component were not of high quality and there continued to be issues with the framing of the programme’s goals. A lessons learned session was held with the M&E provider in late 2019 which will feed into the procurement of any future services.

Evidence

Both agencies under component I play a critical role in data gathering in South Sudan. WFP conducts biannual surveys under their FFA programme as well the nationwide Food Security and Nutrition Monitoring Survey (FSNMS). In 2019 a baseline assessment replaced the first survey, taking place in July 2019, with the second survey carried out in December 2019. To assess agricultural production, an FAO/WFP Crop and Food Security Assessment Mission (CFSAM) took place from 3 to 13 December 2018 to estimate cereal production and assess the overall food security situation. As with previous years, the CFSAM reviewed the findings of several Crop Assessment Missions conducted from May to December 2018 and involved the Ministry of Agriculture and Food Security (MAFS), the National Bureau of Statistics (NBS), FAO and State Ministries of Agriculture.

Under component II, a survey was undertaken from October 27 to November 5 on which their BRACE II annual report was based.

Data collection for the mid-term evaluation was conducted between 20 October and 15 November 2018. A household survey, crop yield assessments and researcher diaries were employed, with analysis and validation between December and March 2019.

Learning

A DFID funded thematic evaluation of multi-year humanitarian financing in four countries delivered its final report in 2019[14], with some crucial findings for multi-year support that aims to build resilience in protracted crises. Those most relevant to BRACE II are included below- challenging some of the assumptions implicit in the programme design.
[14] https://www.odi.org/sites/odi.org.uk/files/resource-documents/12809.pdf
- Resilience is often defined by reference to shocks. The study found that smaller shocks such as ill health were just important and can’t be separated from structural factors that limit people’s agency. ‘For people living in …protracted crises… resilience is reflected in the choices that people are able to make when in difficulty’’.
- Gender was the single biggest determinant of a person’s agency, in and out of crisis.
- Social connections outside people’s locality were an important contribution to coping, especially where these were with people in urban areas.
- The ‘meso-economy’ was the most important in determining livelihood opportunities. This refers to the local economy, but covering a much larger, and typically a combined rural–urban, population than their very immediate, local economy.
- Asset accumulation and business investment played a surprisingly limited role in creating resilience, perhaps because people could not get to significant levels of either.
- Personal adaptive capacity is a critical skill but was comparatively rare. People’s individual ability part skill, part mindset – to take advantage of opportunities that are available is largely neglected in resilience thinking.
- Ill-health is a major impediment to people’s progress towards resilience. It typically robs households of over a quarter of their potential income.
- Access to basic services was critical but was largely determined by political status, and the ability of people to overcome marginalisation

In 2019, WFP conducted a rapid gender assessment of its Food for Assets programme in South Sudan, which DFID invests in under BRACE II. This identified seven ways that women can be empowered through participation in the programme, as well as the key recommendations on ways to advance gender equality.

1. Women had better social organisation and experience better social cohesion, mutual support and solidarity;
2. Improvements in the recognition of women, women’s roles and leadership in the public sphere;
3. Improvements in intra-household dynamics;
4. Reduced women’s workload and hardship;
5. Women had improved skills and confidence and changed perspectives;
6. Women had improved livelihoods, earned more income and had reduced financial dependence
7. Women had a better understanding of their rights and could exercise them.

Recommended adjustments to mainstream good practice include:

- Community Planning: Increase women representatives’ attendance and participation in community based participatory planning (CBPP) meetings by minimising barriers such as meeting location, duration and timing, providing childcare or other support and improving the quality of facilitation.
- Work: For work on community assets, ensure that work norms are designed for women, men and vulnerable groups in accordance with their needs, (practical and strategic) interests and abilities. Work norms need to consider the multiple carer duties that women have.
- Transfers: Ensure participants do not have to walk more than two hours or wait more than three hours for their transfer, distributing to women first.
- Training: Encourage partners who already provide messaging to advance gender equality to share resources and materials with others, and consider developing standard gender messaging alongside nutrition messaging.
- Committees: Ensure committees comprise at least 50 percent women and are elected by participants, with annual re-election in line with guidelines. Provide training so they can take on leadership roles.
- Institutional factors: Take steps to actively recruit women for field positions.

All BRACE II partners have been involved in the evolving Partnership for Recovery and Resilience (PfRR) in South Sudan, including participating in major learning events held in Juba in late 2018 and 2019.

Over the coming year there are two investments in learning which will support and shape the work of partners.
1. World Vision has partnered with John Hopkins University to secure funding from the Research for Health in Humanitarian Crises (R2HC) fund to research the effects of cash transfers on intimate partner violence in humanitarian settings, focused on cash transfers under BRACE II. The first round of data collection is complete, with two more planned for 2020 and findings due in early 2021.
2. WFP has initiated work to evaluate their Food for Assets programme. Preliminary work has started, with field work/data collection due to take place in February/ March and a draft report due in June 2020.

Cross-Partner Learning: Several events were undertaken in the review period to promote learning between partners. In March, DFID hosted a session with tier one and two partners and the M&E provider to discuss the findings of the mid-term evaluation. In July 2019, this was followed by a day-long workshop with BRACE II and HARISS partners working on resilience and livelihoods programming to focus on the uses of cash, changes in agricultural production, models for savings and income generation groups and measuring climate resilience. BRACE II partners also participated in DFID humanitarian partner days in December 2018 and May 2019 and undertook a joint learning visit to sites under both components in December 2019.

Progress on recommendations from previous reviews

Progress has been made on implementing the recommendations of previous reviews, with learning workshops delivered, decisions made on M&E services and an approach taken to align cash transfer values. FAO has worked with DFID programme staff to improve information flow on finances and forecasting, and some downstream partners have promoted financial training and savings groups as a complementary activity and held learning days to scale up field extension to non-beneficiaries. Work will continue to implement other ongoing recommendations such as improving value for money analysis, increasing the quality of nutrition and climate sensitive interventions and coordinating with policy and programmes in South Sudan.

Recommendations

The WFP rapid gender assessment should be shared with all BRACE II partners and discussions held between tier 1 and 2 partners on implementation of the recommendations.

Ongoing/ relevant recommendations from the previous review with updated timelines

BRACE II partners will report on partnerships they have developed to deliver better, more coordinated services to communities in their quarterly updates, including contributions to the ‘Partnership for Recovery and Resilience’

IPs to introduce/ scale up the use of field days or other community dissemination events to promote new skills to a wider audience and multiply benefits of the programme to non-beneficiaries at limited cost

WFP/FAO to analyse any changes to costs and cost drivers between phase I and II of BRACE II and provide a narrative as part of inputs to a final evaluation

DFID and IPs to prepare and agree a contingency plan for increased population movements into BRACE II project areas. This could involve the agreement and use of contingency funding within the overall budget envelope

DFID will undertake a ‘light touch’ conflict sensitivity review of tier 1 partners using the assessment criteria based on the conflict sensitivity minimum standards by July 2020

The mid-term evaluation has produced useful findings which will inform the work of partners and DFID, however, there is no way to confidently attribute change to the programme activities as there is no counterfactual to compare results against. DFID should learn from the mid-term evaluation and look to incorporate a control group in the design of future evaluations

Recommendations from this review

Key Recommendations (page 3)

WFP and DFID will work with World Vision and other development partners to improve the value for money of cash transfers in South Sudan by aligning values and approaches where possible. Opportunities to maximise value through the use of a parallel or negotiated rate will be explored, and the development of a roadmap towards a social protection system will be supported.

DFID will review existing VFM matrices with all partners, aiming to agree the definitions and presentation of a streamlined core set of indicators.

DFID will contract further M&E services (third party monitoring and a final evaluation), in discussion with partners.

DFID will work with partners to update and refine the draft BRACE II theory of change.

Detailed Recommendations

Basic financial literacy training and village savings and loans associations were included in both component I and II for 2019 to increase the benefits of the cash transfers. Partners should submit an update on the implementation of these (number, locations, lessons learnt) in the Q3 report 2020 (page 5).

Partners will discuss options for alignment of cash transfer values in 2020 in coordination with other stakeholders (cash working group coordinator, World Bank safety nets lead) by March 2020 (page 5)

Partners will review plans for the timing of transfers in 2020 based on expected household needs and purchasing power (page 5).

Where possible, partners should test partnerships which can provide access to machinery to support asset creation without large increase of costs to the project. Lessons should be provided to DFID and shared with other programme partners (page 7)

BRACE II partners will coordinate their work with others in Aweil and provide examples of successes or challenges to the annual PfRR learning event due in late 2020 (page 7)

- DFID governance adviser(s) should
  - review governance structures under BRACE II to identify any opportunities to strengthen dispute resolution/ peacebuilding mechanisms and link community planning processes to local governance structures and development plans.
  - approach the CSRF and other UK-funded research programmes to identify whether support is available on land-related issues, including reviewing existing studies on the legal framework for HLP and current efforts to address these issues (page 7)

Partners will continue to look for options to promote fruit trees in a way that they are likely to be maintained. This could include local procurement of appropriate seedlings by partners, communications on their importance and care or a focused effort on promoting them at appropriate sites such as nutrition gardens or institutions with access to water (page 7)

Any extension of activities should include an updated training plan which sets out the skills/ messages that programme participants should be provided with and how uptake is being promoted, learning from adoption rates so far (page 9).

Between February and May 2020, all partners should map available weather/climate information sources and test a simple mechanism to communicate forecasts to downstream partners and BRACE II communities (page 9).

All partners should identify any barriers to feedback being provided through existing mechanisms and redouble efforts to communicate ways for people to provide feedback during the start of transfers in 2020 (page 10).

In any extension partners will demonstrate how they have made adaptations to programme plans based on learning and feedback mechanisms (page 10).

DFID economist to work with partners across the DFID portfolio to support an approach to tracking equity and benchmarking costs (page 17)

Partners should plan for a timely first cash payment in 2020 and consider making a combined cash transfer to households early in the cycle to help them purchase food before market prices peak (page 17)

WFP should work with other agencies, the cash working group and the international community to identify whether and how a strategy can be defined to close the gap between the official and parallel exchange rates or support a shift to use of the parallel rate for cash transfers (page 18)

WFP and FAO should work with OCHA to identify opportunities to improve early warning systems for weather-related shocks in South Sudan (page 18)

An asset spot check will be conducted as part of any DFID field trip to a component II site in 2020 (page 20)

WFP will report on the proportion of SCOPE use and any implementation issues by January 2021(page 20)

The WFP rapid gender assessment should be shared with all BRACE II partners and discussions held between tier 1 and 2 partners on implementation of the recommendations (page 24)

List of Abbreviations

BRACE	Building Resilience through Asset Creation and Enhancement
CBPP	Community Based Participatory Planning
CBT	Cash Based Transfers
CFSAM	Crop and Food Security Assessment Mission
DFID	Department for International Development
FAO	Food and Agriculture Organization
FCS	Food Consumption Score
FFA	Food for Assets
FO	Final Outcome
FSNMS	Food Security and Nutrition Monitoring Survey
FSP	Financial Service Provider
HARISS	Humanitarian assistance and Resilience in South Sudan
HDDS	Household Dietary Diversity Score
ICF	International Climate Fund
IMC	IMC Worldwide
INGO	International Non-Government Organisation
IO	Intermediate Outcome
IPC	Integrated Phase Classification
KPI	Key Performance Indicator
M&E	Monitoring and Evaluation
MTE	Mid-term Evaluation
NBeG	Northern Bahr el Ghazal
NGO	Non-Government Organisation
PfRR	Partnership for Recovery and Resilience
RIMA	Resilience Index Measurement & Analysis
SSP	South Sudan Pound
TPM	Third Party Monitoring
UN	United Nations
VFM	Value for Money
VSLA	Village Savings and Loans Associations
WFP	World Food Programme
WV	World Vision