Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Punjab Economic Opportunities Programme (PEOP)
Programme Value: £ 30 million		Review Date: 8-17th June 2015
Programme Code: 114384	Start Date: 28/01/2008	End Date: 31/12/2015

Summary of Programme Performance
Year	2010-11	2011-12	2012-13	2013-14	2014-15
Programme Score	3	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Low

Summary of progress and lessons learnt since last review

The Punjab Skills Development Fund (PSDF) has developed into a strong institution. It is the first competitive skills financing fund in Pakistan and was established in response to the inefficiencies of public sector delivery of technical and vocational skills training. PSDF seeks to encourage private sector training providers to enter the market to deliver free training to poor and vulnerable men and women. Its unique training delivery model has potential to expand and support the Government of Punjab’s (GoPb) ambitious skills target of training 2 million in its current Growth Strategy.

PSDF is led by a strong, independent Board of Directors comprising both private and public sector members. A lean management structure has helped to reduce unit costs and the Randomised Control Trial (RCT) based research and evaluation conducted by the Centre for Economic Research in Pakistan (CERP) has helped to make training more relevant to the market and demands of beneficiaries.

PSDF has created a niche within the skills sector in Punjab with a role in policy setting with the Government of Punjab (GoPb) as well as training delivery. PSDF and CERP using knowledge gained through their partnership have provided significant contributions to develop the recently launched Punjab Skills Strategy. The Strategy, which in turn contributes to the overall Growth Strategy for Punjab, is an indicator of GoPb’s political will and determination to reform the skills sector in Punjab.

PSDF has demonstrated an impressive trajectory of progress in the last four years and has trained a 50,000 trainees (40% women) in 2015. This will bring the total number of people trained to over 95,000 and the programme is on track to deliver the expected end of programme training target of 135,000. PSDF has successfully partnered with more than 160 individual Training Service Providers (TSPs) in more than 140 training trades. TSPs have reported increased capacity due to rigorous, independent third party monitoring and PSDF’s competitive procurement model. PSDF has demonstrated good value for money (VFM) and the management expects about £3.3 million of DFID funds to remain by the end of the PEOP programme in December 2015.

PSDF has started deliberations at policy level to tackle some of the risks and challenges identified in the last review. However, given that DFID will continue to support PSDF through the recently approved Skills Development Programme (SDP) it is important that the pace is increased and clear delivery deadlines are agreed. These key issues that require attention include:

- Addressing the financial sustainability of PSDF
- Developing an employment facilitation strategy in particular for women
- Completing sector analyses before targeting industrial sectors
- Developing a targeting and gender mainstreaming strategy to ensure inclusion of the vulnerable groups such as women, landless farmers, and the illiterate.
- Refining the partnership arrangement with CERP with clearer results, duration and finances
- Preparing for a seamless transition from PEOP to DFID’s next investment with the GoPb in skills, the Skills Development Programme (SDP).

Summary of recommendations for the next year

DFID and Government of Punjab

Allocate Technical Assistance (TA) funds unlikely to be spent by the end of the programme and other savings realised with programme funds to the financial aid component of PEOP to fund additional skills training.

Provide a no-cost extension to PEOP until the end June 2016. This will ensure successful completion of the ongoing courses as well as one more round of training, funded from programme savings (i.e. underspent TA funds, exchange rate savings and interest rate accruals). This will enable PEOP to train an additional 10,500 men and women above the original end of programme training target. The extension would also allow for evaluation data to be available to inform that Project Completion Review (PCR). The “Exchange of Letters” (EOL) should be amended accordingly.

Update the log frame as a result of adjustments in the evaluation approach to reflect changes in indicators at the outcome and output levels.

Extend CERP’s Accountable Grant (until March 2017) to cover the remaining work on evaluation. This should be completed by the end of September 2015.

Request a Programme Steering Committee Meeting (September 2015) with the Planning and Development Division of the Government of Punjab to agree a process to close PEOP and transition to DFID’s new SDP. Project documentation and negotiations with the Government of Punjab (including the finalisation of the EOL) for the SDP to be completed in September 2015 to allow a smooth transition between programmes.

PSDF

Formal coordination processes between CERP and PSDF should be established to avoid delays and ensure dissemination of research findings to improve the design of skills schemes. The PSDF Board and senior management should provide proactive leadership to embed coordination mechanisms.

When designing skill schemes, PSDF should consult employers from the outset. Formal engagement mechanisms with relevant Chambers of Commerce and business associations need to be established.

PSDF should develop a sustainability strategy including identifying and testing revenue generating mechanisms.

PSDF should put in place formal coordination mechanisms should be in place to avoid duplication with other training programmes offering free skills training in the same market.

PSDF should adopt a targeting strategy for the next phase of the programme should with clear and robust eligibility criteria to attract those poor and vulnerable who are keen to be trained to enhance their incomes.

PSDF should scale up the job facilitation function including creating a communication loop with alumni (i.e. trainees). Lessons from other skills programmes in the region should be reviewed to improve job facilitation services.

A. Introduction and Context

DevTracker Link to Business Case:	NA
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-113484/documents/

Outline of the programme

The Punjab Economic Opportunities Programme (PEOP) is a partnership between the Government of Punjab (GoPb) and DFID. The objective of the programme is to enhance the income earning opportunities of the poor and vulnerable in the 14 target districts. These districts were chosen based on two considerations i.e. the size of their poor and vulnerable population, and concentration of industrial sectors with growth and job prospects for the poor. Both DFID and GoPb have committed to contribute £25 million each over the life of the programme. Additionally DFID provides £5m in technical assistance support, making the total size of the programme £55m. The programme started operations in October 2010 and was expected to close in December 2015. As a result of this review a no cost extension to March 2016 is recommended.

Initially, the programme envisaged two components: i) Workforce development through funding skills training for 80,000 poor and vulnerable in four poor districts of Southern Punjab and ii) a livestock and dairy component to enhance the contribution of the sector to the local economy. The annual review in 2012 recommended closure of the livestock component due to its poor performance. Funds committed to the livestock component were re-allocated to the skills component, which allowed expansion of PSDF to ten additional districts in Southern and Central Punjab providing training to an additional 55,000 people in the newly added districts. This change broadened the focus from increasing the skills base in rural districts to addressing skills gaps in growth oriented industrial sectors.

The skills component is implemented through the PSDF. PSDF is incorporated with the Securities and Exchange Commission of Pakistan (SECP) under section 42 of the companies’ ordinance as a “not for profit” private sector company. PSDF is governed by an independent board of 15 members with membership from both the private and public sectors. Through an Accountable Grant (AG), the Centre for Economic Research in Pakistan (CERP) provides robust and continuous research and evaluation support to PSDF which is being used to refine the training programmes. A separate AG to PSDF is used for conducting sector studies and labour markets assessments.

Expected results of PEOP:

- Train 135,000[1] poor and vulnerable people with a gender focus (40% women)
  [1] 50% ( 67,500) is directly attributable to DFID.
- Develop an effective funding model for delivery of technical and vocational skills
- Develop a competitive market for private sector delivery
- Support the GoPb to improve skills policy and regulations
- Develop a robust research and evaluation framework to test and refine the training programmes and PSDF model

DFID has recently approved the Skills Development Programme (SDP). This is a six year (July 2015 to June 2021) programme and builds on the success of the PEOP. DFID will contribute £89.5 million to SDP, with £69 million allocated for PSDF. GoPb will match DFID’s contribution to PSDF. SDP will enable DFID to train an additional 330,000 men and women; strengthen the technical and organizational capacity of PSDF; work in the regulatory and policy domain; improve public sector delivery of skills; and support innovative modalities for improving the quality and supply of skills. Some lessons and recommendations from this PEOP annual review will be taken forward through SDP.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The Outcome of the programme is “Workforce in PEOP districts who are poor and vulnerable are involved in economic activities” with 3 indicators:

1. Individual earnings
2. Index of well being
3. Index of state engagement

These indicators do not completely track the intended outcome of the programme. As a result of adjustments in the evaluation approach, the review team is recommending to add some indicators to (i) better link the outcome indicators with outcome statement; (ii) disaggregate the indicators for men and women and (iii) monitor the indicators through evidence produced by the programme.

Overall output score and description: A

The review team has monitored and recorded the progress gains 5 outputs in the log frame. A summary of the output scores is given below:

	Output	Weight %	Risk	Output Score
1	Effective model for funding competitive training delivery	20	Medium	A
2	Poor and vulnerable trained	50	Medium	A+
3	Private training places mobilised	10	Low	A++
4	Support to the GoPb for skills policy and regulatory reform	10	High	B
5	Generation of evidence to inform skill delivery	10	Medium	B

PEOP is set to achieve its target of training 135,000 beneficiaries by December 2015. Close to 90% of the training places are provided by the private sector. Successful progress on the first three outputs corresponds to 80% of the weight with the programme achieving an overall output score of “A”.

Output 4 is partially achieved. PSDF has contributed effectively to the development of the skills sector strategy of the GoPb. PSDF regularly advises the government and other stakeholders on policy and reforms in the skills sector. It has acquired credibility and visibility in the sector due to its ability to train beneficiaries in large numbers and its competitive funding model. Despite all the good progress on this output, one indicator on producing and using research in PSDF is lagging behind and has pulled down the output score to “B”.

Output 5 is seriously lagging behind. CERP has produced research and evaluations with some delays. The last two evaluation experiments are delayed and a report covering these is expected in March 2017 which is well beyond the original programme end date (December 2015). Delays in all outputs have led to a score of “B” for this output. It is important to note that CERP evaluation experiments do not conform to a traditional evaluation design which has a base line, a mid-term and a final evaluation. The approach to the Randomized Control Trials (RCT) experiment was adapted to respond to the low uptake of training opportunities. As a result of the low uptake, subsequent RCT designs focused on improving the linkage between inputs and outputs. The focus of the RCT has now shifted to evaluating the linkage between the outputs and outcomes.

Key lessons

- It takes time to build strong institutions. The Board correctly focused initially on establishing an effective business model with transparent systems with no leakages, no ghost trainers and no spurious students. This in itself is a big achievement given high corruption levels in Pakistan. DFID’s and GoPb’s patience to allow the Board time to get the institutional set-up of PSDF right has in turn allowed PSDF to develop robust systems and not overextend itself.
- The critical test for PSDF going forward will be its ability to link training graduates with job markets by strengthening linkages with potential employers and using the alumni network.
- Sophisticated evaluations are not fully understood by sector players including some PSDF staff. Hence, such evaluations need to be supported with more proactive information dissemination and discussion sessions with stakeholders. This will help build broader ownership for the evaluation results and increase the probability of using them to influence policy and practice.
- Complex RCT evaluation experiments need more time than standard evaluations. This needs to be factored into the programme planning cycle. They also require more coordination between PSDF’s operations teams and the evaluators.

Key actions

Coordination: Formal coordination processes are required at three levels between: i) CERP and PSDF to avoid delays and ensure dissemination of research and evaluation findings to improve the design of skills schemes(the PSDF Board and senior management should provide proactive leadership to embed coordination mechanisms); ii) PSDF and other skills initiatives to ensure that students’ data is shared to avoid duplication of students trained; and iii) DFID and GoPb to coordinate closely to ensure a seamless transition from PEOP to the new SDP.

In order for PSDF to meet labour market needs, it should engage with potential employer’s right from the planning and design phase when determining which skills to provide and how to design, deliver and evaluate the training. Formal engagement mechanisms need to be established with relevant Chambers of Commerce and business associations.

In order to ensure comprehensive coverage of the poor, PSDF should develop a targeting strategy for the next phase of the programme. It should have clear and robust eligibility criteria to attract those poor and vulnerable who are keen to be trained to enhance their incomes.

PSDF should scale-up its job facilitation function to strengthen communication with alumni (i.e. trainees). Lessons from other skills programmes in the region should be reviewed to improve job facilitation services.

PSDF should develop a sustainability strategy including identification and testing of revenue generating mechanisms within the next 12 months.

Has the log frame been updated since the last review?

No. The log frame was last updated in March 2014. The log frame is currently being updated in light of the modifications made in the evaluations strategy of PEOP and the recommendations of this Annual Review.

## C: DETAILED OUTPUT SCORING

Output Title	Effective model for funding competitive training delivery
Output number per LF		1	Output Score	A
Risk:		M	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 No. of evidence based products rolled out by PSDF (Cumulative)	6	PSDF has rolled out six evidence based training schemes this year / Skills for Garments / 3 Skills for Job (SFJ) schemes in 14 districts / Skills for Market (SFM) in ten districts / Skills for Biogas in 14 districts / The training design was informed by case studies and various reports (i.e. Garments Report, Construction Report, Logistics Report and a Tracer Study), a series of consultations with private sector / industry, / Beneficiary feedback and evidence from earlier phases of training.
1.2. Number of PSDF Board meetings/annum	4	Four board meetings were held. The board approved the work plan and the budget for FY2014-15 including four new skills schemes and provided strategic advice on other key issues. All the statutory sub-committees of the Board are fully constituted and operational and there has been no unexpected Board turnover.
1.3. No. of operational partnerships developed (Cumulative)	6	Six operational partnerships were developed including with Akhuwat, Bahawalpur Chamber of Commerce and Industry, Information Technology University, Kamata Pakistan, Habib Bank Pakistan Limited and Punjab Board of Technical Education. / Five operational partnerships[2] were previously developed with organisations to support curriculum development and jointly deliver training.
1.4. No. of unqualified reports by independent auditors per annum	1	The external audit report of PSDF for the year ended June 2014 by KPMG has been shared. There are no outstanding observations. The report by the Auditor General has observations that will be resolved through convening the meetings of the Special Departmental Accounts Committee (SDAC). The first SDAC meeting was held in March 2015. All paragraphs on the Project Implementation Team (PIT) were settled. Out of 31 paragraphs on PSDF, 11 have been settled. It is expected that the remaining 20 will be settled once evidence is provided at the second SAC which has yet to be scheduled. / The audit report for CERP by KPMG for the period ended June 2014 is unqualified.
[2] Kamata Pakistan ; Punjab Board of Technical Education (PBTE); Turkish International Cooperation and Development Agency (TIKA) ; Allied Services International Limited (ASIL), GiZ (German Technical Cooperation)

Key Points

PSDF is a sound model for funding competitive training delivery. PSDF should now focus on refining the model to achieve programme effectiveness and strengthen the linkage between programme outputs and outcomes. See section F (Commercial Considerations) for details.

The PSDF Board of Directors has played a proactive role and provided oversight over all elements of PSDF’s work. Yet, the review team found that some PSDF staff lack a bigger picture understanding of the organisational goals and the genesis of their work streams.

The review team analysed the human resources department. PSDF have hired 14 new staff, bringing the total staff to 53. Recruitment is in process to fill four vacant positions including that of HR Manager. The staff turnover rate was quite high in the start of the last financial year, but the upward revisions in salary structure to make it more comparable to the market have reduced the turnover rate. Another important factor that has improved staff retention is the commitment by DFID to support PSDF for a further six years through the new skills development programme (SDP).

Since the programme will soon be scaling-up its activities across Punjab, a detailed HR review is needed to determine the appropriate organisational structure to meet the expanded geographic coverage. This will be conducted as part of the operational review of PSDF.  Both staff performance and morale will need to be managed effectively during the proposed scale-up.

While the Auditor General’s audit report is the primary audit document for the government. The fiduciary risk concerns of DFID are covered through the independent external audit. The key observations in the Auditor General’s report mainly pertain to the decisions of the Board that did not follow the government rules. PSDF is a Section 42 Company and the Board followed the Securities and Exchange Commission (SECP) rules that pertain to Section 42 companies. This contention between which set of rules apply to PSDF governance (government or Section 42) will remain as long as PSDF is a recipient of government funding or until the Government conducts a commercial audit through the Auditor General. It is expected that issues raised by the Auditor General will be resolved through discussions with the Special Departmental Accounts Committee (SDAC), although this process takes on average four years. PSDF and DFID should review similar models such as the Pakistan Poverty Alleviation Fund and the Punjab Education Foundation to learn how other organisations have resolved similar challenges.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review made a suggestion that the organisation’s long-term vision and sustainability strategy needs to be developed and shared with the GoPb and DFID. PSDF has made some effort to define options for the future however more work needs to be done to embed this within PSDF’s business plan.

Recommendations

- A forward-looking organisational vision and sustainability strategy needs to be developed (with a detailed options analysis). The strategy needs to be embedded in the organisation and its operations in a sustainable way. The Board should devise a plan within the next 12 months. The SDP log frame has the relevant output to track progress and implementation of the plan.
- Information flow from Senior Management to PSDF teams and employees should be strengthened and more frequent.
- DFID should request the Board of Directors to pass a resolution that formally allows at least two DFID staff members to attend all Board meetings as Observers. The company secretary should share the agenda and any other working papers with DFID at the same time as with the Board of Directors.

Output Title	Poor and vulnerable men and women trained
Output number per LF		2	Output Score	A+
Risk:		M	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Cumulative number of persons trained in PEOP districts in / (a) South Punjab / (b) Phase 1 districts	88,500	95,787 persons (44% females) completed training by June 30, 2015 / On-track to deliver end programme targets

Key Points

The cumulative number of persons trained in 14 districts has exceeded 95,000 by June 30, 2015. PSDF has already completed the required procurement for training delivery to achieve the programme target of 135,000 by December 2015. Training is provided in over a hundred trades spanning several sectors. Illustrative examples include: auto and machinery mechanics, chefs, secretaries, welders, beauticians, industrial stitchers, plumbers, drivers, carpenters and farm managers.

In order to use PEOP programme savings from the TA component and interest income to launch another round of training from January to March 2016, PSDF will need at least four months to complete the required procurement processes. This would need agreement between DFID and GoPb to provide a no-cost extension to the programme and an amendment in the EOL by end of September 2015.

Good progress has been made on the gender target (40% females). Of the people who have completed training by June 2015 female trainees were 44%. However, the major proportion of this percentage is attributed to a single programme which exclusively targets rural women i.e. Skills for Market. Training provided under this scheme covers trades such as embroidery, tailoring, handicraft-making and beauticians. Under the SDP (the follow on skills programme of DFID) the focus will increase on linking rural women with markets. The programme will also increase its focus on diversifying the skill base of the relatively better educated poor women and facilitating their formal employment. Women’s inclusion will be addressed more comprehensively by the Targeting Strategy that is currently in preparation.

A disproportionate focus on the economically relatively better off segments of the poor and vulnerable has resulted due to efforts to increase the uptake of training in the past two years. The TSPs have no incentive to actively target those below the poverty line because they are reimbursed on the basis of the number of persons trained regardless of the poverty status of the trainees. At the time of enrolment, self-reported household income of trainees is recorded, but this information is never empirically verified nor is it used to determine the eligibility of the applicants.

Some trades chosen by PSDF exclude the less educated and illiterate poor by design because the curricula of the skills service providers require a minimum education requirement, usually middle school and above. Further investigation and disaggregation of the profile of existing beneficiaries by income, education, and other socio-economic characteristics using the comprehensive MIS system that is available at PSDF is needed. PSDF should develop a good understanding of the profile of its trainees in order to make the training schemes relevant for the poor and vulnerable. PSDF should segment the labour market more methodically to meet the needs of employers. Finding the correct balance will be critical to determining the operational plan of the organization.

Some progress is already being made to address these issues. PSDF has prepared ToRs to develop a targeting strategy for the scale-up of the programme and shared these with DFID for feedback. The RCT being undertaken by CERP will provide estimates about the returns to training for groups at different consumption and education levels and for males and females separately. Simultaneously, PSDF can invest more time and resources to understand the profile of existing trainees, and reorient its role to devising training products which are more suitable for the poor and extreme poor. This may require choosing a different menu of trades, designing the training products differently, and linking the training schemes to microfinance and cash transfer programmes.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review recommended that PSDF explore two areas: (1) identification of training opportunities for the less educated and illiterate poor and women along value chains, and (2) preparation of a gender mainstreaming strategy by the next annual review in 2015.

The AR team noted that some progress, albeit slow, has been made. Under the AG, eight sector studies are identified out of which three have been completed[3]. However, the extent to which these studies will identify training opportunities for the less educated and illiterate poor and women is unclear at this stage. A gender mainstreaming strategy was delayed because DFID proposed that PSDF prepare a broader targeting strategy instead. PSDF is currently preparing a terms of reference for this work.
[3] Meat and dairy processing, garment and footwear sector studies completed but reports have not been published yet. 3 workshops held for construction, garments and logistics and reports have been published..

Recommendations

- A thorough analysis of the profile of current trainees should be undertaken. For this purpose, PSDF should consider disaggregating the current trainees by income quintile, education, rural and urban location, etc. PSDF may consider the poverty scorecard data used by the Benazir Income Support Programme to profile trainees by poverty status. This analysis should inform the targeting strategy and design of training schemes. It is important that the development of a targeting strategy is prioritised and completed before the Project Completion Review due by September 2016.
- This output has a 50% impact weighting measured by a single indicator of the cumulative number of persons trained in PEOP districts. In future PSDF should consider additional indicators to monitor the effectiveness of a targeting strategy for women, the vulnerable and the extreme poor.
- The PSDF Board should provide a proactive steer to set the targeting policy and regularly monitor its implementation.

Output Title	Private training places mobilised
Output number per LF		3	Output Score	A++
Risk:		L	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Percent of private sector places created as a result of PSDF funding	70% of total PSDF funded training places	84% of total PSDF funded training places

Key Points

This year, 84% of the training places were provided by the private sector, an increase from 70% from last year. Based on historic data, there has been an encouraging trend in the percentage of private sector places created due to PSDF funding. The progress has exceeded expectations substantially (>10%) and has been awarded an A++ rating.

PSDF has been successful in mobilising privately owned TSPs to enhance their capacity (by working with PSDF and following its rigorous monitoring regime) encourage them to apply for a wide range of PSDF training schemes. PSDF relaxed its condition of audited statements (for three years) but the condition of having a National Tax Number (NTN ) remains. In addition PSDF also arranged information workshops to increase TSPs’ understanding of PSDF requirements and the application process. PSDF has also capped the training contract award limit to cover a maximum 10% of trainees by a single TSP in a training scheme. This has created room for new TSPs to come on board.

TSPs confirmed that their experience with PSDF has been positive. The application process, management of contracts, proposal development, documentation, and the compliance with contract stipulations has improved. For example, Hashoo Foundation confirmed that it has expanded its facility in Rawalpindi by additional 180 slots to allow for more trainees.

The private sector and TSPs are keen to work in collaboration with PSDF towards employment outcomes. They stressed that PSDF should strengthen its job placement cell and take a more structured approach towards job facilitation of trainees. PSDF’s approach of encouraging employers to serve as training providers is a positive development.

The President of Women Chambers of Commerce (WCCI) confirmed that WCCI is open to collaborating with PSDF for training schemes for women and can develop PSDF’s linkages with additional TSPs. This may allow PSDF to have a wider pool of TSPs to choose from and offer more specialised training including for women and girls.

Recommendations

PSDF should plan a structured engagement with the leading Chambers of Commerce and industry associations in the province to create awareness about PSDF’s activities and involve the private sector in training design and delivery.

PSDF should take a more structured approach to employment facilitation as it can help PSDF in terms of longer term sustainability. PSDF neither has a coherent strategy nor the staffing capacity to carry out employment facilitation for graduates. PSDF will need to restructure and strengthen its job placement cell and develop a strategy and test different models to maximise employment outcomes.

The review team has expressed concerns about the weight of this output. 10% seems to be on the high side considering there is only one indicator. The PEOP team should consider adding more indicators under this output. Alternatively, the team can consider decreasing the weight to an appropriate level (e.g. 5%).

Output Title	Support to the GoPb for skills policy and regulatory reform
Output number per LF		4	Output Score	B
Risk:		H	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1. Percentage of skill policy committees (govt. formulated) on which PSDF is represented	PSDF represented on 75% of the committees	PSDF is represented on all five committees for skills development in Punjab including Tribal Area Development Authority of Punjab, Punjab Women Empowerment Initiative, Export of Manpower to GCC Countries, Committee for Skills Development in Baluchistan, and Steering Committee on Skills Development. / Skills related submissions by PSDF include: World Bank Skills Development Program, Tribal Area Development Authority
4.2. No. of skills related briefings/advisory notes made to the Government of Punjab and other stakeholders per annum	4	PSDF contributed to the Punjab Skills Development Sector Plan 2018 and skills chapter in the Punjab Growth Strategy 2018 as well as to the designs of the World Bank’s skills development programme and DFID’s new programme on skills
4.3. No. of skills related sector studies and workshops conducted by PSDF (Cumulative)	Workshops=9 / Sector studies= 8	Three workshops and three sector studies have been held.

Key Points

PSDF’s success and the political attention that it has earned, is influencing the skills architecture in Punjab. The Skills chapter in the recently approved Growth Strategy in Punjab draws heavily on the research, RCT based experiments conducted for PSDF and the operational experience of PSDF. Skills has become integrated with the broader economic growth agenda in the province. This will provide the opportunity to highlight skills sector issues and address them within the growth context and have the buy-in of senior decision-makers.

Despite the strong influence on skills policy and regulatory issues, PSDF has underperformed in completing the target number of sector studies and workshops as per the log frame. The target may have been ambitious, given the capacity of the TA management team at PSDF. It is also unclear how the research requirements of PSDF are integrated into operational planning. PSDF should consider creating an in-house integrated research function responsible for identification of research requirements, commissioning, disseminating, utilising the findings and serving as the knowledge management hub for the Fund.

Going forward, under SDP, DFID will be working on skills policy and regulatory issues in close coordination with the World Bank and GiZ. This will contribute to a unified donor approach to skills development and reduce duplication.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Annual Review 2014 recommended closer coordination with the Industries Department and mobilising adequate donors and stakeholder support to set up a skills sector facilitation and coordination function within the Industries Department. This recommendation was based on a study commissioned by DFID to determine how sector coordination could be improved. A Programme Implementation Unit (PIU) has been established at the Industries Department by the World Bank to implement its $50 million skills project. The PIU provides an effective platform for facilitating coordination of the skills sector and donors working in Punjab. DFID should consider supporting additional positions in the PIU to support the broader skills sector coordination functions.

The Annual Review 2014 recommended strengthening the skills policy and regulatory environment in Punjab and providing TA support to the GoPb as required. PSDF has contributed significantly to the policy and regulatory dialogues in the province. Additionally, building on the work done to date and the political buy-in for reforms, dedicated TA allocations have been made under SDP to support future skills policy and regulatory reforms.

The Annual Review 2014 also recommended that the labour market intelligence is collected by PSDF and disseminated on its website and shared with other relevant government departments with labour and skills related mandates. PSDF places all its research on its website and currently provides free access. TA components under the SDP will need to determine how research generated by PSDF can contribute to the national level labour market initiatives.

Recommendations

The PSDF Board should consider how lessons from PSDF can be used strategically to help reform the policy and regulatory environment in the skills sector and improve skills sector related public sector organisational performance.

While the need for sector studies is determined through the assessment of economic activity in key sectors, PSDF should develop a structured process for defining the research needs of the organisation. This should connect with the annual planning cycle and processes including policy, planning and design of training schemes.

Output Title	Generation of evidence to inform skill delivery
Output number per LF		5	Output Score	B
Risk:		M	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1. No. of survey and experiments related reports shared by CERP	SFM-B Uptake Report (Sept 2014) / Note on Job Placement Design, Calibration of SFJ (Oct 2014) / Impact Evaluation Report of SFM (Dec 2015) / Impact Evaluation Report of SFJ (Dec 2015)	SFM-B report submitted to DFID on Feb 6th 2015 against the deadline of September 2014 in Log frame and January 2015 in AG agreement. / Note on Job Placement Design and calibration of Skills for Jobs was submitted in May 2015 against the deadline of October 2014 in Log frame and March 2015 in AG agreement. / Impact Evaluation Report of Skills for Market is expected to be submitted in March 2016 against the deadline of December 2015 in the Log frame and August 2016 in the AG agreement. / Impact Evaluation Report of Skills for Jobs is expected to be submitted in February 2017 against the deadline of December 2015 in the Log frame and March 2017 in the AG agreement.
5.2. No. of presentations made to BOD drawing on CERP results	Uptake results of SFM / Job placement design calibration of SFJ / Design calibration of Big Push on Skills for Villages Scheme / Evaluation of SFM / Evaluation of SFJ)	Presented to PSDF BoD in February 2015 / Presented to PSDF BoD in February 2015 / Design of BPRE presented to BoD in February 2015 / To be presented in March 2016 / To be presented in March 2017

Key Points

The engagement of CERP is currently at two levels: one, for conducting RCT based experiments that will help inform different aspects of skill provision and employment facilitation and two, for evaluating PEOP.

The second Accountable Grant (AG) between DFID and CERP was signed in December 2014 and subsequently new timelines for deliverables under output 5 were negotiated. The new timelines however, were not reflected in the log frame. This AR evaluates the output against the new timelines as agreed under the new AG. Two RCT experiment reports were submitted with a delay. The evaluation reports will now be submitted in March 2016 (for the Skills for Jobs scheme- SFM) and February 2017 (for the Skills for Jobs scheme - SFJ) respectively.

The current AG contract was due to close in June 2015 but was extended until December 2015, to cover the immediate ongoing activities. CERP is preparing to submit to DFID a proposal covering the remaining activities of the ongoing evaluations and three RCT experiments that are in various stages of design and implementation. These experiments are: (i) Skills for Markets – Market Linkages, (ii) Skills for Jobs – Job Placement; and (iii) the ‘Big Push’. The latter is an agriculture based initiative at the village level.

The review team agreed that DFID should continue fund CERP until the evaluation results of Skills for Markets are available in March 2016 as these will provide valuable inputs and data for the PEOP PCR. From March 2016 onwards, SDP will continue to fund CERP activities to conclude the evaluation of Skills for Jobs and the ongoing RCT experiments by March 2017.

The planning and management of this output will be improved based on the lessons learnt thus far. . Fragmented extensions of the AG, due to the evolving nature of the RCT experiments have led to heavy transaction costs and planning ahead was challenging for partners Going forward, DFID will ensure improved recourse to evaluation advisory expertise for managing this stream of work better..

The skills related RCT based experiments will yield valuable information for: i) how formal mechanisms for effective employment facilitation may be created, ii) how women’s linkages with markets may be improved and iii) how agricultural related knowledge and information for improving farm yields may be transferred to small farmers for improving their incomes. Going forward, this lesson has major implications for the design of the skills interventions and how employment/income earning opportunities for the poor, (particularly women, farmers and those who are already employed) may be improved.

CERP is evaluating the returns to providing skills for women following a RCT based experiment for Skills for Markets – Market Linkages. Interim results will be available by March, 2016, and additional activities/tracers will be needed to determine sustainability (these will be part of the larger proposal of CERP due by November 2015). CERP is also assisting in designing the questionnaire and the sampling strategy for the ‘before and after training’ tracker survey of male graduates.

Recommendations

DFID and CERP should re-validate and agree on realistic timelines for the outputs to be delivered under the new CERP proposal that will see the ongoing experiments to their conclusion in early 2017. The schedule should be closely monitored. DFID and CERP should also agree on an information dissemination plan to share the CERP evaluation reports and learning more widely so that they can influence the practice and policy governing skills provision.

DFID and CERP should agree a process to ensure that the quality of CERP outputs conforms to DFID’s evaluation standards and internal quality assurance mechanisms.

The PEOP log frame should be amended to capture the difference in the evaluation methodology for men and women and areas where gender disaggregated data will be available.

Going forward, especially under the new SDP, DFID and partners need to very clear about their objectives and expectations of the evaluation work and how they would like to take it forward.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost driver under the programme is the training expense. The cost of training (including allowances for lodging and a monthly stipend) accounted for 81% of all expenditure during the review period. A break-down of costs under the programme during the review period is given below:

PEOP Cost Drivers 2014-15
Skills Training Through PSDF	81.3%
Accountable Grant CERP(Evaluation)	11.3%
Accountable Grant PSDF (Institutional Strengthening)	4.0%
EGO WB	3.2%
PSDF Technical Assistance	0.2%

By end of July 2015, 99,675 trainees will have been trained under seven schemes and another 28,287 trainees are currently enrolled at an average cost per trainee of £315[4].
[4] The cost per trainee varies significantly by scheme, ranging from a low of £155 for MVM to a high of £431 for SFJ6.

Economy

PSDF operates primarily as a contracting agency, and the emphasis on the contracting process is reflected in an analysis of its costs. Combined raining, advertisement, and monitoring costs make up 97 percent of total costs. The organisation maintains a very lean structure, and management and operational costs combined are only 3% of total costs, comparing favourably to other DFID funded skills programme such as the Employment Fund for Nepal (5%).

Efficiency

PSDF employs a two-stage competitive bidding process to determine the training fee for all schemes. The trainee support (stipend, allowances) is determined on a scheme-by-scheme basis. The average stipend offered by PSDF is one third of stipends offered by similar schemes within Pakistan, such as the Waseela-e-Rozgar scheme previously offered by BISP.

Training costs vary greatly depending on the location, duration, and trades and skills being taught. As such, a comparison of per trainee costs incurred by PSDF for all schemes for different years is not possible. However, an analysis of average cost per trainee within schemes reveals a decline over time. Average costs per trainee per month under the Skills for Jobs Schemes have fallen by 15% from £72.8 in 2012-13 to £62 during the current year, equivalent to the cost of training an additional 1200 trainees. The reduction in costs points to rising competition in the private sector skills market. Average training costs for PSDF, although considerably lower, cannot be compared to average training costs incurred by public sector training institutes such as TEVTA owing to the nature and duration of courses offered, and the extensive capital and fixed costs of these wholly public sector organisations.

Furthermore, the extensive (albeit primarily quantitative) monitoring system established by the third-party monitors has witnessed significant economies of scale, as monitoring costs have been reduced from Rs. 1200 per trainee per month to Rs. 958; a 20% decrease over two years. An IT-based solution for the programme’s substantial monitoring needs is being developed, and is expected to yield further considerable cost savings.

Effectiveness

A tracer study conducted in 2014[5] indicates that 67%[6] of PSDF graduates are employed within 16 months of graduation. 96% of the graduates were unemployed prior to training[7]. Assuming successful graduates earn a minimum wage, it will take just under four months of employment to recoup training costs. Results also indicate that average income of those graduates employed before training has increased by 12%. However, these results are not wholly attributable to DFID. Evaluation of recently completed and on-going schemes is currently being undertaken, with results expected in 2016.
[5] PSDF Tracer Report – Skills for Jobs, 2014 by Rcon.
[6] Employment rate rises from 60% to 67% after 6 months, if graduates who are involved in unpaid family business are also included.
[7] Only 16% of the students were employed for a month before training.

VfM performance compared to the original VfM proposition in the business case

The training costs estimated in the original business case were undervalued, and have been revised upwards since. The base case assumed that it is the public sector that will apply for PSDF funding and that the private sector response will be limited, at least in the initial few years. Since public sector training is heavily subsidized, the projected per trainee costs were low. Secondly, the comparator training programmes that were reviewed were much smaller as compared to PSDF. They offered training in limited trades and sectors and hence had lower training costs. Contrary to expectation the private sector response to PSDF has been high. PSDF has a large training target spanning over a hundred trades, including some expensive ones, involving heavy machinery. Hence, the e cost structure and cost drivers of the programme have changed.

Assessment of whether the programme continues to represent value for money

Yes, the programme continues to offer value for money. PSDF has successfully trained over 95,000 trainees by June 2015 at almost half the cost of major public sector entities. There are signs of market development, that has had monetary benefits from lower costs per trainee per month over time, and unquantifiable but significant benefits from strengthening of systems, financial and operational procedures, and overall capacity development of TSPs. PSDF continues to exhibit economy and efficiency in the implementation and management of its contracting responsibilities. Based on initial tracer study results, approximately[8] 55,905 trainees (or 64 %) recover training costs within twenty months of training completion.
[8] Assuming that employment yields minimum wage, and is sustained for four months.

Targeting and Relative Benefits:

PSDF does not have an active targeting strategy in place. From a VfM perspective, skills training schemes should be targeted where the potential outcome and impact level benefits are highest. A targeting strategy should be developed and implemented, taking into consideration the potential trainee needs including women, the employment market, the location and the sector/skill best suited for that area.

Placement, Employment, and Sustainability:

PSDF can do more to incorporate prospective employers in the design and implementation of schemes. Research conducted by CERP has found that weak placement services are a major reason behind low uptake of schemes, particularly among the in-service potential trainees. The placement department within PSDF is currently weak with only two members of staff. Stronger placement services will ensure greater interest from trainees, and have the potential to increase employment benefits. Placement should also be seen as a viable instrument for financial sustainability of PSDF. PSDF is ideally placed in the skills market to offer paid-for services to employers and to trainees with the ability to pay. PSDF should plan to be sustainable without donor and government funding.

VfM Considerations during Contracting:

PSDF has enjoyed a degree of success in generating competition amongst private sector training providers. The degree of competition varies by scheme, for example, there were 195 bidders for Skills for Employability 2015, compared to only 46 for Skills for Biogas. However, PSDF does not currently alter its contracting practices according to the degree of competition in the market. In response to niches where the private sector market has developed, PSDF should employ varying contracting and commercial strategies that harness this competition and serve to further drive down the cost of training. For example, the cap on students per training provider could be raised to create more competition among TSPs and further bring down the training cost and improve service delivery.

Better Use of Research and Evaluation:

The two separate components for research and evaluation through the AGsto CERP and PSDF could be utilised more effectively. CERP’s work on identifying constraints faced by women has contributed to the design of the Skills for Market Schemes that has significantly improved uptake as a result. Going forward, similar and timely incorporation of research findings in the design of other schemes can yield higher results. Efforts must also be made to translate sometimes technically complex and analytical findings of CERP into simpler and more actionable recommendations.

VfM Considerations in Expansion:

Future expansion decisions should include cost considerations, and the potential benefit of further economies of scale by first moving into areas and districts that can be covered under the existing infrastructure.

Quality of financial management:

The quality of financial management is maintained on the basis of compliance to the reporting formats agreed with DFID. Four different reports are submitted to DFID by implementing partners including from the Punjab Planning and Development Department (P&D), PSDF, the PSDF-AG team, and CERP. These reports provide progress on activities being funded and predict results to be achieved under PEOP.

Planning and Development (P&D) Department (Financial Aid for Skills component)

The skills training component is funded through financial aid managed by the P&D Department, GoPb. Regular monthly financial reports are submitted to DFID; the quality of these reports is satisfactory and provides a true reflection of the financial status. As of June 2015, The P&D department has consistently matched DFID’s contribution in equivalent Pakistani Rupees.   £17.740 million of funds disbursed by DFID to GoPb have been disbursed by GoPb to PSDF.

PSDF (for Skills training and Institutional Capacity Building AG)

Regular monthly progress reports including financial status are submitted to the Board and DFID at the same time.

As of June 2015, 85% of the released funds have been spent. Currently, per month spend of PSDF is approximately £1.8 million. PSDF’s forecasting has improved significantly since last year. Budgets are prepared annually. They are-based on the enrolment and graduate forcasts along with the actual contract rates agreed with the TSPs. This has not only ensured realistic and accurate forecasting and management of the variance between budget and spend but has allowed the PSDF Board and management to use available/ surplus funds for training more people in future.

PSDF’s AG needs to be more proficient in procuring and quality assuring the outputs to ensure better value for money. The 96% funds utilization in the last quarter is a spurt rather than a regular pattern. Due to the current weak capacity of the AG management team, PSDF is not able to get the outputs in time to inform its operations.

CERP

CERP is technically a strong organisation with expertise in conducting complex research. However, their financial management capacity is weak, especially in financial planning.  Under the existing grant, CERP’s commercial audit report will be made available in October 2015. CERP has shown some improvement in managing/ tracking DFID project accounts separately under the existing AG. This development is result of recommendations from the Annual Statement of Progress 2013. The due diligence assessment of CERP is underway which will provide a fresh stocktake on the quality of its financial management. The report is due in October 2015.

Audits and accounts

PSDF undergoes two audits a year. The opinion of auditors is established by both a commercial audit and the Attorney General’s audit. FY 2013-14 audit reports have been satisfactory and covered significant aspects of financial controls and compliance with rules and effective utilisation of public resources.  The external audit report of PSDF for the year ended June 2014 by KPMG has no outstanding observations.

Recommendation

PSDF should consider VFM when designing strategies to expand its reach to all of Punjab’s 36 districts.

PSDF should design and pilot options for payment by results approaches to deliver training. This should be aligning with PSDF’s sustainability strategy.

PSDF can strengthen its financial management in view of plans to scale up to all 36 districts of Punjab.

PSDF should shift from cash payments of stipends to students via training service providers to e-payment solutions to reduce the transaction costs for its staff, monitors and TSPs and manage risks effectively (see Measures Against Fraud and Corruption below).

The TA team needs to enhance its pace to deliver sector studies against the agreed timelines. These slippages have resulted in gaps in financial forecasts and spending.

Date of last narrative financial report	May 15
Date of last audited annual statement	2013 – 14

E: RISK (½ page)

Overall risk rating: Low/Medium/High

 Low

Overview of programme risk

The overall programme risk has been downgraded from medium to low. This is primarily because the PEOP programme is due to close soon. The key risk therefore is a delivery risk i.e. that the remaining programme outputs, in particular the numbers of men and women to be trained (expected to be revised upwards) and the evaluation outputs required for the Project Completion Review, are not delivered by the close of the programme. This risk will be mitigated by the proposed six month no-cost extension and close monitoring of progress against end-programme targets by the PEOP team.

Given that DFID will continue to fund PSDF through the new SDP programme, lessons and recommendations from this PEOP AR will be used to identify and manage risks in SDP.

Measures against Fraud or Corruption:

A potential fiduciary risk exists on the payment of stipends in cash to the beneficiaries. In order to mitigate this risk, alternate methods of payments need to be explored including branchless banking and other conventional banking methods. Third party monitoring checks need to continue regularly to ensure there is transparency in the payments.

Outstanding actions from risk assessment

The risk matrix was developed after consolidating actions from Due Diligence, Annual Statement of Progress, Fiduciary Risk Assessment and the Annual Review. The actions to be taken were plotted on the Risk Matrix. Actions against these have been followed up on a quarterly basis. Most of the issues and risks have been addressed... The outstanding key actions against the remaining risks include:

Risk	Mitigation
Employed trainees trapped in low paying/casual jobs/informal markets	Employer involvement being explored. Job placement cell established. Experiments to register employers and provide on the job training are being conducted by PSDF.
PSDF’s sustainability beyond DFID’s support	Sustainability plan being prepared to explore viable business models.
Gender exclusion in industrial sectors of growth	Gender strategy as part of the targeting strategy is being prepared by PSDF
Political constraints increases as the programme expands (CM’s directive to train 2 million people could compromise quality of trainings)	PSDF transparent management, monitoring and reporting to ensure quality and compliance

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

PSDF is on a positive trajectory in delivering against timelines. It has exceeded the agreed target of 88,500 trainees (40% women) by June 2015. PSDF has established strong systems for timely delivery and achieving results. Improving the quality of targets and outputs is the next challenge for PSDF.

PSDF is currently experimenting with cost sharing mechanisms with the private sector to support its emerging sustainability strategy. Skills for Garments includes on the job training to more closely link PSDF with the private sector, however this does not currently include an investment by the private sector.

Performance of partnership(s)

Currently there is a range of partnerships between PSDF and a number of organisations in areas such as evaluation, certification/assessment and enabling graduates access microfinance services. In preparation of the SDP, a partnership strategy could be developed so that there is a systematic method for the Board to identify appropriate potential partners and their contribution to achieving specific outcomes. The quality of those partnerships can then be reviewed in a systematic way.

The collaboration between DFID and PSDF has been positive to date and DFID has been able to engage effectively with both the PSDF Board of Directors and management when required. DFID is keen to partner further e.g. by attendance at Board meetings and by assisting in the roll out of the new SDP. The dashboard that was referred to in the previous annual review should be tested to ensure that it’s being used. The frequency of the reporting has improved although there is room for improvement on the quality of analysis in the report.

Asset monitoring and control

The Assets Register is checked by the Attorney General Punjab, the independent auditors of PSDF and DFID. The 2013/2014 Audit Report confirmed that all assets were recorded satisfactorily with no irregularities in purchase and maintenance. The cost of fixed assets in the audited financial statement is PKR 34,853,050 for the year ended 2013-14.

Two minor recommendations were cited in the AG Audit Report 2013/2014.
1. Supervisory controls of the PSDF management in asset keeping and declaration of assets as unserviceable must be scrutinised.
2. Purchase of items (especially laptops) must be accompanied with a strong justification for requirements.

An asset verification spot check was conducted by DFID during the Annual Review. The asset inventory was up to date and 94% of the items were functional (6% of dysfunctional items included furniture items, a generator and other electrical and computer equipment). 86% of the assets of the livestock and dairy component transferred to PSDF are in use.

Recommendations:

In preparation of the SDP, PSDF should conduct a lean commercial and procurement analysis to develop a commercial strategy and ensure that the Public Procurement Regulatory Authority (PPRA) rules are applied in the most appropriate manner in accordance with the organisational risk appetite. Evaluation criteria and the balance between technical and commercial priorities should be reviewed on a case by case basis. PSDF can further develop an early market engagement plan that builds the capability of the market to respond to tenders. Different terms of contracts can be applied where markets are more competitive. Longer term contracts (with appropriate break clauses) can be used where required. This recommendation should be taken forward to the new SDP.

For SDP, PSDF will remain the implementation partner for training delivery. The DFID team should seek internal approval to shift PEOP assets to SDP in PDF and accordingly inform PSDF to align its asset tagging.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

As per the Exchange of Letters signed between DFID and the Government of Pakistan, both the parties agreed that funding is based on the Government of Pakistan’s commitment to poverty reduction, protection of human rights and strengthening public financial management and accountability.

We assess that steady progress is being made against the four Partnership Principles which have superseded the DPA. Entrenched poverty denies opportunities to millions of people and undermines stability and prosperity. The 2014 DFID Operational Plan refresh states that social and economic rights are on a positive trajectory with improving school enrolment rates and reducing maternal and child mortality, but inequality persists and serious concerns remain, particularly with regards to the rights of women and girls. There are currently no concerns that would change the continued provision of financial aid. If, however, there are significant changes, these would be discussed with the Economic Affairs Division at federal level.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

PSDF has a robust third party monitoring system covering its regular training schemes. Extensive contract compliance frameworks have been developed with penalties varying from nominal fines to black listing a training provider.

The current monitoring framework checks quantitative and tangible indicators such as student attendance and availability and adequacy of training materials and facilities. In case of certified training (such as those affiliated with City & Guilds, Adexcel etc.), the quality of training is partly ensured by verifying the availability of the curriculum, materials and facilities. However, the missing link is the quality of training delivery i.e. content of the curricula, teaching standards, quality/credibility of assessment etc.

There are a number of other training schemes which are managed by provincial and, in some cases, the federal government. It is important that PSDF checks its trainees’ database against other training schemes to avoid duplication and possible poaching of trainees by other training schemes offering higher stipends.

The PSDF monitoring system has checks built in which do not allow the same person to take more than one PSDF-supported training (through Computerised National Identity Card (CNIC) verification). However, there is no check to see if multiple members from the same household can enrol in PSDF training. This may create perverse incentives for trainees to get enrolled to exploit the award of the stipend as well as for TSPs to enrol more people. PSDF should determine if it wants to allow multiple members of the same household to enrol in PSDF training and if it wants to provide training at a higher level to a person already trained at another public training programme.

While PSDF’s stipend disbursement seems robust and is designed to be released in tranches after dues deductions based on TSP[9] reports, some TSPs employ exploitative and unethical practices in order to retain trainees. This includes retaining original matric degrees of trainees until after they have completed a month of On the Job (OJT) training. The trainees are supposed to find the OJT opportunities themselves which can be challenging as their degrees remain with the TSP until they finish the OJT.
[9] PVTC- this was uncovered through beneficiary feedback sought during field visits in Lahore district

Beneficiary feedback also revealed that some TSPs did not give stipends to students on a monthly basis as stipulated in their agreement with PSDF. Stipends are given after delays (of months) and payments made are sometimes partial as TSPs withhold some portion of the stipend in order to retain trainees. These practices exploit the position of trainees and can cause distress. PSDF should consider expanding its grievance redressal systems to allow trainees to lodge stipend related issues and service them in a definitive time frame. Alternatively, PSDF can also consider the BISP model of disbursing stipends through other solutions including mobile banking.

The full results of the RCT experiments will be available after PEOP’s closure. In view of this, the evaluation approach has been slightly modified, with the RCT based strand of evaluation results for women available in March 2016 and for men in March 2017. By May 2016, however, a survey of male graduates will provide interim information about male graduates’ income/employment status that will feed into the PEOP PCR. The complete RCT experiment results that will be available in March 2017 will be valuable in shaping the employment and market linkage strands of the skill schemes.

Employment outcomes related to skills training will become exceedingly important, particularly for SDP. Currently, TSPs have no incentives to monitor and track employment status of their training after the training is complete. Also as discussed earlier, PSDF’s placement cell has very limited capacity and is unable to systematically track trainees. One of the reasons provided by PSDF was cancellation of mobile numbers due to a nationwide mobile number verification drive. PSDF should consider taking a more structured and integrated approach to facilitate trainees’ employment- this will include negotiating employment-based contracts with TSPs and greater and more structured engagement with the private sector including Chambers of Commerce and industry associations.

Recommendations:

PSDF should develop suitable mechanisms to capture the qualitative dimension of training delivery.

In order to incorporate the lessons learnt from PEOP’s monitoring and evaluation and apply them to the new SDP, the TA supplier firm engaged should thoroughly consult DFID, PSDF and CERP in the SDP design phase.

Monitoring progress throughout the review period

The Annual Review Team has studied all the evidence produced by Government of Punjab, PSDF, CERP and DFID Programme team including quarterly management review reports. The team met all the stakeholders including PSDF where it met with all sections separately, followed by meetings with senior management and the Board of Directors. In the Government of Punjab the team met with the Planning & Development Department and the Finance Department.

The team also met representatives of three Chambers of Commerce in Lahore and Multan and visited ongoing training sites in these two districts. The team also met a group of beneficiaries in Muzaffargarh who completed training in 2013.

Feedback of the beneficiaries is as follows:

- The graduates are very happy with the training offered and many are keen to receive follow on training. Currently, PSDF offers only one training opportunity per person. Going forward this policy will be reviewed to enable people to further develop their skills. However, the associated risks will be managed carefully to ensure that people genuinely interested in building their skills are enrolled rather than those interested only in stipends.
- Beneficiaries were very keen to have more employment facilitation support from PSDF. All graduates do not have recourse to the more effective and prevalent informal employment facilitation channels.
- All of the graduates that the team met with were employed but not necessarily in the trades in which they had received training. This issue will be probed in future graduate trackers to assess the value of the training received in enabling people to find employment.
- Beneficiaries complained that some of the TSPs hold their qualification documents and part of their stipend in order to ensure student retention. This causes difficulties in enabling students to meet their expenses and can hinder the students in getting employed on graduation. The complaint has been conveyed to PSDF for investigation.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process