Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to Malaria Control in the Democratic Republic of Congo
Programme Value: £39.5 million (£36 million contracted)		Review Date: 07/05/2016
Programme Code: 203458	Start Date: 8/05/2013	End Date: 30/09/2019

Summary of Programme Performance

Year	Year 1 / 2013	Year 2 / 2014	Year 3 / 2015
Programme Score	A	A	B
Risk Rating	M	M	Moderate

Summary of progress and lessons learnt since last review

This programme has been established in order to support the implementation of several aspects of DRC’s National Strategic Plan for Malaria Control. The progress made by the programme and the lessons learnt since the previous annual review are best understood in relation to each of the programme’s three components, each of which corresponds to an output:

Component 1: Distribution of bednets
Following the mass distribution successfully implemented in 2014 (year 2), continuous distribution of bednets through schools and households is underway in twelve health zones, in addition to the conventional mechanism for continuous distribution of bednets through health services. This will be evaluated with a view to scaling it up if it is successful.

Results from the mass distribution post-campaign survey became available in year 3, and demonstrate substantial progress in terms of ownership and use of bednets: for example, utilisation amongst pregnant women rose from 20.7% before the campaign, to 73.4%. However, the target of 80% was not achieved for all indicators. The continuous distribution described above is intended to maintain the increase in bednet ownership and use achieved by the mass campaign, over time.

Lessons learnt:
An increase in bednet ownership achieved through a mass distribution may not translate fully into an increase in utilisation, and more than one campaign may be required in order to achieve the target level of utilisation. This emphasises the need to have a well-developed behavioural change component in bednet distribution activities.

There is an ongoing need to identify effective and cost-effective mechanisms for maintaining bednet ownership and utilisation over time, during the three-year interval between successive mass distributions. Continuous distribution of bednets through schools and households is a potential method being trialled in this programme.

Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa
This component is intended to improve the extent to which people are able to access quality-assured artemisinin-based combination therapies (ACTs) for the treatment of malaria through private sector outlets in Kinshasa province, by addressing six market constraints: the high ex-factory price of QAACTs (Quality-Assured Artemisinin-based Combination Therapy ), poor coordination in the pharmaceutical supply chain, low consumer demand for QAACTs, high taxes and tariffs, the absence of an enabling regulatory environment and the absence of quality malaria case management by private providers. This part of the programme is now underway: since the last annual review, the Ministry of Health has issued a Circular authorising the use of Rapid Diagnostic Tests (RDTs) in pharmacies, contracts have been signed with five manufacturers of quality-assured ACTs, and the drugs are now available in 684 pharmacies. However, implementation of this component of the programme is behind schedule.

Lessons learnt:
It took longer than anticipated to put contracts and agreements into place and to procure and receive the first shipment of QAACTs. This in turn led to delays in other aspects of implementation (such as training), although the programme has managed to coordinate events in order to contain these knock-on effects. Now that preparatory activities are complete and full implementation is underway, the programme has a critical year ahead to ensure that further delays are avoided and that substantial progress is made.

Several important issues are emerging which will need to be addressed over the coming year, including non-respect of negative results and clinical guidelines by service providers, insufficient awareness of and adherence to maximum prices, and the need for improved waste management for pharmacies. Considerable work remains to be done in relation to all six of the market constraints to be addressed by this programme, including the weak regulatory environment and taxes and tariffs. The programme will need to continue to work towards change in each of these areas, whilst recognising that this is likely to be a difficult and slow process.

Component 3: Increased capacity of the Programme National de Lutte Contre le Paludisme (National Malaria Control Programme) to generate and use data
The third component of the programme is intended to enable the National Malaria Control Programme to produce, access and use epidemiological and other information more effectively, in order to enhance malaria control in DRC. Over the past year, a Sentinel Sites Working Group (SSWG) has been established, with the objective to define an integrated system for malaria surveillance in DRC. Needs assessments for three initial sites have been completed. However, this component of the programme is also considerably delayed as it had been expected that all three of these sites would have been rehabilitated or built by the end of this year.

Lessons learnt:
This part of the programme is now behind schedule, and a revised workplan is needed to get this component back on track.
Acronyms

ACT	:	Artemisinin-based Combination Therapy

AL	:	Artemether-Lumefantrine

AMF	:	Against Malaria Foundation

AMF-m	:	Affordable Medicines Facility – malaria

ASAQ	:	Artesunate-Amodiaquine

ASF	:	Association de Santé Familiale (PSI’s affiliate in the DRC)

ASSP	:	Accès aux Soins de Santé Primaire (DFID funded Access to Primary Health Care)

CHAI	:	Clinton Health Access Initiative

CHW	:	Community Health Workers

DFID	:	Department for International Development

DHIS2	:	District Health Information System 2

DPM	:	Direction de Pharmacie et Médicament (Pharmacy and Medicines Directorate)

DPS	:	Division Provinciale de la Santé (Provincial Health Division)

DRC	:	Democratic Republic of the Congo

FDSS	:	Fonds de Développement des Services de Santé (Health Services Development Fund)

IMA	:	IMA World Health

ICP	:	Inter-Personal Communication

LLIN	:	Long-Lasting Insecticide-Treated Nets (generally referred to as ‘bednets’ in this document)

MSP	:	Ministère de la Santé Publique (Ministry of Public Health)

OJEU	:	The Official Journal of the European Union

PMI	:	President’s Malaria Initiative

PNLP	:	Programme National de Lutte Contre le Paludisme (National Malaria Control Programme)

PSI	:	Population Services International

RDT	:	Rapid Diagnostic Test

STPHI	:	Swiss Tropical Public Health Institute

SSWG : Sentinel Sites Working Group

QAACT	:	Quality-Assured ACT

WHO	:	World Health Organization

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/

Outline of the programme

Through this programme, the UK has so far supported the delivery of approximately 2.8 million long-lasting insecticide-treated bednets (LLINs) through a mass distribution campaign in Kasaï and Kasaï Central provinces, followed by a pilot of continuous distribution in those same provinces through schools and households. In addition, the programme supports other key objectives of DRC’s National Malaria Control Programme (Programme National de Lutte Contre le Paludisme, PNLP) in order to address some of the major constraints to improved malaria control in the country, namely: (i) limited availability of quality-assured Artemesinin-based Combination Therapies (ACTs) for the treatment of malaria, and (ii) a lack of information and capacity for effective strategic planning of the response to malaria.

The contract value for this “design and build” programme is £36 million over six years (2012/13-2018/19), out of a total programme value of £39.5 million approved in the business case. Following an initial design phase, the implementation of the programme is being carried out according to three components, which correspond with each of the areas described above. These are:

Component 1 (£15.8 million) – Distribution of bednets
The availability and use of bednets is a key component of DRC’s National malaria Control Programme. At the outset, 4.4 million bednets were purchased by this project, sufficient to cover all 44 health zones in Kasaï and Kasaï Central provinces (former Kasaï Occidental). However, it was subsequently agreed that Against Malaria Foundation (AMF) would provide sufficient bednets for nine of these health zones, to be distributed using a door-to-door approach through DFID DRC’s programme Accès aux Soins de Santé Primaires (ASSP). As a result, of the 4.4 million bednets procured, 2,813,925 were utilized for mass distribution in the remaining 35 health zones. Of the balance of 1.61 million bednets, 935,000 are being used for continuous distribution (in order to maintain the increase in coverage achieved by the mass distribution over time), and 676,000 have been transferred for use by ASSP.

Component 2 (£14.5 million) - Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa
The private sector accounts for approximately 70% of antimalarial drugs dispensed in DRC, but only 2.6% of these are quality-assured ACTs (QAACTs). This means that a large number of people are receiving inappropriate or ineffective treatment, which puts them at risk and has the potential to drive the emergence and spread of artemisinin resistance. The PNLP has identified this as a priority issue, and the programme is responding in partnership with drug manufacturers, the Global Fund and the PNLP by addressing six market constraints: the high ex-factory price of QAACTs, poor coordination in the pharmaceutical supply chain, low consumer demand for QAACTs, high taxes and tariffs, the absence of an enabling regulatory environment and the absence of quality malaria case management by private providers. In light of the innovative nature of this component, the intervention is initially being provided in Kinshasa, so that lessons learnt may in due course be applied elsewhere.

Component 3 (£4.7 million): Increased capacity of the PNLP to generate and use data
There are limited data on the epidemiology of malaria in DRC, on the availability and effectiveness of key interventions in the country, and on the best mechanisms for delivering these. This is a key constraint to the effectiveness of malaria control in DRC, and hinders the PNLP in fulfilling its strategic leadership function. The programme is responding to this by developing malaria sentinel surveillance sites in ten provinces and by strengthening the capacity of the PNLP in this regard. This is in partnership with the Global Fund and USAID, who are supporting similar interventions in the remainder of DRC’s 26 provinces.

The programme is being delivered by a consortium led by PSI-ASF (Population Services International and their local affiliate Association de Santé Familiale). Implementation of components 1 and 2 is led by PSI, whereas component 3 is sub-contracted by PSI to the Swiss Tropical Public Health Institute (STPHI). Implementation of component 1 began in December 2013, and the contract for the implementation of components 2 and 3 was signed in November 2014 following an extended design phase.

Expected results

Through this programme, the UK will:

Support the distribution of approximately 3.7 million bednets in Kasaï and Kasaï Central provinces

Help to make 13 million doses of QAACTs available to the population of Kinshasa through the private sector

Set up or rehabilitate ten sentinel surveillance sites for malaria.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

This annual review was conducted in April 2016 and covers the period from April 2015 to March 2016. It draws upon data provided by the quarterly narrative and financial reports, a presentation given by PSI on 24 March 2016 on the progress of the programme, and findings from annual malaria partners’ workshop held from 12 to 14 April 2016.

The overall progress and performance of the programme since the previous annual review has been as follows:

Component 1:

Following completion of the mass distribution in 2014, the post-campaign survey was carried out in June / July 2015, and the results of this became available in September.

In June 2015, a pilot of school and household-based continuous bednet distribution was started in twelve of the 35 health zones in which the mass distribution had been carried out, using remaining bednets and financial savings from the mass distribution campaign. The purpose of this is to maintain the level of bednet coverage and utilisation achieved by the mass distribution, over time. The pilot will be evaluated with a view to potentially scaling up this approach in the other health zones.

Component 2:

PSI has signed contracts with five manufacturers of quality-assured ACTs in order to gain access to preferential prices negotiated by the Global Fund

Initial orders of RDTs and quality-assured ACTs have been placed and received, and commodities are now in place in 684 pharmacies in Kinshasa

Capacity building of private sector providers on clinical case management of fever, ACT and RDT stock management and quality assurance is underway

Mystery client survey and supply chain assessment exercises are being carried out

The Ministry of Health has issued a Circular authorising the use of RDTs in private sector pharmacies

Mass communication in order to stimulate demand for quality assured case management of fever has commenced.

Component 3:

In-depth technical needs assessments for three selected sentinel sites have been completed, and procurement of equipment is underway

Community-level surveys have been implemented, and will enable the extent to which data generated by the sentinel sites is representative of the population as a whole

A Sentinel Site Working Group (SSWG) has been established and is operational

Technical assistance was provided to the PNLP during the annual PNLP performance review (the Revue des Performances du Programme) and the elaboration of the Malaria Strategic Plan 2016-2020. Three technical assistants are now placed with the National Malaria Control Programme (PNLP).

Despite these achievements, the implementation of components 2 and 3 is behind schedule, and this is explored further in section C.
Annual outcome assessment

The anticipated outcome of this programme consists of improved control of malaria in DRC. Progress towards this outcome is assessed according to the following three outcome-level indicators:

Indicator	Milestone / (March 2015)	Milestone / (March 2016)	Progress / (March 2016)	Comments
1 - % of individuals in households who slept under a bednet the previous night in targeted health zones in Kasaï and Kasaï Central	≥ 80%	Not applicable	66.4%	The results of the post-campaign survey carried out in June / July 2015 show substantial progress in relation to baseline (18.5%), but the milestone of ≥ 80% was not achieved
2 - % of children under 5 years who received quality-assured ACT among those receiving any antimalarials in the private sector in Kinshasa	10%	Not applicable	No data available	The survey required to measure progress against this indicator has been postponed, as the supply chain for ACTs has only recently been put into place
3 - Cumulative number of quarterly data validation sessions held by the PNLP at central level	2	6	1	During the course of the past year there has been a single national data validation meeting, but this has not been followed by routine quarterly meetings

Indicator 1: % of individuals in households who slept under a bednet the previous night in targeted health zones in Kasaï and Kasaï Central

No milestone for this outcome indicator was set for March 2016, as the mass distribution of bednets was completed in 2014. Instead, progress was due to be assessed at last year’s annual against a March 2015 milestone of ≥ 80%. However, it was not possible to do so at that time, as data from the post-campaign survey were not yet available (the post-campaign survey was scheduled to take place six months after the mass distribution had come to an end, ie in June 2016). These data are however now available, and show that 66.4% of individuals slept under a bednet the previous night in targeted health zones in Kasaï and Kasaï Central, against a baseline (determined through the pre-campaign survey) of 18.5% (additional results from the post-campaign survey demonstrate progress against output-level indicators, and are presented in section C).

This shows an important increase in the use of bednets, but nonetheless the target of ≥ 80% was not achieved. Likely explanations for this are provided by the findings of a DFID-funded survey carried out in 2015 on the determinants of bednet use and non-use among the population in DRC. The main obstacles to bednet use identified by this survey were poor knowledge of the efficacy of bednets for malaria prevention, low perception of malaria risk by parents, and poor knowledge of bednet installation and maintenance. The findings of this survey were not available when this mass distribution was being designed and implemented, but could inform future campaigns in order to maximise bednet utilisation.

Indicator 2: % of children under 5 years who received quality-assured ACT among those receiving any antimalarials in the private sector in Kinshasa

A key objective of component 2 is to increase the proportion of malaria cases that are correctly treated with a quality-assured ACT, particularly amongst young children. It was originally anticipated that a survey of private sector outlets in Kinshasa would be carried out shortly after the start of component 2, in order to collect data on the availability and use of QAACTs at that stage. On this basis, a milestone of 10% (against a baseline of 9.5%) was set for March 2015, and no milestone was set for March 2016 as it is not cost-effective to repeat the survey annually. However, it has not yet been feasible to carry out this survey, due to extensive delays in the implementation of component 2. As a result, data are still not available to determine progress against the March 2015 milestone, one year one from this date. Even now, the milestone has almost certainly not been met, as implementation of component 2 has only recently commenced. It is now expected that the survey will be carried out in February 2017 and a revised logframe with milestones that take into account the delays in implementation will come into effect immediately following this annual review.

Indicator 3: Cumulative number of quarterly data validation sessions held by the PNLP at central level

A four day workshop was held with key actors from provincial and health zone levels (malaria coordinators, data managers and Médecins Chefs de Zone) from eleven existing sentinel sites, in order to:

Validate data from 2011-2015

Evaluate the implementation of technical guidelines and recommendations for each level involved in the data production process

Check the consistency and quality of data at all levels of the reporting system

Analyse strengths, weaknesses, opportunities and threats in relation to the reporting system

Make recommendations for improving data collection and analysis.

Although this national meeting took place, it has not been followed by subsequent routine quarterly data validation meetings, and so no further progress has since been seen in relation to this outcome indicator. This is despite the fact that resources are available to enable these meetings to take place, and so is more likely due to that fact that the SSWG has only recently been established, and sufficiently strong leadership is not yet in place.

Overall output score and description

Output title	Overall output score	Impact weight
Output 1: Increase to at least 80% the use of LLINs by pregnant women and children under 5 in Kasaï and Kasaï Central by 2018.	B	50%
Output 2: Increase the availability, accessibility and affordability of QAACTs in the private sector in Kinshasa.	C	30%
Output 3: Improve the availability and use of information for malaria control in DRC through increased capacity of the malaria control interventions	C	20%

Based on these scores and weightings, the overall programme performance score at this annual review is

B: Outputs moderately did not meet expectation

Given the current impact weighting of the different outputs, the overall score is a B. However, over the 12 months of this review, the majority of programme spends and activity has been on outputs 2 and 3, both of which have not reached their milestones. In terms of overall performance, the programme team would allocate a score of C.

Component 1: Distribution of bednets

The results of the post-campaign survey (which have become available since the previous annual review) show that the increase in bednet ownership led to an increase in utilisation, but not to a sufficient extent to meet national targets. Information from the 2015 survey suggests that this is due to a combination of social factors and gaps in knowledge, which will require high-quality behavioural change interventions to address.

In order to maintain and build upon the level of bednet ownership and utilisation achieved through the mass distribution, continuous distribution and future rounds of mass distribution will be required. Maintaining adequate coverage over time will be a challenge.

Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa

There have been considerable delays to the start of implementation of component 2, primarily as a result of negotiations with suppliers of QAACTs having taken longer than expected. These negotiations are now mostly concluded, and this component is now up and running. Nonetheless, it will be difficult for the programme to recover these delays.

Although implementation of component 2 has only recently commenced, several critical issues are already emerging and need to be rapidly addressed. Most of these correspond to the six market constraints identified during the design phase and which the programme is addressing. These include non-adherence to clinical guidelines (particularly in the context of negative RDT results), exceedances of the maximum agreed prices for QAACTs and RDTs, poor waste management, and resistance from those with a commercial interest in drugs other than the quality-assured ACTs being promoted by the programme.

The context within which component 2 is being implemented remains challenging, particularly as the market for antimalarial drugs is poorly regulated, and tariffs and taxes continue to be levied. It will be difficult for the programme to effectively displace drugs that do not comply with national and international guidelines from the market, in the absence of an improved regulatory environment.

Component 3: Increased capacity of the PNLP to generate and use data

The rehabilitation of sentinel sites has also met considerable delays, in part due to the abrupt resignation of the contractor recruited by STPHI for this work. It will be a challenge for the programme to recover this delay, the no extension’s option could be explored after the discussion with PSI and STPHI.

Key lessons

Component 1: Distribution of bednets

An increase in bednet ownership achieved through a mass distribution may not translate fully into an increase in utilisation, and more than one campaign may be required in order to achieve the target level of utilisation. This emphasises the need to have a well-developed behavioural change component in bednet distribution activities. Future programmes should draw upon and generate evidence to identify the most effective means available of achieving behavioural change, in order to optimise the effective utilisation of bednets that are distributed.

There is an ongoing need to identify effective and cost-effective mechanisms for maintaining bednet ownership and utilisation over time, during the three-year interval between successive mass distributions. Continuous distribution of bednets through schools and households is a potential method being trialled in this programme.

Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa

It took longer than anticipated to put contracts and agreements into place and to procure and receive the first shipment of QAACTs. This in turn led to delays in other aspects of implementation (such as training), although the programme has managed to coordinate events in order to contain these knock-on effects. Now that preparatory activities are complete and full implementation is underway, the programme has a critical year ahead to ensure that further delays are avoided and that substantial progress is made.

Several important issues are emerging which will need to be addressed over the coming year, including non-respect of negative results and clinical guidelines by service providers, insufficient awareness of and adherence to maximum prices, and the need for improved waste management for pharmacies. Considerable work remains to be done in relation to all six of the market constraints to be addressed by this programme, including the weak regulatory environment and taxes and tariffs. The programme will need to continue to work towards change in each of these areas, whilst recognising that this is likely to be a difficult and slow process.

Component 3: Increased capacity of the PNLP to generate and use data

This part of the programme is now behind schedule, and a revised workplan is needed to get this component back on track.

Key actions/ recommendations

Component 1: Distribution of bednets

By July 2016, PSI should design the evaluation of pilot continuous distribution of bed nets through school and households in order to enable the following to be determined: (i) the degree to which any observed effect is attributable to the intervention, and (ii) the cost and cost effectiveness of the intervention, relative to other available mechanisms for maintaining bednet coverage over time. This evaluation is required to inform any future decision on the scale-up of continuous distribution of bednets through schools and households.

Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa

In view of the fact that the implementation of this component is behind schedule, PSI should prepare and present a revised workplan by the end of May 2016. As the first of the two years in which QAACTs were to have been subsidised to a high level has now been lost, PSI should identify options for adjusting the progressive decrease in subsidy. This should be presented to DFID for consideration before the end of June 2016.

The programme needs to continue to work to address all six of the market constraints: some progress can be seen in relation to each of these, but there is a great deal more to be done. DFID and PSI should commission political economy analysis to inform the approach to improving the regulatory environment and advocating for changes in taxes and tariffs by December 2016.

In partnership with the Ministry of Health, PSI should reinforce measures to ensure that healthcare workers adhere to clinical guidelines (including prescribing an antimalarial only to those patients that have a positive test result), and to monitor this. Similarly, PSI should strengthen measures to ensure that recommended pricing for malaria testing and treatment is understood by consumers and adhered to by service providers during the implementation of the programme. PSI should produce a plan for improved waste management relating to the use of RDTs by the end of May 2016.

Pre- and post-training assessments should be carried out to measure and document the effect of training on service providers’ knowledge, and to inform improvements to the content and delivery of training where necessary. PSI should discuss with the PNLP the possibility of issuing a certificate to those who successfully complete training.

Component 3: Increased capacity of the PNLP to generate and use data

By the end of May 2016, STPHI and PSI should revise their workplan to ensure that implementation of this component is back on track to achieve six rehabilitated or newly constructed sentinel sites by the end of year 4.

Additional recommendations relating to Risk and to Monitoring and Evaluation

By July 2016, PSI should develop a comprehensive, up to date fiduciary risk management plan, with a particular emphasis on component 2 of the programme.

In light of the additional risk in several programme areas, PSI and DFID should review the overall risk assessment for the programme and update the risk matrix each quarter.

By the end of July 2016, PSI/STPHI and DFID should develop and agree an updated evaluation plan for component 2, with the involvement of Ministry of Health and the PNLP.

Each quarter, STPHI should identify and document instances in which decision-making for malaria control has been supported by data and information that have been generated as a result of the intervention.

Has the logframe been updated since the last review? NO

The existing logframe has been used for this annual review. However, a comprehensive review of the logframe has been carried out, and the resulting revised logframe will come into effect immediately after this annual review (and will therefore be used to assess progress at next year’s annual review).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increase to at least 80% the use of LLINs by pregnant women and children under 5 in Kasaï and Kasaï Central by 2018
Output number per LF		1	Output Score	B
Risk:		Minor	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / (March 16)	Progress	Comments
Number of LLINs distributed during the mass LLIN distribution campaign in targeted health zones in Kasaï and Kasaï Central	Not applicable. The mass distribution of bednets was completed in 2014.	Not applicable. The mass distribution of bednets was completed in 2014.	An assessment of subsequent progress may be made in relation to the pilot of continuous distribution (see text below)
% children under 5 years old who slept under an LLIN the previous night in targeted health zones in Kasaï and Kasaï Central	Not applicable. The mass distribution of bednets was completed in 2014.	Not applicable. The mass distribution of bednets was completed in 2014.	Data were not available at the time of last year’s annual review to assess progress against these indicators. These data are now available and progress in relation to the March 2015 milestones is assessed below.
% pregnant women in Kasaï and Kasaï Central who slept under an LLIN the previous night in targeted health zones in Kasaï and Kasaï Central
% households with at least one LLIN in targeted health zones in Kasaï and Kasaï Central
Number of radio and TV spots broadcasted in Kasaï and Kasaï Central on LLIN	Not applicable. The mass distribution of bednets was completed in 2014.	Not applicable. The mass distribution of bednets was completed in 2014.	-

Key Points

No milestones were set for this output for 2015/16, as it was anticipated that the mass distribution of bednets would be completed in 2014, as has been the case. Nonetheless, it is possible to make some assessment of progress against this output. At the time of last year’s annual review, data from the post-campaign survey were not yet available to assess progress against the March 2015 indicators, because according to national policy a post-campaign survey should be carried out no sooner than six months after the campaign. These data are now available, and so achievement against these milestones can now be determined, as follows:

Indicator	Milestone / (March 2015)	Achievement / (post-campaign survey)	Comments
% children under 5 years old who slept under an LLIN the previous night in targeted health zones in Kasaï and Kasaï Central	≥ 80%	71.1%	The programme achieved a significant increase in bednet utilisation amongst children under five (from a baseline of 24.3%), but moderately failed to meet the expectation of ≥ 80%
% pregnant women in Kasaï and Kasaï Central who slept under an LLIN the previous night in targeted health zones in Kasaï and Kasaï Central	≥ 80%	73.4%	The programme achieved a significant increase in bednet utilisation amongst pregnant women (from a baseline of 20.7%), but moderately failed to meet the expectation of ≥80%
% households with at least one LLIN in targeted health zones in Kasaï and Kasaï Central	≥ 80%	90.5%	The programme achieved a significant increase in bednet ownership (from a baseline of 18.5%), and achieved the expectation of ≥80%

The post-campaign survey has demonstrated substantial progress in term of ownership and use of bednets amongst key target groups, namely pregnant women and children under five. However, the increase in bednet utilisation has not been sufficient to meet the target of ≥ 80% amongst these target groups, despite the ownership of bednets having exceeded the target level.

The disparity between bednet ownership and utilisation suggests that whilst the mass campaign succeeded in reaching a large number of individuals and households through the distribution, it was not as successful in terms of behaviour change, with the result that the increase in ownership did not fully translate into an increase in utilisation. This is not to say that the programme was a failure in this regard, as a considerable increase in utilisation was nonetheless achieved. However, it does highlight the importance of having a robust behavioural change component in order to fully bring about the desired public health impact of a mass distribution campaign. Operational research carried out in the context of a separate bednet distribution in the former province of Equateur (also funded by DFID) provides further insight to this: a survey carried out following behavioural change activities found that 25% of respondents continued to have a low perception of malaria risk, and poor knowledge of the efficacy of bednets for malaria prevention and of their installation and maintenance[1].
[1] PSI / ASF (2015): Étude sur les Déterminants de la Non-utilisation des Moustiquaires en République Démocratique du Congo (unpublished report).

In addition to achieving a high level of bednet utilisation, a further challenge is to maintain that level over time, until the next mass distribution is carried out three years later according to the national schedule. In order to maintain the level of coverage achieved by the mass distribution, in the past year this programme has started a pilot of continuous distribution through schools and households in twelve health zones alongside the standard mechanism for continuous distribution (through antenatal care and immunisation) that is currently supported by other partners such as PMI and the Global Fund, as well as by DFID through our health programme ASSP. This is in response to WHO’s recommendation to national malaria control programmes, that they identify mechanisms to maintain universal coverage through continuous distribution, using mechanisms additional to the traditional channels of antenatal care and immunisation.

The pilot commenced shortly after the previous annual review, using savings achieved from the mass distribution. Given the fact that this approach is new in DRC, it was decided to start with a pilot in 12 health zones out of 44 in Kasaï and Kasaï Occidental. The following activities have so far been carried out:

Design of new indicators relative to the continuous distribution that could be integrated in the updated logframe (which will come into force immediately following this annual review).

Identification of criteria to be applied to select beneficiaries in schools and the community.

Identification of interpersonal communication (as opposed to mass communication) as the most appropriate means of communicating with the population in order to support uptake and utilisation of bednets.

Training of teachers and community health workers (to date, 1258 teachers and community health workers have been trained, against an expectation of 620).

Household visits by community health care worker have commenced (to date, 230,552 household have taken place, against a planned 261,000 by now).

Since the pilot of continuous distribution began in July 2015, 28,301 bednets have been distributed through 100 schools, against an anticipated 35,000 bednets in this period. As a result, delivery of this intervention has fallen moderately below expectation. This is due to delays in the mobilisation of local non-government organisations to co-implement the intervention with PSI, and to jointly supervise school and community health workers. Immediately following this annual review, progress will be monitored through a revised logframe which includes annual milestones for continuous bednet distribution. An evaluation of the pilot activities in the 12 HZs is planned for in July 2016 in order to determine whether to scale up the intervention, through this programme or through others.

Lessons learnt

As is often the case in other settings and programmes, an increase in bednet ownership achieved through a mass distribution such as this one may not translate fully into an increase in utilisation, and more than one campaign may be required in order to achieve the target level of utilisation. This emphasises the need to have a well-developed behavioural change component in bednet distribution activities. Future programmes should draw upon and generate evidence to identify the most effective means available of achieving behavioural change, in order to optimise the effective utilisation of bednets that are distributed.
A further key challenge is to identify effective and cost-effective mechanisms for maintaining bednet ownership and utilisation over time, during the three-year interval between successive mass distributions. Continuous distribution of bednets through schools and households is a potential method (alongside the continuous distribution through antenatal care and immunisation), and the evaluation of the pilot will be important to inform a decision on the potential scale-up of this approach through this programme or others.

Recommendations

By July 2016, PSI should design the evaluation of pilot continuous distribution of bed nets through school and households in order to enable the following to be determined: (i) the degree to which any observed effect is attributable to the intervention, and (ii) the cost and cost effectiveness of the intervention, relative to other available mechanisms for maintaining bednet coverage over time. This evaluation is required to inform any future decision on the scale-up of continuous distribution of bednets through schools and households.

Output Title	Increase availability, accessibility and affordability of QAACTs in the private sector in Kinshasa
Output number per LF		2	Output Score	C
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / (March 16)	Progress	Comments
Number of treatments (doses) of QAACTs supplied through private sector importers in DRC	1,900,000	528,480	Substantially did not meet expectation
% of selected private sector outlets in project areas with Green Leaf QAACTs in stock (among outlets with any antimalarial in stock)	20%	Not known	Due to the delay in beginning the distribution of QAACTs, the survey to collect data for these indicators has been postponed until later this year. It is therefore not possible to determine progress against these indicators at this stage.
% of private sector outlets in project areas selling project supplied QAACT for children at or below the recommended retail price	50%
Number of radio and TV spots on GreenLeaf broadcasted in Kinshasa	14,850	2,233	Substantially did not meet expectation
Number of RDTs distributed to private sector outlets/clinics in Kinshasa	131,460	131,475	Met expectation

Key Points

The objective of this component is to improve the availability and accessibility of QAACTs in the private sector in Kinshasa by addressing six market constraints: the high ex-factory price of QAACTs, poor coordination in the pharmaceutical supply chain, low consumer demand for QAACTs, high taxes and tariffs, the absence of an enabling regulatory environment and the absence of quality malaria case management by private providers.

Overall progress has fallen substantially below expectation, as there have been significant delays in getting this part of the programme underway. To date, 528,480 doses of QAACTs have been supplied through private sector providers, which is well below the milestone of 1.9m doses. Full implementation of this component was expected to start in June / July 2015, but this did not occur until February 2016. The reasons for this delay are as follows:

The process of negotiating contracts between PSI and manufacturers for the supply of QAACTs took much longer than had been anticipated. This was partly due to the fact that contract negotiation was handled by PSI headquarters rather than by their local office: whilst this provided additional expertise, it also meant that lines of communication were more complex, and it made the follow-up of progress more difficult. It was not until June 2015 that the contracts began to be put into place, whereas the original expectation was that they would all be in place by July 2015. This in turn led to delays in the procurement of QAACTs and in other dependent activities such as behavioural change communication and training. As of early this year, contracts are now in place with all five participating manufacturers, and a sixth has expressed interest in joining the programme.

Discussions between PSI and the Global Fund on the content and terms of a Trade Licensing Agreement (TLA) for the use of the Green Leaf Logo to promote QAACTs in Kinshasa also took longer than expected, as did the integration of the terms of this TLA into PSI’s contracts with manufacturers. The reasons for this delay were similar to those for the delays in signature of contracts with manufacturers.

Following signature of contracts, two orders of QAACTs were made in quarters 3 and 4 of this financial year. However, before these could be delivered, product testing needed to be carried out at an accredited laboratory in Vietnam, in order to ensure that the product was of sufficient quality to bear the Green Leaf logo. This took thirty days to do, and the additional time that this added to the total shipment time had not been anticipated in the planning process. In order to recover this time, DFID authorised PSI to use air transport for the delivery of the first batch of ACTs, on an exceptional basis. The thirty days required for quality assurance testing is now integrated into PSI’s procurement plan.

QAACTs are now available in 684 pharmacies. Nonetheless, the delays set out above have had knock-on effects on other indicators relating to this output, because the implementation of several aspects of the intervention was dependent upon the rate-limiting step of securing the supply of QAACTs:

A local marketing and communications agency has been recruited to design a marketing campaign to promote Green Leaf branded QAACTs and RDTs to consumers. However, mass communication activities could not start before QAACTs were available in private sector outlets, as this would have prematurely created demand that could not be met. As a result, these activities started in late February 2016 (against an anticipated start date of July 2015), and the number of TV and radio spots broadcast to date falls substantially below expectation.

A survey to determine the presence of QAACTs in the market following the initiation of the intervention had to be postponed, as it made no sense to do this before QAACTs had been made available. As a result, data on this are not available to measure progress against relevant logframe indicators at this stage.

The process of getting RDTs into place has also met delays, but to a lesser extent. Authorization for the use RDTs in private pharmacies was given by the Secretary General of the Ministry of Health in October 2015. This policy change was necessary in order for this component of the programme to proceed. RDTs therefore began to be made available to private clinics that month[2], and the effect of this policy change will be evaluated through this programme. The programme managed to coordinate the initial distribution of RDTs well with the authorisation of their use, the start of the training programme and the arrival of QAACTs. As a result, there was minimal further delay at this stage.
[2] RDTs were in the first instance made available to private clinics which already had access to ACTs, albeit not yet to QAACTs provided to this programme. Once QAACTs were available, these too were provided to these clinics, and both RDTs and QAACTs began to be provided to pharmacies.

To date, 699 private providers have been trained in malaria case management, against an expectation of 564. This has been achieved despite the delays described above, as training began shortly after the Secretary General’s authorisation, but before the arrival of the first batch of QAACTs. The approach used for training is to provide it to a sub-set of staff from a number of facilities at a central location. Subsequently, the trainer visits each participating facility to hold a session with all staff (including but not limited to those that attended the initial training day), in order to recap the key points. In the interim, those who participated in the initial training day are expected to have shared their learning with their colleagues. This model is intended to efficiently reach a large number of individuals, and to minimise disruption to the day to day functioning of participating facilities. In view of the number reached to date, the training programme does seem to be successful, but it is important that a mechanism be put into place to determine whether the anticipated learning is indeed occurring, not just amongst those that participate in the initial training day, but also amongst their colleagues.

Even though full implementation has only recently begun, some important issues are already beginning to emerge. During a field visit on 22 March (a few weeks after implementation began), the following points were observed:

In one clinic, staff complained that a high proportion of test results were negative, and admitted to prescribing anti-malarials to patients with a negative result. Further questioning suggested that this was not due to a lack of knowledge, but was motivated by financial considerations (ie the opportunity to sell an anti-malarial to the patient regardless of the negative result). This is a practice that is far from unique to this programme or to DRC, but which nonetheless poses a significant threat to the efficacy and cost-effectiveness of the intervention. It is essential that this problem be quantified and better understood, and that mechanisms be identified and put into place in partnership with the PNLP in order to minimise this practice and to monitor the situation. ‘Mystery shopper’ exercises are already anticipated in order to identify pharmacies at which individuals known to be negative are nonetheless treated as positive, and at what price.

It was noted that the price being charged for QAACTs and RDTs varied between pharmacies. This in itself is not necessarily a concern, as it is expected that individual pharmacies will set their own prices within limits. Nonetheless, maximum prices are set, not by the programme but by the law: medicines may not be sold at a profit margin that exceeds 35% of the price at which they were purchased from the supplier. For QAACTs provided by this programme, this equates to a maximum sale price of approximately $1.50 per treatment course, and in some cases this was being exceeded. It is important that the programme, in partnership with the PNLP and the Division de la Pharmacie et des Medicaments (DPM), identifies and applies mechanisms to determine and monitor the scale of this practice, and to minimise the extent to which it occurs. In addition to protecting the investment made by this programme, this would be an opportunity for the DPM to exercise its regulatory function in relation to the sale of medicines.

Early indications are that potential consumers are insufficiently aware of the maximum prices. This may have two effects: firstly, they are less able to apply a downward pressure on the sale price, and secondly they may fail to enter the market because they assume that the sale price is too high for them. In order to address this, it is important that the maximum price be communicated to potential consumers and to the population as a whole. However, a constraint to this being done is that current policy is that medicines may not be marketed, and inclusion of the price in the mass communication information may be interpreted as a violation of this. The programme should therefore discuss with the DPM whether the maximum price could nonetheless be communicated to the population. The mass communication component should also track the population’s awareness of the intervention and of the maximum sale price, and to design and modify messages accordingly (eg through successive focus groups). A hotline for consumers to report exceedances of the maximum price should also be considered (this could also enable consumers to locate the nearest outlet).

A system for handling clinical waste generated by RDTs is in place for private clinics, but is not sufficiently so for pharmacies. The programme should urgently conduct a situational assessment of waste disposal at participating pharmacies, and design mechanisms to improve this where necessary.

It was originally anticipated that the subsidy towards the cost of QAACTs would be 65% in years 1 and 2, 25% in year 3, 15% in year 4 and 0% in year 5. However, due to the delays in implementation, virtually no distribution of QAACTs took place in year 1. This means that one of the two years in which the position of QAACTs would be established in the market through a high level of subsidy has been lost, and the programme now faces a critical choice in how to address this.

Significant challenges remain in relation to each of the market constraints being addressed by the programme. Several of these (such as absence of quality malaria case management by private providers) are set out above, but two in particular merit further discussion:

High taxes and tariffs: Taxes and tariffs imposed upon antimalarial drugs continue to present two problems: firstly, they raise the price of quality-assured drugs, thereby reducing their accessibility to the population, and secondly, they create ambiguity in relation to unlicensed drugs that should not be permitted entry into the country at all. PSI are recruiting a local agency to advocate for the reduction or elimination of taxes and tariffs on quality-assured, licensed malaria drugs, in order to reduce the financial barriers to their use. The programme is also in discussion ALMA (the African Leaders Malaria Alliance, a coalition of 49 African heads of state and governments working to eliminate malaria by 2030) to collaborate on this issue. Reductions in taxes and tariffs are necessary if further price reductions are to be achieved, and if existing price reductions are to be maintained as the subsidy provided by this programme is progressively withdrawn.

Absence of an enabling regulatory environment: The supply chain survey carried out by this programme confirmed that the regulatory framework for excluding antimalarial drugs that are not quality assured and appropriate remains weak and is poorly applied. During the field visit on 22 March, no less that fifteen ACT brands were being sold with the authorisation of the DPM, although the majority of these are not prequalified by WHO. An unpublished study by the University of Kinshasa in 2015 demonstrates that this is a manifestation of a wider problem: 72 ACT brands were found to be on the market, of which 52 had a license from the DPM, but only fourteen were prequalified by WHO. This situation has the potential to undermine the capacity of this programme to displace substandard or inappropriate antimalarial drugs from the market.

Lessons learnt

Implementation of this component is significantly behind schedule, as it took longer than anticipated to put contracts and agreements into place and to procure and receive the first shipment of QAACTs. This in turn led to delays in other aspects of implementation (such as training), although the programme has managed to coordinate events in order to contain these knock-on effects. Now that preparatory activities are complete and full implementation is underway, the programme has a critical year ahead to ensure that further delays are avoided and that substantial progress is made. Future programmes should draw upon the experience of this programme to avoid, minimise and plan for the delays that have been encountered.

Recommendations

In view of the fact that the implementation of this component is behind schedule, PSI should prepare and present a revised workplan by the end of May 2016. As the first of the two years in which QAACTs were to have been subsidised to a high level has now been lost, PSI should identify options for adjusting the progressive decrease in subsidy. This should be presented to DFID for consideration before the end of June 2016.

The programme needs to continue to work to address all six of the market constraints: some progress can be seen in relation to each of these, but there is a great deal more to be done. DFID and PSI should commission political economy analysis to inform the approach to improving the regulatory environment and advocating for changes in taxes and tariffs by December 2016.

In partnership with the Ministry of Health, PSI should reinforce measures to ensure that healthcare workers adhere to clinical guidelines (including prescribing an antimalarial only to those patients that have a positive test result), and to monitor this. Similarly, PSI should strengthen measures to ensure that recommended pricing for malaria testing and treatment is understood by consumers and adhered to by service providers during the implementation of the programme. PSI should produce a plan for improved waste management relating to the use of RDTs by the end of May 2016.

Pre- and post-training assessments should be carried out to measure and document the effect of training on service providers’ knowledge, and to inform improvements to the content and delivery of training where necessary. PSI should discuss with the PNLP the possibility of issuing a certificate to those who successfully complete training.

Output Title	Improve the availability and use of information for malaria control in DRC for increased capacity of malaria control interventions
Output number per LF		3	Output Score	C
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / (March 2016)	Progress	Comments
Cumulative number of sentinel sites rehabilitated/created and provided with equipment	3	0	Substantially did not meet expectation
Cumulative number of quarterly sentinel site data validation sessions by PNLP at central level	1	1	Met expectation
Cumulative number of sentinel sites providing timely and complete reports	3	2	Moderately did not meet expectation
Cumulative number of surveys (insecticide and drug resistance, pre- and post-campaign surveys) implemented	8	4	Substantially did not meet expectation

Key points

Through this output, Swiss Tropical Public Health institute will support ten sentinel surveillance sites for malaria, out of a total of 26 (one per province) that are anticipated across the country. Of these ten, three sentinel sites have been prioritised in the first instance, at Kimpese (Kongo Centra), Vanga (Kwilu province) and Kenge (Kwango province). Two of the sites (Kimpese and Vanga) are already in existence and require rehabilitation, and the third (Kenge) needs to be built from scratch. These sites have been prioritised for logistical as well as epidemiological reasons, as they are not too far from Kinshasa. This will enable lessons to be learnt from implementation before beginning work at other sites in more remote areas. In partnership with this programme, a further 16 sites will be rehabilitated or established in the remaining new provinces, with the support of the PMI and the Global Fund.

Overall progress against this output falls substantially below expectation:

It had been expected that the rehabilitation or construction and equipment of all three initial sites would be complete by March 2016, but this is still only in the preparatory phase, and the needs assessment of the three initial sentinel sites was undertaken as late as December 2015. Progress has been further impaired by the sudden withdrawal of the project manager recruited for the construction and rehabilitation work. A subcontractor for this role is now expected to be in place by May 2016.

Two of the three sites (those that are already in existence but require rehabilitation) are providing timely and complete reports. However, this cannot be attributed to the programme as these sites were already submitting reports prior to the start of the intervention, and reporting is not yet being performed by the third site as it is not yet in existence.

Although at the outset of the programme it was anticipated that eight surveys would be carried out by year 3, to date only four have taken place. The PNLP included only four in their workplan for this year: all four were carried out, but two consisted of the pre- and post-campaign surveys conducted by this programme, and two consisted of community surveys carried out in January 2016 in order to determine the degree of generalisability of the data collected at the sentinel sites to the population as a whole.

In early 2016, a four-day workshop took place to validate data generated by the surveillance system since 2011. This in effect represents the first regular data validation session, and further sessions should now take place on a quarterly basis (the next one is due in May 2016).

There has been some additional progress relevant to this output that is not directly captured by the indicators:

In addition to the data validation meeting, STPHI provided technical and financial support for the development of an integrated database for sentinel surveillance data at a two day workshop held in October 2015, with the involvement of Global Fund, PMI, WHO and MoH.

The Sentinel Sites Working Group (SSWG) was also launched at this workshop, and the participation of provincial and health zone management teams enable them to understand the purpose and objectives of the sentinel sites programme.

STPHI has recruited three technical assistants (for operational research, IT and finance) to enable the PNLP to more effectively manage data and resources.

STPHI and the PNLP organised a national Scientific Forum on Malaria in April 2016, at which key findings from surveys and research carried out in DRC were presented and discussed.

To date, 54 members of staff from the PNLP and from Congolese research institutions have been trained through targeted training sessions, against an expectation of 50.

This component of the programme has contributed to the development of the Malaria National Strategic Plan 2016-20, and STPHI led the working group on epidemiological surveillance.

Lessons learnt

This part of the programme is now very much behind schedule, and insufficient progress is discernible. It is therefore essential that STPHI and PSI develop a revised workplan in order to get this component back on track, and that this be rigorously implemented over the coming year. Should any further delays occur, they must be identified and communicated early to DFID so that they can be rapidly addressed.

Recommendations

By the end of May 2016, STPHI and PSI should revise their workplan to ensure that implementation of this component is back on track to achieve six rehabilitated or newly constructed sentinel sites by the end of year 4.

Summary of responses to issues raised in previous annual reviews

Recommendations	Status	Comments
By June 2015, PSI should develop a plan for a continuous distribution mechanism to maintain the level of coverage by using the remaining 934,548 bednets.	Done	A pilot of continuous community and school based distribution of bednets is underway in 12 health zones, and may be extended to other health zones depending on the findings of an evaluation of this pilot.
By June 2015, PSI and DFID should discuss with the PNLP how to develop a strategy (and associated guidance) to pilot school- and community-based distribution	Done	See above. This strategy was developed under the leadership of PNLP.
By May 2015, PSI should review the budget for component 1 in light of savings made by the programme, taking into account plans for continuous LLINs distribution.	Done	The budget was reviewed, and the savings identified have been deployed towards the continuous distribution described above.
By June 2015, PSI should update the logframe, taking into account plans for continuous LLINs distribution and anticipated changes to the market for QAACTs in Kinshasa.	Done, but behind schedule	The logframe has been updated, and will come into effect immediately following this annual review.
DFID should work with PSI to improve the financial forecast and increase accuracy before the new financial year.	Done	DFID staff met with PSI to discuss this issue. An improvement plan was developed and has been successfully implemented over the two last quarters of this financial year.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Overall disbursement and expenditure
DFID disbursed £2.7 million for the programme in financial year 2015/2016, bringing the total disbursement over the first three first years of the programme to £18.9m, out of the total contract value of £36 million. Of this, the programme has so far spent £18.9This includes £914,632 for design work over the first two years of the programme, and £10.9 million for the mass distribution which is now complete.

In addition to the £2.7 million disbursed in year 3, the programme had an unspent residual of £1.5 million from year 2, meaning that the total available funds in year 3 were £4.2 million. At the end of the financial year the programme had spent £4.3 million, meaning that there was a slight overspend in year 3.

Expenditure by component
Expenditure over the first two years of the programme was mainly in relation to component 1, and expenditure on this component has now reached 95 of budget because implementation is now largely complete. All that remains is the continuous school- and household-based distribution. This takes place at a much lower intensity than mass distribution, and accordingly the rate of expenditure against this component has fallen significantly in year 3.

Expenditure on component 2 is at 15% of budget at the end of the second out of five years of implementation. This reflects the prolonged design period and the delays in implementation that have since occurred. These delays have affected activities such as training and mass communication, leading to an underspend during the year. Now that ACTs have started arriving in country and are being distributed to clinics and pharmacies, it is likely that the rate of progress and therefore of expenditure will increase in the coming year.

Expenditure on Output 3 is at 19% of the total component budget, and this similarly reflects delays in implementation.

Table 1: Expenditure to date by year of implementation and by output / component:

Output	Output Impact weight	Y1 / 13/14	Y2 / 14/15	Y3 / 15/16	% of Y3 expenditure by output
Design and build phase	0%	£353,668	£560,964
Output 1: Increase to at least 80% the use of LLINs by pregnant women and children under 5 in Kasai and Kasai Central by 2018	50%	£6,938,985	£6,308,995	£1,631,739	38%
Output 2: Increase availability, accessibility and affordability of QAACT in the private sector in Kinshasa	30%	£0	£314,422	£1,931,520	45%
Output 3: Improve availability and use of information for malaria control in DRC through increased capacity of the malaria control interventions	20%	£0	£174,263	£736,525	17%
Total	100%	£7,292,653	£7,358,644	£4,299,784	100%

Table 2 Expenditures by PSI

Budget category	Budget total (Contract Budget)	Total FY 15-16 expenditure	% of total expenditure
Staff	£ 4,459,865	£1,252,485	29%
Subcontracts – STPH	£ 4,342,429	£526,441	12%
Consultants and services	£ 1,352,545	£487,654	11%
Promotion and communication	£ 3,241,106	£389,753	9%
Research and evaluation	£ 2,438,647	£366,754	9%
Other direct costs	£ 944,976	£411,779	9%
Administration and procurement fees	£ 2,383,929	£313,208	7%
Training	£ 1,691,822	£195,173	6%
Health supplies and related cost (LLINs, RDTs, gloves)	£ 10,389,579	£123,805	2.8%
Travel	£ 2,032,010	£140,004	3%
Furniture/equipment	£ 512,826	£71,554	2%
QAACTs subsidies	£2,263,950	£21,174	0.4%
Total	£ 36,053,684	£4,299,784	100%

The major cost driver for the third year of the programme has been human resources, accounting for 40% of expenditure in the year. This is followed by STPHI’s sub-contract for component 3 (12% of expenditure), research and evaluation (9%) and other direct costs (9%). The high proportion of total expenditure on human resources is a reflection of the fact that a number of key activities (such as advocacy for the reduction of taxes/tariffs and working with the DPM to strengthen regulation) are human resource intensive. Furthermore, component 2 has only recently moved into full implementation, which itself is reflected by the relatively small amount spent in the year on QAACTs subsidies[3]. Now that full implementation is underway, we expect to see the relative contribution of drug subsidies to total expenditure to increase, and that for human resources to decrease even if absolute expenditure remains stable. In addition, we expect expenditure against component 3 to increase in the coming year, as implementation of this component catches up. Over the coming year, it is important that these shifts in the profile of expenditure occur and that they are accompanied by accelerated achievement of results, in order to ensure that the programme continues to represent value for money.
[3] Furthermore, the figures that are presented do not capture the full contribution to the cost of health supplies procured and distributed: in addition to the subsidy presented in the table, the manufacturers have also reduced their prices in response to the programme. If the value of these cost reductions were taken into consideration, the relative importance of subsidies to the cost of ACTs (provided not just by DFID but also by the manufacturers) would in fact be higher than that presented above, and that of other items of expenditure (including human resources) would be lower.

VfM performance compared to the original VfM proposition in the business case
The total programme cost for the mass distribution of bednets in Kasaï and Kasaï Central is £13.2 m and 2,813,925 bednets were distributed. This equates to a unit cost of £3.88 per bednet. This compares favourably with the unit cost set out in the business case (£4.57), and is also lower than the unit cost achieved by DFID DRC’s mass distribution in Equateur province in 2011-12 (£4.76). The lower cost in Kasaï and Kasaï Central compared to Equateur is largely explained by the greater accessibility by road. Savings from the mass distribution have been redeployed to enable the pilot of continuous distribution through schools and households to take place, and this in turn has the potential to protect the investment made in the mass distribution by maintaining the levels of coverage that this achieved over time.

Programme	Number of bednets distributed	Total programme cost	Total unit cost	Expected unit cost
Mass distribution Equateur	4,211,779	£19,857,073	£4.71	£4.76
Mass distribution Kasaï and Kasaï Central	2,813,925	£15.8 m	£3.88	£4.57

The unit cost of community- and school-based continuous distribution is not yet known: to date, 28,301 bednets have been distributed through this modality, but data on the costs of distributing these is still being collated and will be determined during the evaluation of the pilot phase. In due course, it will be possible to benchmark the unit costs of this intervention against those achieved through DFID DRC’s continuous distribution of bednets in Equateur province, which is now complete (although it is important to consider that the unit costs are not directly comparable as the distribution modality differs somewhat, as does the context).

Programme	Number of bednets distributed	Total programme cost	Total unit cost	Expected unit cost
Continuous distribution Equateur	605,473	£4,236,560	£7.00	£5.99

Assessment of whether the programme continues to represent value for money
The recent Project Completion Review (http://devtracker.dfid.gov.uk/projects/GB-1-202251/) of DFID DRC’s malaria programme in Equateur province concluded that the mass distribution campaign implemented there achieved satisfactory value for money, in that the estimated health benefits substantially outweighed the costs. In view of the fact that the unit costs of the mass distribution carried out through this programme are lower than those achieved in Equateur, a similar conclusion may be applied to this intervention.

Quality of financial management
PSI has produced timely quarterly narrative and financial reports as per an agreed schedule in the contract. PSI has consistently underspent relative to their forecasts: for example in FY 2015/16 they spent £4.2 million against a forecast of £5.1 million. The accuracy of annual forecasting could have been improved by better anticipation of contracting and procurement delays. Quality of forecasting has been raised with PSI, and as result a quarterly budgeted workplan and quarterly updated forecasts for each invoice were put in place.

An Annual Audited Statement for programme for 2014 was provided by Deloitte, and was satisfactory. An audit for 2015 is planned in 2016.

Date of last narrative financial report	19/03/2016
Date of last audited annual statement	10/12/2015

E: RISK (½ page)

Overall risk rating: Moderate

Given the current impact weighting of the different outputs the programme has an overall risk rating of moderate. However, going forward, the revised logframe will significantly increase the impact weighting of output 2. The overall risk rating of the programme will therefore be elevated to major.

Overview of programme risk

The risk matrix for the programme is currently being updated in light of DFID’s new format which includes the external context and operational and safeguard risk in addition to fiduciary, delivery and reputational risk.
A summary of key risks and significant changes in the assessment of these is set out below:

External context
The uncertainty surrounding the elections due in November 2016 makes it difficult to predict the external environment and the extent to which this will be conducive for the implementation of the programme. There is a risk of political instability and disrupted security. Mitigation measures include political economy analysis and business continuity and contingency planning.

Delivery risk
The risk of delays in the negotiation of contracts and in procurement has been realised in relation to component 2, and to an extent in component 3. Recovery of delays in each of these two components is dependent upon implementing partner capacity as well as other factors. There was a high degree of confidence in the delivery of the mass distribution, as this is a tried and tested model. However this activity is now complete, and the remaining activities (components 2 and 3, as well as a pilot of continuous distribution of bednets through schools and households through component 1) are all innovative and untested in DRC. Furthermore, delays have already occurred in the delivery of components 2 and 3. As a result, the overall level of delivery risk in the programme has increased.

Operational risk
Changes in DFID DRC staff and potential difficulty in filling posts could undermine our ability to provide effective oversight of the programme.

Fiduciary risk
The level of fiduciary risk in the bednet distribution has been considered to be relatively low, as experience has shown that mitigation measures are largely effective and that cases of theft or fraud tend to be relatively minor and contained. However, this component is now complete, and there can be less confidence regarding fiduciary risk in relation to the remaining activities, particularly component 2 (as QAACTs represent low volume, high value items). Specific measures are in place or are anticipated to mitigate these risks, such as client exit interviews and outlet surveys. Nonetheless, it is important that these measures are reviewed and strengthened systematically (see recommendation 8).

Safeguard risk
Safeguard risks are greatest in relation to component 2. Risks of harm arise through issues such as non-compliance with clinical guidelines, and poor waste disposal. Additional measures to mitigate these risks have been identified in existing recommendations made in this annual review.

Reputational risk
As with safeguard risks, reputational risks are greatest in relation to component 2. Risks to the reputation of the programme and to DFID may arise from resistance from unintended consequences to changes in the market for QAACTs, withdrawal of the subsidy, or resistance from those with a commercial interest in the current configuration of the market. Additional risks include the emergence of counterfeit QAACT, and stock-outs of drugs.

Outstanding actions from risk assessment

Existing recommendations of this annual review are that PSI/STPHI should develop revised workplans for components 2 and 3, in order to mitigate the additional delivery risk in these areas. In addition, a fiduciary risk plan should be developed to take into account changes to the programme since the last annual review, with a particular emphasis on component 2.

By July 2016, PSI should develop a comprehensive, up to date fiduciary risk management plan, with a particular emphasis on component 2 of the programme.

The current overall risk assessment for the programme is moderate. However, in light of the additional risk in several programme areas, PSI and DFID should review the overall risk assessment (with a view to increasing it to high) and update the risk matrix each quarter.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Component 1 was implemented on time and below budget, enabling savings to be transferred into the continuous distribution which is now underway.

As set out elsewhere in this annual review, considerable delays have occurred in the implementation of components 2 and 3. Both of these components are now underway, but it is imperative that further delay is avoided over the remainder of the programme period.

Performance of partnership(s)
The programme is implemented by PSI, who have been active in the health sector in DRC for many years and have developed excellent relationships with the Government and key health donors such as USAID/PMI and the Global Fund.

In implementing component 1, PSI have collaborated with the PNLP, provincial Ministers of Health and Education and IMA World Health to coordinate logistics and communication activities, to advocate to health workers and health zone management staff on good governance of programme assets, and to prepare for school-based continuous distribution.

In implementing component 2, PSI have worked closely with the Global Fund and private sector partners to negotiate reductions in the price of QAACTs with four manufacturers (MacLeods, IPCA, CIPLA, and SANOFI) and their local importation agent (Pharmex), to secure use of the Green leaf Logo, and to fill gaps in supply of QAACTs in Kinshasa. The Global Fund have provided a financial contribution to meet this gap, sufficient to procure 6.6 million QAACTs and 1.7 million RDTs. PSI have also worked with the Clinton Health Access Initiative (CHAI) to initiate the national strategy for malaria case management in the private sector in DRC.

Component 3 is implemented by STPHI, who are working with the PNLP and with national research institutions (the University of Kinshasa).

Asset monitoring and control
Regular updates of the asset register are included in the reporting cycle, and constitute one of the annexes to the quarterly reports. The majority of assets remain in good enough condition to be used, and spot checks performed by DFID staff confirmed that the assets that were checked are in place.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable to this programme.

H: MONITORING & EVALUATION (½ page)

Component 1: Distribution of bednets

Results from the mass distribution post-campaign survey became available in year 3 and are set out elsewhere in this review.

An evaluation of the pilot of continuous distribution through schools and households is planned in order inform decisions on the potential scale-up of this approach. A specific recommendation regarding this evaluation is also set out elsewhere in this review.

Component 2: Improved availability and accessibility of quality-assured ACTs in Kinshasa

Mechanisms in place to monitor component 2 consists of two dimensions, both of which use new technologies. The first of these tracks QAACTs and RDTs stock and caseload at the facility level, and the second focuses on behaviour change of providers in the use of QAACTs and RDTs. The development of the data system for calculating consumption of QAACTs by age bands is underway and will be implemented soon.

The following studies were implemented as the baseline studies that will be used to monitor the progress of the project:

Exit Interview: The objective is to check the adherence of health workers to the recommended retail price for RDTs and QAACTs, and to monitor the level of the implementation of national clinical guidelines in the private sector. At baseline, it was noted that the average price of RDTs is higher in non–accredited pharmacies ($2.20) than in the private clinics ($1.10), and that fewer than 30% of people presenting to private clinics with fever were tested for malaria.

Mystery client: The objective is to monitor implementation of malaria case management guidelines, initially in in 65 private health facilities. At baseline, a sample of 122 individuals who had been tested negative for malaria was selected and sent to facilities as mystery clients. 63% of the clients were given a positive test result and treated with antimalarial. 35% of the clients were given a negative result, but nearly 90% of these were nonetheless given an antimalarial. This demonstrates the poor quality of malaria case management in the private sector at baseline.

Supply chain assessment in the private sector: The objective was to assess the functionality of the private sector supply chain for ACTs and to develop an improvement plan. The assessment found that there is a multitude of supply sources and a presence of a large number of wholesale distributors involved in the trade of medicines. An action is recommended to strengthen and support the drug regulatory authority in the implementation of regulatory functions.

In addition to the above, it was initially anticipated that the effect of the intervention would be determined through successive ACTWatch surveys. However, funding for this survey is now not secured, and so alternative means of evaluating the intervention will need to be identified. A midterm evaluation is planned in 2017 and a final impact evaluation in 2019.

PSI/STPHI and DFID should develop and agree an updated evaluation plan, with the involvement of Ministry of Health and the PNLP. The evaluation should enable change in relation to each of the six market constraints and in the overall availability and utilisation of QAACTs through the private sector (relative to other forms of malaria treatment) to be determined. In order to allow lessons to be learnt for future programming, it should also seek to explain any change or lack thereof, and to identify the cost-effectiveness and any positive or negative unintended consequences of the intervention.

Component 3: Increased capacity of the PNLP to generate and use data

No formal evaluation is planned for component 3. However, in addition to routine monitoring of progress, there is an opportunity to document the impact of the intervention by identifying instances in which decision-making by the PNLP and other actors has been strengthened through improved availability of data and information for malaria control in DRC.

STPHI to identify and document instances in which decision-making for malaria control has been supported by data and information that have been generated as a result of the intervention.

Monitoring progress throughout the review period

Routine monitoring of progress has been carried out over the past year through regular monthly meetings between DFID and PSI, and through routine quarterly reporting. Component 1 has also been assessed during the course of a field visit to Kasaï Central in December 2015.

This annual review process was led by the SRO / Health Adviser, and consisted of the following:

A PSI presentation on annual progress on 24 March 2016

Review of quarterly financial and narrative reports

A field visit to private sector clinics and pharmacies on 22 March 2016

The annual malaria partners’ meeting with participation of WHO, PMI/USAID, private sector partners and the Ministry of Health.