Annual Review - Summary Sheet

Title: Support to Girl Effect Rwanda (Phase 2)
Programme Value: £4.2m		Review Date: 28th April – 2nd May
Programme Code: 203949	Start Date: 1/06/2015	End Date: 31/5/2017

Summary of Programme Performance
Year	2016
Programme Score	A
Risk Rating	Minor

Summary of progress and lessons learnt since last review
This review took place 9 months after signature of the accountable grant, and so has assessed progress against milestones based on the first three quarters of activity. Girl Effect has focused on delivering the programme outputs and despite significant staff changes over the first three months when almost the entire management team and several technical specialists changed, it has made good progress against all three outputs.

The programme is on track to contribute to a strengthened environment for adolescent girls in Rwanda in a number of tangible ways:

- By reaching a significant proportion of girls in Rwanda, their families and communities with a positive girl brand, Ni Nyampinga, influencing their knowledge, attitudes and beliefs
- By providing practical tools to develop and sustain girls’ own clubs (content material and inspiration).
- By strengthening girls leadership at the local, village level through supporting girls to stand for election in the National Youth Council elections 2016, and building the leadership skills of 100 girls in 100 villages through a pilot. This has included influencing legislative change to enable adolescent girls and boys to be defined as youth (now 16-30 years).
- By improving the effectiveness of the community of practitioners working on adolescent girls in Rwanda
- Exciting interest in and commitment to positive change for adolescent girls through their brand, their focus and their influence, including with senior policy makers.

Over this past year Girl Effect has demonstrated quite significant effiency gains by being clearer about the linkages across teams and how these linkages can improve the content of Ni Nyampinga, streamline production and better support eventual impact.

Girl Effect’s work on girls’ formal leadership in local decision making illustrates that successful influencing is a combination of relationships, strategic objectives and opportunism. The path taken has differed from that envisaged. Building on the opportunity that local elections represented, Girl Effect worked with counterparts in National Youth Council to amend the definition of youth (to 16-30) and to enable youth representation at lower levels of the administrative structure (village level). NN radio supported awareness raising, promoting the elections and girls ability to stand as representatives at village level. As a result the number of girls in formal leadership positions has increased.

Summary of recommendations for the next year
Update performance against indicators 1.2 and 1.3 and VfM performance indicators once Ni Nyampinga Wave 4 data is available in September

Girl Effect to consider how to build on COP4G to raise voice for girls with policy makers responsible for programming and resourcing. MIGEPROF in particular was cited as lacking clear strategy on adolescent girls.
The relationship between the core (Girl Effect London) and country offices, in financial terms, remains unclear. The practical dimensions of this for the future of Girl Effect Rwanda should be discussed between Girl Effect and DFID Rwanda over the next 6 months.
A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203949/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203949/documents

DFID Rwanda’s support to Girl Effect is a two year programme of support to strengthen the enabling environment for the empowerment of adolescent girls in Rwanda. Funds are provided to GirlEffect through an accountable grant to deliver results and increase the sustainability of GER outputs, in particular its brand work – Ni Nyampinga.

The programme seeks to achieve an outcome of “strengthened enabling environment for adolescent girls in Rwanda through the delivery of three outputs”:
- Girls are repeatedly exposed to and understand transformational messages on economic secutrity, safety and voice and agency, communicated through Girl Effect’s branded media platforms
- Girl Effect brokering activities promote stronger focus on girls
- Increased operational and financial sustainability of Ni Nyampinga brand

The programme contributes to DFID Rwanda’s Operational Plan (2011-2016) which commits to place girls and women at the centre of DFID’s work to take advantage of the high returns to investments in girls and women. It is in line with the Country Poverty Reduction Diagnostic analysis and Business Plan (2016-2020) priorities, which commit to increase DFIDR’s focus on women and girls to ensure that they are not left behind (including by focusing on the enabling environment, and within this attitudes and behaviours).

The programme directly contributes to delivering the UK’s Strategic Vision for Women and Girls, in particular to strengthening the enabling environment for girls and women’s empowerment.

Since the business case was approved, Girl Effect (previously GirlHub) has become an independent organisation. This is a key part of the transition to increased sustainability for Girl Effect. Girl Effect incorporates all of GirlHub’s previous work and is a registered charity, independent of DFID and Nike Foundation (GirlHub founding organisations). Girl Effect continues to be a brand led organisation, with a specific interest in how to increase the depth of engagement with brand (in Rwanda this is Ni Nyampinga) in order to contribute to social change for adolescent girls. This has not affected the scope or the delivery of the business case (Girl Effect Rwanda Phase 2).

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
On the basis of this first annual review of a two year programme of support, we assess that the outcome “enabling environment for adolescent girls in Rwanda is strengthened” will be achieved. A contribution to strengthening the enabling environment will be delivered in a number of different ways.

Creating an enabling environment means addressing the barriers to girls’ and women’s voice, choice and control over their lives. These include the negative attitudes and gender norms that prevent them from fulfilling their potential by shaping how they are valued in society, the power they hold and the opportunities available to them. Reflected in the formal structures of society and its informal rules, attitudes and behaviours, social norms are some of the most powerful constrainers of girls’ and women’s choice and control over decisions about their own lives and bodies.

The programme is on track to contribute to a strengthened enabling environment in a number of tangible ways:
- By reaching a significant proportion of girls in Rwanda, their families and communities with a positive girl brand, Ni Nyampinga, influencing their knowledge, attitudes and beliefs
- By providing practical tools to develop and sustain girls’ own clubs (content material and inspiration). An estimated 10,000 girls are involved in self starting NN clubs, effectively reading and discussion groups. Approximately 35,000 more girls use NN in other formal clubs, such as Girl Guides (based on clubs scoping research).
- By strengthening girls leadership at the local, village level through supporting girls to stand for election in the National Youth Council elections 2016, and building the leadership skills of 100 girls in 100 villages through a pilot. This has included influencing legislative change to enable adolescent girls and boys to be defined as youth (now 16-30 years).
- By improving the effectiveness of the community of practitioners working on adolescent girls in Rwanda
- Exciting interest in and commitment to positive change for adolescent girls through their brand, their focus and their influence, including with policy makers.

Overall output score and description
This review took place 9 months after the signature of the accountable grant, and so has assessed progress against milestones based on the first three quarters of activity. Girl Effect has focused on delivering the programme outputs and despite significant staff changes over the first three months when almost the entire management team and several technical specialists changed, it has made good progress against all three outputs. Whilst there has been a three month delay in undertaking the Wave 4 research, which captures reach, understanding and impact of NN, all other main activities have been delivered on time and with some quite significant improvements in efficiency and economy. The overall output score is A – outputs met expectation.

Key lessons
Over this past year Girl Effect has demonstrated quite significant effiency gains by being clearer about the linkages across teams and how these linkages can improve the content of NN, streamline production and better support eventual impact. The evidence, girl specialist and brand team generates ideas for content, based on consultation with girls using market research techniques, content developed by the editorial team is evidence based and assured by technical girls specialist team, monitoring and evaluation activity feeds this cycle and also seeks to improve the evidence base on whether and how brand contributes to changing attitudes and norms.

Successful influencing is a combination of relationships, strategic objectives and opportunism as illustrated by Girl Effect’s work on girls formal leadership in local decision making. The path taken has differed from that envisaged. Building on the opportunity that local elections represented, Girl Effect worked with counterparts in National Youth Council to amend the definition of youth (to 16-30) and to enable youth representation at lower levels of the administrative structure (village level). NN radio supported awareness raising, promoting the elections and girls ability to stand as representatives at village level. As a result the number of girls in formal leadership positions has increased.
This annual review will be shared online through Development Tracker and lessons learned will be presented to DFID Rwanda’s policy meeting.

Key actions

Update performance against indicators 1.2 and 1.3 and VfM performance indicators once Ni Nyampinga Wave 4 data is available in September

Girl Effect to consider how to build on COP4G to raise voice for girls with policy makers responsible for programming and resourcing. MIGEPROF in particular was cited as lacking clear strategy on adolescent girls.

Has the logframe been updated since the last review?
The logframe was updated as part of the inception phase, where indicators were finalised to improve measurability and reflect available data and monitoring plans. There were no changes to agreed outcome or outputs.

## C: DETAILED OUTPUT SCORING

Output Title	Girls are repeatedly exposed to and understand the transformational messages on economic security, safety and voice and agency, communicated through Girl Effect’s branded media platforms
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	60
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of Ni Nyampinga magazine publications and radio shows produced	4 new magazine editions and 156 new radio shows (July 2016)	Met expectation. / Magazine issue 13 was released in Sep 2015, issue 14 in Jan 2016, issue 15 in March 2016 and issue 16 is currently in print to be released in May 2016. / 3 radio shows have been regularly broadcast each week throughout the year and a total of 156 radio shows will have been delivered by July 2016.
% adolescent girls (10-19) reached by NN media platforms (disaggregated by age, education, location, disability and vulnerability status)	52% all girls (10-19) are reached by NN magazine or radio / 36% all girls (10-19) reached by NN radio show / 33% all girls (10-19) reached by NN Magazine / (July 2016)	Not yet possible to measure hence moderately did not meet expectation. / As a result of delays in launching Wave 4 of the NN quantitative research the survey will be undertaken in July and evidence will be available in September.
% girls (10-19) reached by NN media platforms who have shared what they read or heard with others	36% girls (10-19) reached by NN radio say they share what they heard on the radio with someone / % girls (10-19) reached by NN magazine say they share what they read in the magazine with someone / (July 2016)	Not yet possible to measure hence moderately did not meet expectation. / As a result of delays in launching Wave 4 of the NN quantitative research the survey will be undertaken in July and evidence will be available in September.

Key Points
Indicator 1 is met. Girl Effect has focused its new team on delivering NN radio and magazine to ensure that girls are repeatedly exposed to transformational messages on economic security, safety and voice and agency by ensuring the production targets were met. In partnership with Facebook, a new website NiNyampinga.com was launched in February 2016, and has applied the content from NN magazine issues 13 onwards, in Kinyarwanda.

Girl Effect has improved linkages across teams to streamline production, to ensure content is informed by both girls’ voices and evidence, and to deepen understanding of messages by repeating content across its channels and encouraging sharing and discussion of content by groups of girls. This has improved efficiency and has the potential to improve the effectiveness of the brand work.

Indicators 2 and 3 are assessed as ‘moderately did not meet expectation’ since the evidence against which the milestones will be assessed will not be available on time. Wave 4 of the NN quantitative survey (which captures brand, brand engagement and outcomes amongst girls and others) is slightly delayed due to methodological development work required to strengthen the quality of measurement overall. Final results are expected to be available in September.

However consideration of a wider range of evidence indicates that both the reach of NN and the sharing of key messages will have increased as a result of several factors. First, the radio footprint (the most accessible platform) has increased from 4 community radio stations and Radio Rwanda to 6 community radio stations and Radio Rwanda. This has been achieved at no additional cost by re-negotiating broadcast contracts and bringing radio production in house. The community radio footprint reaches a potential population of 7 million, of which almost 683,000 are estimated to be girls aged 10-19. The NN magazine is now distributed in 1,500 outlets from 800 (including some schools and health centres, youth centres, the Catholic Church and refugee camps), with Girl Guides of Rwanda (AGR) acting as ambassadors for the brand in each of Rwanda’s 30 districts.

Sharing (indicator 3) is understood to be a key driver of impact by ‘elongating’ the reach and understanding of key messages. Radio shows ask girls to talk or share what they have hears and to text in responses to questions and stories, to promote discussion of messages. Ambassadors are asking girls to discuss the magazine content and to form reading groups (clubs) to do so. ‘Inspiring stories’ based on real life individuals eg the story of Esther (a 12 year old girl with a disability in primary 3) in issue 15, also promote sharing and discussion.

Based on this wider evidence, output 1 is scored an A, met expectation.

Summary of responses to issues raised in previous annual reviews (where relevant)
Girl Effect has taken on board discussions on vulnerability and reach in its efforts to expand reach and the use of inspiring stories, helping the brand speak to a range of Rwandan girls.

Recommendations
It is recommended that performance against indicators 2 and 3 is updated once the NN Wave 4 data is available.

## C: DETAILED OUTPUT SCORING

Output Title	Girl Effect brokering activities promote stronger focus on girls
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of organisations actively participating in a community of practice and using evidence and tools produced to apply best practice in girl centred programming	Community of practice established and meeting regularly to share best practice, improved understanding and build evidence of girl centred programming (July 2016)	Met expectation. / CoP4G established in October 2015, with 35 members registered and a leadership group of 6 practitioner organisations. 3 quarterly meetings held and 3 hot topics discussed.
Number of open source learning documents and briefings shared with partners	9 briefs and one programming tool produced (July 2016)	Met expectation. / Briefs from hot topic discussions and economic empowerment curriculum available in Kinyarwanda and published on website cop4g.org/learning-briefs
Number of girls trained in leadership skills at the community level with support from Girl Effect	NYC curriculum pilot designed and operational (July 2016)	Moderately exceeded expectation. / There has been substantial work against this indicator which has exceeded original expectations.

Key Points
Indicator 1 has met expectation. The previously existing 4GN (for girls network) has been reinvigorated as the COP4G (community of practice for girls). The COP4G aims to create a shared space for girl focused organisations across all sectors “combining expertise and energy while championing innovation, so that together we can deliver on our joint vision for every girl in Rwanda to fulfil her potential”. A leadership group representing 6 practitioner organisations ensures ownership and promises sustainability of the community of practice. Of three hot topic sessions held (voice and empowerment, economic empowerment and GBV and reporting) two have been hosted by network members with particular expertise (Care and Educate).

During annual review consultations with partners, Girl Effect was credited with providing the energy and focus to drive the establishment of the COP4G, linking practitioners to learn from and support each other and helping practitioners engaged with adolescent girls “to do it better”. Girl Effect’s “magnetic force”, convening power and local authority on evidence based policy advocacy were noted.

Indicator 2 has met expectation. 6 learning briefs have already been produced in English and Kinyarwanda from hot topic sessions on voice and empowerment and economic empowerment. These are written for and target different groups (practitioners, girls and influencers). GBV briefs are currently being prepared. The briefs capture a mixture of evidence and experience on key topics and signpost further resources. They have been distributed through COP4G and on the recently launched website, www.cop4g.org. An economic empowerment curriculum (programming tool) has been designed, tested and translated into Kinyarwanda and a training of trainers session has taken place to promote its use.

Indicator 3 has moderately exceeded expectation. The original expectation was that Girl Effect would support girls at community level to develop their leadership skills through training and that they would then seek out local leadership positions. In practice Girl Effect has adapted to take advantage of the opportunity represented by local elections in February 2016. Girl Effect worked with Ministry of Youth and ICT to influence the definition of youth (bringing it down from 18-35 to 16-30 years) and with National Youth Council to extend this formal representative structure to the village level. NN radio publicised the opportunity for girls to stand for formal leadership positions at village level and Girl Effect built awareness of 100 practitioners working with girls on the law and the elections. Initial information on elected girls indicates that hundreds of 12+ mentors have been elected, and some NN journalists. The pilot intends to engage 500 elected girls in a youth camp in July from which 100 girls will be selected for further leadership training. A draft MoU for the pilot has been developed with NYC and is awaiting signature in order for the pilot to become operational.

On the basis of the above assessment and feedback during the annual review, progress towards this output is scored an A+ moderately exceeds expectation.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA

Recommendations
Girl Effect consider how to build on COP4G to raise voice for girls with policy makers responsible for programming and resourcing. MIGEPROF in particular was cited as lacking clear strategy on adolescent girls.

## C: DETAILED OUTPUT SCORING

Output Title	Increased operational and financial sustainability of Ni Nyampinga brand
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Production costs of Ni Nyampinga magazine	Reductions in production costs to $3.40 per copy (July 2016)	Substantially exceeded expectations / Production costs have been reduced to $2.74 per copy, as a result of efficiency savings (gathering content for multiple issues), economy savings (size and quality) and re-negotiating contracts and transferring production in house.
New partnerships developed to enhance sustainability of Girl Effect Rwanda work	Sustainability plan developed (July 2016)	Met expectations

Key Points
Indicator 1 has substantially exceeded expectations, with production costs reduced and almost meeting the end of project target of $2.64. This has been achieved through efficiency savings ie collecting content for two issues at a time; distributing the magazine through a partnership with AGR; bringing magazine and radio production in house with quality assured through a network of ‘friends of NN’ who provide advice pro-bono; and making small savings when re-negotiating contracts (all supplier contracts have been re-procured over the past 6 months).

Indicator 2 has met expectations. Girl Effect was established as an independent organisation in September 2015 and registered in Rwanda. Earlier analysis on the potential for strengthening sustainability through advertising concluded that the Rwanda market was not yet mature enough. Building on this analysis Girl Effect Rwanda estimates that the Ni Nyampinga brand will be 100% self-sustaining by 2021. Over the past year the team has done significant work on understanding and reducing cost drivers, and aligning along the value chain to maximise both efficiency and quality. Increased focus on quality/rigour of content to ensure that it is aligned to specific behaviour change objectives that can be tracked and measured should improve Girl Effect’s ability to demonstrate the impact of its work. A strategic decision making framework to evaluate potential partnership opportunities has been put in place to enable Girl Effect to assess potential revenue generating opportunities.

Girl Effect global is building partnerships to diversify funding sources and to leverage assets for girls at a greater scale. This includes Gates and other family foundations, which are now providing core financing, and Girl Effect is now seeking to grow its projectised in kind and grant financing.

On the basis of the above assessment performance towards this output has been scored A+, moderately exceeded expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)
Many of the issues raised in previous annual reviews of GirlHub and in ICAI and IAD reviews have been addressed for Girl Effect Rwanda over the past year with the establishment of Girl Effect as a separate entity. See section below.

The business case for support to Girl Effect Rwanda was part of DFID’s overall vision for supporting the transition of GirlHub into an independent organisation. Two years of additional support to Girl Effect Rwanda was intended to support both the delivery of results and the sustainability of investments in Rwanda. This review’s assessment is that the additional support is performing as intended.

Recommendations
The relationship between the core (Girl Effect London) and country offices, in financial terms, remains unclear. The practical dimensions of this for the future of Girl Effect Rwanda should be discussed between Girl Effect and DFID Rwanda over the next 6 months.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

Key cost drivers are staff costs and production costs associated with Ni Nyampinga. As a result of staff gaps in core positions in the first three months savings were made overall. Production costs associated with NN magazine and radio have been driven down as set out in the assessment of output 3.

VfM performance compared to the original VfM proposition in the business case

Implementation has performed well against the original VfM proposition in the business case. Costs of production have been reduced. The level of DFID support has been manageable since relationships were already established, Girl Effect had a strong track record in Rwanda and clear reporting mechanisms and expectations were established during the inception phase. Assumptions on working directly with key stakeholders and beneficiaries have held true – with a focus on girls’ leadership in partnership with NYC with real potential to increase voice and representation; and a community of practice which promises to be a platform for more effective advocacy. Complementarities within Girl Effect’s brand value chain have been improved – brand and brokering have continued to be mutually reinforcing, with the energy, style and vision of NN providing legitimacy for Girl Effect’s brokering and advocacy work.

Several of the performance indicators identified in the business case will be available after the results of NN quantitative survey Wave 4 are published. It is recommended that the assessment is updated then.

Magazine:
- Percentage of girls (10-19) that has ever read the magazine, disaggregated by age, gender, location, Ubudehe category and disability status
- Percentage of boys and gatekeepers/parents that ever read the magazine
- Percentage of girls (10-19) that has regularly read the mag, disaggregated by age, gender, location, Ubudehe category and disability status
- Percentage of girls (10-19) who say they have ever shared the content of the magazine with others
- Cost per mag
- Cost per girl reached

Radio:
- Number shows per week
- Percentage of girls (10-19) that has ever listened to the radio show, disaggregated by age, gender, location, Ubudehe category and disability status
- Percentage of boys and gatekeepers/parents that ever listened the radio show
- Percentage of girls (10-19) that has regularly listen to the radio show, disaggregated by age, gender, location, Ubudehe category and disability status
- Percentage of girls (10-19) who say they have ever shared the content of the radio shows with others
- Cost per show
- Cost per girl reached
- Cost per all audience reached
- Time of broadcast

Branded media platform
- Percentage of girls (10-19) reached by NN branded media platforms who believe that girls are as valuable as boys in their families
- Percentage of girls (10-19) reached by NN branded media platforms who believe that adults will listen if they express their views or opinions
- Percentage of girls (10-19) reached by NN branded media platforms who believe that they are able to take steps to achieve goals for their future

Assessment of whether the programme continues to represent value for money

For the reasons set out above, we assess that the programme continues to represent value for money.

Quality of financial management

Overall financial management is good. A two month inception phase focused on profiling expenditure across the project’s lifespan and reporting formats for financial and programme performance reporting were agreed. Variance against forecast is acceptable compared to similar projects in DFID R, averaging 8% in the first three reporting quarters.

Date of last narrative financial report	https://devtracker.dfid.gov.uk/projects/GB-1-203949/documents
Date of last audited annual statement	https://devtracker.dfid.gov.uk/projects/GB-1-203949/documents

E: RISK

Overall risk rating: Minor

Overview of programme risk

The overall risk for this programme has reduced to minor, on the basis of performance to date and an updated assessment of the risk matrix. The programme is now in its final year. Girl Effect has established itself as an independent organisation with clearer governance and clear relationships between Girl Effect London and Girl Effect Rwanda, including reporting lines. In Rwanda it has an energetic and dedicated team focused on delivery and ensuring sustainability.

Outstanding actions from risk assessment

A due diligence assessment of Girl Effect was commissioned which has informed the management of this accountable grant. Girl Effect London and Girl Effect Rwanda have acted on the observations and recommendations. 90% of the action points have been completed.

IAD and ICAI recommendations have been taken into account in managing this AG and follow up reports have been successfully responded to by DFID R.

There are no other outstanding actions.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Despite delays in the first quarter as a result of staff recruitment and the on boarding of a number of key staff, delivery against planned timeframe has been good. The production of Ni Nyampinga to time and quality, whilst making efficiency savings and increasing the rigour of content, has been the primary focus. New workstreams under brokering have been successfully delivered. The main delay has been to undertaking Wave 4 NN quantitative survey. This has been the result of a combination of staff changes, and improvements to the approach and methodology to better capture outcomes as well as performance of NN.

Performance of partnership (s)

Girl Effect Rwanda holds a range of well performing partnerships at a range of levels. These relationships are healthy and mature, with Girl Effect’s technical support to members of COP4G and its ability to broker new partnerships for other actors appreciated. It applies its comparative advantage (branding and communications) to support its relationships, including the Girl Champions Group, a group of influential policy makers.

The partnership between GER and DFID is also maturing. Girl Effect is “growing up and leaving home”, with new dimensions to the relationship going forward eg 12+ and the ideas around integrating implementation of 12+ with brand in order to sustain the assets built, leveraging respective resources in a different way.

The next year will be key to mapping out what the partnership going forward means in practice.

Asset monitoring and control

The following assets have been purchased using DFID funds under this grant. An asset register is maintained.
- 1 x Mac Laptop
- 3 x Flight case for NN mobile radio studio

G: CONDITIONALITY

Update on partnership principles (if relevant)

The business case is delivered through an accountable grant arrangement with Girl Effect, and so the partnerships principles are not applied to its management. Activities supported under the grant have the potential to strengthen commitment against partnership principle 1 “commitment to reducing poverty and achieving the MDGs” and partnership principle 4 “commitment to strengthening domestic accountability” for adolescent girls.

H: MONITORING & EVALUATION

Evidence and evaluation

The key evaluative evidence is the NN Wave 4 and 5 surveys. The approach to these has been updated to better capture NN performance, engagement with brand and outcomes of the brand amongst girls, boys and gatekeepers. To do this the sample size has been increased and Wave 4 will interview a sample of 4,200 girls and 1,600 community members. This is a sizeable increase in sample size from the previous three waves of the Ni Nyampinga audience monitoring survey (e.g. wave 3 comprised of a sample of around 2,900 girls and community members). However the increased power of this sample will enable Girl Effect to establish stronger evidence of the relationship between the brand and outcomes for girls and others than previous years, accounting for potential confounding factors (such as education or exposure to other social communication interventions). This enhanced monitoring survey therefore serves to provide evaluative evidence of Ni Nyampinga and is a more cost-effective approach than commissioning a separate impact evaluation study.

The survey will be representative at national level and at district level for girls. It includes quantitative and qualitative components. Methodological improvements are being considered to make the survey more appropriate for children. The survey is expected to be underway in July, with results available in September.

GH’s theory of change is based on evidence that the empowerment of girls requires (a) changes in informal structures including discriminatory social norms that prevent girls from reaching their potential and (b) changes in formal structures that can provide or limit the opportunities and assets that girls have to fulfil their potential (including policy and legal frameworks, programmes, services and assets). Therefore Girl Effect’s theory of change is that to achieve the empowerment of girls requires an integrated strategy that addresses barriers and influences change at the level of the girl (knowledge, attitudes, beliefs and behaviours); level of the family and community (attitudes and behaviours, social norms); level of the environment (policy, programme and investment decisions which affect the assets and opportunities that girls have access to). This programme operates at all three levels combining brand and brokering work.

It is of key importance that Girl Effect is able to communicate the impact of brand on social changes and the role that brand plays, following investments in NN over the past 5 years. The evaluative work underway has this objective - to generate evidence against the theory of change.

Monitoring progress throughout the review period

This annual review was undertaken largely as a desk based exercise, supplemented with a small number of interviews with key informants (Girl Effect Rwanda staff, partner organisations from COP4G, and a representative of GoR). It was led by Social Sector Team Leader (SRO) and supported by Social Development Adviser and Deputy Programme Manager, DFID R’s Social Sector Team. Participation in a recent NN distribution in Bugesera District by SDA and accompanying a visit to Musanze by international journalists (when radio content gathering and NN engagement with a 12+ safe space was observed) has also fed into the assessment. Feedback has been incorporated into the assessment above.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process