Business Case

18 month Cost Extension of the Somaliland Election Programme (SEP)

What support will the UK provide?
As a result of the delay in the Somaliland district council elections, no activities have taken place under the March 2010- March 2012 Somaliland Election Programme (Annex 2) for the past 12 months. There remains an unspent balance of £1,303,715.30 under the SEP. / This cost extension will provide an additional £797,093 of funding, and extend the period of the programme by 18 months up until the end of September 2013. The total amount to be spent over the cost extension period is £2,100,808. / The total of amount of actual and planned expenditure under the SEP is: £3,447,093. / The programme will support the deepening of democracy in Somaliland.

Why is UK support required?
What need are we trying to address? / The District Council elections in Somaliland will define the political landscape in Somaliland for the next ten years. From these elections, three political parties will emerge who will contest the next round of presidential and parliamentary elections. The district council elections are now five years overdue and are scheduled to take place in 2012. / HMG has funded two recent studies to review the district council elections: the first by DFID in 2011 and the second by FCO in 2012. The studies have identified a number of gaps in current support to the district council elections which need to be filled to ensure elections are credible. The gaps identified are as follows: / The provision of international election observers. / Training of Election Day staff. / Support to develop a process for election dispute resolution. / Support to the new political associations, the political associations registration committee and the newly elected councillors. / Enhancing the engagement of Somali citizens and non-state actors in policy dialogue with government. / Enhancing the voice of pastoralists, women and youth in the election process / What will we do to tackle the problem? / DFID’s contribution to the election process will be the provision of technical and management expertise at key parts of the election process to ensure that there is full and adequate support to the election process. Support will be provided to cover the gaps identified above. / Why is DFID funding required / Existing donor (EU, NORAD, DANIDA, USAID, SDC, and SIDA) and Government of Somaliland support to the district council elections amounts to US$4.4 million. DFID funding is required to provide complementary support to meet the identified gaps.

What are the expected results?
What will change as a result of our support / The intended outcome of this intervention is: democracy strengthened in Somaliland. / The expected outputs are as follows: / 225 political association representatives (35 women) trained on electoral procedures; / 300 (50 women) representatives from the political associations trained on political party development and organization as well as campaign skills; / Increased participation of women and youth in elections campaigns - 150 (90 women) targeted with 3 intensive one week-long youth and women campaign schools on youth and women outreach skills, campaign message development; / Party agent training - 2750 (500 women) party poll agents trained; / The promises and community commitments of 267 political candidates tracked; / 216,000 voters in 6 districts (targeting marginalised groups such as pastoralists, rural, youth and minorities) are aware of political candidates and their agenda; / 2,600 youth are empowered and active in seeking their own political solution though their participation in 26 democracy café centres. / Formation of the Somaliland Civil Society Election Forum (SCSEF) and a minimum of two dialogue meetings between SCSEF and state/government structures. / Process for election dispute resolution developed and in place. / International election observers reporting on the elections. / Medium term democratisation strategy developed. / The Somaliland Non State Actor (NSA) platforms are actively engaged in policy dialogue with Somaliland authorities. / The NSA platforms have developed realistic strategies to improve their sustainability and ensure independence. / How will we determine whether the expected results have been achieved? / The programme will be monitored by the implementing partners throughout the programme period, and there will be an Annual review by the end of December 2012. An independent evaluation will take place at the end of the programme, the results of which will be used to guide and consider the nature of further funding to elections in Somaliland.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Since 1991, Somaliland has stood out from the rest of Somalia as a result of its relative peace and stability. A successful home-grown, clan-based mediation system has helped deliver peace and reconciliation, and major outbreaks of conflict have been avoided. / The series of elections since 2002 (municipal 2002, presidential 2003, parliamentary 2005 and presidential 2010) have been critical events in post-conflict peacebuilding and state building in Somaliland. Enthusiastic public participation in the elections reflects both a desire for better governance and an aspiration for international recognition of Somaliland. / Despite the overall positive progress, elections are often faced with delays and irregularities. The most marked example of this was the introduction of a voter registration system in 2007/2008 prior to the Presidential elections. Massive fraud took place with clans attempting to use the process to conflate their individual clan numbers with the ultimate aim of winning the elections and maximising control of resources. As a consequence, there was a political crisis where the National Election Commission (NEC) declared that elections could be held without a voter list and Interpeace, the agency through which donors channelled their elections funding, was expelled from Somalia. The international community, led by the Ethiopia and UK, managed to bring back Somaliland from the edge of a potentially violent election dispute by facilitating a six point agreement between the political parties. / Presidential elections took place in 2010 after a delay of 2 years. As in the Presidential elections in 2003, there was a peaceful transfer of power to the opposition, this time led by Presidential Silanyo. The relative free and fair manner in which the 2010 presidential elections was held demonstrates a continuing commitment among the people of Somaliland to a political system of multiparty representative democracy. At the same time, the success of staging the election owes much to international diplomacy and technical assistance. / Despite the relative success of the 2010 presidential election, there remains an underlying fragility to Somaliland’s democratisation process. A key message from the World Development Report (WDR) is that institutional legitimacy is the key to stability. Governments are more likely to be stable if they are accepted by the people as legitimate, with their government able to rule by consent. Research conducted for the WDR 2011 found that where this environment is not provided, and institutional legitimacy is at its weakest, countries are most vulnerable to conflict and violence. / The next elections due are the district council elections. In February 2011 President Silanyo told the Somaliland Parliament his government was committed to holding new district council elections in 2011. This commitment was extended in January 2012 to hold the elections within 2012. By the end of 2012 the councils have been in post for nine years and their re-election is five years overdue. / A stable Somaliland that builds on its recent political, security and economic developments is of high strategic importance to UK. DFID’s engagement is aimed at supporting long lasting political settlements by building state structures and services to confirm the state’s legitimacy. The benefits of success in Somaliland are integral to the short and long-term development of the wider Somalia. The district council elections are important since, in addition to electing district councillors, they will elect from a long list of six political associations and three political parties, which three political parties will be eligible to stand in the next parliamentary and Presidential elections. / The UK has strong historic links and good relations with the Somaliland government and plays a leading role amongst the international partners. / The risk of not intervening is that we fail to consolidate the relative stability currently enjoyed in the majority of Somaliland and the region remains fragile. At worst, there is a risk of state failure and a return to conflict, development failure and a humanitarian crisis. / Support to Somaliland is consistent with the UK Somalia strategy 2011 which states that HMG should, inter alia: / Continue increasing development support to Somaliland. / Plan how the international community can support emerging administrations to provide local security, basic services and an environment that supports legitimate economic activity. / Coordinate international support to emerging administrations. / This programme will contribute clearly to DFID’s Business Plan objective to strengthen governance and security in fragile and conflict-affected countries. / At the February 2012 London Conference the international community expressed a strong political will to see Somalia’s stability, prosperity and human development levels improve. Embedding democratisation within Somaliland is an important element of the state and peace-building agenda for both Somaliland and Somalia. / A number of different international partners (EU, NORAD. DANIDA, USAID, SDC, and SIDA) are supporting the election process in Somaliland. All of this is through a basket fund to support the INGO Interpeace and their work with the National Election Commission. The value of the basket fund is US$4.4m, of which US$1.1m is a contribution from the Government of Somaliland. There are a number of important areas of the election process that are not covered by the Interpeace programme. These areas require support to better enable free, fair and credible elections to take place. DFID is well placed to provide funding to these complementary areas of election support.
B. Impact and Outcome that we expect to achieve / Our Theory of Change is that by having better managed elections with increased voter turnout, the new district councils will have a greater legitimacy and authority. This will lead to a more accountable district government, which with parallel service delivery reforms at the district government level (e.g. supported by the UN Joint Programme for Local Government and Joint Health and Nutrition Programme which are both funded by DFID) will lead to a more peaceful and stable Somaliland. / Expected impact. / The expected impact is to deepen peace and stability in Somaliland. / Expected outcome. / The expected outcome of this intervention is: democracy strengthened in Somaliland. / Planned outputs / The planned outputs are as a shown on page 2.
[note] World Development Report 2011, p7
[note] DFID: Governance and Peace-building Theory of Change for Somalia, 2011
[note] Somalia Strategy, Somalia Unit, 2011 unpublished (restricted)

Appraisal Case

What are the Feasible Options / Other donors support a basket fund managed by the Interpeace, through which UK support was previously channelled. However, DFID concerns around the quality of some of the technical inputs, and the management and reporting of the Interpeace managed basket fund contributed to DFID’s decision not to contribute to the donor basket fund. / In addition, two recent reports have identified a number of gaps in support to the election process that are not presently being covered by the Interpeace managed basket fund as below: / Support for international election observers. / Training of Election Day staff. / Support to develop a process for election dispute resolution. / Support to the new political associations, the political associations registration committee and the newly elected councillors. / Enhancing the engagement of Somali citizens and non-state actors in policy dialogue with government. / Enhancing the voice of pastoralists, women and youth in the election process. / In addition, both the 2010 Annual Review of the SEP, and the Rift Valley Institute Report on Options for Supporting the SEP recommend providing support for stabilising the electoral calendar and developing a more strategic approach to democratisation. A detailed list of the activities and results proposed under this Cost Estimate can be found in Annex 1. / Without the support to address the gaps outlined above, there could be increased challenge on the legitimacy and authority of the new district councillors, and the three new political parties that will emerge from the district council elections. / The donor basket fund exclusively channels support through Interpeace to the NEC. The gaps identified require a skills set which is not available within Interpeace, nor within the mandate of the NEC. The feasible options for delivering this range of outputs are as follows: / Option1: Up to three partners implementing accountable grants / This option would involve selecting three partners to either implement all or some of the above outputs. / Option 2: Two partners implementing and managing Accountable Grants. / In this Option, two partners would be selected to lead on the management of Accountable Grants for support to government agencies (supply side reforms) and to civil society (demand side reforms). / International Republican Institute (IRI) leading and coordinating on supply side reforms: / Support to the Political Associations (PA), the Political Associations Registration Committee (PARC) and new councillors (implemented by IRI). / Training of Election Day staff (implemented by Interpeace). / International election monitoring (implemented by Progressio). / Oxfam leading and coordinating on supply side reforms: / Election dispute resolution (implemented by the Centre for Humanitarian Dialogue (CHD)). / Support to non-state actors and a new NGO Election Forum (implemented by Saferworld). / Improving the voice of pastoralists and youth (implemented by Oxfam). / Option 3: Interpeace managed donor basket fund. / In this Option, all DFID funds would be allocated to the Interpeace managed donor basket fund. / Option4: The do nothing counterfactual / Under this option, no DFID resources would be allocated to supporting the district council elections. / Appraisal of Options / Option Appraisal Overview / Option1: Up to three partners implementing Accountable Grants A diverse range of skills and experience are required to deliver on all the gaps. The experience of INGOS presently working in Somaliland in delivering the outputs is shown below: / Progressio – experience in managing international election observers for the 2010 Presidential elections. / Interpeace – experience from the 2010 Presidential election working with NEC and election day management. Providing on-going support to the NEC through the donor basket fund. / CHD – developed a process for election dispute resolution for the 2010 Presidential elections. / Saferworld - experience working with non-state actors and NGO forums in Somaliland. / Oxfam – extensive working with pastoralist communities and women and youth in rural areas. / IRI - working with Somaliland House of Representatives on policy development, and international experience working with political parties. / Within this Option of having three partners, the alternatives would be to either drop some of the activities or have partners implement activities outside of their existing expertise. For the former, the reports mentioned above state that all of the outputs are priorities for delivering on programme objectives. For the latter, given the range of outputs and existing expertise, proven track record and partnerships built from the Presidential elections there would be no comparative advantage in an INGO taking on an output in which they have no experience. / Due to the necessarily political nature of the elections it would be not possible for one partner to work with both government agencies and civil society. Even within the proposed work with government agencies, for example working with the National Election Commission and the Political Associations Registration Committee (PARC) and the Political Associations (PA), partners have expressed reluctance to work across agencies with different mandates where the impartiality of technical advice may be questioned. / Option 2: Two partners implementing and managing Accountable Grants – one for demand side reforms, one for supply side reforms. Option 2 would bring the following advantages: / All outputs would be delivered by partners with a track record and expertise in delivering similar outputs in Somaliland. / Through coordination of outputs by the lead partner election support will be more strategic and coordinated – this role would otherwise revert to DFID. / Through adopting a more comprehensive role in the election process, partners will be better able to understand and manage risks. / A challenge however will be for the partners to coordinate and manage the Accountable Grants. From our experience of working with Oxfam and IRI these two INGOs have sufficient capacity to manage Accountable Grants. / Option 3: Interpeace managed donor basket fund. In this option the district government elections would only be receiving support from DFID and other donors through the Interpeace managed donor basket fund. / Whilst the NEC would be better funded, the evidence discussed below shows that a more integrated and balanced approach to election support is required. There is a risk that as a consequence of not providing support outside of the donor basket fund that there would be a higher risk that conflict could increase. / Additionally, without the support outlined above, there could be lower election turnout than could be expected, and this will challenge the legitimacy and authority of the new district councillors, and the three new political parties that will emerge from the district council elections. / Option 4: The do nothing counterfactual The counterfactual would be not to provide support to the elections. As discussed above, evidence shows that additional support is required to improve the election process in Somaliland. Should support not be provided, there is a risk that conflict could increase. / The preferred option as a result of this appraisal is Option 2: two partners implementing and managing Accountable Grants – one for demand side reforms (IRI), one for supply side reforms (Oxfam.) / What is the evidence and the response of the Somaliland Election Programme Cost Extension? / Elections are increasingly accepted as a key component of establishing and maintaining state legitimacy, an important step on the path to forging an inclusive and stable political settlement. However, poorly conducted elections – for example those that are carried out prematurely, those without adequate inclusion, or without transparent procedures – can easily exacerbate elections. Delivering free, fair and credible elections is therefore a considerable but important challenge, logistically, financially and politically. / A range of evidence suggests that international support to elections often falls short of desired standards. DFID suggests nine principles for election support: / 1. Understand the wider context within which elections occur: Evidence suggests that for the democratic process to take root in a country, the international community needs to give consistent attention to every election, and that local elections are often crucial arenas for deepening democracy. / The district level elections in Somaliland will define the political landscape for the next 10 years. The three leading political associations in these elections will become the three political parties that will contest the next House of Representatives and Presidential elections. / Support under the SEP: An integrated and balanced support will be provided to the district council elections, and the study will allow for the development of a more strategic approach to election support for all donors. / 2. Be clear when to advocate for and support elections and when to hold back: The district council elections in Somaliland are long overdue. There is pressure from within Somaliland to carry out these elections as soon as possible. / Support under the SEP: Support provided through Interpeace, and IRI is focusing on ensuring that technical, legislative and capacity issues are addressed so that when GoSL decides to hold elections, they will be free and fair. Through the Saferworld NGO Election forum, civil society will be better able to articulate and advocate for timely and fair elections. Running parallel to this, the FCO and Donor Democratisation Coordination Committee (DCC), of which DFID is a member, are in regular contact with the NEC and GoSL discussing the timing of the elections. In addition, DFID support has been held back pending clarity on decisions on the timing and technical aspects of the elections. / 3. Analyse electoral risk at all stages: The two reports discussed above have identified areas of risk that require support. In addition, the implementing partners and donors will hold regular meetings to discuss on-going risks. / Support under the SEP: Two direct risk mitigating measures that are part of the Cost Extension will be to develop a process for election dispute resolution, and also to bring in international election observers. / 4. Integrate diplomatic with financial and technical support: There is an important inter-relationship between diplomatic/political, financial and technical support before, during and after elections. / Support under the SEP: The CE allows for continued long-term support of the electoral cycle, and will provide relevant technical support. To ensure integration of support, DFID will attend regular meetings of the Democratisation Coordination Committee, and will require its partners to meet regularly in Hargeisa to coordinate on election support. / With respect to coordinated diplomatic and technical support, DFID and the FCO in Addis are in regular contact regarding the elections in Somaliland. This builds upon previous close coordination between the FCO in Addis Ababa and DFID in Nairobi around the time of the Presidential elections. / During the run up to the elections, it will be important that the FCO’s contacts and opportunities for high level meetings are used to unblock any continuing issues, and that DFID funded technical support is mindful of the political context. / 5. Systematically adopt the electoral cycle approach: Experience shows that support to elections in conflict situations must not be treated as “one off” events, and that elections must be embedded in an entire electoral cycle that is part of a broader process of democratisation. / Support under the SEP: A longer term strategy will be developed by IRI to advise DFID and other donors. In addition, work on both the demand side and supply side reforms is concerned with developing longer term capacity of both politicians and civil society and the links between both. / 6. Recognise the limitations of development partners’ role in elections support: The ability of the international community to leverage positive change may be limited and dependent on a much wider and deeper political context alone. / Support under the SEP: The approach being followed by all development partners including DFID is to see incremental improvements rather than transforming the political settlement overnight. / 7. Support election observations: Election monitoring can add significant depth to an election observation effort. / Support under the SEP: Progressio will coordinate and manage international election observers as part of this CE. / 8. Support women’s political participation: Programmes encouraging the participation of women are crucial to ensure greater gender equality in both local and national elections. / Support under the SEP: The work to be carried out by Oxfam and Saferworld will enhance the role of women and youth in the election process. / 9. Follow principles of harmonisation, alignment and ownership: Broad consensual networks are central to the effectiveness of the international support for good governance. / Support under the SEP: DFID and its partners will meet regularly with the Democratisation Steering Committee to ensure alignment of approaches and objectives. / What measures can be used to assess Value for Money for the intervention? / Under this CE, VfM measures will be developed by the partners and agreed by the Head of Governance and Peacebuilding Section before Accountable Grants are awarded. A number of approaches will assist with the identification of VfM measures including: / Structuring budgets according to activities rather than line item so that total costs of activities and outputs can be gauged over time. / VfM measures that link the different levels of the log frame i.e. inputs to outputs and outputs to outcomes. This adds value to the results framework by putting values on the steps in the intervention logic. / Implementing partners have started to identify a number of measures of the economy, efficiency and effectiveness of projects, which include: / Economy / Cost per output per number of programme beneficiaries / Unit cost per person/day / Overhead costs. / The key cost drivers will be security, consultant, staff costs, and fuel In addition, the management costs of IRI and Oxfam will be limited to 7% of the programme costs. / Efficiency / Core and Integrity Costs: The core costs are more or less the fixed cost of an election that would be incurred regardless of the electoral environment while the integrity costs are incurred because there is a precarious electoral environment that requires extra effort and investment to secure the electoral process. In post-conflict countries, integrity costs drive up the per capita costs of election. The per capita cost of the district council elections, the per capita cost of the 2010 Presidential elections and per capita international election costs will be compared. / Effectiveness / Given the economic costs of instability and violence a useful way in which to consider effectiveness is through the counterfactual. If Option 2 was not funded and there was violence there would be considerable negative benefits in Somaliland and perhaps in the wider region. The UK could be faced with both increased humanitarian costs and state and peacebuilding costs. / Demonstrating VfM under this CE is challenging because: / At this stage it is not known if there will be an open or a closed list for the elections, nor is the number of political associations that will contest the elections known. / Heterogeneity of outputs between projects. / The complex link and longer term between achieving outputs and outcomes. / Few outcome indicators are easy to quantify in monetary terms. / Programme Costs / The spend will be split between interventions and financial years as follows: / Area of Support April 2012 - March 2013 April 2013-September 2013 / Supply Side / Support to PA, PARC and new councillors (IRI) 380,800 150,000 / Training of Election Staff (IP) 375,000 / International Election Monitoring (Progessio) 65,000 / Demand Side / Election Dispute Resolution (CHD) 150,000 / Non State Actors and NGO Forum (Saferworld) 150,000 / NGO Forum (Saferworld) 162,680 / Voice for Pastoralists and Youth (Oxfam) 531,388 71,000 / Studies and Evaluation / Democratisation Planning (IRI ) 50,000 / End of Programme Evaluation 15,000 / Total 1,864,868 236,000
[note] Options for Supporting the Implementation of DFID’s Somaliland Election Programme, Rift Valley Institute, 2011
[note] Draft Somaliland Pre-election assessment report , Progression, March 2012
[note] Electoral Assistance and Politics: Lessons for International Support, DFID

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / In Somalia’s challenging operating environment working with partners with a track record is critical. All outputs involve indirect procurement from INGOs. Accountable Grant letters will be used with NGO partners. / DFID will rely on the partners contractual/management arrangements which will be assessed on an on-going basis. In addition, we are considering a due diligence assessment of one or both partners as part of our prioritisation of due diligence assessments across the Somalia programme. / From a limited pool of delivery partners, is it considered that those selected under the cost extension are able to deliver the results DFID is targeting; and account for funds in an accurate and transparent manner. / As above we work with partners to improve VfM. Improvements will include: / Verifying adherence to strong corporate procedures for procurement and expenditure authorisation that stresses VfM. / Cost comparison for similar interventions. / DFID will negotiate consistent administrative charges with all implementing partners, with NGO partners charging 7% as overhead costs. We will also examine budget lines across partners to ensure consistency and request justification for any variance.

Financial Case

Programme finances are profiled as follows: / Item £ / Original SEP Budget 2,650,000 / Expenditure to March 2012 1,346,285 / Unspent Funds 1,303,715 / New funds requested 797,093 / Total of SEP including Cost Extension 3,447,093 / Funds required for Cost Extension 2,100,808 / The programme covers one financial year and 6 months covering the pre and post-election period. Expenditure is profiled as follows: / 2012/13 £m 2013/14 £m Total £m / 1,864,808 236,000 2,100,808 / All NGOs will provide monthly projections of spend. A close working relationship between the IRI, Oxfam and DFID Somalia staff will help DFID ensure sufficient priority is given to accurate forecasting. Relationships have already been established with international NGOs through previous DFID Somalia funded programmes and work has already been undertaken to improve the accuracy of forecasting. / How will it be funded: capital/programme/administration / All interventions will be funded from programme funding. An amount of £2.10m will come from the Somalia Governance and Peacebuilding pillar Operational Plan allocation. / Funding is not considered sensitive, novel or contentious at this point. Due to the political environment, the Head of DFID Somalia will be updated regularly on programme implementation and any significant changes to risk factors. / How will funds be paid out? / Funds to IRI and Oxfam will be paid through Accountable Grant arrangements DFID will make funds available at quarterly intervals in advance, if necessary, upon receipt of a detailed forecast of the expenditure requirement for the period. IRI and Oxfam will manage the flow of funds to the sub-grantees. / How will expenditure be monitored, reported, and accounted for? / All payments will require submission and approval of narrative reports as follows: / Quarterly narrative and financial reports by INGOS – payments only to be made against satisfactory reports and progress on results. / Annual audited accounts statement – to be submitted to DFID within three months of the conclusion of the programme. / Assets register to be kept by all partners for assets worth over £1000. / Monthly financial forecasting – partners to alerts us to any under spend and accruals by the 15th of every month to adjust ARIES forecaster figures in advance. / We will constantly monitor partners spending through financial forecasts and will re-allocate prospective underspend in a timely manner. We will undertake rigorous scrutiny of our partners’ financial reports and suspend funding in case of any financial malpractices or discrepancies in the financial transactions or persistent submission of wrong forecasting figures.

Management Case

A. Oversight / The programme will be overseen by the DFID Somalia Governance and Peacebuilding team which is responsible for tracking progress, monitoring, reporting and evaluating success. / Seminars have been held with partners to increase their capacity to meet our management needs on VFM, monitoring and evaluation, results and transparency. This will also assist in reducing DFID transaction costs of management. / Oxfam and IRI will be responsible for managing and coordinating sub-grants to Interpeace, Progressio, CHD and Saferworld. Both organisations are well established international NGOs and have experience of working in Somaliland. Management responsibilities will include support in the finalisation of proposals from sub-grantees, including quality assurance of monitoring frameworks and VfM indicators; compilation and quality assurance of financial and monitoring reports, preparation of invoices and payment to sub-grantees upon satisfactory completion of activities/outputs. Additionally, Oxfam and IRI will arrange regular meetings in the field to ensure activities are coordinated; cross-cutting issues such as gender are addressed in coordinated way, and that learning is shared and any lesson learned can be adopted across the programme at the earliest opportunity. / DFID has good experience of managing an Accountable Grant with sub-grantees, notably through PSI who manage the Health Consortium Programme for Somalia. Lessons learned from this experience will be applied to the management of Accountable Grants with Oxfam and IRI. / A variety of tools will be used by DFID in oversight of the programme including, but not limited to: / Participation in the Democratisation Steering Committee and Donor Coordination Committee meetings. / Project financial and monitoring reports / The Governance and Peacebuilding section will hold weekly management meetings and DFID Somalia will hold quarterly pillar review meeting to maximise the development impact of the programme and understand its impact by: / Reviewing the results of the programme against a results framework / Promoting best practice in use of evidence, monitoring and evaluation / Reviewing risks / Reviewing internal project management plans, including reviews and related submissions.
What are the risks and how these will be managed? / A number of risks have been identified. These are shown below along with mitigating actions. / Risk Probability of risk occurring Impact on success Mitigating action / Inadequate financial controls - fiduciary risk. Inflated operating costs and diversion of funds. Medium Medium Due diligence assessments of IRI and/or Oxfam. / Work with partners to ensure timely audits and remedial action. / No direct funding of GoSL. / Payments will be dependent on full use of and accounting of funds in accordance with agreed programme expenditure. / Programme interventions are poorly implemented by contracted partners Low-Medium High Regularly monitor programme implementation against agreed plans. Ensure quarterly reports capture actual progress against key performance indicators (results focused) and where necessary institute remedial action promptly. / Resistance by INGOs to co-ordinate and share information / platforms Low-Medium Medium Ensure terms of reference, objectives and performance indicators foster co-ordination and use these to monitor and dialogue on progress. / Inadequate donor coordination around the democratisation process. Medium Medium Continue to work with the Democratisation Coordination Committee. / Insurgents attacks on international staff resulting in evacuation or potential harm of personnel. High High Local partners on the ground can in some cases continue to implement projects in the absence of foreign staff. No press attention that staff are funded externally. / Duty of Care check list to be completed by IRI and Oxfam to confirm their awareness and management of risk. / HMG assistance seen to be politically biased Low-Medium High Working through a variety of international partners with a focus on technical advice focused on capacity building and institutional strengthening.
C: Conditionality / No funds are being provided directly to the Government of Somaliland or to the Somaliland NEC so conditionality does not play a part in this programme.
D. Monitoring and Evaluation / Under the programme, each partner will be responsible and held accountable for monitoring of their programme delivery. Monitoring will provide regular data to compare achieved against planned results and therefore enable programme performance to be systematically reviewed. / Oxfam and IRI will provide to DFID a quality assured and consolidated monitoring report at the end of every quarter. The report will document progress against the monitoring plan and log frame. Partners will use a common template to report results. / Towards the end of the programme, DFID will commission an independent end of programme review to assess overall results achieved and the extent to which the programme has met expected outcomes and impact. Evaluation of single interventions will be conducted by the partners but DFID will commission an external evaluation. The purpose and structure of the evaluation and questions to be asked will be determined at an early stage drawing on the expertise of DFID Somalia’s Evaluation Advisers.
Log Frame / Quest No of logframe for this intervention:

Annex 1. SEP Cost Extension Interventions

	Activities, Results delivered	Indicative Amount
		FY 2012/13	FY 2013/14
IRI	IRI will support the newly formed political associations and existing political parties to effectively participate in the local elections by: improved understanding of the election process; improved campaign strategies and election monitoring. / Results: / Political parties and political associations understand Somaliland’s electoral system. / Training of 225 reps (35 women) from the three existing political parties and associations on electoral procedures; / PARC empowered to serve a supporting role to political associations during the election. / Political parties and political associations engage in constructive pre-election dialogue with government and civil society stakeholders to address electoral issues - 18 election stakeholder dialogues facilitated by IRI; / Increased organizational capacity for newly formed political associations to effectively participate in the local elections. / 300 (50 women) reps from the political associations receive training on political party development and organization as well as campaign skills; / Increased participation of women and youth in elections campaigns - 150 (90 women) targeted with 3 intensive one week-long youth and women campaign schools on youth and women outreach skills, campaign message development; / Party agent training - 2750 (500 women) party poll agents trained by IRI;	380,800	150,000
Oxfam	Oxfam will implement a pilot project to address two inter-related problems: 1. Low participation by rural communities in terms of awareness of rights, entitlements and responsibilities and 2. Weak institutional accountability to citizens with the emerging local governance systems. The pilot will strengthen community participation in local government affairs and to promote greater institutional accountability. / Results: / The promises and community commitments of 267 political candidates tracked; / 216,000 voters in 6 regions (targeting marginalised groups such as pastoralists, rural, youth and minorities) are aware of political candidates and their agenda; / 2,600 youth are empowered and active in seeking their own political solution though their participation in 26 democracy café centres.	531,388	71,000
Interpeace	Training of NEC Headquarters staff, NEC Regional staff and NEC Polling station staff on election management. / Results: NEC staff trained on election management and election day implemented successfully.	375,000
Saferworld	Saferworld would work on two areas: / 1. A short three month intervention would support a co-ordination and advocacy forum - the Somaliland Civil Society Election Forum (SCSEF) - for civil society actors engaged in the local elections and the wider democratization process. / 2. Support to non-state actors to engage in decision making processes that affect their lives. / Results / Formation of the Somaliland Civil Society Election Forum (SCSEF). / Minimum of two dialogue meetings between SCSEF and state/government structures. / The Somaliland NSA platforms are actively engaged in policy dialogue with Somaliland authorities and key members of the international community on issues relating to peacebuilding and statebuilding, democratisation, aid effectiveness and public services. / NSA platforms provide relevant, accurate and timely information to their constituencies on priority policy issues. / The NSA platforms have realistic strategies to improve their sustainability and ensure independence.	312,680
CHD	Building on experience and team used for the 2010 Presidential Elections, CHD will develop a process for election dispute resolution. / Results: Election dispute resolution mechanism in place for the elections.	150,000
Progressio	Recruitment of a team of international election observers. / Results: Team of international election observers reporting on the district council elections.	65,000
IRI	Development of a longer term democratisation strategy for Somaliland. / Results: Strategy developed and agreed with all stakeholders.	50,000