SOMALIA CONFLICT SECURITY AND STABILITY FUND
Delivering Credible Electoral and State Formation Processes STRAND
FINANCIAL YEAR 16/17
Total Allocation: £6.2 million / 2016/17 2017/18 2018/19 / Output 1: Support to State Formation through the Somalia Stability Programme £1.7m £1.0m £1.0m / Output 2: Support to UNDPs STeFS programme on State Formation £1.0m £0.5m £0.5m / Output 3: Political economy of revenue £300k £100k £100k / Total £3,900,000 £1,600,000 £1,600,000
Total ODA: £6.2 million
Convening Department: DFID
Strand Board: CSSF Senior Project Manager (political), DFID Governance and Security Team Leader, Somalia Unit Head Political and Economic, 2nd Secretary Political, DFID Governance Adviser
Approval Process: / This draft business case was designed by DFID’s Governance and Security and CSSF Senior Project Manager (political),. It will subsequently be submitted for approval by the Strategy Board, Joint Secretariat and Whitehall Africa Group.
Supplementary Documents (as required): / This business case has attached an results framework and State Formation document for UNDP/UNSOM
Strand Summary
This strand aims to support a credible state formation process in Somalia. This contributes to Pillar 3 of the NSC strategy, on Politics and Governance - “ Elections, state formation and the development of state institutions support stable inclusive and increasingly accountable governance throughout Somalia”. The proposed intervention is at the core of the UK Aid Strategy objectives on stability and resilience. Key NSC contributions include: / NSC Strategy 3.6 (Political) – Improved Human Resources capacity, policy and planning systems and more accountable and transparent public financial management in FGS, Federal States. / NSC Strategy 3.2 (Development) Increased domestic revenue and health and education services delivered. / Specifically this means the results the strand will achieve “Strengthened foundation for viable states”. / Progress in Somalia is contingent on a more durable political settlement. The current state formation process and upcoming electoral process are both key staging posts towards a more representative and credible government. Both are highly contentious and have the potential to generate as well as mitigate conflict. The main objective of this strand is to support these Somali-led processes in a way that avoids potentially destabilising conflict and delivers an incremental improvement. The proposed intervention has 3 outputs: / Support to state formation through the Somalia Stability Programme. £3.7 million. / Capacity of key actors in the state formation process enhanced so they can broker sustainable and conflict sensitive settlements through UNDP. £2.0 million / Identify revenue potential and the political economy around key revenue sources in ports and other main revenue areas in emerging federal states. £0.5 million / The proposed intervention complements and builds on CSSF work from 20015/16 and wider political and development interventions – notably Somalia Stability Programme and the Core State Functions Programme. The proposed intervention is based on evidence from the CSFP evaluation as well as a body of reviews and evidence from the UN, EU and DFID. / Delivery: Outputs 1 and 3 will be delivered through the Somalia Stability Programme. Output 2 will be delivered through the UNDP Support to Emerging Federal States (StEFS) programme (part of a planned multi-year support: £2 million over 3 years). The Governance and Security Team Leader will be the Senior Responsible Officer for this work. The strand will be overseen by the Strand Board. / Risk assessment: Outputs 1 is medium risk while outputs 2 and 3 are high risk. The risks under output 1 are primarily fiduciary risks. Output 2 depends on wider political and security progress on state formation. Output 3 is potentially very high risk with severe challenges in terms of access and delivery of the work.

Strategic Case
The Federal Government of Somalia (FGS) is the country’s first internationally recognised government since 1991. Its appointment in 2012 signalled the end of an extended transitional period and repeated failed attempts to re-establish central government. However, whether the FGS indeed offers a turning point in Somalia’s history will depend on how far it is able to negotiate a more durable and inclusive political settlement, which enables the development of a functioning system of government across Somalia. This is a challenge for an administration that is in reality extremely weak, with limited outreach outside Mogadishu, and in a country that remains deeply socially and politically fragmented. / Some progress has been made to pave the way for a federal government, with the formation of new regional administrations across South Central Somalia. This process has been aided by territorial gains achieved in the military push by African Union forces (AMISOM) and their allies against Al Shabab, and is backed by neighbouring countries. Three interim administrations are now formed (Jubaland, South West State and Galmudug), with dialogue underway in Hiiraan/Middle Shabelle. Formal dialogue on Benadir is yet to start. / Security and state formation: Despite progress in defeating Al Shabaab in most urban areas, Al Shabaab can move freely across many parts of South-Central Somalia and worryingly they continue to have the capability to take selected urban areas when they want. This impacts negatively on the state formation process in a range of ways as the state is not capable of delivering basic security, rule of law deliver services and collect revenue. In many cases AS seem to use blocking of urban areas as a deliberate tactic which remains an effective tool to undermine state formation. Blocking off urban areas de facto leaves citizens in very poor conditions, no trade, no emergency aid, no development or even ability to grow food and above all with a sense that the government (state or federal) is not in control and cannot be trusted. / The 3 formally created states are at different levels of consolidation, with Galmudug being the most fragile. All struggle with the above challenges across their territory. / Elections The state formation process is widely recognised as key to future stability, but the context remains highly charged with constant setbacks and potential for resumption of violence. Serious negotiations have yet to progress on how these states will relate to the FGS, each other, and their own constituencies, including on contentious issues such as security and resource sharing. It will take time to agree these regional and local level political settlements. Many in the FGS are ambivalent about the federalism ‘project’, which they believe will weaken the state and amplify clan divisions. Nonetheless, the process has momentum, and looks likely to result in a new federal map by the end of 2016. An agreed federal map should be seen as a first step. As indicated above, new states will inevitably be extremely fragile for a while and will struggle with performing most or all of their functions.
Strategic Fit
This intervention contributes to Pillar 3 of the NSC strategy, on Politics and Governance - “ Elections, state formation and the development of state institutions support stable inclusive and increasingly accountable governance throughout Somalia”. The proposed intervention is at the core of the UK Aid Strategy objectives on stability and resilience. The intervention strongly complements other DFID interventions – notably work on reconciliation, public sector and public financial management at state and local government (through PREMIS and SSP) and it strengthens overall UK engagement. / Gender Equality Act - Gender impact assessment: State formation has major short-, medium- and long term implications on gender issues: In the short run, the quality of the state formation process itself can prevent or drive violence and instability which tends to impact disproportionately on women and children. A relatively better process would also allow for better involvement of women in decision making, initially at state level, but in turn that would also lay the foundation for involvement in local government issues. In the medium and long term, improved state capability and settlement will continue to minimise risks of instability and gradually begin to collect revenue and deliver basic services – both of which women benefit disproportionately from. / Space for engagement and UK comparative advantage: The UK has particular comparative advantages in this area – both as the leading technical donor and through the BEM presence and engagement. The CSSF is well-placed to address some of these issues due to the need for flexibility and cross-HMG engagement. The proposed intervention will be closely coordinated with other planned and on-going programmes, both within the CSSF, DFID and with external UN and USAID programmes. While it is recognised that the overall state formation and consolidation process will take several years and that there will be regular setbacks it is clear that the CSSF can add value in a number of ways, especially if seen within a wider context of HMG political, security and development work. It is envisaged that there will be future bids on state formation to CSSF; much depending on progress of the present on-going state formation process. At this stage the most likely area of additional funding requests will relate to elections and democracy interventions. / Stakeholders: Emerging states and the Federal Government of Somalia are the primary stakeholders. A range of other stakeholders will be involved – incl. clan leaders, civil society and youth.

Appraisal Case
For this intervention, 5 key questions and options were considered: / 1) Do nothing. / 2) Only support the UNDP state formation project, StEFS / 3) Only support infrastructure / 4) Only support Political Economy study of revenue / 5) Combination of some or all of options 2-4. / In addition, in the initial stages of design, there were discussions on including support to elections work in both Somaliland and Somalia South-Central. However, it was assessed that elections work is partly already covered (through the UN programme on elections and CSSF supported USAID and additional work on elections would require a bigger and more consolidated package around democracy. It was therefore not included as an option. / Key criteria in the assessment of options are around results/impact, fiduciary risks and value for money, but equally fit with other interventions and management/transactions costs are important parameters. Relevant reviews and evaluations (primarily from the DFID CSFP programme), and analytical/research reports from SAHAN, EU (see http://www.iss.europa.eu/uploads/media/Brief_17_Somalia.pdf ) and the UN (notably SEMG reports and programme reports have informed both the type of options and the content of each option. / In addition, there were discussions on including support to elections work in both Somaliland and Somalia South-Central. However, it was assessed that elections work is partly already covered (through the UN programme on elections and USAID and additional work on elections would require a bigger and more consolidated package around democracy. It was therefore not included as an option. / Option 1: Do Nothing / The team also considered the counter-factual “do nothing” option. The principal arguments for supporting this option are staff time savings and results risks and that critical state formation activities would happen without the additional support from CSSF. Counter to that are the risks that critical state formation support will not happen or would not at the required time and that DFID/HMG would not be able to influence UNDP's state formation programme in a constructive, strategic direction. We assess that work key office space and the political economy of revenue sources and areas would certainly not happen. UNDP’s state formation project would probably happen, but not certain. If it went ahead, it would likely have a more operational focus and with higher risks of overlap with DFID’s PREMIS and SSP programmes. / Option 2, UNDP stand-alone support / Description: This option is part of a support of £2 million in principle for 3 years, of which £1 million is planned in 2016/17. The Support to Emerging Federal States (StEFS) Project represents key United Nations proposed support to the Somalia Government state formation work, addressing needs primarily at the emerging federal state level but also supporting those federal government structures that critically facilitate new state formation. StEFS has been designed in consultation with the FGS and representatives from new federal states in south and central Somalia, and is designed around five key outputs. These are: / Output 1: Supporting the political dialogue and consultations around federalism and state formation. / Output 2: Strengthening the capacity of the SFG, particularly those institutions engaged in the federalism process. / Output 3: Providing foundational support to Interim State Administrations to ensure an appropriate physical working environment. / Output 4: Enhancing the capacity of Interim State Administrations with a dedicated focus on ‘core public sector capacities.’ / Output 5: Strengthening civic participation and engagement with Interim State Administrations. / Assessment: Depending on StEFS’ ability to deliver and manage – which we judge to be medium (they will deliver, but they will struggle with strategic interventions), the option provides an opportunity to support a range of state formation areas with limited staffing costs and in a coordinated manner. It also provide a strong opportunity to ensure coordination – incl. that StEFS does not enter into areas where the programmes does not have a comparative advantages – especially around PFM at state level, which is being delivered by PREMIS. As a stand-alone option, there is a risk that the option will not be strategic at that it will focus on basic operational issues. It would build some infrastructure across emerging states, but it would not lay the foundation for future revenue streams. / Option 3, support to office infrastructure in Jubaland and South West State and strategic state formation interventions through the Somalia Stability Fund / Description: £3.7 million over 3 years for construction of office buildings and office space (main work in year 1) and strategic state formation activities (years 2 and 3). ISWA: development of additional office space for the Ministry of Finance and the State Minister to the Presidency in Baidoa. SSP are simultaneously investing in buildings in Barawe. Kismayo: Design of office buildings - NIS was awarded the contract for design and they completed this work, but an independent assessment uncovered some concerns, so SSP have undertaken additional work to address this. SSP confirms ability to complete the work within 2016/17. In addition, strategic interventions supporting the state formation process and complementing the UNDP StEFS activities will be supported. / Assessment: The option fills critical gaps for two of the new states and complements, strongly complements other Somalia Stability Programme interventions. ISWA and Jubaland are the most advanced states in the Somalia state formation process. Having basic office space and facilities will serve as visible signs of state authority and crucially provide acceptable office facilities which will help attract and retain core staff. In terms of programme management and advisory inputs it is simple as the support would be transferred through the SSP and reporting would follow existing reporting mechanisms. This option would not significantly be able to influence and drive coordination with the UNDP StEFS programme and it would not drive future revenue collection. / Option 4, Only support Political Economy study of revenue, £ 0.3 million. / Description: This option would identify the politics and scope of revenue with an objective to support leaders to find ways to establish a settlement with the main elites and tax-payers. Focus would be on the ports and possibly other main revenue sources. The most likely places for this work to commence include Jubaland and ISWA, but in principle other states could also be interested. The work builds on earlier experiences from DFID's accountability programme. The option would be implemented through the Somalia Stability Programme. Having SSP as the implemented is based on lessons from the Accountability Programme – especially that the implementer needs to be strong enough to have access as well as technical/political analysis capacity. / Assessment: This option is a small, strategic, high-risk/high-return intervention. If successful, it would provide a major step forward for new states both in terms of viability and political settlement. Administratively and in terms of advisory engagement it is relatively simple as reporting and engagement is through the Somalia Stability Programme. The option would not drive coordination and engagement with the StEFS. Risks of failure would be high so careful management and political supportive engagement would be required. / Option 5, Combination of some or all of options 2-4. / Description: As per descriptions of options 2-4 above. / Assessment: The primary advantage of this option is that it maximises synergies between components. The fit and complementarity between all three options 2-4 is high. In terms of programme management and advisory inputs the workload would be manageable/minimal as engagement would be through two existing partners. Option 4 is high-risk and would require substantial advisory engagement, but equally the chances of success for option 4 is higher if implemented jointly with options 2 and 3. Key synergies are between the UNDP state formation project (option 2) and the the SSP work on office space (works both ways and boosts overall UK credibility/influence vis-à-vis the state formation process. Similarly, the highly political option 4 largely depends on having sufficient political capital to convince local leaders (state presidents) of the importance of understanding the nature of the “tax gap” and reaching a settlement. As already indicated, there are additional synergies with other DFID programmes (SSP, PREMIS) – and option 4 will be useful in its own right for wider technical and political objectives. This comprehensive option is also well-placed to influence and coordinate with external UN and USAID programmes.
Theory of Change, Prerequisites & Assumptions
Logic of Theory of Change: / The intervention seeks to support and consolidate the state formation process by providing a combination of physical infrastructure, basic capacity building, and reconciliation support. Finally, the analytical work on the political economy work on main power holders and potential tax payers (focused on the ports and possibly other key revenue areas) will help the political settlement as well as lay the foundation for future service delivery. / Outputs 1 and 2 focus on the short and medium term and output 3 focuses on the medium and long term. Specifically, output 1 will provide tangible outputs at the end of the intervention and the results of the initial capacity and reconciliation work under the StEFS programme will start to materialise. Output 3 is the beginning of a 3-5 year process, but if successful it will be at the very core of state formation. / The intervention covers key gaps in the existing support (based on analysis and consultation with UNDP (StEFS) and the SSP), which focuses on reconciliation, basic PFM support and the political levels of state formation. To maximise effectiveness, the intervention will be closely coordinated with other relevant programmes (DFID, UN and WB) as well as the wider political dialogue. Output 3 is particularly risky and hard to predict and will require careful handling. It may fail due to political resistance by local elites and even if the output is achieved, it may not succeed in generating additional revenue if political leaders are unwilling or unable to use the knowledge to reach a deal with local elites on taxation. At the same time, output 3 is at the core of making progress towards functional, sustainable states.

Commercial Case
The Appraisal case already sets out the planned project partners for the interventions under this business case. Value for money will be sought in each case on the basis of: economy (ensuring input costs, eg payment for advisers, are in line with comparator costs in other projects, construction costs are within comparable units costs etc); efficiency (maximising the outputs achieved through the inputs provided – including limiting the level of running costs paid to government partners that are not directly tied to outputs); and effectiveness (ensuring that the programmes as designed will achieve their desired outcomes by making sure they are feasible, relevant and timely). The following gives details on how performance will be maximised with each partner: / UNDP – StEFS / The main risk with this work is that UNDP fails to implement the programme in a strategic coordinated manner. . We will ensure that the MoU reflects this. / A project board including all contributing donors has been established, and any major shift in programming, will be put to the Board, including the UK, for approval. We will pay specific attention to willingness to coordinate with DFID’s PREMIS programme on PFM in new states. / DFID will use the on-going due diligence of UNDP (under JPLG) to inform needs for further commercial capability strengthening and/or safeguards. / Somalia Stability Programme / The SSP is procured by DFID through an open tender process (OJEU). A new fund manager/service provider is in the process of being found. Until October 2016 ASI remains the fund manager – after October a new service provider will take over. Since the start in 2013, the programme has built up substantial capability and experience in line with DFID’s best practices for commercial capability and practice. All of these practices will be applied to outputs 1 and 3. / For purposes of this business case, the main area to monitor and manage is the construction of office space for ISWA and Jubaland. The SSP has got strong procedures and safeguards related to construction work (see the SSP business case for further details).

Financial case
Intervention 2016/17 2017/18 2018/19 Total / Output 1, Support to State Formation through the Somalia Stability Programme £1,700,000 £1,000,000 £1,000,000 £3,700,000 / Output 2, support to UNDP’s StEFS programme on State Formation £1,000,000 £500,000 £500,000 £1,000,000 / Output 3, Political economy of revenue £300,000 £100,000 £1,100,000 £500,000 / Total £3,000,000 £1,600,000 £1,600,000 £6,200,000 / Outputs 1 and 3 will be managed through the SSP and use their management systems. / Output 2 will be managed through the UN-MPTF, the PSG structure (StEFS project board). / Costs that will be incurred directly by HMG outside of the CSSF spending entail the advisory and programme management inputs required to oversee the programmes. These include co-chairing the PSG1 sub working groups on elections and federalism into which some of this work will report. Output 3 may require additional high-level political engagement beyond the SSP secretariat by DFID and FCO. / The project does not envisage the provision of financial aid. However, the UN will provide smaller grants to a number of implementing partners. Any local consultants or advisory positions will be paid in line with salary scales agreed as part of the UN/World Bank salary harmonisation proposals. / The main fraud risks relate to: / Mishandling of advances provided by UNDP to implementing partners / Non-merit based recruitment of advisers and consultants / Diversion/over-charging on construction work / Mitigation measures for each will comprise: / Advances handled in accordance with UNDP requirements on cash transfers, including UN oversight of expenditure and full accounting for funds before any further support is disbursed / UNDP participation in all recruitment of advisers and consultants / Use of SSP procedures and oversight for construction work. / The on-going due diligence assessment of UNDP will be used to inform further mitigation work where appropriate (output 2).

Management Case
Outputs 1 and 3 will be delivered through the Somalia Stability Programme. Output 2 will be delivered through the through the UNDP Support to Emerging Federal States (StEFS) programme (part of a planned multi-year support: £2 million over 3 years - it is planned to bid for CSSF funding for this project again next year). The Governance and Security Team Leader will be the Senior Responsible Officer for this work. The strand will be overseen by the Strand Board, incl: CSSF Senior Project Manager (political), DFID Governance and Security Team Leader, Somalia Unit Head Political and Economic, 2nd Secretary Political, DFID Governance Adviser (responsible for StEFS). / Results framework / See attached logframe. / Management focus and monitoring against logframe: / Output 1: This output will be managed through the SSP. Monitoring, reporting and dialogue will be through the regular channels of communication. / Output 2: This output will be managed through UNDP. Reporting and dialogue will take places at a number of levels: / PSG 1 for high level reporting and coordination. / Working group and project board for more detailed project management and strategy/policy issues. / Bilateral engagement with the project team and UNDP. DFID lead adviser and TL are already engaging with the project team on specific issues (especially coordination with PREMIS, capacity development issues and UNDP strategic steer) / Informal engagement, incl. with other donor support (especially USAID programmes), the UN and UNDP’s StEFS project. / Output 3: This output will be managed through SSP. Monitoring, reporting and dialogue will be through the regular channels of communication. However, given the strategic nature and high risks, the lead adviser on state formation and the SRO will work closely with the implementing partner to ensure appropriate risk management and coordination with political levels where/when needed. / Risks: / The SRO will be overall responsible for risk management. Core risk management channels will be through the SSP programme management and the UNDP StEFS project board – both of which are managed by DFID Governance and Security team members. There are a number of risks. These relate to: / Political and security risks – relates to all engagement in Somalia. / Delivery risk 1 –UNDP/StEFS unable to provide clear strategic steer and activities on state formation. / Delivery risk 2 Poor coordination with other programmes: This risk relates particularly to output 2, where the UNDP programme tends to be over-ambitious in scope and not always recognise its own limitations and comparative advantages. Particular risks related to DFID PREMIS programme, but also with SSP. / Delivery risk 3, resistance to analytical work on revenue and local elites - experiences from DFID Accountability Programme indicate that undertaking the proposed political economy assessments will attract substantial resistance (output 3) / Delivery risk 4: Fiduciary risks. This risks covers all three proposed outputs, but the risks related to output 1 are particularly high due to the large amounts and challenges in monitoring procurement and construction. / Overall oversight of these interventions will be provided by the CSSF strand board. Third party monitoring for all projects will be provided through IBTCI, DFID’s third party monitor – for this project third-party monitoring is particularly relevant for outputs 1 and 2. IBTCI will provide safeguards at input and activity level. The table below summarises the risks and mitigation measures: / Key risks Risk level Mitigating measures Residual risk / Generic political and security risks H Political dialogue, comprehensive HMG and international community engagement, DFID and other donor support. H / UNDP/StEFS unable to provide clear strategic steer and activities on state formation. H Close oversight and engagement through the PSG/project board structure, supported by bilateral lead adviser engagement and SRO dialogue with UNDP Country Director. MoU structured to incentivise better performance. M / StEFS poor coordination with other programmes M Close oversight and engagement through the PSG/project board structure, supported by bilateral lead adviser engagement and SRO dialogue with UNDP Country Director. L / Resistance to analytical work on revenue and local elites. H Close bilateral dialogue through SSP and at political level. Recognition that this output may delay or have to be postponed or abandoned. H / Fiduciary risks. This risks covers all three proposed outputs, but the risks related to output 1 (construction) H Regular SSP monitoring, third party monitoring. M / UN ability to achieve deliverables H Post Implementation Review to be conducted after each year. M