ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Scaling Up Family Planning Services in Zambia Project
Country or region targeted	Zambia
Type of cost extension (if applicable)	Costed Project Extension
Original project budget	£11,913,792
Original project start and end dates	01/03/2011- Aries start date. / 01/03/2012– Contract start date. / End date - 28/04/2016
Cost extension value (if applicable)	£10,000,000
New project end date (if applicable)	31/03/2019
Business Case Quest Document No.	3717521

INFORMATION
What is the project’s purpose?
The Scaling Up Family Planning Services in Zambia (SUFP) project purpose is to increase the use of family planning methods in Zambia through the provision of family planning services and products to women and girls. This will be achieved through: / Expanded availability of choice of family planning methods; / Increased access to family planning services for under-served areas and populations; / Increased community support to family planning; and / Increased public sector capacity to provide comprehensive family planning services.
What is the objective of the cost extension or other changes?
The three year costed extension to the SUFP project will enable the adaptation of the successful SUFP model to enable the complete transition to full government management of the programme at all levels, based on lessons learned to date. Extending the project will maintain the momentum in delivering family planning (FP) results in underserved areas, sharpen the focus on adolescent reproductive health (ARH) given Zambia’s alarmingly high rates of early pregnancy and marriage; and leverage the existing partnerships between our current implementing partners, the Ministry of Health and stakeholders at national, provincial and district levels towards attainment of Zambia’s FP 2020 targets, set at the London Summit in 2012. / The project to date has consistently demonstrated success in meeting its objectives with 295,104 additional women and girls using modern FP methods (147% above the programme’s target of 200,000); generating 578,241 total Couple Years of Protection. Access to FP methods has increased through community structures with over 2,500 Safe Motherhood Action Groups (SMAGs) members and community leaders trained as Community-Based Distributors (CBDs) to generate demand and provide FP services. Public sector capacity to deliver services increased with 752 health workers and 65 FP mentors trained to provide comprehensive FP services, including long-acting and reversible contraceptives (LARCs) through health facilities and a greatly expanded outreach programme in target districts. Annual review scores of at least an A reflect the overall success of the programme and the programme is on track to again score an A+ in the 2016 project review due in May 2016. / VfM / Overall, the SUFP project to date has represented good value for money. Within budget, it surpassed many of the key output targets, some significantly, such as the rapid scale up in demand for modern family planning. Compared to economy benchmarks, the project fared favourably on key costs such as remuneration costs of technical assistance that made up more than half the total project cost. Various measures of efficiency over the project lifecycle are very good, and these include the marginal cost of training family planning resources to be used in supporting the system. Assessed against cost effectiveness, SUFP is highly cost effective. The final cost per disability adjusted life year (DALY) averted was £67/DALY against a projected £116/DALY averted in the original business case, making this a highly cost effective intervention[1]. / Although the SUFP project has been instrumental in turning around outcomes for family planning and reproductive health in Zambia, a mixed picture prevails with regards sustainability. Positively, the project trained and used MoH staff, health facilities and outreach structures and embedded capacity and ‘know how’ within government systems. The project however moderately failed to meet its target of increasing the public sector’s capacity to provide comprehensive family planning services, a component that constitutes 25% of the project. The MoH has expressed the need for the SUFP project to support the government to improve on its coordination and management of district-level family planning programmes, and better understand how it can enhance its own programming from a national perspective. It is also evident that irregular and insufficient government resources mean that interventions cannot continue at their current level of activity without continued external assistance by SUFP or another external donor. Currently donor funding for Family Planning is limited to USAID operations in three of the 10 provinces in Zambia / The 2013/14 DHS records progress in total fertility, which dropped from 6.2 to 5.3 between 2007 and 2013/14[2], and an increase in the demand for and uptake of modern FP methods in rural areas. Over the same period, the contraceptive prevalence rate rose from 32.7% to 45%, and the unmet need for FP among married women (or women in a union) declined from 27% to 21%[3]. On the current trajectory, the Zambia FP 2020 target of a contraceptive prevalence rate of 58% is within sight. / Based on the above, DFID Zambia responded positively to a DFID headquarters call for additional FP results as part of the bilateral aid review (BAR) process for the fiscal year 2016/17 onwards and chose to deliver this result through the SUFP project for high impact at good value for money.
What is the additional and total support the UK will provide?
The UK will provide an additional £10,000,000 to the Scaling Up Access to Family Planning in Zambia project (SUFP) over a further 3 year period from 1 March 2016 to February 2019. The total DFID contribution to SUFP will therefore increase to £20,913,792 over 7 years, from 2012 to 2019.
What are the expected results?
The impact will be improved maternal health in Zambia. By 2019 the project will contribute to: / Reducing maternal mortality from 395/100,000 to 300/100,000. / Increasing the contraceptive prevalence rate to 58% and meet the FP 2020 target. / The outcome will be increased access and equitable use of quality family planning services in Zambia. / This will be achieved by: / Expanding the choice of family planning methods available, especially long term reversible methods. / Increasing demand and access to family planning services for adolescents and community based family planning services in under-served areas and populations. / Increasing capacity of government health facilities to provide quality comprehensive family planning services. / Increasing capacity of government systems to provide effective oversight, planning, procurement and advocate for sustained financing of family planning interventions. / Project results will include the following / An additional 495,000 women and girls over the life of the project. This includes 215,000 new female users of family planning methods under SUFP II. / A national health financing strategy that articulates sustainable financing for reproductive health commodities / Reduced inequalities in access to family planning (rural versus urban) / An estimated 2,193 maternal deaths and 300,000 unintended pregnancies could be prevented by 2020. Of this, 202,714 pregnancies and 1,149 maternal deaths will be averted[4] through SUFP II.
What is the approach to implementation?
The second phase of Scaling Up Family Planning project (SUFP II) will be aimed at contributing to the implementation Zambia’s 8 year Family Planning Scale Up Plan (2013-2020) and attainment of the targets therein. This will be done by embedding the SUFP model in the Ministry of Health (MoH) systems, adapting the model as necessary, and the provision of tools and support to enable the expansion of the SUFP model to non performing provinces and their districts. The project will technically work through government systems to ensure capacity strengthening and full government ownership. The end result will be the institutionalization of the SUFP model and sustainability of FP interventions within the public health system. / The SUFP II represents a major shift in focus towards capacity building and systems strengthening. This approach will strengthen the governance systems in the Ministry of Health for effective health care service provision and enhance value for money. / Under SUFP II we intend to continue work with UNFPA on increasing availability of FP commodities in Zambia and strengthening of capacity to procure and achieve good value for money through procurement. In addition, we are currently exploring two options in terms of technical support and delivery of SUFP II, these are; / Extension of the current contract with Abt Associate Inc. / The SUFP I was implemented by a consortium led by Abt Associates with procurement of commodities done by UNFPA. Abt Associates and UNFPA have a strong track record of delivering FP programmes that specifically target women and girls, and are versed in monitoring results in ways that help us understand how best to get the most out of all our interventions for women and girls. / Abt Associates is therefore well positioned to support DFID in the delivery of the SUFP II project that will help Zambia achieve its Family Planning 2020 commitments to increase access to family planning and continue to contribute to overall DFID manifesto targets on family planning and maternal health. / A tender waiver will therefore be requested to allow for the costed extension of the current contract with Abt Associates and subjected for formal approval. Technical and commercial proposals have been submitted by Abt Associates and are currently under review in support of a tender waiver application. / Using the OJEU process / If the tender waiver is not approved, DFID Zambia will go to the market and tender through a competitive process to procure a service provider and two routes will be considered; restricted and open tendering. / The challenge with the OJEU process is that there will be the need to develop a fresh terms of reference and initiate a new procurement process for a reproductive health service provider. The implications of this course of action are; / Heavy administrative costs associated with implementation of closure processes such as project completion review, audits and handovers conducted; and the setting up of a new project. Overall, the process would be extremely labour intensive and will not represent good value for money. / Going back to the market would entail a 6 month timeframe for contracting a new service provider and a further 2-3 months to set up operations, establish networks and relationships. The timeframe would remain the same even if the existing contractor is the successful bidder. / Extension of the existing contract therefore is a better option and represents good value for money to deliver the SUFP II. Contracting through the OJEU process would mean previous investments would be largely lost, expected results would not begin to materialize until well into the second year of the programme and the risk of poor performance against the agreed timeframe would be increased. / The approach to implementation proposed is as follows; / National Level: The SUFP II will work closely with the leadership of the Ministry of Health and other health care institutions and partners to building both technical and policy capacity for overall and effective management, coordination and implementation of FP interventions aligned with the Government of Zambia’s 8-year Family Planning Strategy (2012-2020). The approach will ensure the Ministry of Health is fully capable of effectively managing the implementation and oversight of FP programmes country-wide. The project will: / Facilitate capacity strengthening including for procurement and supply chain, to guide scale and reach of FP programmes, support identification of challenges and addressing management and policy weaknesses for effective implementation of FP initiatives country-wide but with a particular focus on under-served communities. / Strengthen coordination and joint workings between the Mother and Childhealth department of the MoH and other MoH departments including Procurement, Research and Quality Assurance, Financial management, Human Resource for health and Monitoring and Evaluation for integrated approaches and effective delivery of FP services. / Work closely with partners and the government to support the technical working groups and ensure monitoring of progress and provision of resources at national level is sustained. / Improve multisectoral coordination through support to the Ministry of Health to engage and coordinate with other stakeholder ministries including the Ministries of Finance, Community Development, Gender and Chiefs and Traditional Affairs. / Part of the aim of the implementation at national level is to strategically ensure the government responds, in a sustainable way, to increasing demand of FP services by communities. / Provincial level: SUFP II will work with Provincial Medical Offices (PMOs) to strengthen the capacity for planning, oversight and directing of resources in the province in a sustainable and prudent manner for quality delivery of FP services across all districts in the province with particular attention to underserved districts. / The SUFP II team will produce implementation guidelines/plans and develop organizational frameworks and district scale-up plans aimed at supporting capacity building in target provinces and districts for planning, monitoring and oversight of FP services within an integrated public health system. The project’s monitoring and evaluation (M&E) plan and logframe will use the Ministry of Health data collection systems, but also support its improvements. / District and Community level: At district level, SUFP II will support District Medical Offices (DMOs) to adapt and implement FP activities to context. Activities will include management capacity strengthening of district level structures and systems as well as strengthening the linkages and coordination between community-based FP interventions, health facilities and the district management systems. / The model will include trainings and strengthening of the mentoring programme for healthcare providers in comprehensive FP services established under the first phase of SUFP; jump starting mobilization of communities and opinion leaders in target catchment areas through scaling up the successful SUFP camping approach modified to context; and strengthen inventory management to meet increasing demand for FP products. / Collaboration with other Programmes: SUFP II will collaborate with other system strengthening and capacity building programmes such as the Systems for Better Health (SBH), funded by the United States Agency for International Development (USAID) and the Swedish Embassy’s health systems strengthening for Reproductive, Maternal, Newborn, Adolescent and Childhealth programme in ensuring provinces and districts improve their capacity to implement the SUFP II model. In addition, the links to DFID Zambia’s Adolescent Girls Empowerment Programme (AGEP) established during the first phase of SUFP will be maintained for the mutual benefit of both projects. / Gender Equality Act / Gendered power relations at all levels, particularly in rural poor settings and cultural norms further increase inequalities between men and women and prohibit access to FP for women and young girls in particular. Among married women aged 15-49, only 64.3% with primary or no education made decisions for their own health, compared to 82% with secondary level education; only 19% of women with no education could decide on how many children to have, a stark contrast to 83% for women with secondary education[[1]]. Although less evident in urban centres, rural Zambia is largely conservative and traditional. Young people, especially girls cannot always acquire family planning products without the fear of being stigmatised[[2]]. / The SUFP project’s focus on girls resulted in increasing use of FP methods by young girls between 15 to 19 years over the first four years of the project to reach 24% of the total number of additional users of FP methods. SUFP II will continue to work to empower women and girls to exert informed choice and control over their reproductive health by increasing access to health services in ways that address the main barriers to healthcare and FP services in particular. / Family Planning services are delivered free of charge through the public health system (at health facilities and through public health outreach services) to meet the needs of the poorest and most underserved women and adolescent girls in Zambia. Working through local health services including integrated health outreach services delivers FP within the context of family health and promotes uptake by ensuring that FP and other health needs of women are conveniently addressed. Through the first phase of SUFP, an integrated model of couples based HIV/AIDS counselling and testing and provision of FP services was successfully implemented, increasing access to both sets of services. This integration of HIV/AIDS and FP service model will continue to be promoted under SUFP II. / The SUFP model specifically targets communities, particularly the poorest and most at risk[[3]] for increased impact on women and girls by expanding access to services and addressing social and cultural barriers to FP, including male attitudes. In communities, SUFP will continue to increase action and demand for FP services through working with community based distributors, established community groups and active engagement of opinion leaders. At health facilities, SUFP II will continue work to strengthen health facilities through ensuring that FP services are adolescent friendly by establishing standards for this, promoting improvements in staff/client engagement, ensuring well trained staff and linking those to community action and mentorship and supportive supervision processes. SUFP II’s work in improving governance and management of FP activities nationally and at provincial level will include ensuring that interventions continue to be informed by analysis of the existing situation for women and girls, their involvement in community decision-making and monitoring the prevailing social norms that influence the health of women and girls and their rights. SUFP will leverage the AGEP programme and other youth empowerment projects as necessary to increase address barriers to access to FP products and services by young girls.
Describe any key changes to the original business case?
The project extension, SUFP II, stays true to the objectives of the original business case in its aim of decreasing maternal mortality through the scaling up FP services and use in Zambia. It however supports additional activities that focus on transforming the SUFP model from a donor funded intervention to a government led programme that is fully integrated within the public health system and coordinated at a national level. In contrast to the original business case, project targets are now directed towards sustained delivery of FP services nationally for an additional 215,000 users of modern FP methods through UK support and attainment of Zambia’s FP2020 targets. / To achieve this objective, the following amendments to the project are proposed: / Support for Increased National Oversight of FP Activities: In addition to the existing support by SUFP to the FP and Adolescent health technical working group, SUFP II will now expand its remit to work directly with the Maternal and Childhealth director and her team to strengthen their leadership and management of the 8 Year Family Planning Plan 2013-2020. / Increased Focus on Adolescents: SUFP sought to improve FP services for adolescents, particularly young girls, through clinical training to ensure that health facilities provide adolescent friendly services, community outreach programs and peer education. However, a 2015 gatekeeper analysis suggested that deep-seated cultural barriers continue to hinder the provision of FP/reproductive health (RH) information services to adolescents. Work will continue through SUFP II to analyse the legal environment for adolescent reproductive services, including interpretation of existing laws and policies. SUFP II will work to strengthen the policy environment and create an enabling environment for adolescents living in traditional and remote communities through advocacy and the integration of promising approaches into the SUFP model. This will include strengthening collaboration between the Ministry of Community Development and Ministry of Education. / Strengthening Community-based FP Services: Increasing the proximity of service providers and commodities to potential users was one of the strengths of the SUFP model. In March 2016, MoH responded to intensive advocacy from the FP technical working group and formally approved the delivery of injectable contraceptives through community based distributors. SUFP II will therefore work to operationalize and monitor this approach to increase access of underserved and rural communities to FP services. The project will leverage the recently created MoH cadre of Community Health Assistants (CHA) for this purpose. / Strengthening Government capacity to ensure availability of FP Commodities: The project will intensify technical support to strengthen procurement processes of the Ministry of Health and Medical Stores Limited (MSL). This will now include work with procurement units to build capacity in financial and contract management and enable the government of Zambia achieve greater value for money through procurement of FP products. UNFPA will support this process and facilitate GRZ direct access to manufacturers of competitively priced FP commodities negotiated through the Global Reproductive Health Securities programme, co-funded by DFID. / Implementation of Studies to Improve Programming and Track Results: SUFP II will undertake studies and operational research as appropriate to support the refining of the SUFP model for integration through the public health system and track progress towards the FP 2020 targets. Underperforming provinces will be prioritized for intensive support. / Risks / The project has consistently been rated as low risk despite the associated risks associated with implementation of family planning activities in Zambia. Although project risks will increase under SUFP II with greater dependence on government systems for project implementation, mitigation actions have been incorporated into project activities for SUFP II and will build on lessons learnt through the first four years of programming. The overall risk rating for the project is therefore Moderate when judged against the risk categories of context, delivery, operational, fiduciary, safeguarding and reputational risks. / The current upward FP trajectory with the contraceptive prevalence rate rising from 32.7% to 45% in 2014[5] suggests that Zambia FP 2020 target of a contraceptive prevalence rate of 58% is within sight. DFID will continue to implement through tried and tested partners and contribute to meeting the gaps for FP commodities and strengthening FP supply chain. This coupled with the strong political will to address the unmet need for family planning and the increased focus of SUFP II on national oversight and provinces underperforming for FP mitigate against the major risks to the project. In addition, donor support to overall health systems strengthening in Zambia focused on reproductive, maternal, newborn and childhealth has increased with additional funding from USAID, the Swedish Embassy, UNFPA and the World Bank and will provide a strengthened platform for FP interventions. / Assessment of top 5 risks to project delivery for SUFP II / Impact / Insignificant Minor Moderate Major Severe / Likelihood Almost Certain / Likely / Possible Weaknesses in supply chain for commodities to district and facility level / Project fails to reach adolescent girls, especially in rural areas / GRZ fails to provide adequate resources for sustainability and fails to prioritise Family Planning resulting in loss of project momentum / Unlikely Community opposition from traditional/religious leaders and men to family planning affects uptake of services / Rare
[1] Zambia 2011-2015 lives saved tool (LiST) analysis: figures from business case and performance are excluding procurement costs.
[2] ZDHS 2007, and ZDHS 2013/14
[3] ibid.
[4] MSI Impact Calculator: 2009
[[1]] Central Statistical Office, Ministry of Health. Zambia Demographic and Health Survey. 2013-14.
[[2]] UNFPA Zambia. 2013. Prioritizing Reproductive Health Issues for Adolescents and Youth. http://countryoffice.unfpa.org/zambia/2013/01/03/6041/prioritizing_reproductive_health_issues_for_adolescents_and_youth/
[[3]] Ministry of Health, Zambia. Roadmap for Accelerating the Attainment of the MDGs related to MNCH in Zambia. 2011.
[5] ZDHS 2007 & 2014