Annual Review - Summary Sheet

Title: English In Action
Programme Value: £50,000,000.00		Review Date: 15th April 2016
Programme Code: 107480	Start Date: May 2008	End Date: March 2017

Summary of Programme Performance
Year	2009	2010	2011	2012	2013	2014	2015	2016
Programme Score	2		2	A+	A+	A+	A+	A+
Risk Rating	Low		Low	Medium	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The EIA programme continues to achieve innovative and quality teacher education at scale, exceeding targets in terms of numbers of teachers trained and pupils reached. The programme is now institutionalising teacher training methodology into Government systems. It also delivers training in different parts of the country including socio-economically disadvantaged regions.

Recommendations made during the last annual review 2015 placed a particular emphasis on the need for the project to improve procedures for the institutionalisation and sustainability of project activities. This has been done with a view to better ensuring uptake and integration of EIA-based approaches and materials within mainstream education sector programmes and practices beyond the project lifetime, both at central and regional levels. As part of this, EIA has developed strategy documents for Advocacy and Institutionalisation & Sustainability covering the final 18 months of delivery, and restructured the project’s internal mechanisms in order to focus on identified I&S priorities. In addition, they have engaged with relevant GoB departments and bodies, securing both stakeholder involvement in and awareness of EIA initiatives, and EIA’s participation in the design of the two sector programmes in primary and secondary education. To ensure evidence based policy influencing for institutionalisation the project has also commenced a quasi-experimental study focussing in particular on analysis of teachers’ and students’ classroom practices and English language competence, comparing EIA treatment schools with control schools, before and after treatment schools participate in EIA. Two noteworthy examples of institutionalisation include: uploading EIA teacher training materials (audio, video and print) to the website of the national curriculum and textbook board (NCTB); and integration of EIA teacher professional development methods in the primary teachers’ guides for English textbook.

Summary of recommendations for the next year

School component
Prioritise further development of regional programme delivery mechanisms and Institutionalisation and Sustainability (I&S) for secondary education, including undertaking an analysis of I&S approaches used within Primary sector with a view to identify those that are most successful and adapt those to support I&S activities within the secondary sector.

Continue to work with Directorate of Secondary and Higher Education (DSHE) and other central GoB bodies to facilitate awareness and inclusion of EIA approaches into strategic planning and implementation of secondary teacher training;

Identify necessary capacity development requirements to prepare central and regional secondary stakeholders for the institutionalisation and sustainability of EIA within the sector.

Research and monitoring
Continue the publication and dissemination of evidence-based research briefings, particularly those aimed at local level practitioners and designed to support institutionalisation of administrative and support mechanisms.

Explore approaches to establishing the activities and outputs of the ‘Teachers’ Voice’ initiative as a feature within the GoB educational structure, thereby contributing to the institutionalisation and sustainability of quality research, monitoring and evaluation within the education system. (to note here that considering the brief remaining period of the project only a feasibility of approaches can be expected)

Institutionalisation
Further refine ToRs of the teams under the revised organogram to include team objectives, specific timeframe of activities, and QA mechanisms.

The additional funds secured under the recent 12-month extension to be used to further support initiatives associated with the institutionalisation and sustainability of the project, with a particular focus on secondary education.

Continue to enhance current Advocacy and I&S strategy documents, especially in light of the cost and time extension, by including: schedules for specific activities; QA mechanisms for measuring or assessing the impact of particular advocacy inputs; further descriptive detail of specific activities; allocation of responsibility for delivery of specific activities to current I&S Teams or to existing units within EIA.

Value for Money
EIA develop a plan to implement selected VfM enhancements, implement these over the first 3 to 6 months of the next review period and build capacity to monitor these so that performance can be assessed at the next review.

A. Introduction and Context

Outline of the programme
English in Action works to improve levels of English language with the ultimate aim to aid economic growth. This has been implemented through two main components - a school based programme aimed at bringing about change in English teaching and learning in primary and secondary schools and an adult (15+) learning programme that uses electronic and print media e.g. television, website, mobile and newspaper to teach communicative English. The adult learning component i.e. output 2 have closed in 2015. In order to improve the quality of student learning in English, teachers have to find ways to improve the teaching and learning practices in their classrooms. EIA is designed to help teachers do this through a one-year programme of teacher professional development. EiA is a £50 million programme being implemented over nine years (2008-2017). However, during the review period the project received the approval of 12 month time and cost extension. It is a discrete project under a multi donor funded and government led sector-wide primary education programme i.e. Third Primary Education Development Programme (PEDP3).
Expected Results / EIA expects to increase social and economic inclusion for more than 25 million Bangladeshis by developing English language skills for school pupils and adult learners over the lifetime of the project. The project also expects to contribute to the economic growth of Bangladesh by providing English language as a tool for better access to the world economy. EIA has taken this forward through the development and delivery of inclusive national programmes. The beneficiaries are adults in urban and rural communities, teachers of English, and school-aged children. Progressive and innovative approaches to teaching and learning ensure that all beneficiaries have the opportunity to develop English as a practical skill. / By the end of the final year of the programme the following logframe outcomes are expected to be delivered: / Increase in the proficiency in communicative English among the population of Bangladesh measured objectively against recognised international frameworks. / Increase in employer satisfaction (with employees’ communicative English). / Increase in motivation for learning and using English among the population of Bangladesh / Increase in use of English language media products. / Bangladesh Context / English in Action was designed in response to a request from the Government of Bangladesh: English language skills are in short supply. This is as a result of two main factors - poor quality English teaching in schools and limited access to high quality English learning materials for students and adults. Few people under fifty are confident, fluent English speakers, and English is the most commonly failed examination subject at the secondary certificate level. Lack of English language skills is regarded as a constraint to economic development. For example, employers state that job applicants and employees lack English language skills necessary to work effectively. A pre-appraisal mission recommended that the problem be addressed at scale, through a project that would have substantial reach and impact. Previous shorter term, smaller scale interventions were not fully successful and results were not sustained. Reasons for this included the lack of scale, the lack of extended timeframes, and an absence of focus on adult learners. / The context has not changed significantly and the original activities and assumptions are still appropriate. Updated research carried out for EIA by Euromonitor (2013) found that candidates with good English skills have a 30-50% higher chance of being employed in the formal sector and were likely to receive an income premium of 25-30% compared to candidates without good English skills.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Indicator	Milestone	Progress
1a. Increases in English language competence (ELC) among the population of Bangladesh (teachers & students) at Trinity GESE level[1]:	Milestone 2016 will report on pre-test results of quasi-experimental (QE) study	Primary students / 43% achieved GESE level 1 or above / 10% achieved GESE level 2 or above / Secondary students: / 37% achieved GESE level 2 or above / 22% achieved GESE level 3 or above
1b: Increases in ELC among the population of Bangladesh (adults)	N/a (no milestone and planned assessment this year)	N/a
2: Employer satisfaction (with applicants’ / employees’ communicative English)	Applicants not having necessary EL skills: 40% / Employees having necessary EL skills: 76%	Applicants not having necessary EL skills: 28.3% / Employees having necessary EL skills: 89.3%
3: Motivation for learning and using English among school population of Bangladesh	N/a	N/a
4: Use of English Language news & media	N/a	N/a
[1] GESE: Trinity Grade Scale is developed based on the common European framework of language testing, developed to assess students’ English Language ability objectively. It is a 12-grade scale. Attainment levels for the first four grades on the scale is as follows: - Grade 1 – requires knowledge of greetings and some basic personal information - Grade 2 – speakers can offer and respond to short, simple questions, requests and statements relating to personal details and situations - Grade 3 – speakers can exchange basic everyday information, asking and answering questions using simple sentence patterns - Grade 4 – speakers can talk about a prepared topic, asking and answering questions about it

In accordance with logframe design, English language competence (ELC) testing of students in 2015-2016 recorded pre-test results associated with the Quasi-Experimental (QE) study, with particular focus on performance at two criterion grades for primary (students at or above grade 1 and at or above grade 2) and two criterion grades for secondary (students at or above grade 2 and at or above grade 3) on the Trinity GESE scale.
The quasi experimental research will focus in particular on analysis of teachers’ and students’ classroom practices and English language competence, comparing EIA treatment schools with control schools, before and after treatment schools participate in EIA.

The results of the Employer Satisfaction survey indicate an increase in positive outcomes in this indicator area for the review period, including when compared with Annual Review (AR) 2015 figures. However, it is important to note that there has been no analysis of the specific English language skills required by employers in various sectors, and so available data is based on purely on employers’ perceptions. As also noted in AR 2015, these results may be partly influenced by changing perceptions of English language usage and skills in Bangladesh, possibly as a result of the popularity of various BBC Janala media broadcasts. For instance, as English language competence is traditionally associated with both high status and high levels of education, there may be a greater general appreciation, including among employers, of English as a functional, context-specific set of skills attainable by the general population. In keeping with this, 27% of employers surveyed in 2015-2016 reported that they would employ an English-speaker over a non-English speaker.

Overall output score and description
The overall output score is A+. Results have exceeded targets in all outputs. Output 2 has come to an end so there are no further targets.

	2016 Milestone	Achievement
OUTPUT 1 (Primary)		A++
O1a: Reach	Teachers: 17,500 / students: 1.3m	Target exceeded / 22,974 teachers / 1.7m students
O1b: Implementation	Milestone 2016 will report on pre-test results of quasi-experimental (QE) study	23% student talk in a lesson / 87% of that talk is in English
OUTPUT 2 (Adult Learning)
O2a: Reach	N/a	N/a
O2b: Perception	N/a	N/a
OUTPUT 3 (Secondary)		A+
O3a: Reach	Teachers: 7,000 / students: 2.91m	Target exceeded / 7,471 teachers / 3.06m students
O3b: Implementation	Milestone 2016 will report on pre-test results of quasi-experimental (QE) study	18% student talk in a lesson / 78% of that talk is in English
OUTPUT 4 (RME)		A+
O4a: Knowledge products	4 research reports; 3 research briefs;	Achieved / 4 research reports; 4 research briefs;
O4b: Research dissemination	4 conferences	Target exceeded / 13 conferences; 4 papers; 4 book chapters
OUTPUT 5 (I&S)		A+
O5a: Strategic partnerships	Education partnerships: 3 or more / Existing media partnerships: continue	Target exceeded / 5 / Continued
O5b: Policy seminars	2	Achieved / 2

Key lessons
Evidence cited in earlier Annual Reviews suggests that EIA’s school-based, peer-supported approach, supplemented with enabling technology providing offline audio-visual materials for professional development and classroom use, is capable of improving classroom practices at large scale. Further, that improved classroom practices among target teachers have been consistently translated into improved learning outcomes for students at school level.

In the interests of Institutionalisation and Sustainability (I&S), EIA’s dialogue with government policymakers is focussing on how key elements of effective teacher development, as exemplified by EIA, can be incorporated within government programmes in order to maintain and build upon improvements in the quality and equity of classroom practice and learning outcomes. Since AR 2015, significant achievements have been made in securing GoB support for and engagement with EIA as a result of the project’s multi-level advocacy strategy. Evidence of the impact of this approach includes GoB’s pro-active request to DFID for a 12-month cost and time extension that will provide an opportunity to strengthen the integration of EIA practices and materials, particularly in relation to teacher professional development, into education sector policy and practice at both central and regional levels.

Has the logframe been updated since the last review? Yes
Based to the 2015 annual review recommendations, specific indicators within the logframe were updated during reporting period as follows:
Indicator	Change	Function of change
Outcome Indicator OM1a: / Increases in proficiency in communicative English among the population of Bangladesh (teachers & students)	Changed milestones for 2017 / Measurement of teacher English language proficiency (ELP) is ‘not applicable’ for milestone 2016 and target 2017	EIA evidence has shown over the years no obvious correlation between teacher and student ELP / International evidence confirms EIA evidence / Measuring teacher classroom use of English is not possible due fund constraint
Output 4 Statement: / Increased information available around improving English language competency	Amended output statement to: ‘Increased knowledge available around improving English language competency and teacher practice’	Rewording provides clearer expression of project output
Output 5 Statement: / Strengthened capability of key organisations and professionals in the education and media sectors to adopt EiA approaches	Amended output statement to: / ‘Collaboration with key organisations and professionals in the education and media sectors to adopt EiA approaches’	Rewording provides clearer expression of project output
Output Indicator O5a: / Number and extent of strategic partnerships with key organisations in education and EL media sectors; and number of sector professionals (broadcast and ELT) taking part in ELT media capacity building initiatives	Added to source / ‘DFID PSC quarterly reports’	Adds data source for extent of strategic partnerships
Outcome Indicator OM1a: / Increases in proficiency in communicative English among the population of Bangladesh (teachers & students) / Output Indicator O1b: / Implementation: The numbers of teachers using Communicative Language Teaching (CLT) approaches in their classroom practice / Output Indicator O3b: / Implementation: The numbers of teachers using Communicative Language Teaching (CLT) approaches in their classroom practice	Amended the milestones for 2016 and 2017 / Include note that ‘milestone 2016’ is to report on pre-test results of quasi-experimental (QE) study’ and that ‘target 2017’ is to report on post-test results of quasi-experimental study	EIA resources enable two evaluation studies to take place in Phase IV. Originally, study was planned in 2015 and in 2016 which would have assessed improvement against baseline collected in 2009. / Instead, drawing on 2014 AR feedback, a QE study (involving pre-test evaluation and post-test evaluation) has been designed in consultation with DFID. This will provide robust evidence of improvement between post-test, pre-test, intervention and control group. / The pre-test study in 2015 will be reported for AR in 2016 and post-test in 2016 will be reported in late 2016 / early 2017.

Impact Weightings
AR2014 recommended reviewing the impact weighting to reflect the end of component Output 2 in this final phase. The current impact weighting across the final phase of the project is as follows:

	Previous	Now
Output 1	25%	25%
Output 2	25%	0%
Output 3	25%	25%
Output 4	10%	25%
Output 5	15%	25%

## C: DETAILED OUTPUT SCORING

Output Title	Greater access to and use of EIA English classroom methods for primary school teachers and students
Output number per LF	1	Output Score	A++
Risk:	Minor	Impact weighting (%):	25%
Risk revised since last AR?	New criteria applied	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach / The cumulative numbers of teachers and pupils participating in English in Actions primary intervention	Primary teachers / 17,500 (50%/50% M/F) / Primary pupils / 1.3m (49%/51% M/F)	Substantially Exceeded Target / Primary teachers / 22,974 (44%/56% M/F) / Primary pupils / 1.7m (49%/51% M/F)
Practice / The number of teachers incorporating EIA approaches in their classroom practice.	Milestone 2016 will report on pre-test results of quasi-experimental (QE) study.	23% of student talk in a lesson / 87% of that talk is in English

Key Points
EIA is designed to enable teachers to improve the teaching and learning practices in their classrooms, through a one-year programme of teacher professional development.

During the review period, the project substantially exceeded the achievement of targets on coverage of students and teachers. Despite increase in scale of teacher training during 2015/16, similar levels of progress are being shown with previous cohorts, both in terms of teacher activities and their impact on classroom activities. Classroom use of pair and group work at the conclusion of the initial teacher development meeting for this cohort are on track to reach the same level of previous cohort. Among students, 45% of observed classes used English for 50% of the time. This suggests the current cohort is on-track to achieve similar levels of classroom change and English language competence as seen on previous cohorts despite a reduced level of support.

Previous annual reviews have commented on the lack of a counterfactual or a quasi-experimental design for attribution of English language learning skills to the EIA intervention. In response, a quasi-experimental research tool has been developed, in consultation with DFID, covering students and Teacher’s Language attainment and also classroom Practice at both primary and secondary schools. This research is beginning to offer initial insight into EIA’s attributive role in these areas, and it has contributed the pre-test data presented during this Annual Review. The quasi-experimental study is discussed further in this report under Output 4.

Overall, the number of students reached is well above the milestone for the review period. This is particularly noteworthy as the project has trebled its coverage between 2014/15 and 2015/16. The coverage of students and teachers continues to maintain good gender balance on participation.

The successful achievement of scale-up can be attributed to a large extent to the further extension of decentralised approaches adopted at the level of sub-districts, including the engagement of local education authorities as delivery and support frameworks instead of the project. This has been validated through a field visit that demonstrated that EIA regional teams have developed a strong relationship with local education officials and teachers which assists a great deal with training plan and implementation. Detailed findings from the field visit are attached as Annex A.
During the review period here were 8 bi-monthly Cluster Meetings conducted for each Teachers’ Groups of 20-30 teachers led by EIA-recruited Teacher Facilitators - experienced practising school teachers who guide the teachers through the materials and facilitate practice and reflection on new techniques. During Phase IV, there are 4 such meetings scheduled across the year for each teachers’ group. For the primary 2016 cohort, these practice and reflection sessions will take place through government mechanisms.
This strategy of integrating EIA practice into local level mechanisms also provides a basis for the further institutionalisation and sustainability of EIA-based mechanisms for teacher training delivery, as well as acting as conduit for the handover of practical field-based tasks. This decentralisation-based approach allows for a differentiation in project delivery based on the location, capacity and need of Division, District and/or Upazila. In its turn, there is some evidence that the impact of this approach is resulting in local education officers taking autonomous responsibility for co-ordinating the scheduling and delivery of follow-up support to teachers.

Currently, the project is working across 210 Upazilas. A number of key delivery issues were identified in a review of Divisional Reports in November 2015, including concerns over the quality of new teacher facilitators (TFs) (including recruited GoB Teacher Trainers), and the extent of motivation and support from Upazila Resource Centre Instructors (URCIs) and Upazlia Secondary Education Officers (USEOs). Suggested responses include strengthening the role of head teachers in supporting the teacher development process, both administratively and in terms of increasing motivation and engagement.

As per the original project plan and in light of the shift in direct face-to-face support, the project has also revised and reorganised the latest versions of the digital and print materials so that they can be followed in shorter, more self-standing units and they now contain locally-specific guidance for use by individuals and small groups of teachers working in schools.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations for primary and secondary schools intervention (Output 1 and Output 3) made during the 2015 Annual Review are related to institutionalisation and sustainability. Hence all responses are placed under Output 5 (institutionalisation and sustainability).

Output 2 Title	Change people’s perceptions of English language learning, reduce barriers to English, and support the development of an English language media sector through the innovative use of television, mobile phones, and other media platforms
Output number per LF	2	Output Score	N/A
Risk:	N/A	Impact weighting (%):	N/A
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Note that this output has completed delivery. Milestones shown here are targets for 2017 (end of project).

Indicator(s)	Targets (2017)	Progress
Reach / The cumulative number of Bangladeshis regularly accessing BBC produced EIA media products	A cumulative total of 9 million people (60%/40% M/F)using BBC produced EIA media products	Exceeded / At least 28 million people have accessed at least one BBC Janala product. / 10.25m (46% M/54% F) are highly exposed.
Perception / The number of Bangladeshis accessing BBC produced EIA media products, who report reduced barriers and increased positivity towards learning communicative English	43% of people who have used BBC EIA products will report increased motivation to learn and /or increased confidence to use English in their everyday lives / (47% of men; 35% of women)	Exceeded / 60% of those who are exposed to BBC Janala products have reported increased motivation and/or confidence towards English (62% of men, 59% of women).

Key Points
Output 2 is now closed and has exited from DFID funding. All output indicators have exceeded their end-of-programme (2017) target. The priorities have been to ensure a smooth administrative close-out of the output as well as attempting to ensure that learning content produced by the project can be kept available to audience beyond the end of DFID funding. A number of local, private-sector partners have been identified who may be in a position to take over provision of some or all of the BBC Janala learning materials. Request for Proposals (RFP) for license of BBC Janala media content has been completed and signed off by the BBC legal department, incorporating comments from DFID-B and BMB. The RFP have now been issued, with submission date of 20th March 2016. In the meantime, BBC Media Action have successfully negotiated with existing technical partners to ensure that mobile and web content remains accessible to audiences, at no cost to the project.

Summary of responses to issues raised in previous annual reviews (where relevant)

One recommendation for this output came out of the Annual Review 2015:

All EIA project partners (BMB Mott McDonald, Open University, BBC Media Action, DFID B, GoB) should ensure a clear mutual understanding of the future use of BBC Janala materials, both by private sector partners within Bangladesh and in other contexts.

Response:
The recommendation was accepted by project partners, while noting that BBC Media Action is not resourced to undertake additional work under the EIA project. The project team have continued to liaise with BBC Media Action, and will be briefed on the final outcome of the BBC Janala RfP and tendering process.

Output 3 Title	Greater access to and use of EIA English classroom methods for secondary school teachers and students
Output number per LF	3	Output Score	A+
Risk:	Minor	Impact weighting (%):	25%
Risk revised since last AR?	N/A – new criteria applied	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach / The cumulative numbers of teachers and pupils participating in English in Actions secondary intervention	Secondary teachers / 7000 (69%/31% M/F) / Secondary pupils / 2.91m (48%/52% M/F)	Exceeded target / Secondary teachers / 7,471 (81%/19% M/F) / Secondary pupils / 3.06m (47%/53% M/F)
Practice / The number of teachers incorporating EIA approaches in their classroom practice.	Milestone 2016 will report on pre-test results of quasi-experimental (QE) study	18% of student talk in a lesson / 78% of that talk is in English

Key Points
Output 3 is essentially similar to output 1 but covering secondary schools. EIA is designed to enable secondary teachers to improve the teaching and learning practices in their classrooms, through a one-year programme of teacher professional development.

During the review period, the project exceeded the achievement of targets on coverage of secondary students and teachers. Despite an increase in scale of teacher training during 2015/16, similar levels of progress are being show with previous cohorts, both in terms of teacher activities and their impact on classroom activities. Classroom use of pair and group work at the conclusion of the initial teacher development meeting for this cohort are slightly under those seen at the three-quarters stage of the previous cohort (74% compared with 80%). Among students, 51% of observed classes used English for 50% of the time, compared with 63% of observed classes at the three-quarters stage of the previous cohort (Ref: presentation by EIA staff). It is reported that this suggests the current cohort is on-track to achieve similar levels of classroom change and English language competence as seen on previous cohorts.

Under output 1 we have already mentioned about the ongoing quasi-experimental study for both primary and secondary schools for attribution of English language learning skills to the EIA intervention that has been designed based on previous review observation on the lack of a counterfactual.

The coverage of students and teachers continues to show an upward trend in maintaining good gender balance on participation. Overall, the number of students reached is well above the milestone for the review period, and is noteworthy as the project has increased its cohort intake between 2014/15 and 2015/16.

As with the Primary programme, school- and cluster-level support is provided by Teacher Facilitators. However, under Secondary education, this TF cohort is made up of experienced EIA TFs and new EIA teachers. The new EIA teachers are currently participating in the training as learners as well as facilitators, and were selected for the role of Teacher Facilitator by the EIA Divisional team during the initial EIA teacher development meeting.
As with output 1, a number of key issues associated with the delivery of secondary interventions were identified in a review of Divisional Reports in November 2015. These included concerns over quality of new TFs (including Government teacher trainers), a reported lack of motivation in secondary teachers to attend Teacher Development Meetings (TDM), and the extent of motivation and support from Upazila education officials. Suggested responses include strengthening the role of head teachers in supporting teacher engagement, and adjusting the timing of teacher training interventions for secondary teachers to the early part of the academic year, as secondary teachers are particularly dominated by exams in the second half of the school year, reducing their levels of engagement with new methodologies.

Outside of these specific issues, there are a number of wider practical challenges to the implementation of central and local-level project activities at secondary level that do not occur in the Primary system. These include the following:
- The EIA Project Management Unit sits within the Directorate of Primary Education, and there is no counterpart within the Directorate of Secondary & Higher Education (DSHE). It is reported that this impacts on levels of GoB ownership and engagement within the secondary sector. It is also reported that DSHE has slower processes for decision-making when compared with DPE, making it difficult to maintain progress with project activities under Output 3.
- The mechanisms for Continuous Professional Development (CPD) in secondary are different from primary and the project is yet to explore how EIA could fit in within these mechanism. The secondary working group, formed earlier this year, is expected to identify those mechanisms and develop a plan based on that. .
- At district and local level, because of the very different nature of work, the GoB District or Upazila administrative infrastructure for secondary education is much thinner than primary education.
- Secondary schools have greater independence and autonomy within the state system. Each school is run by a School Management Committee, decision-making is decentralised and rests with the school rather than with DSHE.

Given the above, provision of training to secondary teachers in 2015-2016 will continue to be delivered largely under EIA project mechanisms, rather than in collaboration with local education systems. As part of this process, EIA teams work primarily in establishing relations with secondary education officers, secondary head teachers, and secondary teachers themselves. The project is also engaging with Upazila Academic Supervisors and School Management Committees. It is noted that the English Clubs, partly established in association with BBC Janala under Output 2, have been reported by EIA field staff as acting as a non-formal local level forum for peer-to-peer support among secondary teachers. With this in mind, it would be appropriate to consider utilising the Clubs to enhance the project’s local-level support to secondary teachers.

Some minor changes have been made to the existing teaching and learning materials for the secondary component.

A number of further initiatives have been undertaken associated with the institutionalisation and sustainability of the secondary component. These are discussed in more detail under Output 5. Overall, progress on the achievement of target numbers of teachers reached is excellent.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations for primary and secondary schools intervention (output 1 and output 3) made during the 2015 Annual Review are related to institutionalisation and sustainability. Hence all responses are placed under Output 5 (institutionalisation and sustainability).

Recommendations for 2016
As a result of the comparative limitations of administrative and teacher support frameworks for secondary education at the regional level, the project faces potential challenges in the current implementation of project activities for secondary teachers. These challenges also hold some implications for the long-term institutionalisation and sustainability of EIA activities in a secondary context. With this in mind, and in light of the strong progress reported in the Primary sector under Output 1, it is recommended that the project prioritise the further development of regional programme delivery mechanisms for secondary education, including:

Prioritise further development of regional programme delivery mechanisms and Institutionalisation and Sustainability (I&S) for secondary education, including undertaking an analysis of I&S approaches used within Primary sector with a view to identify those that are most successful and adapt those to support I&S activities within the secondary sector.

Continue to work with Directorate of Secondary and Higher Education (DSHE) and other central GoB bodies to facilitate awareness and inclusion of EIA approaches into strategic planning and implementation of secondary teacher training;

Identify necessary capacity development requirements to prepare central and regional secondary stakeholders for the institutionalisation and sustainability of EIA within the sector.

Output 4 Title	Increased knowledge available around improving English language competency and teacher practice”.
Output number per LF	4	Output Score	A+
Risk:	Moderate	Impact weighting (%):	25%
Risk revised since last AR?	N/A – new criteria applied	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of knowledge products developed	4 research reports / 3 research briefings	Exceeded / 4 research reports / 4 research briefings
Amount of research disseminated via conferences/ book chapters/ presentations peer reviewed, journals chapters in academic books/ distribution of reports to key stakeholders in Bangladesh and to research databases	4 conferences	Exceeded / 13 conferences / 4 papers / 4 chapters

Key Points
EIA research outputs continue to represent the project and its achievements at an international level, including at international and regional conferences and through peer-reviewed journals. As a result of these and other research dissemination activities undertaken over the project lifetime, EIA is increasingly regarded as a key case study for innovative approaches to teacher education at scale. This status will contribute to the on-going dissemination and uptake of the programme’s approaches and methodologies at a wider level.

During the review period, the project has been undertaking four specific research, monitoring and evaluation (RME) activities:

Evidence-based research briefings
In response to recommendations made in AR2015, the project is in the process of producing a series of thematic research briefings that showcase to national stakeholders the impact of both EIA, and its individual methodologies and components, as an ‘approach’ rather than as a project. These documents include:

- Technical research reports placing EIA within the context of international evidence of best practice
- Practitioner-orientated summaries outlining key approaches and delivery mechanisms

The documents are designed to support activities associated with enhancing the project’s institutionalisation and sustainability strategies. The audiences for these documents include: GoB policy makers; donors; NGOs; regional and local education offices; and other stakeholders. Depending on the audience and the content, these documents have also been translated from English to enable wider dissemination of information. A research production schedule has aligned each of these outputs with particular forums or milestone events for project advocacy at which the reports might be disseminated. Dissemination takes place through various mechanisms, including at face-to-face meetings at central and district level with GoB and Divisional staff; at technical forums; and via email to Upazila-level Education Officers. Finally, the regional Teacher Facilitators also receive details of findings.

To date, approximately 11 documents have been produced and re-purposed for various audiences. It is reported that these evidence-based research briefings are used to engage with policy-makers, education officers and educational staff at central, district and school-levels, and to supplement activities such as: project field visits for senior GoB staff; technical forums for policy-makers and practitioners; project inputs on working committees associated with policy and strategy, such as the PEDP3 Working Group.

Technical Forums Series
The project is in the process of implementing a series of Technical Forums, designed to present senior GoB staff with an overview of EIA’s approaches, methodologies and achievements, including within the context of international best practice, and to foster their integration into mainstream educational policy and strategy at various levels. In addition, the Technical Forums also seek to bring together central GoB staff with divisional and school-level staff, in order to foster exchange and information-sharing between policy-makers and practitioners.

There are 3 Technical Forums currently programmed, two of which have been delivered and a third scheduled.

The first two technical forums, delivered in Dec 2015 and March 2016, covered Primary Education. Based on the stakeholder engagement and the technical outcomes resulting from these forums, the project is intending to extend their process of working within and alongside the post-PEDP3 design team working groups.

The third Technical Forum will focus on secondary education (Provisional Delivery Date: May or July 2016). The EIA team are also considering implementing a fourth Technical Forum, also focussing on secondary education, building on the outcomes from the first secondary forum. As with the Primary technical forums, it is intended that the outcomes of both secondary forums will feed into the design for the secondary sector-wide programme and give EIA the leverage to participate in secondary working groups around teacher professional development, curriculum development, assessment and other relevant topics.

‘Teachers’ Voice’ research
The project has implemented a programme of teacher-led research designed to capture, from the teachers’ perspectives, the range of school- and classroom-level challenges and the process of professional change. Support is provided in the form of training for interested teachers on research methodology, data capture and presentation. The primary forum for the sharing of findings and teacher-authored research is the upcoming series of ‘Teachers’ Voice’ conferences: 4 divisional events in April-May 2016, and 1 national event in June 2016.

The ‘Teachers’ Voice’ programme is designed to serve several functions, including those which feed into supporting advocacy and I&S strategies. Firstly, it is designed to establish a body of experienced researchers operating at school-level. Secondly, primarily through the divisional and central conferences, the programme aims to enable the presentation and sharing of evidence-based research between teachers, and between teachers and policy makers. Thirdly, the divisional seminars in particular are designed to facilitate engagement and support for EIA-associated approaches among GoB and state officials at the divisional level.

Based on the information available, the ‘Teachers’ Voice’ initiative also has potential to act as a forum for establishing quality research within mainstream educational practice in Bangladesh. With this in mind, it would be useful to investigate further the levels of on-going support that it would require to continue its activities beyond the project lifetime.

Quasi-experimental study
A quasi-experimental research tool has been developed to help with the attribution of English language learning skills to the EIA intervention, covering students and teacher’s Language attainment and also classroom practice. This research has contributed the pre-test data presented during this Annual Review. The post-test data will be gathered in June 2016 and is scheduled to be analysed and presented in Sept 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)

There was one recommendation from this output:
EIA to continue to consolidate available data, and prioritise existing research plans towards development of evidence that are key to supporting Phase IV objectives for the institutionalisation and sustainability of the programme, including the publication of evidence-based research briefings aligned with the Phase IV Advocacy Strategy.
Response:
The project has developed and is implementing a budgeted schedule for the production of research briefings. Each output is aligned with a particular advocacy goal, in terms of anticipated audience, forum and publication deadline.

Recommendations for 2016
Continue the publication and dissemination of evidence-based research briefings, particularly those aimed at local level practitioners and designed to support institutionalisation of administrative and support mechanisms. Accordingly, prioritise allocation of RME dissemination funds to local- and national-level research briefings and events to ensure a maintained focus on project I&S.

Undertake an assessment of outcomes from the upcoming ‘Teachers’ Voice’ events, with a view to exploring the opportunities and support necessary for establishing the ‘Teachers’ Voice’ initiative as a feature of RME within the GoB educational infrastructure.

Output 5 Title	Collaboration with key organisations and professionals in the education and media sectors to adopt EiA approaches”.
Output number per LF		5	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N/A – new criteria applied	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number and extent of strategic partnerships with Key organisations in education and English language media sectors: number of sector professionals taking part in ELT media capacity initiatives	Education Partnerships / 3 or more / Existing media partnerships continue	Exceeded / 5 education partnerships (with primary and secondary ministries, directorates, textbook board and teacher training apex body) / Media partnerships under review
Number of policy seminars with key decision makers on English language education policy reform to support communicative teaching and learning	2	2

Key points
Project activities to support the adoption and institutionalisation of EIA approaches have continued during the review period. EIA are making progress in encouraging the uptake and embedding of EIA methodologies through a dual-level approach that operates at both GoB and district levels. This has been facilitated in part by an internal process involving the re-structuring and re-prioritisation of project activities, and in part through particular approaches to delivering I&S-related activities across central and local levels.

Firstly, the project-based re-structuring process is summarised as follows:

1. Establishment of strategic teams to support overall I&S
The project has formalised the roles of three teams within EIA, each with responsibility for overseeing different aspects of the overall approach to I&S. The teams are as follows:

- Institutionalisation & Sustainability Team
- Advocacy & Communications Team
- Technical Team

As part of their establishment, each team has developed a set of ToRs covering, in general terms, their key roles and responsibilities.

The Institutionalisation & Sustainability Team’s function is to coordinate with other teams and units to influence relevant state and non-state agencies and education programmes in order to help mainstream EIA methods and techniques into the GoB system. Specifically, this includes:
a) maintaining regular contact with relevant GoB departmental bodies
b) advocating for GoB participation in key EIA events and scheduled review and planning meetings e.g. Annual Development Plan meetings, Project Steering Committee meetings etc.,
c) advocating for EIA’s participation in and contribution to GoB events for strategic planning and decision-making in education.

The Communications & Advocacy Team’s objectives are to establish a “knowledge pool” to support and attain the advocacy objectives, goals and milestones set in the EIA Advocacy Strategy 2015, and engage in developing, supporting and maintaining the flow on information for advocacy towards both internal and external stakeholders.

The Teacher Development Team aligns their activities with the three stated project priorities, specifically: Priority 1 has a focus on building capacity among local-level stakeholders – teachers, , head teachers, master trainers, teacher trainers, education officials; Priority 2 has a focus on providing technical support to central stakeholders in association with design and integration of materials; Priority 3 implies a focus on providing technical support to central stakeholders in the context of policy making and programme design.

A fourth team, the Materials Development Unit, is also involved in key tasks supporting overall I&S, primarily associated with re-development of existing EIA materials and in supporting the curriculum development process.

Comment on strategic team ToRs:
The Team ToRs in their current form are useful in general terms. However, they would also benefit from being developed or refined further in order that they can better operate as practical working documents. The ToR for each team include a series of activities to undertake, but in their current form do not provide a timeframe for when the Team will achieve each of these activities. Similarly, while Quality Assurance is prioritised through a dedicated column, the ToR do not specify the actual QA mechanisms for ensuring achievement of specified tasks, or indicators for measuring their impact in terms of project institutionalisation.

2. Re-prioritisation of I&S strategy
The project has re-developed its formal strategies for Project Advocacy, and for institutionalisation and sustainability at Central and Local levels. These strategies focus on three priority areas:

a) implementation of project activities for 2015-2016
b) integration of EIA materials into existing GoB systems;
c) integration of EIA-based good practice into primary and secondary sector-wide programming.

In relation to the three priority areas, the Advocacy Strategy identifies a number of tasks and goals to be achieved, including, for example, the production and dissemination of advocacy documents, the arrangement of meetings and discussion forums etc.

The Central and Local Level I&S Strategies are respectively subtitled ‘Towards better TPD practice’ and ‘Sustaining good practices at local level’. Each strategy identifies, firstly, the rationale behind each strategy, and secondly a number of specific tasks to undertake and goals to be achieved in relation to the 3 priority areas. For example: engaging with particular departmental or regional representatives; facilitating the hand-over of sets of materials etc.

The project’s approaches to implementing I&S-related activities across central and local levels is summarised as follows:

Approaches to achieving I&S at local level
Local level I&S activities have been based on EIA taking a decentralized approach to programme delivery. EIA teams have provided a strong visible presence at the local level, building relationships with local education officers and gaining access to state-led venues, networks, and forums. At secondary level, due to the reduced administrative infrastructure for educational support, other than the school management bodies themselves, engagement has been limited to working with Upazila Secondary Education officers (USEOs).

The decentralised approach allows for a differentiation in project delivery based on the location, capacity and need of Divisional, District and/or Upazila. In its turn, there is some evidence that the impact of this approach is resulting in local education officers taking autonomous responsibility for co-ordinating the scheduling and delivery of follow-up support to teachers. The project has undertaken an assessment of regional readiness to take on ownership and delivery of EIA’s approaches and materials, and in this regard have graded the characteristics of each Upazila in terms of their current capacity and willingness assume responsibility.

Approaches to achieving I&S at central level
In parallel with this, the project is also working at a central level to engage with various GoB departments[2] . This has been undertaken with the general objective of ensuring the integration of these components into emerging policy and practice, and the specific objective of sharing best practice in local level decision-making in project implementation..
[2] Directorate of Primary Education and the Ministry of Primary & Mass Education (MoPME); the Directorate of Secondary & Higher Education (DSHE) and the Secondary Education Sector Investment Programme (SESIP); the National Curriculum & Textbook Board (NCTB) and the National Academy for Primary Education (NAPE)

Partially as a result of these approaches, EIA has seen an increase in time allocation at regular GoB Annual Development Plan (ADP) meetings, chaired by the Minister. Awareness of and interest in EIA activities is increasing among departmental representatives, as indicated among the range of questions asked of EIA during these meetings. EIA have also held two separate progress sharing meetings with DPE and DSHE, chaired by Director Generals, and attended by all Directors plus senior representatives from the major secondary institutions and projects. The DG, DPE and ADG, DPE are reported to have shown considerable commitment and support to taking responsibility and inheriting the EIA approaches and methodology at field level, including through a DPE letter sent to all regional education officials telling them to support EIA through the provision of venues for orientation and follow-up events.

Approaches to facilitating central-local exchange to support I&S
As a third strand of activity to support I&S, the project has also undertaken activities to foster closer links between stakeholders at both the central and district-level, including through co-ordinating field visits to EIA schools by senior GoB representatives, and facilitating forums for exchange between central, district and school-level staff, including policy-makers, local education officers and teachers.. The forums include EIA’s emerging series of Technical Forums and policy seminars, which commenced in Dec 2015, and the January 2016 strategic meeting designed to share best practice among local level stakeholders in the presence of central stakeholders and external parties including DfID, JICA and NGOs. The Technical Forums are discussed in more detail under Output 4.

Challenges to I&S
The challenges to the effectiveness of the strategies and approaches to advocacy and institutionalisation and sustainability remain similar to those reported in previous Annual Reviews, and centre around existing GoB organisational infrastructures and administrative procedures. However, the multiple and individualised advocacy approaches undertaken by the project are going some way to address and overcome these challenges and to mobilise a ‘critical mass’ of support for the uptake, integration and mainstreaming of EIA content and methodologies by operating at both central and school-levels.

Key I&S activities and achievements during the review period
During 2015 – 2016, key I&S activities for Output 5 across each component have included:

1. Primary (Output 1)
As discussed under Output 1, above, the project has delivered a scale-up of training for primary teachers, and the success of this can be attributed in part to the further extension of decentralised approaches to programme delivery. These include:
- the establishment of delivery and support frameworks delivered by local education authorities rather than by the project, including peer support at the school/cluster level and the provision of regular follow-up meetings;
- a differentiation in project delivery approaches based on the location, capacity and need of Divisional, District and/or Upazila;
- the increased presence of EIA staff at the local level establishing closer working relationships with various offices and representatives associated with the local education authorities.

These approaches have resulted in a number of achievements, including:

Evidence of an increase of local education officers taking autonomous responsibility for co-ordinating the scheduling and delivery of follow-up support to teachers.

22 Upazilas are actively planning for the continuation of EIA-based training and support activities, and are approaching the relevant departments within the Ministry of Education to secure support through existing funding mechanisms to support this. A further 40 Upazilas have expressed interest in taking similar steps towards ensuring their capacity to continue delivering the EIA training model.

EIA acting in an advisory role and sitting on the Working Group for the design of the upcoming primary sector programme. Made possible due to strong advocacy from DFID.

EIA materials for Primary education, including audio and video materials, are being made available for access and download from the DPE and NCTB websites, accompanied by guidelines for usage. As part of this process, EIA gave training to NCTB Primary Curriculum Dissemination Master Trainers on the use of EIA digital materials, and distributed DVDs with EIA digital materials to the Master Trainers and Key Trainers for further nationwide dissemination. This will help ensure continued availability of EIA material resources, although there are logistical challenges in terms of internet access for teachers, particularly those in rural settings.

EIA approaches to teaching & learning are being integrated into existing programmes and materials for pre-service and in-service Primary teacher training, particularly in relation to subject-based training for English, and into teachers’ handbooks and classroom guidelines. EIA has also provided feedback during the development process of the new primary textbooks for class 4-5 English and integrated its materials and approaches into the supporting Primary Teacher Editions (class 1-5). This will help ensure continued reference to and use of EIA resources by on-going programmes. Further to this, Primary Teacher Training Institutes (PTI) Instructors are involved in disseminating EIA materials and approaches to the teacher trainees through TPD programmes.

More widely, an agreement with DPE is supporting plans for the integration for EIA approaches, including technical support from EIA staff to a number of on-going Primary education initiatives associated with: teacher CPD, both in-school and out-of-school; leadership training for Head Teachers; school monitoring by education officers; and ICT in education.

2. Secondary (Output 3)
As discussed under Output 3, above, there are a number of additional challenges to the institutionalisation and sustainability of central and local-level project activities at secondary level that do not occur in the Primary system. These include the following:
- The absence of GoB District or Upazila educational administrative infrastructure to take over administration and delivery of EIA approaches to secondary teachers;
- Greater levels of independence and autonomy for secondary schools within the state system, making them independent of centralised DSHE-led decision-making over adoption of EIA.
In addressing this, the project is focussing on engagement with DSHE stakeholders at central and local level, and on the identification of potential advocates within the secondary system. Firstly, an EIA Working Group has recently been established within DSHE, made up of representatives of DSHE, National Curriculum and Textbook Board (NCTB), National Academy for Education Management (NAEM) and EIA, with a particular focus on ensuring the sustainability of EIA approaches within secondary. Secondly, the Project sharing meeting for secondary partners (Feb 2016) identified scope for EIA collaboration with Secondary Education Quality and Access Enhancement Project (SEQAEP), NCTB and NAEM.

Further planned activities include EIA-coordinated field visits by senior GoB staff to secondary schools; working with Upazila Academic Supervisors; and contributing to relevant secondary teacher professional development activities under the National Academy for Educational Management.

In terms of the integration EIA approaches and materials into mainstream teacher training, EIA will be part of the group of experts assigned by NCTB to the development of English Teacher Curriculum Guides for Classes 6-8 under Secondary Education Improvement Programme (SESIP). In addition, EIA has also been invited to support the capacity building of local education officers and Upazila Academic Supervisors.

EIA has also contributed to the SESIP framework under DSHE, supporting opportunities for embedding EIA’s approaches to secondary teacher training and teaching and learning into the sector-wide programme.EIA’s secondary TPD materials have been uploaded in NCTB website. MOE has sent a circular to all schools to buy mobile and speakers to support this implementation. .

3. Research, Monitoring & Evaluation (Output 4)
As discussed under Output 4, RME have been undertaking a number of research and dissemination activities that have contributed to the Advocacy and I&S Strategies. These include:
- Thematic research briefings for central and local audiences that showcase the impact of EIA.
- Technical Forum events designed to present senior GoB staff with an overview of EIA’s approaches, methodologies and achievements and to further support EIA’s integration into mainstream educational policy and strategy.
- Teacher-led research (‘Teachers’ Voice’) designed to capture the range of school- and classroom-level challenges and the process of professional change from the teachers’ perspectives.

GoB Project Cost Extension Request & Approval
In addition to the Output-specific activities outlined above, a further key development intervention for institutionalisation and sustainability of the EIA project which has occurred during the review period is the GoB’s request to DfID for a 12-month cost extension to the EIA programme, which has been approved by DFID. The extension is designed to focus EIA activities on four areas:
- Supporting Local Education Officers in developing their capacity to enhance local teacher CPD systems and provide effective support to teachers based on EIA methodology and approaches;
- Supporting to establish Teacher Facilitators as a local-level skills resource for enhanced CPD
- Facilitating the further integration of EIA materials into existing and emerging GoB programmes
- Supporting the design and development of planned-for sector-wide programming in Primary (PEDP IV) and Secondary (SESIP) sub-sectors.

The key objective of the Cost Extension is to support the future sector planning process and strengthen the capacity of education officials and teachers of both primary and secondary schools to: / a. Improve classroom teaching methods / b. Improve support to teachers / c. Establish a teachers’ network within GoB framework / d. Improve monitoring and mentoring of classroom practice / This will be delivered through a series of scheduled training and capacity development activities at both central and regional levels. Alongside that, the Cost Extension will also enable EIA to deepen engagement with the planning process of both sector programmes – in order to embed EIA developed methods – but more to contribute to the teacher professional development concept in general.

Summary of responses to issues raised in previous annual reviews

There were five recommendations from this output made in the Annual Review 2015 all of which has been addressed by the project.

Responses
The project have updated and restructured its I&S strategy to closer reflect the 3 prioritised targets for a) the integration of EIA approaches into mainstream educational planning, b) the integration of EIA materials into the national curriculum, and c) engagement and support for EIA approaches among central and local stakeholders. This includes sub-strategies specific to engagement with local and central stakeholders. The emphasis the project places on I&S is also reflected in the restructuring of the project team to address these priorities, and also changes to the project’s quarterly reporting framework.

Each of the 3 project teams (Institutionalisation & Sustainability Team; Advocacy & Communications Team; Technical Team) has made a plan, linking their areas of work to the three I&S priority areas. They have developed Terms of Reference, which have been shared with their staff. They are planning and budgeting their I&S-related activities on a quarterly basis, linked to the overall planning framework. Further action is required to further develop these strategic documents to operate as practical tools to support implementation, particularly in terms of providing: staged and structured activity schedules, delivery timelines, detailed EIA staff roles and responsibilities, QA mechanisms, and budget and human resource allocation for each task.

Recommendations
The recommendations in relation to Output 5 are as follows:

Further refine Team ToRs to include team objectives, specific timeframe of activities, and QA mechanisms.

Continue to enhance current Advocacy and I&S strategy documents, especially in light of the cost and time extension, by including: schedules for specific activities; QA mechanisms for measuring or assessing the impact of particular advocacy inputs; further descriptive detail of specific activities; allocation of responsibility for delivery of specific activities to current I&S Teams or to existing units within EIA

The additional funds secured under the recent 12-month Extension to be used to further support initiatives associated with the institutionalisation and sustainability of the project, with a particular focus on secondary education.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers associated with this programme are:

1. Teacher face to face meetings and support
2. Development and production of audio and video materials
3. Equipment (speakers, SD-cards and mobile phones)

Collectively these account for 75% of the total costs and individually face to face meetings and support to teachers is the most substantial cost incurred at 50% (in phase IV of the programme). In the past 8 years these costs have decreased and have remained within budgetary expectations.

VfM performance compared to the original VfM proposition in the business case

Value for money for English in Action has been assessed on three levels.[3] Firstly, whether the programme continues to produce additionality (positive net benefits) relative to DFID not intervening in this programme (do-nothing); Whether the programme continues to produce additionally relative to the next best alternative means of delivering the same strategic objective i.e. enhancing teachers professional development; And whether there are any lessons that can be incorporated into the English in Action programme that enhance elements of value for money – economy, efficiency and effectiveness – without compromising performance in any of the other VfM elements.[4]
[3] An important caveat to this analysis is that the additionality calculations focus only on the primary education sector. EIA provide support to teachers to impact teaching outcomes in the secondary sector but the nature of these interventions are difficult to model and monetise in the NPV calculations and so have been omitted. As a consequence, and in addition to other qualitative benefits that have been identified during the VfM assessment but not monetised the net benefits measured for EIA are a conservative estimate of the total. Also the nature of English tuition at secondary level is more reliant on private provision raising strong issues on the relevance of GoB SBT as a useful comparator. For example, the Teaching Quality Improvement Project 2 focuses on Classes 11 and 12 (which EIA does not cover) and the Secondary Education Sector Investment Programme is yet to start its teacher development programme.
[4] See Annex [x] for a full explanation of the VfM asasessment.

Taking each in turn:

English In Action continues to produce additionality relative to doing nothing (government provision of English subject based training). That is, when assessed over a horizon of 19 years (the useful lifetime of the programme, EIA produces additionality of £9.5m and a benefit-cost ratio of 3.5.[5] Sensitivity analysis conducted to check the extent to which net benefits are affected by changes in key assumptions - changes in the discount rate, unemployment rate and learning gains – shows positive additionality for EIA.
[5] Using a discount rate of 10%.

For whether EIA continues to produce additionality over and above a next best alternative means of delivery, BRAC Primary Education Programme (BEP) is used as a suitable comparator.[6] Assessed over the same time horizon using the 10% discount rate shows that EIA produces additionality over and above its next best alternative of £8.5m. In addition, there are a number of non-monetised benefits associated with EIA that indicates what has been monetised is a conservative estimate. Sensitivity analysis applied to both EIA and BEP show that these findings remain robust.
[6] While there are differences in the delivery channels used between EIA and BRAC for primary education there are elements within these delivery channels that are comparable. Also both serve to achieve very similar outcomes and impact and therefore on the basis for assessing EIA relative additionality, BRAC primary education programme is judged to be the most suitable comparator.

Finally, whether there are any lessons that EIA could adopt from the best practice of the next best alternative across the elements of value for money (economy, efficiency and effectiveness) the comparisons are shown in table [1]. For this exercise, delivery channels and processes are important, as well as data availability, and so taking into account both considerations it was judged that the 3e’s comparison as better suited to a comparison between the existing government models of English subject based training.

Table 1: Value for money comparison between EIA and Subject Based Training
Value for Money measures
	Phase II	Phase III	Phase IV	SBT
Economy
Unit cost per teacher for face to face support	270	176	38	42
Audio and Video materials	105	35	16	-
Equipment	225	81	2	-
Total	600	292	56	42
Efficiency
Reach	400	7,500	33,500	70,000
Student talk time	27%	27%	20%	5%
Student use of English in the classroom	81%	91%	60%	5%
Effectiveness
Proportion of students getting access to the income premium on English	40%	30%	15%	1%
Cost per learning outcome	17	13	8	58
Increased likelihood of finding work	10%	10%	10%	1%

Across economy indicators, EIA has been successful in reducing unit costs substantially since phase II across all areas of economy measured. In Phase IV EIA aims to reduce unit costs of face to face support below SBT. On efficiency, while the alternative GoB SBT continues to have greater reach, student talk time as well as use of English in the classroom remains superior for EIA. Finally on effectiveness and cost-effectiveness, EIA achieves a higher proportion of students with and increased competency grade in English than GoB SBT and in spite of higher unit costs in some areas of economy are able to achieve a higher impact more cost effectively than the governments SBT. An additional measure covered in this review is the increased likelihood of finding work of EIA students. Comparted to SBT, students who complete EIA studies have a much higher change of finding work than others who have not received EIA.

Assessment of whether the programme continues to represent value for money

Overall, on the basis of the analysis undertaken to judge EIAs VfM performance, this review concludes that EIA continues to provide VfM for DFID. However, this exercise has revealed a few areas where VfM can be improved over the next year. These are mainly in the areas of economy and efficiency:

Assessment of actions taken by EIA on last year’s VfM recommendations

On economy, to bring the unit cost of one day EIA on last yeart oVfM rGoB levels (i.e. PEDP3 unit costs) the budget was set at Tk800 per teacher per day in line with the GoB subject-based training rate and divisional budget holders informed. Actual spend has been within budget, despite some challenges when GoB venues could not be secured for these meetings. Actual spend has been within budget, despite some challenge Upazila Education Officers and schools through strategy meeting sessions. Almost all teachers are using their own mobile phones. To date, 25% of primary and 20% of secondary schools in intervention areas have purchased a speaker, with many schools and teachers now waiting for SLIP and similar funds to be disbursed to their schools. On using lower cost printed materials, following market research with vendors and decision to print multiple guides in large quantities to benefit from economies of scale, cost of print per page is Tk0.70, compared to Tk1.00 for previous cohort. Also, EIA materials are now available on the DPE and NCTB websites. ,. Finally on decentralising operations to assure quality of implementation and minimise cost of logistics; fuel, lodging, per diems, overtime, etc., work remains in progress. Divisional offices have been operational since February 2015, and planning and logistical arrangements are being made at divisional level.

On efficiency, on exploring opportunities for ensuring face-to-face support through GoB system, work remains in progress. Technical forums and work with DPE has focused on continuous professional development for teachers in primary education, and similar conversations are happening in the secondary sector. At the local level, there are now over 60 ‘demand-led’ Upazilas coming on stream, who are taking on EIA-promoted approaches in a variety of ways. On capacity building to improve EIA’s value for money, this has been achieved. The VfM strategy and plan has been shared in staff meetings, and VfM sessions have been included in Divisional teams’ workshops. The results of this are illustrated by the significant savings (approx. £80K) made on the organisation of teacher development meetings in the Upazilas by making use of GoB venues and equipment.

Value for Money recommendations for FY16.

This VfM assessment has revealed a few further areas where VfM could be improved in the next year. These are again in the areas of economy and efficiency:

Economy
- Explore opportunities for moving into government offices to save cost on office rent and utilities.
  - Explore the possibility to move into local offices such as PTI’s and TTC’s and/or other local government offices by talking to the relevant people at local level institutions.

Efficiency
- Make more use of Teacher Facilitators (TF’s)/Teacher Trainers (TT’s) in our next and final cohort.
  - Persuading Government Officials to use EIA TF’s/TT’s for all English TPD activities in their Upazila/district.
  - Make use of EIA TF’s/TT’s for orientation trainings for other trainers/education officials.
- Make more use of AUEO’s and Head Teachers to promote in school support.
  - Provide resources and tools to the AUEO’s and Head Teachers.
  - Leveraging the Teacher Support Network for English TPD

In the first month of the next review period EIA will update the plan to implement these VfM enhancements, and start implementation from September 2016. EIA will also continue progress on delivering last year’s VfM recommendations

VFM Recommendation EIA develop a plan to implement selected VfM enhancements, implement these over the first 3 to 6 months of the next review period and build capacity to monitor these so that performance can be assess at the next review.

Date of last narrative financial report	QPR Q4 FY7 / November ‘15
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Moderate (Note: new risk matrix criteria applied).

In the Project Memorandum the key risks identified are:

Political/policy change – High level political commitment not maintained
Lack of training capacity developed
Sufficient human and physical resources are not made available
The design of the programme and its envisaged scale up leads to reduced quality and impact
Corruption in the procurement  of goods and services

Subsequent reviews of the risk management matrix have identified the main risk to the programme as sustainability and resulted in revisions at Impact and Outcome levels (a,b) and for Outputs 1 and 3 (c)  :

Major political instability at national level: probability increased, with some additional information surrounding recent attacks on foreign nationals (Nov 2015).
Current political commitments to prioritise English learning for economic development not maintained, related to the upcoming elections and possible change of power.
Failure to gain timely and effective access to schools and teachers.

Overview of programme risk
Under Phase IV of the programme, the main risk for EIA is ensuring the institutionalisation and sustainability of the EIA content, methodology and materials. In order for the project’s outputs to become sustainable, key elements need to become fully absorbed and utilised within government structures. The main challenges to achieving institutionalisation, and hence sustainability within the education system, are, at this stage of the project:
- Status of partnership activities with GoB and key stakeholders
- GoB capacity
- Project human resources (i.e. relevant team members to continue till the end)

In addressing these challenges, enhancing the Advocacy and Institutionalisation & Sustainability Strategy documents will help to rationalise activities, prioritise areas of primary interest and identify best ways to effectively and efficiently implement procedures over the coming 24 months to March 2018.

The project should continue to take a multiple-stakeholder approach to advocacy, the effectiveness of which is already demonstrated by current activities. Specifically, this will involve engaging with the centralised GoB system and also with local and regional educational stakeholders and with ‘external’ partners – donors and NGOs – to raise awareness and encourage uptake and utilisation of EIA outputs. Within this, there is a particular need to focus on I&S within the secondary sector, and to capitalise on recently-established working relationships with DSHE and other secondary bodies.

The key challenges will continue to remain in place for the project, simply because both primary and secondary education sector operates a large multi-layer, multi-stakeholder system with more than 27 million students. Changing any system/processes within that would require long term on-going intensive engagement, for which the project has limited ability given the resource constraints.

Outstanding actions from risk assessment
1. Continued prioritisation of Phase IV Advocacy and I&S tasks
2. Enhancement of implementation plans and other strategic documents for all Advocacy and I&S tasks
3. Strategic focus on secondary sector

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project is proceeding well against the planned original timeframe. During the approval of 12 month extension the plan has been adjusted and refined in the cost extension document. The review team did not assess these documents as it was not part of the TOR.

Performance of partnerships
Partnerships between EIA consortium members are operating well. As a result of Open University (OU) reducing their levels of involvement in the delivery of project activities, and BBC Media Action no longer part of the project in a formal sense, the project has taken the opportunity to reassess roles and responsibilities in planning for the implementation of key advocacy and I&S tasks during final 12 months of programme delivery under Phase IV. However this is now being re-assessed considering the recently approved cost and time extension. The project has also seen successful collaboration between DFID Bangladesh and EIA in implementing advocacy initiatives associated with engagement with upcoming GoB and donor-led programmes, and participation from GoB and external donors in EIA’s various technical review events.

Asset monitoring and control
DFID conducted a spot check of EIA Chittagong regional office and two schools in Anwara Upazilla in March 2016 and observed that the EIA team monitored and registered it assets satisfactorily.
The previous annual review also highlighted DFID concerns about the number of laptops – 4 in total – which had been registered as lost/stolen over the then previous 12 months. In response EIA provided a separate document with all items lost and stolen, brief description of the incident and relevant documents such as police reports and management decisions. In addition, the lead managing agent also agreed to pay for the stolen laptops based on a recommendation from DFID. The asset register as well as the list of any lost and stolen are now available online and accessible for DFID. Both lists are updated on a monthly basis.
As per the recommendation of the DFID programme team, EIA prepared an Anti-Fraud Policy aiming to reduce any risks related to misappropriation of funds and equipment. The key issues around the policy have been shared amongst the EIA staff (including regional offices) and beneficiaries.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The Annual Review, conducted by an independent consultant with support from DFID Education Adviser, Programme Manager and Economic Advisor in relation to the VfM component, took place as a desk-based ‘light touch’ review involving 8 days for preparation, review planning, scheduling, interviews, documentary analysis and report writing, delivered within a period running from 7th March – 15th April. DFID undertook a monitoring field during 22nd-23rd February to feed field observation into the report. Information and data was gathered through reviews of project documentation, interviews and discussions with EIA project management and staff, and GoB staff. Due to time limitations, there has been no independent verification of the data presented to the review team.

Monitoring progress throughout the review period
EIA have considered the implications of the evaluation findings for the project as a whole, and, in response to recommendations made in AR 2014, have put in place a Quasi-Experimental research tool that will better reflect the cohorts of teachers covered during the scale-up period. However, the new research tool will only be able to yield findings in time for AR 2017. As an interim measure, the Annual Review 2016 is reporting the pre-test results of the quasi-experimental (QE) study.