Annual Review

Title: / Private Sector Development in DRC
Programme Value £ (full life): £102.5m		Review Date: March 2020
Programme Code: 203161	Start Date: 27/01/2012	End Date: 30/09/2024

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Year (being reviewed)	2012	2013	2014	2015	2016	2017	2018	2019
Programme Score	A	A	B	B	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203161/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203161/documents

A. Summary and Overview
Description of programme
The Private Sector Development (PSD) programme aims to address poverty alleviation in the Democratic Republic of the Congo (DRC) through a £100m Private Sector Development programme. The programme has three components: market systems development (ELAN – implemented by Adam Smith International), business environment reform (Essor – implemented by PwC) and a Decision Support Unit (DSU – implemented by Oxford Policy Management).
Market Systems Development - ELAN: a £50m, Making Markets Work for the Poor (M4P) component, working through the private sector to address bottlenecks that prevent the poor from participating in and benefitting from markets. Now in its second phase, the project aims to improve the income of 1 million people, including 250,000 women with cumulative reported income increases of £88 million. The sector portfolio has been consolidated to focus on perennial agriculture; non-perennial agriculture; renewable energy; cross-border trade, and; access to finance (for consumers and SME’s).
Business Environment Reform - Essor: a £35m flexible facility that works to design and implement interventions which improve the DRC’s business environment for micro, small and medium enterprises (MSME) to create jobs and services for the poor. The project now has two focused workstreams: (a) Access to Energy (A2E) which addresses a key operating constraint to business by improving access to renewable energy through the development of the first three off-grid solar hybrid mini-grids in the DRC; and (b) Organisation pour l'Harmonisation en Afrique du Droit des Affaires (OHADA), which includes support for the Guichet Unique de Création d’Entreprise (GUCE), a one-stop shop for business registration which reduces time and costs incurred by small businesses.
Decision Support Unit (DSU): a £3.48m component which provides ongoing performance assessment of implementing partners (reviews, results verification and evaluations), contextual analysis and support to internal programme learning (research studies, learning workshops) and external communications. This project started in August 2016 and will run for seven years.
Summary supporting narrative for the overall score in this review
The report draws upon an independent evaluation of the programme components conducted by the DSU, in addition to the programme monitoring reports. The DSU component was subject to a separate review conducted by DFID DRC.
Overall the project scores A having exceeded targets on ELAN and met expectations on majority of targets for Essor and DSU.
ELAN scores an A+ as overall it has met or exceeded all its output level logframe targets by supporting changes among market actors and reaching women. It has met or exceed 7 of the 9 target sub indicators and partly achieved 2.
Owing to uncertainty and time delays around the contract extension of the management agency a large part of 2019 was spend on consolidating programme activities under the previous contract (ELAN 1.0) and early 2020 spent on inception phase under the new contract (ELAN 1.2) to realign the programme to DFID in country forward strategy and provincial footprint. This impacted the on-ground implementation of the programme and the score mostly is generated due to overachievement of targets in the previous year. There may be a risk of the targets for the future years are overambitious since ELAN in order to align with DFIDs Strategic direction, will narrow down operations to fewer sectors and geographies that are not naturally conducive to private sector participation.
Essor scores an A based on its output achievements. Of the four outputs – it over achieved one target and achieved one (75% weighted score) and partly achieved two targets. In light with the changing political context in the DRC Essor has shown evidence of focusing away from activities towards an approach which is focussed on sectoral changes. Examples are technical secretariat for the Business Environment multi-donor technical group, greater collaboration and influence on governments overall strategies in the sectors like Renewable Energy. The management agency has been granted a two-year extension to align with the project end date and focus in the next two years will be on ensuring sustainability of the interventions while providing policy lead in prioritised areas.
DSU scores an A given achievements against agreed targets. The progress made in 2018 has been continued and the DSU is has been providing a good balance of constructive engagement and robust challenge. The DSU has been able to draw up on its expertise and institutional knowledge to provide valuable inputs in evaluation design and the projects measurement of results: this should be continued and built on in the coming year.
Recommendations for the year ahead
Programme Level:
1. Continued coordination between the components and consolidation to strengthen the impact both on policy and operational level in few sectors.
2. Adequate attention to the development and implementation of the sustainability and exit plans
ELAN
1. Greater coordination and collaboration with other programmes including CMPS like FSD
2. Develop intervention summary plan that can be reviewed on a quarterly bases to assess progress.
3. Review and design strategies for sharing learning among private sector stakeholders with the objective of stimulating interest in the business model.
Essor
1. Focus the extension primarily on the sustainability of the current workstreams, including targeting a handover of the GUCE, Collateral Registry and Accounts systems to government by the end of 2020. (Essor)
2. Ensure any new interventions are implemented based on a clear process including analysis of Vfm, likelihood of success, strategic relevance and logic chains linked to impact. (Essor)
3. Prioritise the efforts to embed reforms through strengthening communication and lobbying institutional key players in various government agencies and other development partners to have a sectoral impact.
 DSU
1. Consolidate and prioritise on core DSU activities in order to maximise the impact of resources (human / financial)
2. Explore more cost-effective ways of conducting evaluation piece, evidence building studies and lesson learning in coordination with ELAN and Essor.

DFID:
1. Reflect on and mitigate risks linked to internal decision-making processes (contract extensions), make early decisions to initiate processes.
2. Ensure higher level of strategic and technical engagement in the programmes.
## B: DETAILED OUTPUT SCORING

Component	Weight	Score	Explanation
Component 1 (ELAN)	50%	A+	Moderately Exceeded Expectations
Component 2 (Essor)	40%	A	Met Expectations
Component 3 (DSU)	10%	A	Met Expectations
Total	100%	A	Met Expectations

Component 1: Market Development (ELAN), 50%

Output Title	Partner market actors have successfully taken-up pro-poor innovations and have invested in order to sustain these innovations independently of programme support [Adopt, Adapt].
Output number per LF		1 (Innovation)	Output Score	A++
Impact weighting (%):		45%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Cumulative number of programme partners who have invested resources in an initial pro-poor innovation as a result of direct support from the programme and intend to sustain this investment	80	119
1.2 Cumulative number of programme partners who continue to independently pursue activities which support the initial pro-poor innovation/change after the initial pilot has ended	20	30
1.3 Cumulative amount of investment made by programme partners in support to the initial pro-poor innovation/changes as a result of direct support from the programme.	6,000,000	8,315,210
1.4 Percentage of interventions that specifically aim to provide poor women more beneficial roles.	15%	34%

Provide supporting narrative for the score
Output scores A++ as it has exceeded all its indicator targets under this output area for 2019. This is an area in which ELAN has consistently shown strong performance throughout its implementation in identifying and working with appropriate partners for piloting pro-poor innovations.
Lessons identified this year, and recommendations for the year ahead linked to this output
Based on the future direction set for the programme which is to focus on fewer geographies and sectors
Output 1 has been replaced by a new output: ‘ELAN 1.2 implements strategies and interventions in selected sectors with a focus on pro-poor benefit.’
Sector strategies have already been developed for key ELAN 1.2 sectors. Acknowledging the short inception period, the strategies, are highly summarised results chain for sectors - renewable energy, and transactional definitions of intended Market System Changes (MSC) for non-perennial agriculture rather than actual market system changes (e.g. input supplier sell inputs to Small Holder Farmers). These need further development in the next few months.
Our recommendations are:
- Ensure that the 50% target for interventions working with actors at the macro/meso level of the sector does not lead to a high number of small, limited impact interventions in this area.
- Ensure that sustainability and exit plans are built into the implementation plans from the start of the interventions. Clear action plans are delivers and agreed against the sector strategies.
Output Title	[Expand + Outreach] Market actors who are competitors to those that pioneered the pro-poor innovation have copied the pro-poor changes or offered variants of it. This, along with the initial innovation, results in large numbers of poor people accessing and using improved goods or services.
Output number per LF		2 (Crowding-in)	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Cumulative number of poor people showing significant changes in their practices as a result of market system changes supported by the programme. / (Women) [Poor: *below $1.9PPP; **below $3.2PPP]	1,497,862 / (374,466)	1,312,204 / (397,937) / [866,054] / {1,062,885}
2.2 Cumulative number of competing market actors supported by ELAN that expand on innovations introduced by the programme.	36	45
2.3 Percentage of market system changes which have resulted in at least two competing market actors expanding an innovation introduced by the programme.	50%	68%
[note] ELAN's poverty profiling found 66% of their beneficiaries are below the $1.9PPP poverty line in 2011 PPP values.
[note] ELAN's poverty profiling found 81% of their beneficiaries are below the $3.2PPP poverty line in 2011 PPP values.

Briefly describe the output and provide supporting narrative for the score
This output captures how ELAN’s work with its initial partners encourages other competing market actors to replicate similar practices. ELAN scores an A given that it has exceeded 2 of the 3 targets but missed on one as implementation activities in 2019 were suspended due to contract not being extended on time. For indicator 2.1, the DSU verification study in 2018 highlighted concerns around the methodology used by the programme in defining the ‘poor’. If the definition of ‘poor’ was strictly taken as below the $1.9PPP/ $3.8PPP poverty lines, the targets would not be met. The DSU does believe the target here was set too high for the DRC context and the methodology is being reviewed in consultation with the DFID results adviser.
Lessons identified this year, and recommendations for the year ahead linked to this output
Output 2 has been replaced by: ‘ELAN 1.2 implements interventions where partner market actors successfully take up pro-poor innovations and make investments’.
Majority of current ELAN 1.2 proposed intervention are geared to work with ELAN 1.0 partners, with similar business models used previously, but expand into new geographical locations. This is a pragmatic strategy in the tight timeframe for the remainder of the project period.
It is recommended:
ELAN 1.2 takes a renewed look at the strengths and weaknesses of those business models, review its learning from ELAN 1.0 interventions and identify ways to review the partnership agreements to achieve greater scale. Review of the knowledge products and studies done under ELAN 1.0 could provide some insights into areas where such opportunities exist. For example, a previous study on the tax elasticity of renewable energy products found that customers were price sensitive, more likely to buy solar products if they understood about the products and costs, and more likely to understand benefits if they had some level of education. Future marketing opportunities for the renewable energy products can be improved by assessing the customer profiles and spending capacities and finetuning the communications campaigns to the segment.

Output Title	Non-competing market players have adjusted their own practices in reaction to the pro-poor market system change. [Respond]
Output number per LF		3 (Market Response)	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Cumulative number of market actors who are not competitors to the programme partners who change their practices, reinforcing the market system changes supported by the programme.	20	21
3.2 Percentage of market system changes which have resulted in market actors who are not competitors to the programme partners changing their practices, reinforcing the market system changes supported by the programme.	45%	50%

Provide supporting narrative for the score
This output captures how ELAN’s work with its initial partners have stimulated a change in non-competing market actors and how those changes affect the Market system changes (MSC) that ELAN targets. It is based on the concept that if changes/ modles supported by ELAN result in the development of stronger supporting functions in the market then the new practices will be more resilient to external shocks and become a norm for the sector. ELAN scores an A+ for this output because it had already overachieved on both its targets under this output. DSU has highlighted the logframe definition for indicator 3.1 allows ELAN to count actors who have been supported or funded by ELAN to support pro-business ideas introduced by ELAN, this is not in line with the conventional definitions of market response (market facilitation) in M4P programmes. ELAN maintains that DRC being a high-risk market with a zero-base standard definition cannot be applied as in its context of operation ELAN is responsible for market building rather than facilitation. The overwhelming constraints affecting the private sector in DRC, such as no government interventions or facilitation, a lack of information and visibility preventing ‘second movers’ replicating innovations.
Lessons identified this year, and recommendations for the year ahead linked to this output
Output 3 has been replaced by a new output: ‘ELAN 1.2 implements interventions that influence food security, and climate change favourably’. DFID have asked ÉLAN that the project “does what it can” in demonstrating it is tackling these cross-cutting DFID priorities and monitoring results, hence its inclusion in the logframe as an additional indicator. Two of ÉLAN’s three core sector areas and a number of its target MSCs are clearly linked to climate change and food security. While accepting the time and capacity constraints facing the ÉLAN 1.2 team, we recommend that:
Consider whether ELAN can use their planned impact evaluations in non-perennial agriculture and renewable energy to collect data on the extent to which interventions have a positive effect for beneficiaries in terms of food security and climate change respectively, to support the implicit assumptions within this indicator.
Component 2: Flexible Facility for Private Sector Development (Essor) – 40%
Output Title	A public sector-driven electricity tendering process launched in DRC
Output number per LF		1	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	Yes – previously 32%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Project preparation for the public sector tendering of solar mini-grid concessions	Project-specific tender package documents submitted to UCM. / Comments received from both DFIs and bidders on the RfP package (including on Concession Agreement) and integrated in an updated version.	Mostly Achieved / Project-specific tender package documents submitted to UCM and tender launched in May 2019. (ACHIEVED) / Comments and queries have been provided directly thorough emails from bidders to UCM with Essor in Cc. The tender package has been revised following extensive feedback and comments from potential bidders. Comments largely responded to, but incorporation into tender package still to be completed. (MOSTLY ACHIEVED)
1.2 Project finance facilitated for the tendering of solar mini-grid concessions	Additional funding request(s) sent to DFI(s) / Site visits facilitated for shortlisted bidders at RfP stage. / Updated financial model based on Term Sheet / Letter of Interest (TS / LOI)	Achieved / Investec, an asset management company have provided a preliminary non-binding letter of interest for debt financing of the project. Letters of Intent (LOI) were provided by Proparco and Camco/REPP. The investment committee of Camco/REPP approved the provision of an indicative term sheet for a subordinated loan facility of up to US $10m to all pre-qualified bidders in the tender. FMO and Electrifi have also provided termsheets. (ACHIEVED) / The A2E team led a delegation of 15 people with four candidates to three sites for the solar mini grid systems (ACHIEVED) / Financial model has been updated based on the received term sheets and letters of intent from DFIs. The mechanics of the model might be audited by the AfDB and further be updated after the audit is finalised. (ACHIEVED)

Provide supporting narrative for the score
Access to Electricity is supporting the GoDRC, through Unité de Coordination et de Management (UCM), in a public tendering process for the installation of solar mini-grids in three selected sites in the DRC (Bumba, Isiro, and Gemena). This output is scored A as the A2E workstream has largely achieved all its planned logframe milestones, though there has been a significant delay of 4-6 months in the tendering process due to the government ministers not being in place. In 2019 the A2E team has continued to move the tender process forward through its in-house project management and remote technical support to UCM. The A2E component has made good progress on preparing the documents and facilitating additional project finance for the tendering of solar mini-grid concessions.
Essor’s work with UCM has led to the development of a comprehensive legal framework, regulatory set-up, and financial packages for the concession. While the three projects have been important the interventions and processes have gained recognition by the government and other development partners such as the World Bank and AfDB. The Essor consultants are now working to support the government at a more strategic level, this is a greater achievement than implementation of the pilot itself (and the logframe indicators).
Lessons identified this year, and recommendations for the year ahead linked to this output
Recommendations are:
- Clear capacity building plan in place with Essors role limited to handholding to ensure sustainability.
- Support UCM to ensure templates and learnings from this project are shared with other relevant government bodies and continue to widely disseminate learnings.
- Given the commitment of some of the Development Finance Institution (DFI) partners to gender mainstreaming, Essor should proactively engage with these partners and DFID to explore how to adapt GESI requirements to this project.
- Continuously ensure transparency of the tendering process through regularly communicating with the shortlisted bidders and updating them with regards to the process.

Output Title	A transparent business environment with easily accessible company financial information
Output number per LF		3	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Yes – previously 9%

Indicator(s)	Milestone(s) for this review	Progress
3.1 Develop database and design process for functional Collateral Registry.	1. Signed cooperation agreement with a major bank in order to extend the collateral registry pilot. / 2. Final version of collateral registry system designed. / 3. Digital system for submitting collaterals into RCCM deployed to at least 2 banks. / [Deployed: banks are able to submit collaterals from their offices] / 4. Centrale d’engagements created and populated with data from RCCM	Partly Achieved / Signed cooperation agreement with RawBank in order to extend the collateral registry pilot. On 27 November an agreement was signed with a third Bank. (ACHIEVED) / The collateral registry has been designed and tested. Registered collaterals are visible using the rccm.cd website. (ACHIEVED) / The registration procedure for uploading collaterals into the RCCM has been developed and deployed in two banks. (PARTLY ACHIEVED) / 4. The concept of Central Engagements had been envisaged at the time the Government was not receptive to the idea of a "credit bureau". (NOT ACHIEVED)
3.2 Banks populate Collateral Registry with useable information on collateral.	1. At least two banks register collaterals via digital system linked to RCCM. / 2. Banks trained to populate collateral registry upon request.	Partly Achieved / Rawbank has uploaded a number of collaterals. The process was initiated in 2019 and completed in early 2020. Equity bank had uploaded collaterals – these have not been transferred to the RCCM since payment has not been made by the banks to the government. (PARTLY ACHIEVED) / Essor has engaged closely with the banks (Raw Bank, Equity and BCDC), including holding at least 3 workshops with them. (ACHIEVED)
3.3: Develop database for submission of Annual Accounts (Companies House).	1. Final Annual Accounts database designed. / 2. Final version of Annual Accounts database handed over to CPCC. / 3. Self-learning control system established and handed over to CPCC.	Partly Achieved / Annual Accounts database designed (ACHIEVED) / The system has been officially handed over to the CPCC, but full transfer of ownership has not yet taken place. (PARTLY ACHIEVED) / Learning system is in the process of being developed (NOT ACHIEVED)
3.4: Companies populate Annual Accounts database (Companies House)	1. Population of accounts database by CPCC.	1. The objective for 2019 was for all Kinshasa 2017 annual accounts to be uploaded by CPCC staff - completion expected mid-Feb 2020 (PARTLY ACHIEVED)

Provide supporting narrative for the score
Output 3 describes progress in two independent systems, grouped by their common link to the Registre du Commerce and Crédit Mobilier (RCCM) and use of IT to improve access to information by the banks in a centralised manner. This will also improve the transparency in the financial sector by making the information accessable.  One system focuses on the design and implementation of data services called Centrale des Bilans (Company house in English) to be linked with the RCCM and the database for financial accounts annually submitted by companies.  The uptake and handover has been slow due to limited capacity of the Comité Permanent de la Comptabilité au Congo (CPCC). The second system deals with the implementation of the electronic registration of collaterals to the RCCM and an additional database called Centrale des Engagements as a prerequisite to a credit bureau. Whilst good progress has been made here in partnering and piloting with three partner banks (Rawbank, Equity and BCDC), the Centrale Bank has shown slow progress in setting up the Credit Bureau that will support the Collateral registry system in the long run. This output is scored B as none of the output indicators have been fully achieved.
Lessons identified this year, and recommendations for the year ahead linked to this output
- Conduct a viability assessment of the intervention as a part of the join review in partnership with the Ministry of Plan and CPCC keeping in view the vfm and sustainability of the intervention.
- Develop a sustainability plan including handholding and coaching of the CPCC team, as well as clear expectations for their roles and responsibilities.
- Essor should review its engagement in the light of the decision by the Central Bank to establish a Credit Bureau and continue the discussions at the highest levels.
Output Title	A national system of business registration and a digitised commercial register deployed
Output number per LF		4	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	Yes – previously 38%

c	Milestone(s) for this review	Progress
4.1 – Support the deployment of the Guichet Unique (GUCE) antennae and bureau across the DRC.	1. Advocacy document and budget calculations submitted to the GUCE for GUCE financial autonomy. / 2. GUCE antennae in Goma and Bukavu operational. / 3. 4 GUCE bureaus set-up	Achieved / Advocacy document submitted and received on 28th June 2019 to the GUCE. ACHIEVED / GUCE Goma operational from January 2019 and GUCE Bukavu operational from November 2019. At time of writing ongoing registrations had not been evidenced. ACHIEVED / All 4 bureaux opened in December 2019 and registered at least one business in 2019. Transfer of their archives to Kinshasa will take place in Q1 2020. PARTLY ACHIEVED
4.2 – Deployment of a commercial registry – Registre du Commerce et du Crédit Mobilier (RCCM) – national and digitised, and accessible regionally via the Cour commune de justice et d’arbitrage (CCJA) in Abidjan.	1. Agreements reached with CCJA on the terms of linking the RCCM to the regional RCCM. / 2. RCCM server handed over to GUCE Gombe IT team. / 3. V3 of RCCM software complete and operational. / 4. Eligible paper archives digitized and centralized for all operational GUCE antennae.	Achieved / 1. Agreement reached with CCJA on the terms of linking the RCCM to the regional RCCM. ACHIEVED / 2. RCCM server handed over to GUCE Gombe IT team. ACHIEVED / 3. The GUCE NG software has now been rolled out to all existing antenna and bureaux. Deployment of the software was preceded with training for GUCE staff on the new features of the software, and how to use it. ACHIEVED / 4. All GUCE antennae paper archives were digitalised and uploaded into the RCCM by the end 2019. Bureaux archives will be digitalised and uploaded in 2020 – although these are expected to be of poor quality. ACHIEVED

Provide supporting narrative for the score
Output 4.1 relates to the progress in rollout of the GUCE to two more antennae and four bureaux, which has been partly achieved. One antenna opened in Goma in January 2019, and the next antenna opened in Bukavu in November 2019. Four bureaux opened in December 2019. Reasons for the slower than anticipated progress were the lack of budget allocated to the GUCE and their inability to pay for the new staff required to manage the new antennae and bureaux. The project was able to largely hit its targets under this output towards the end of 2019 however the government allocations are key to ensure the sustainability of these interventions. Output 4.2 relates to a number of enhancements to the electronic database and all four milestones have been achieved.
Lessons identified this year, and recommendations for the year ahead linked to this output
- Resolving the business model and financial stability of the GUCE is essential. GUCE cannot sustain its operations without Essor’s support at this moment. This has been raised and discussed with the government in the Steering committee and the proposal is pending a cabinet decision.
- Essor should complete a capacity gap assessment covering: individuals, organisations, institutions. It is recommended that Essor aims to handover the intervention by the end of 2020 and spends the following year embedding the systems and communicating progress.
- To support the alignment of both databases national and that at the OHADA headquarters (RCCM and CCJA) on an ongoing basis, consider engaging a consultant for several days per month who is dedicated to this task and is connected to the OHADA WB team in Abidjan.

Output Title	Systems and procedures in place to give force to embed OHADA Law in the DRC legal framework and commercial practices
Output number per LF		5	Output Score	B
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Yes – previously 21%

Indicator(s)	Milestone(s) for this review	Progress
5.1 Assistance to creation and sustainability of the Association des Amis de l’OHADA (AdO), supporting the capacity of the Commission Nationale OHADA (CNO) and the dissemination of OHADA Law.	1. Training strategy for 2020-2022 is designed, published on the CNO website and endorsed by the ADO. / 2. AdO conducts at least 1 fee-based training session on OHADA Law.	Achieved / 1. The training strategy for 2020-2022 is designed and has been endorsed by the DG of the CNO. / Additionally, the strategy has been uploaded to the CNO website and can be accessed using this link: http://cno.ohada.cd/realisations.html ACHIEVED / 2. On 10 & 11 Dec, the AdO delivered its first fee-based training session. Fifteen delegates signed up for the course, but only 13 attended (and paid). PARTLY ACHIEVED
5.3 Informal businesses provided with greater incentives to become formalised through the Entreprenant pilot in Kinshasa.	1. New strategy on potential Entreprenant Pilot Phase 2 based on progress made by DGI and CNSS. / 2. Tax single window payment system proposed.	Partly Achieved / 1. Whilst Essor is working on the Entreprenent, a strategy document has not yet been developed and accepted. PARTLY ACHIEVED. / 2. Partnership Accord signed with DGRK on 8th August 2019 related to the Entreprenant but no process map or proposal for a single window system. PARTLY ACHIEVED.

Briefly describe the output and provide supporting narrative for the score
Output 5 describes a set of initiatives designed to improve implementation of the OHADA law within the DRC. Support to the AdO and CNO has been focussed on building their capacities to deliver training to helping to address the lack of understanding OHADA law. A training plan has now been developed. The Entreprenant study has provided useful insights into the new status which, under OHADA law, provides a level of formalisation for micro businesses. This output is scored a B because three out of four milestones are only partly achieved. These milestones are judged as more important to the overall output than the ones which have been achieved.
Lessons identified this year, and recommendations for the year ahead linked to this output
- Given CNO’s importance as a stakeholder, it makes sense to continue to provide light touch support to CNO through guidance on training and strategy.
- Essor should publish its research findings and share insights on the entreprenant pilot with the rest of the development community and Government, both to inform development programming and to raise the profile of its activities.

Component 3: Decision Support Unit (DSU) (10%)
Output Title	Performance Assessment – The performance and effectiveness of the PSD programme and its component projects are regularly assessed.
Output number per LF		3.1	Output Score		A
Impact weighting (%):		50%	Impact weighting % revised since last AR?		Yes
Indicator(s)				Milestones		Progress
3.1.1 Number of high-quality Annual Reviews conducted annually, in a timely manner, approved and rated as at least 'good' by DFID as part of impact & outcome assessment tool, in accordance with DFID standards and format for the PSD programme and its component projects.				3		3
3.1.2 Number of high quality annual evaluation reports undertaken in a timely manner, approved and rated as at least 'good' by DFID as part of impact & outcome assessment tool.				1		1

The DSU scores an A on this output having conducted a comprehensive annual review process within the agreed timeframe. The process required coordination with ELAN and Essor and was conducted in a way that provided challenge in a constructive manner. The final products were completed to tight timescales and provided assurance as well as pragmatic recommendations.

Over the course of this year significant progress has been made in defining the evaluation approach and developing reports which will feed into the final evaluation. This culminated in the production of the first Annual Evaluation Report (AER) in January 2020 which synthesised six other reports, including three which had been produced under the DSU during the review period, namely the Programme Management Implementation Review (PMIR); the ELAN sector study and the ELAN intervention study. The AER was subsequently validated by the Evaluation Advisory Group (EAG). The DSU should continue to use this mechanism to help steer the direction of the evaluation and ensure that it is right fit to the programme and includes ample coverage of the key evaluation questions.

Output Title	Reviewing the Problematique – The PSD portfolio's "Problematique" is regularly reviewed, including testing the validity of the theories of change underlying the PSD programme and its component projects.
Output number per LF		3.2	Output Score		A
Impact weighting (%):		20%	Impact weighting % revised since last AR?		No
Indicator(s)				Milestones		Progress
3.2.2 Number of discrete research activities undertaken annually on a demand-driven basis, in a timely manner, approved and rated as at least 'good' by DFID as part of impact & outcome assessment tool, in line with DFID's research guidance.				1		2

The DSU scores an A on this output have completed three research pieces over the course of 2019, two of which were considered by DFID to have been of ‘good quality. These include (i) Aquaculture report and (ii) Disruptive Technology report which were both strong and (iii) Political Economy Analysis (PEA) which did not fully meet expectations of the product.

The value of client engagement throughout the process to tailor the final product to the needs of the programme can be seen throughout the process: Aquaculture study is a case in point where the DSU responded to a tight specification, engaged DFID throughout, and created opportunity for product to be steered towards the needs of PSD. This has informed ELAN’s decision not work in this area in the coming two years. In contrast, on the PEA piece there was a greater disconnect between the design process and the expectations of the DFID team, so that while the requirements of the ToRs were met, the value in terms of their contributions to the future direction of the PSD programme was more limited.

Output Title		Learning & Adaptation Support – The PSD programme and component projects are supported to operationalise learning and recommendations derived from performance assessment and problematique review components.
Output number per LF			3.3	Output Score		A+
Impact weighting (%):			30%	Impact weighting % revised since last AR?		Yes
	Indicator(s)				Milestones		Progress
	3.3.1 Number of workshops facilitated to review key learning points and recommendations for implementation, held on agreed dates at least once annually.				1		1
	3.3.2 Number of discrete areas of useful and high-quality TA provided to PSD programme component projects to enhance project performance, provided on a demand-driven basis on agreed dates.				1		4
	3.3.3 Number of briefing notes in relevant formats and tailored to relevant audiences beyond PSD programme implementing partners and DFID DRC PSD team to showcase results and learning from the PSD programme and component projects, approved by DFID.				1		3
	3.3.4 Number of events for external audiences supported, beyond PSD programme implementing partners and DFID DRC PSD team, incorporating the presentation of DSU learning products.				1		5

The DSU scores an A+ on this output having made significant efforts to drive forward programme improvement through operationalising learning and expanding the reach of key lessons. This output was developed to improve the working relationship and constructive learning between the three components.
There is a visible improvement in the sessions and technical assistance being demand driven. Expectations have been exceeded against the set targets both in terms of the number of engagements and quality: given the DSU’s accumulated experience on the PSD programme and expertise, particularly in monitoring and results measurement, this is an increasingly valuable line of activity and this is reflected in the greater level of demand from the project vis-à-vis last year. The DSU has identified areas where it can usefuly supplement the communications work of the projects and has exceeded the number of high-quality research briefs which disseminated to a wide level of targeted audience. Throughout this year lessons have been learnt on audience targeting and DSU’s strategy going forward will be focussed on where communications work has the greatest impact.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change and any major changes in the past year
The PSD programme business case was approved before the ToC was integrated into the business case format and therefore the programme does not have an explicit overarching ToC. The two main component projects instead have their own ToCs that have guided their implementation. The components work towards the overall programme outcome "increased access to financial services, well-functioning markets, and an enabling business and the environment that foster economic opportunities for poor people" and overall programme impact "improve incomes of the poor".
The PSD programme has been realigned to the changing in country strategy for DFID operations. This has meant focusing down on a limited sector within limited / new geographies. While the Logframes have been recently reviewed and aligned to the strategic steer, the overall ToC of the project has not yet been updated. This observation is also reflected in the summary of each of the components below.
ELAN
Originally an “overall complexity-based theory of change ‘compass’ was drawn to guide a responsive, iterative, and non-linear programming approach”. This recognised the complexity of market systems in DRC and the inherent uncertainty about the numbers, types and relationships between different market actors. However, the compass was not useful in guiding project implementation and did not clearly articulate assumptions around how change should happen. There was an attempt to develop one in 2017 during the MTE but it was not completed instead specific ToCs for each sector were drawn in consultation with DFID. Over its extension period ELAN 1.0 focused on documenting its learning, developing knowledge products, closing interventions and there was little rationale for the project TOC to be updated.
[note] PSD Business Case
Over its inception phase ELAN 1.2 focused on refining its logframe and developing sector strategies with sector level results chains but could not consolidate the sector results chains (RCs) into one project level theory of change rendering to changes in sectors and geographies. This is a missed opportunity in crafting a uniform vision and strategy for the project. Theories of change are particularly useful for market systems projects to articulate clear pathways to achieving systemic change and can serve to harmonise work across different sectors and create a strategic coherence within the project.
Sector RCs should all be revisited and revised after the first few partnership agreements in the sector have been signed – potentially in the second quarter of 2020. This will provide an opportunity to draw on both the institutional knowledge in the project and on recent experience of implementation to further strengthen the RCs, and likely improve the project’s ability to reach its quantitative and qualitative targets. This will also be an opportune time to review the assumptions in the sector results chain and agree how the sector RCs fit into the overall programme outcomes.
Essor
Since project inception, the project has seen a comprehensive revision and refocus of the project logic and workstreams, which resulted in the scaling back from six to two workstreams. In 2018, the ToC and logframe were overhauled, with the logframe re-structured to provide milestone targets for the two remaining workstreams. In 2019, an exercise was undertaken to align the Impact and Outcome targets of the PSD and Essor logframes, which were out of alignment due to the restructuring. At the same time, modelling of the expected benefits from the Essor interventions led the project to scale back their ambitions for Impact 1 (NAIC). Since restructuring, the assumptions for the project are included in the logframe rather than within the Theory of Change.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
With the slow progress made since the completion of ELAN phase 1and delays in getting ELAN 1.2 off the ground and change I the sectors and geographical footprint the programme is currently off track to achieve many of the expected logframe outcomes and impact based on reported results for 2019 (see below).
Impact indicator 1 – Cumulative Aggregate Net Attributable Income Change (NAIC) among poor producers and entrepreneurs
2019 target: £69,016,671 (£11,093,591 for women)
2019 result: £40,664,590 (not disaggregated by women)
Impact Indicator 2 (ELAN) – Cumulative number of people who have experienced net positive income change as a result of the programme support
2019 target: 748,931
2019 result: 855,071 (697,417 – below $3.2PPP) [568,266 – below $1.9PPP)
Impact indicator 3 (Essor) – Cumulative number of companies experiencing net positive income change as a result of Essor supported business environment reforms, disaggregated to show cumulative number of MSME’s
2019 target: 65,500 (40,000 SMEs)
2019 result: 21,688 (21,541 SMEs)

Together ELAN and Essor are supposed to generate £108,661,030 NAIC which is the aim of the PSD programme. Essor so far has only generated less than £2m, with projections of £19m to the end of the programme. The closing of the workstream were not reflected in the target and the new targets were developed in the last yaer as per the recommendation of the Annual Review. If the overall target is to remain the same, it would mean around £100m would have to be cumulatively generated by ELAN. While ELAN 1.0 and ELAN 1.2 interventions are supposed to jointly contribute to the PSD logframe, ELAN 1.2 only has a target of £1.56m, which the DSU doubts it can achieve just through its planned interventions with a smaller sector set and focus geography even with a certain percentage of its recorded results that will come from ELAN 1.0 interventions. ELAN’s projections were based on the assumption that businesses will continue to grow at the same or similar rates as they have done with ELAN support.
The verification report conducted in 2018 highlighted concerns around the methodology used by the programme in defining the ‘poor’. If the definition of ‘poor’ was strictly taken as below the $1.9PPP or $3.8PPP poverty lines, the targets would not be met. In addition, A2E will contribute to NAIC through cost savings and other income benefits from the provision of electricity through planned solar mini grids. OHADA will contribute to the NAIC indicator through time and cost savings within the GUCE business registration process. Contributions to the more qualitative systemic impact indicator are set out in the new logframe. If the revised methodology is being agreed in consultation with the results adviser, if the methodology is revised the targets will be adjusted accordingly.
However, previous Annual Reviews have made clear that many of the short-term quantifiable targets and results are excessively high for the context, and do not take into account some of the deeper, qualitative systemic change the programme is working towards. This will require strong, plausible impact narratives from both projects. For Essor, this is against the project specific indicator (not captured in the PSD logframe) on the systematic impacts and spill overs linked to business environment reform; for ELAN, this requires an unpacking of its new outcome indicator on market system changes to demonstrate less tangible project impact. Recommendations are included further below.
Explain major changes to the logframe in the past year
While there are no new changes to the PSD programme logframe at the outcome and impact level. The PSD logframe comprises of combined logframes of all three components. The ELAN and Essor Logframes have changed in line with the recent shift in overall priorities and strategies. These changes and their impact at the outcome and impact level need to be reviewed and incorporated into the PSD overall logframe in the coming months. The detailed changes are as below:
Essor
Major changes to the project specific logframe in the past year include:
- Within Outcome 5, indicator 5.2 (related to training of judges) was collapsed into 5.1;
- During the project restructuring process in 2018, targets for impact indicators 1 and 2 were removed pending the completion of evaluation studies, and this year these were reset. The achievements within impact 3 were also clarified to an extent; and
- The targets for Impacts 1 (NAIC) and 2 (Number of Beneficiaries) were scaled back compared to PSD targets (projected to be USD34m and 145k respectively in 2021). This reduction increased the relative importance of Impact Target 3.
ELAN
In 2019 as part of the inception of ELAN 1.2, the project redesigned its logframe based on recommendations made during the ELAN 1.0 MTE and PCR reports. ELAN’s current logframe is an improvement over its previous logframe and better aligned with a typical M4P programme theory of change. The logframe now emphasises the design and development of well thought out strategic interventions with a view towards sustainability at the output level. At the outcome level the new logframe emphasises the stimulation of systemic change which should lead to improved access to products and services for the poor leading to an impact level change of greater incomes for the poor. Thus, the revised logframe moves indicators of systemic change from the output level to the outcome level. The new logframe is better aligned with the market systems development approach applied by the project. The revised logframe is also well-calibrated to capture GESI achievements and reflects the GESI activities well.
DSU
- Indicators related to post-implementation monitoring, verification of ELAN and Essor results, and the ‘Problematique’ review were collapsed into the overarching final evaluation process;
- Milestones for research studies and external learning events from 2020 onwards have been reduced and those for Annual Reviews have been increased to account for budget re-prioritisation decisions based on the continued implementation of both ELAN and Essor;

Describe any planned changes to the logframe as a result of this review
Both ELAN and Essor logframes are currently fit for purpose and consistent with their respective ToCs these changes need to be appropriately reflected in the PSD impact and outcome indicators
## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year
Assessing VfM for ELAN is problematic in a year when the project has spent the majority of its efforts in closing down and then starting-up again, which includes recruiting and on-boarding of a largely new team, setting up project offices etc. Relatively little was spent via the flexible facility, which represents one of ELAN’s key efficiency indicators. The project also did not have the resources (nor was it an objective) to capture additional achieved NAIC in 2019 across ELAN 1.0 interventions to support further judgements related to project effectiveness indicators. Ultimately it was the late decisions and delayed procurement processes around the initial one-month extension, followed by an additional six-month extension, and then another late decision in July to award ASI the ELAN 1.2 contract that can be seen as poor VfM for DFID, rather than anything related to the supplier’s project performance.
For Essor, the VfM modelling and the assumptions underlying the assessment have been updated based on the Lubumbashi GUCE impact study for time and cost-savings for businesses, the expected two-year extension (cost projections include 2020-21), and the DSU’s feedback. The VfM reporting remains limited to quantitative indicators only; there is still need for a qualitative assessment of to what extent the reforms implemented by Essor offer good value for money in terms of their quality and sustainability.
For specific economy indicators, 2019 was a relatively poor year for ELAN (in the context of high performance over the first project phase). Average daily cost of TA rose substantially during the extension phase, with costs of £495 in Q1 and £572 in Q2, compared to £440 over the course of the project. This is accounted for by the fact that responsible exit and project closedown required a consolidated team of largely senior, international experts; this is hardly surprising during project close-down, particularly given the air of uncertainty surrounding the project and the need for experienced staff to mitigate against reputational risk. This trend has since been reversed, with a cost for TA of £439 during inception, and £425 for the short period of implementation in 2019.
Essor’s performance in this area is generally weaker than ELAN’s: the average daily cost of a long-term international consultant is £792 for those working remotely and £714 for the DRC-based consultants. Although these figures are not directly comparable to last year’s figures, they indicate that the remote TA comes at much higher cost mainly due to the additional expenses (flights, DSA’s, etc.). It is possible that the market rates for A2E financing expertise are driving this increase. The higher cost might also be due to the higher average fees, as indicated by the increase of average fee rates for long term, international consultants from £667 in 2018 to £698 in 2019.
Both ELAN and Essor have efficiency indicators related to investment generated by project partners in relation to workstream interventions. Essor made good progress on this front through leveraging between US$ 111.5-151.5 million under A2E including grant for technical assistance. ELAN had limited engagement with partners in 2019, so the proportion of investment leveraged against project spend is significantly lower than in previous years, though the effect on efficiency performance over the project lifetime to be limited.
In terms of equity, ELAN has historically performed well in measuring disaggregating impact especially based on gender. Towards the end of ELAN 1.0, the project developed detailed poverty profiling of its beneficiaries, while moving forward the project will include the ratio of disabled people in proportion to total beneficiaries, following agreement with DFID that this is now an important cross-cutting focus. On the contract, there is a need for Essor to develop a more detailed profiling of its beneficiaries as the current information is very limited. Given the nature of the interventions neither workstream VfM assessments include disaggregation for gender or poverty profile.
For Essor’s A2E work, given the nature of the technical assistance, it is difficult at this stage to assess the impact of the project on the poorest and the most vulnerable especially given the need for the projects to be commercially viable. Though there is an assessment (AfDB project concept note) done on the indirect benefits to the poor and women it will be difficult to attribute the benefits till the projects are up and running. An analysis of the GUCE registration records reveal women constitute a sizable segment of the current customer base. The GUCE is particularly responsive to financial and time constraints that face female business managers more so than male business managers seeking to register their business. Therefore, tailored outreach to women business managers could have the effect of yielding a significantly higher number of users, supporting equity claims for the project, and without having to alter the current GUCE operations.
The key quantitative measure for the programme’s overall VfM performance (cost-effectiveness) is in terms of cost per NAIC achieved. As discussed in Section C, the programme has not yet developed the evidence to demonstrate why non-quantified benefits will be sufficient to justify DFID’s investment.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
It would be relatively unusual for a programme to have achieved and captured monetised attributable impact before the end of its implementation period that goes beyond its costs. Our earlier assessment suggests that the programme may not reach its short-term impact targets for aggregate NAIC as included in the PSD log frame. ELAN 1.2 terms of reference required the project to demonstrate that broader impact in terms of long-term transformational impact is significantly greater than the gap between project cost and NAIC.
With ELAN 1.2 increasingly focused on catalysing systemic change in target sectors that may have the deepest and most sustained impact for markets in the DRC, it is possible that DFID’s investment in ELAN will be good VfM, but this judgement is dependent on the extent to which achievements with respect to systemic change can be demonstrated. Following the work ELAN intends to do in Q2 2020 in clearly defining its outcome indicator 4 on market system changes, the project should then invest resources into defining criteria and standards which allow for a qualitative assessment of project performance and contribute to the evidence base regarding the VfM achieved by the project.
The VfM case for Essor in its entirety is less persuasive given there has been a significant reduction in NAIC targets, which are well below the cost of the project; a strong story on the impact indicator 3 results, backed by good evidence, is needed to justify why the project should continue from a VfM perspective. Currently, it is not clear whether the project overall is on track to achieve sufficient impact (whether quantifiable or not). All the impact benefits so far come from just two outputs (A2E and GUCE). The other interventions are not assumed to contribute to impact. The project needs to make a clear case for why the current (and new) interventions offer good VfM in terms of overall expected impact relative to cost. If the project is not able to show clear (expected) impacts for the interventions other than A2E and GUCE, then Essor should shrink down to these two functional interventions.
Ultimately the rationale for extending both project’s implementation periods beyond 2019 was to increase the likelihood that the investments made so far achieve sustainable impact, given there was a significant risk that without extension that little in the way of genuine market system change would occur in the case of ELAN, while Essor’s interventions could not yet be managed alone by GoDRC. From that perspective, both projects have a strong VfM argument for continuation over the remainder of their contracts.
E: RISK
Overview of programme risk (noting the rating from p.1) and mitigation
Risk rating of the entire PSD programme is Major mainly driven by an uncertain, unstable and non-transparent political environment in which projects and DFID are operating. A detailed Risk Matrix for the PSD Programme is updated quarterly, using quarterly risk updates from partners (ÉLAN and Essor), as well as regular meetings between DFID and its partners. Net significant risks are identified and raised with the Team Leader and if needed to the Senior Leadership Team.
Essor has revised its risk management procedures and aligned terminology with DFID’s approach, to improve conformity with how risks are reported across DFID projects. For ELAN, the DSU has recommended that this is done as soon as possible. While ELAN provides risk assessment at various levels to impressive effect, it is recommended that the project expands upon its risk matrix to allow for an understanding of residual risk remaining following mitigations, and for the risk matrix to show previous updates (rather than a quarterly ‘snapshot’) so that both ELAN and DFID can understand the extent to which treatable risks are escalating or de-escalating.
Whereas ELAN has consistently impressed with its use of political economy and conflict analysis, this was historically an area of weakness for Essor. While the project does now use political economy analysis (PEA) across its two workstreams, there is a need for future PEA to delineate the processes needed to operationalise findings, given this has been suboptimal in 2019.
Context risks
Political tensions, that appeared to be reaching boiling point in late 2018, largely dissipated over 2019. Felix Antoine Tshisekedi was declared the winner of the Presidential elections by the national independent electoral commission, although results were contested by independent sources. While peace and stability were largely maintained related to the election, the business of government has been disrupted by the political transition which has slowed executive decision making, impacting both projects. ELAN’s extension phase Political Economy and Conflict Analysis (PECA) indicated that there are lingering concerns among businesses about the stability and durability of the current political settlement, leading to caution when considering new investment. For Essor, project progress has been hampered by decisions related to the GUCE’s financial stability, whilst a Minister of Energy was only appointed in September 2019.
Delivery risks
While both projects have received extensions to allow for implementation to continue, previously identified risks around hastily organised transitions between contract phases have been realised to various degrees for ELAN. The project has lost many of its former staff members, forcing the project to spend most of its inception on recruitment. There has been some erosion of its relationship with partners. Uncertainty around the length of ELAN 1.2 poses a significant reputational risk to the programme, as well as weakening the likelihood of achieving impact and VfM.
The programme scope has been made narrower in terms of sectors and geography to align with DFIDs strategy in country. This undermines the previous mitigation measure of casting the net wide to balance successes and failures for private sector participation across sectors and geographies. This is a new risk that will require ongoing monitoring and mitigation.
Update on partnership principles
The Partnership Principles (PPs) are not being applied to this project and it is recommended that this continues to be the case as no financial support is being provided directly to government.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
Key cost drivers for all projects this year have been for fees and expenses.
ELAN’s spend in the extension period was £1,966,314 against a budget of £1,981,829. ELAN 1.2 spend in 2019 (for inception and initial implementation) has been £907,414. In the last few years of ELAN 1.0, the project’s main cost driver had been its flexible facility, which was significantly reduced this year due to the nature of 2019 for the project. Essor’s total project spend was £5.68M for the period of January to December 2019; while higher than usual, this is due to a reconciliation invoice of just under £0.4m (reason for this invoice is explained in detail further below). This brings down the project’s remaining budget from January 2020 to £10.37M. The DSU’s spend was just under £0.7m, largely in line with its anticipated spend.
In early 2019 (on 20 March), PwC UK received a formal communication from DFID to initiate a substantial no cost amendment to extend the project beyond its current end date in January 2020. Essor, under no-cost extension, is intended to make use of the remaining budget (the value is estimated at £10M for two years in line with Essor’s underspend of £10.37M). The Essor extension process was, however, considerably delayed and a two-year extension contract was only signed between the two parties in December 2019, just before the end of Essor’s current contract (5 January 2020). The project will now continue until January 2022.
Financial reporting has been mixed for both projects in 2019. Essor’s financial reporting has been timely, with invoices and rolling three-month forecasts received on a monthly basis. There was, however, a significant underspend against projections for 2019. The overambitious workplans and the accompanying forecasts have not been realised, meaning that the project has struggled to meet DFID requirements on forecast variance. ELAN has a long track-record of timely financial reporting, but similarly struggled with meeting DFID’s variance requirements on forecasting during the ELAN 1.2 inception period, due to slower than anticipated recruitment.
Both projects are behind schedule with their annual financial audits. For Essor, this has been due to the significant financial reconciliation and financial restructuring Essor has gone through over the past year; it is now scheduled to be finalised in December 2019. There will be a second audit in the first quarter of 2020. While ELAN has conducted a number of timely internal and external audits throughout its implementation, actively following up on recommendations, the audit for the last phase of the project has been continuously delayed over the last few months, causing some frustrations for DFID. This audit is currently underway and is expected to be completed during the first quarter of 2020.
In terms of improving financial management, ELAN has developed financial improvement plans following previous audits, with trackers shared with DFID as part of quarterly reporting; these appear to be useful for DFID DRC’s understanding of the quality of financial performance and we would advise they continue following the latest audit, particularly given that the large turnover in core team members might lead to a loss of some of the learnings over the first phase of the project regarding optimal financial management.
Essor experienced serious financial reporting and internal financial management issues in 2017 and 2018 that have only been uncovered over the past year. Since the start of 2019, the Essor finance team has conducted a reconciliation of costs billed to DFID and costs paid to suppliers between January 2017 and December 2018. This review highlighted a significant variance, principally related to invoices that were submitted late or contained inaccuracies that were subsequently not billed to DFID. Going forward, Essor will complete a reconciliation every two months in order to comply with DFID’s three-month billing requirements.
Partnerships between DFID and the projects are largely focused on the operational aspect, and there is clearly a need for a rebalancing of this with more strategic level engagement. For Essor, there is significant value for the project in tapping into sectoral expertise within the wider DFID network (particularly in the area of A2E), and leveraging DFID’s existing relationships with other development partners in the DRC and beyond. Given the challenge ELAN faces in its work supporting meso and macro level market actors in catalysing systemic change in the short timeframe, support from DFID will be required in ensuring that interventions can either be picked up by other development partners in the DRC or other DFID funded programmes such as FDSA.
Coordination and collaboration between ELAN and Essor has been promoted in areas where there is synergy between the components. The sharing of a range of consultants between the projects in part-time PEA and GESI advisors as well as the new project manager of the A2E workstream (previously part of ÉLAN’s A2E team), who have built in-depth institutional knowledge of the overall PSD programme and the DRC context, does have the potential to facilitate further synergies between Essor and ÉLAN 1.2 where they exist (particularly in relation to work in the energy sector and in Goma, as ÉLAN will continue working on A2E issues and mainly operate out of Goma moving forward). The recommendation in this Annual Review for Essor to design and implement a structured private sector engagement strategy would be made more feasible through utilising ELAN’s experience and network with the private sector, including with private sector groups and associations in Goma.

The vfm of the DSU component has not been assessed however there are lessons for future programmes that can be learnt from having a standalone M&E component. A strong QA function from appropriate levels of seniority is essential to ensure that it is not resource and cost intensive compared to the overall quality of the outputs and result achieved. Future PSD implementation will need to carefully consider how there can be greater complementarity between the different components of the programme.

G: MONITORING, EVIDENCE & LEARNING
Monitoring
Essor’s MRM system has been designed to enable monitoring, guide strategic planning, inform resource mobilisation as well as take corrective actions. The system as a whole incorporates the ToC and results chains underpinning project and workstream logic, and a repository to collect, store and report evidence against the logframe. We recommend that the Essor M&E team should be engaged in supporting learning and intervention design, as well as monitoring and evaluation.
2019 saw little in the way of monitoring of results for ELAN, given the nature of the extension phase and the subsequent inception period. In preparation for the Annual Review the ELAN 1.2 team followed up with a number of ELAN 1.0 partners to ask whether they had continued or expanded upon the practices introduced by the project, to support results collection for this Annual Review. The MRM team are producing a new MRM manual in March 2020 to lay the foundations for monitoring for the second phase of the project.
Monitoring, measuring, and attributing gender and social inclusion impacts continues to be limited in the Essor project, whereas the revised ELAN 1.2 logframe is well-calibrated to capture GESI achievements; historically this has allowed ELAN to be more ambitious than Essor in its work in the GESI space. Mixed performance from Essor is also an outcome of their modest engagement with the GESI space more generally: there is a limited range of meaningful gender impacts to report on. The PAM dashboard has been a positive step to address the problem of systematising and recording the project’s work on GESI mainstreaming – it is updated quarterly and used for planning. In 2019, the current GESI advisor again reviewed the logframe, but there was limited scope for modification given the impending project closure. While plans have been made to ‘measure more’ in the coming year, we note that measurement remains very limited. Having the same international GESI adviser across both ELAN and Essor could allow for some synergies to be realised between the projects in their respective approaches.
Evidence
Given the year ELAN has undergone, there’s not been much in the way of generation of evidence. Quick assessment studies were undertaken by the ELAN 1.2 teams for the intervention on an agriculture helpline (partner: Viamo) and on reducing taxes and harassment on cross border trade (partner: ACT Kasumabelasa and ACT Goma) captured data on number of women and men changing their practices.
Essor has completed significant studies this year which have strengthened the evidence around its theory of change and results reporting: (1) Essor commissioned an evaluation of the GUCE single window (antenna) in Lubumbashi, finalised in August 2019, which provides a clear estimate of the changes that the GUCE single window has brought about; (2) Essor completed an evaluation of the Entreprenant pilot, informing an interim report and the design of the next phase of quantitative data collection. The quantitative survey took place in March 2019 to follow up with 174 of the 432 Entreprenants registered during the pilot.
Essor is yet to complete its planned evaluations of the financial and functional sustainability of the RCCM/GUCE; the creation of the RCCM as a fully national system linked to the regional database in Abidjan, and an assessment of the business extension services including the accounts register and the collateral registry. These are part of the project’s third impact indicator but as the interventions are not yet complete (and hence the impacts not yet apparent) an assessment of actual impact is not appropriate. However, at this stage the project should assess the likely impacts and develop a set of projected impact targets.
The DSU completed its Final Evaluation design in May 2019 and has undertaken several initial evaluation activities that culminated in the generation of an Annual Evaluation Report in December 2019. Given there have been significant changes to the programmatic context, with both projects now in implementation until 2021 (and perhaps longer in the case of ELAN), there will a redesign process in 2020 to ensure that the timing and scope of activities is better aligned with ELAN and Essor’s implementation plans moving forward.
Learning
Programme wide learnings have been developed in 2019, led by the DSU, with collaboration from ELAN, Essor and DFID:
- Two research papers to support Essor were developed: Lessons from the Introduction of the Entreprenant Status in OHADA Countries, and Lessons from Implementing ‘One-Stop Shop’ business registration in OHADA countries;
- A programme wide external learning event was held in Kinshasa in June, where ELAN and Essor both presented to development partners to showcase programme work;
- Research studies on Agriculture and Artisanal and Small-Scale Mining, Disruptive Technologies, and a Political Economy Analysis in the DRC were developed to support DFID’s ongoing development of the PSD Programme 2.0 business case;
- Research briefs were developed for three of the studies (both OHADA studies and the Disruptive Technology study). A learning brief was developed on GESI mainstreaming in programmes and lessons learnt from the PSD programme, which derives some key lessons and recommendations for others working on similar programmes.
Much attention during ELAN’s extension period was on developing knowledge products based on learning from ELAN 1.0 interventions, which provided a critical analysis of the strategies and drivers of success for the business models ELAN 1.0 introduced and the challenges faced. These products can provide learning for the new project team. The number of studies and knowledge products are quite extensive and cover most of the major areas of work for ELAN 1.0, though it seems little of the learning has been incorporated into sector strategies and planned interventions for the second phase of the project.
ELAN has three GESI learning briefs planned for the next few months: the first presents a business case for GESI in MSD programming; the second reviews existing literature in order to develop and present frameworks capturing GESI in MSD programmes, while the third will present guidelines developed for ÉLAN’s GESI work. Additionally, ÉLAN is developing a set of TORs for an independent piece of research on women’s voice, representation and participation in MSD programming.
Essor is yet to produce significant learning outputs from its closed workstreams as evidence to how those workstreams have contributed to project outcomes and impacts This could be generated in workstreams such as the potential application of the work on provincial taxes and harassment carried out by the Anti-Corruption workstreams to the plans of the BER workstream. The project has completed two evaluation studies (discussed above), with another on A2E close to finalisation, and which provide useful learnings and insights for government and the development community; as of yet, these have not been repurposed for communication and dissemination to a wider audience.

Progress on recommendations from previous reviews
Out of 27 recommendations from the last Essor Annual Review, 11 were implemented, one was rejected, and seven are works in progress. The remainder of those not implemented are largely irrelevant given the changes to the project. Given the last review of ELAN was a project completion review, no recommendations were directly made to the ELAN team, but rather for future DFID DRC. Most recommendations made to DFID across both the last annual reviews have been partially adopted. Some of those recommendations were related to the PSD 2.0 programme, such as reviewing the results framework and reducing the emphasis on achieving NAIC versus more substantive market systems and business environment changes and so only become implementable once that programme is underway.