Conflict Pool Project Form v.2

PLEASE REFER TO THE GUIDANCE WHEN FILLING IN THIS FORM
Summary

Project title:
Support to IGAD mediation and ceasefire monitoring and verification in South Sudan

Country/Countries:
South Sudan

BSOS objective(s):
Early warning
Rapid crisis prevention and response
Investing in upstream prevention – one of the following: / helping to build free, transparent and accountable and inclusive political systems / Strengthening Security and Justice / Building the capacity of local populations to resolve the conflicts that affect them / Building the capacity of regional and multilateral institutions to prevent and resolve conflicts

Total Cost to CP:	Duration:
Flexible up to £1m		August 14 – March 15

Implementing partner(s):	Lead department:
Intergovernmental Authority on Development (IGAD) and contracted expertise		FCO/DFID

HMG Project Officer:	Date submitted:
Funa Sepiso		July 2014

Approved by:
Matt Cannell

*Seen and agreed by:
BE Juba, BHC Khartoum, Sudan/South Sudan Unit London, MOD IPP, RCA Addis Ababa,

Part One: Strategic Case

Why are we carrying out the project: context, aims and background
1.1 Programme:
Africa

1.2 Results Offer:
Sudan – South Sudan

1.3 Result/impact the project will contribute to (taken from Results Offer):
Strengthened international, national and sub-national peace processes and peace building efforts which are more effective and contribute to the reduction of conflict related violence / More inclusive and accountable governance and deepened democracy.

1.4 Project outcome:
To contribute to a resolution of the conflict in South Sudan by supporting IGAD’s effort to maintain an effective ceasefire and enabling mediation between the parties so that an inclusive and lasting political settlement is agreed. The settlement is expected to address the political, governance, social and economic dynamics which have contributed to the crisis in South Sudan.

1.5 Theory of change (maximum 200 words):
If IGAD’s overall capability is strengthened by the inclusion of experts and military advisors, it will be better able to: / Support IGAD mediation between the parties to the current conflict in South Sudan; / provide support and expertise to an inclusive negotiation process; and / Support IGAD in fully establishing and sustaining an effective mechanism to monitor the ceasefire and generate trust and confidence across a broad range of constituents. / This will help build the foundation for durable peace, stability and sustainable development in South Sudan. / Through this financial and manpower support, the UK is better positioned to influence the overall IGAD-led processes and ensure technical capacity is strengthened. The effectiveness of the IGAD process should ensure that: / the agreement on cessation of hostilities agreement holds; / improved stability and humanitarian access; / inclusion of key issues and stakeholders in the political talks; and / progress towards national reconciliation and an inclusive and durable political settlement.

1.6 Implementing partner(s):
IGAD is a regional organisation[1] that aims to expand regional cooperation, increase members' dependency on one another and promote policies of peace and stability in the region in order to attain food security, sustainable development and environment management. / The UK has supported IGAD’s Transitional Support Unit (TSU), in particular the Joint Political and Security Mechanism (JPSM) which was part of the AU High Level Implementation Panel. The TSU was established in November 2011 recognising that a regional mechanism was needed to provide financial and logistical support for talks on unresolved CPA issues between Sudan and South Sudan. It has been funded to date by UK, Norway and the Netherlands and with seconded staff from Norway and the Netherlands. / The UK provided £625k ($1m) to IGAD in March 2014 through the co-financing arrangement with Norway to specifically support mediation and the political talks for the period to July 2014. Norway has a programming agreement with IGAD with provisions on the use of all funds including the UK contribution. To manage additional work in support of mediation efforts in the South Sudan conflict, we are discussing potential options for streamlining support we provide through IGAD and AU. / Funds agreed in March 2014 have also provided expertise to fill technical gaps needed for the establishment of the Joint Technical Committee (JTC) for IGAD’s Monitoring and Verification Mechanism (MVM). / This bid seeks/recommends: / a financial contribution to support the full deployment of the MVM (£625k) / continued secondment of expertise to the MVM (£300k); / ad hoc support to IGAD for the talks (funding is flexible, up to £75k). / The financial contribution can either be funnelled through donor agreements currently being coordinated by Denmark or through a US contract for support to the MVM. / In parallel the UK is also supporting IGAD’s work in Somalia, and is considering how best to help support building the organisation’s capacity in the future.
[1] Members are Djibouti, Ethiopia, Kenya, Somalia, South Sudan, Sudan and Uganda. Eritrea has suspended its membership but its request to re-join has not yet been approved by IGAD member states.

1.7 *Background (maximum 500 words):
The current crisis in South Sudan started in Juba on 15 December 2013 and quickly spread to other parts of the country, triggered by violence between factions of the presidential guard. President Kiir quickly labelled it an attempted coup led by the ex-Vice President Riek Machar, who denies involvement in any coup attempt and suggests that GRSS used this narrative to try and silence Kiir’s political opponents and critics. / Over six months on, the picture remains bleak. Although in many areas the intensity of fighting between Government and opposition forces has subsided, fighting continues in some locations, despite Kiir and Machar agreeing a cessation of hostilities in January and recommitting to a ceasefire in May, people still fear being targeted on the basis of their ethnicity. Atrocities committed by both sides, including by the military and the police, against civilians in Bentiu and Malakal in April have particularly reinforced these fears. The humanitarian situation is desperate, with over a million people displaced, up to a 100,000 of whom are in UN bases, and thousands more fleeing to neighbouring countries. / Under Ethiopian leadership, the regional Inter-Governmental Authority on Development (IGAD) is mediating a political solution and has convened talks in Addis Ababa. Strong support for mediation efforts by IGAD and international pressure on the parties has yielded some results with the ceasefire agreement, the release of political detainees, recommitment to the ceasefire, and agreement in June to resume inclusive talks towards a transitional government. The most pressing need remains for the parties to engage in meaningful dialogue and make progress towards a political solution. The adoption of a new UNMISS mandate on 27 May with authority to provide force protection and other support to IGAD monitors should enable the gradual withdrawal of Ugandan forces to pre-conflict locations. Their continued presence risks undermining the whole process by providing one side with a pretext for not engaging in meaningful talks. / The UK with our fellow Troika countries (US and Norway) and the EU, continue to fully support the IGAD process, delivering coordinated messages to both sides on the need for: the cessation of hostilities to hold; humanitarian access; and political dialogue. We are also taking forward EU and UN sanctions regimes which will send clear messages to the parties by targeting those who obstruct peace efforts and commit atrocities. / The two main parties to the recent violence have committed to an IGAD-mediated process which requires all military and other action likely to undermine the peace process to cease. Monitoring and verification arrangements have been developed and some Monitoring and Verification Teams have been deployed. The UK intends to build on technical assistance already provided and improve the effectiveness of the mechanism by continuing to deploy technical advisors. / In addition financial support will be required for the MVM to operate effectively. The US has already deployed support worth $6m, which includes funding for vehicles, IT, facilities, helicopters, equipment, personal protection equipment, and fuel. This is expected to cover the period to August 2014. UK funding could contribute directly to US support arrangements already in place.

Part Two: Appraisal Case

How the project will work theory of change, outcomes, activities, indicators and
the risks.
2.1 Outcome:
To contribute towards a resolution of the conflict in South Sudan, by supporting and enhancing IGAD’s mediation between the two parties to maintain the ceasefire agreement, and achieve progress towards an inclusive and durable political settlement,

2.2 Outcome Indicators:
Indicator	Baseline	Target / ( March 2015)	Source of information & who will collect
Number, range and timeliness of experts provided to support talks and mediation in response to IGAD’s requests.	Initial talks started and a cessation of hostilities document has been signed by both sides. But IGAD’s technical capacity is weak and there is a strong requirement for additional experts to support various aspects of the process	IGAD able to effectively facilitate negotiations and mediation between the two parties and establish and sustain robust monitoring and verification arrangement in order to maintain the ceasefire agreement.	Existing TSU narrative and financial reporting / Internal UK reporting on talks
Monitoring and Verification Mechanism (MVM) has the capacity to implement its mandate	Joint Technical Committee (JTC) set up and initial guidance for establishing MVM agreed. Three MVM teams have deployed. Awaiting deployment of IGAD Protection Force (approved by UNSC)	JTC fully operational in Juba; / Ten effective Monitoring and Verification Teams (MVT) deployed to several locations in South Sudan, allowed necessary access to be fully operational and producing good quality and independent reports.	IGAD/JTC daily situation reporting; / Post reporting; / UN and partner reporting; / Reporting by the parties;
The Special Envoys’ Secretariat is functional and supporting the work of the Envoys	Some secretariat support available to IGAD envoys but some capacity gaps. IGAD staff are currently redeploying from lower priority tasks.	IGAD Special Envoys have a clear mediation strategy, developed and supported by the Secretariat. / IGAD is delivering effective meetings	Minutes from Secretariat Meetings / UK envoy reporting / Partner views

2.3

Output 1: Strengthen IGAD Envoys’ secretariat in Addis Ababa
Activities
Activity	Expected date
Strengthen secretariat in Addis Ababa and recruit effective personnel.	By March 2015

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Meetings taking place, effectively facilitated by IGAD, leading to decisions which support a positive trajectory in the peace process.	Initial meetings have taken place.	Meetings continue to take place with both parties, demonstrating clear movement forward including a possible summit.	IGAD, BE Addis, UK Special Envoy
Technical support provided to the Envoys	Little technical support in place	Technical support provided in line with HMG and IGAD priorities	IGAD, IGAD Envoys’ Secretariat, BE Addis, UK Special Envoy

Activities
Activity	Expected date
Provision of diplomatic and technical support to IGAD to facilitate dialogue and meetings between two parties	Ongoing

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Qualified experts and technical advisers in place,	Ad hoc approach: some experts and technical advisers recruited in response to urgent requests.	IGAD mediation is supported by effective experts and advisors	IGAD Envoys’ Secretariat, BE Addis
IGAD clarifies its priority requirements	Ad hoc approach: IGAD is not coordinated in its requests	IGAD better at articulating formal requests for assistance

Output 2: An effective Monitoring and Verification Mechanism is in place
Activities
Activity	Expected date
Continued support to MVM‘s deployment	March 2015

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect

MVM deployed and operational	Three MVM teams deployed	10 MVM teams deployed and operational	Post reporting; / IGAD MVM reporting / UN/partner reporting; / Reporting by the parties; / Secondees’ reporting
HMG has visibility of the MVM’s performance	Some reporting and insights	Continued reporting of insights	Secondees’ reporting

2.4 Risks
Risk	Likelihood	Impact	How we will mitigate risks	Risk owner
Assistance is not requested or deployed in a timely or effective way.	M/H	H	The UK has responded promptly to requested for support and will continue toencourage IGAD to take a more systematic approach to requests for support, which are based on sound capability assessments.	IGAD/HMG
Mismanagement of funds / lack of financial control	M	M	IGAD staff have to date been obliged to reconcile the financial demands of donors with the political pressures of IGAD and the IGAD Special Envoys. Clear donor regulations for the use of funds, combined with a strong programme coordinator, have helped. / IGAD has agreed to the establishment of Budget Committees, involving IGAD and donor country staff (including the UK), which will assist in overseeing spending. / The Danish government is also seconding an individual to work on budget issues for the IGAD MVM in Juba.	IGAD, through close coordination with donors
IGAD unable to recruit suitable staff or experts to properly handle negotiations	M/H	H/M	There is the potential for IGAD staff to be overwhelmed, and we will therefore look to provide assistance, in tandem with other donors wherever possible. / For example we have supported Norway to set up formal budget committees with IGAD, / The Troika and the EU continues to provide political and technical support to IGAD in taking negotiations forward.	IGAD
Delayed deployment of MVM	H	H	Not within full control of programme, but planning expertise would help mitigate potential delays. HMG strategic engagement	IGAD
Interference by parties in operation of MVM	H/M	H	Not within control of programme, but timely reporting from programme would inform high level political messages. HMG strategic engagement	IGAD
Duty of care for seconded experts	M/H	H	Security provision included in contracts; Engage IGAD on establishing a clear duty of care regime	HMG/IGAD

2.5 * Why we should still go ahead if this is a high risk project:
Ministers have indicated that South Sudan is a priority. The potential benefits of peace in South Sudan justify both the risk and the relatively high expenditure. They include a reduction in lives lost and humanitarian emergencies, enabling the UK to refocus its energies on recovery and poverty reduction; and increased stability, trade and investment. / To assist with follow up programming risks will be reviewed quarterly.

2.6* Compliance with the International Development Act (Gender Equality) 2014
The primary aim of this intervention is to contribute to the resolution of conflict in South Sudan with a view to progressing towards an inclusive and lasting political settlement agreement. Whilst gender inequality is considerable in political, social and economic contexts in South Sudan, underpinned by the existence of a strongly militarised male dominated political elite, this intervention will not address gender equality issues, but focus mainly on strengthening the secretariat in Addis Ababa through the recruitment of effective personnel and the provision of diplomatic and technical support to IGAD to facilitate dialogue and meetings between the two parties. IGAD will work with primary stakeholders to support engagement in a constructive and inclusive dialogue based on respect for human rights, the rule of law and the rejection of the use of force. The immediate priority is cessation of hostilities.

2.7 * Sustainability:
It is difficult to predict the trajectory of the peace process for South Sudan – progress has been erratic. There are currently significant gaps in the funding required by IGAD, and high levels of spending. We may therefore need to return to this area in FY 15/16 and provide further support subject to progress, or the lack thereof. / The deployment of technical advisers into the IGAD Secretariat will not formally build capacity but IGAD’s overall capabilities and performance are likely to be enhanced indirectly.

Part Three: Commercial Case

To ensure that the department meets its legal obligations in terms of procurement and contracts

3.1: Which of the Departments’ procurement and contracting regulations will be used?
DFID regulation for procurement of civilian expertise; FCO administrative arrangements for co-financing with other donors;

3.2 Contracts: will the project implementers have a commercial contract, MOU or an accountable grant?
Technical assistance to IGAD will be provided through commercial contracts; The financial contribution to IGAD MVM will be made through an administrative arrangement with a donor partner and/or an MoU with IGAD;

3.3 Procurement: if using a contract, will the project involve a procurement process (Y/N)?
N

3.4 EU regulation: will the process follow EU guidelines (Y/N)?
Y

3.5 Templates: has the template being used been shared with implementers? (Y/N)
N

Part Four: Financial Case

How will the project be funded: who else is financing, budget, multi-year funding and activity costs. An activities-based budget must be submitted with the project form, showing activities, their cost, and timings.

4.1 Total cost to the Conflict Pool:
£1,000,000

4.2 * Funding breakdown by year:
Project start date: August 2014 Project end date: March 2015
2012/13	2013/14	2014/15
£		£ 1,000,000

4.3 * Other partner funding:

A number of other partners have either already provided funding (US, Japan, EU, Norway, Switzerland), are looking to do so (China, Netherlands) or are seconding staff (Denmark). The US is the largest donor this financial year, and only their contribution is recorded below, although more detail is available if required.

Project start date: Aug 2014 Project end date: Mar 2015
Partner contributing:	2012/13	2013/14	2014/15
US			$6m

4.4 ODA/non-ODA split:
Total ODA:	As a percentage: 100%
Total non-ODA:	As a percentage:

Part Five: Management Case

How the project will be run: monitoring, evaluation and human rights
5.1 Monitoring:

Method	Intervals	Carried out by	Follow up activity
Regular meetings with seconded experts	At least fortnightly	BE (HMG) Juba	As necessary
Meetings with MVM chairman / Chief of Staff	At least monthly	HMA / DHM	As necessary
Report on overall MVM performance	Monthly	Experts / DA	UK Special Rep engagement with IGAD envoys
Narrative financial reporting	Quarterly	Joint IGAD-donors budget committee	RCA / BE Addis

5.2 Evaluation plan:
Evaluation to be carried out at end of project will also inform wider/strategic approach to UK support to IGAD

5.3 * Human rights assessment (for security and justice projects only):
Refer to: Overseas Security and Justice Assessment for wider UK assistance to the sector; UN Security Council Resolution 2155 (2014) authorising support to IGAD MVM;