Project Annual Review

Title: Scaling Up Family Planning (SUFP) in Zambia
Programme Code: 202342		Review Date: March 2016
Project Value: 14,853,793	Start Date: 1 March 2012	End Date: 28 February 2019

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score		A	A+	A+	A+
Risk Rating	High	High	Medium	Low	Moderate

Financial Position

Original Programme Value	£10,000,000
Extensions/ amendments	£4,800,000
Total programme spend to date	£14,800,000

Summary of progress and lessons learnt since last review

The Scaling Up Family Planning programme provided £14.9m over four years (2012–2016) to increase use of family planning in 26 districts of Zambia; and build the capacity of the public sector to deliver quality comprehensive family planning services. During the course of the programme completion review, the Minister approved a £10million costed programme extension to continue the programme to February 28 2019, increasing the total programme value to £24,913,792 (Quest No. 5412520).

The programme has been successful and cost-effective, giving almost 300,000 women and girls access to family planning (50% more than the original target of 200,000). More than 70% of beneficiaries have been poor rural women. This has enabled DFID to save the lives of an estimated 1,000 women from 2011-15. The final cost of each disability adjusted life year saved was £67, compared to the £116 estimated in the original business case.

The three year costed extension to the SUFP project will enable the adaptation of the successful SUFP model to enable the complete transition to full government management of the programme at all levels, based on lessons learned to date. This annual review will therefore serve as a review of the SUFP programme from 2012-2016.

Recommendations
Key recommendations to be incorporated in the SUFP II programme design and implementation strategy include:

1. Intensify the focus on adolescents and explore cross-office collaboration with the still developing DFID Empowering Adolescents in Zambia Initiative. This will include improved targeting of adolescent boys and girls with services and behaviour change communication and supporting the implementation and monitoring of the national adolescent health strategy (DFID, SUFP II)
2. Empower the districts to manage their own family planning programmes and establish mechanisms for district-led performance monitoring, reporting and planning for family planning. (SUFP II)
3. Provide technical support for the implementation of the new Community-Based Distributor (CBD) Strategy and support the monitoring, evaluation, and supervision of this cadre for the provision of injectable family planning methods, and ensure they are affiliated to the MoH (SUFP II)
4. Facilitate dialogue with government to amend current procurement arrangements, and convert to procurement through WHO pre-qualified suppliers. (UNFPA under SUFP II)
5. DFID to commission an evaluation of the first phase of the SUFP programme by December 2016 to inform family planning scale up plans – this will include community understanding of family planning and reproductive health issues and an assessment of the five-day training model for long term family planning methods and its effectiveness in equipping health providers.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3958281.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4379973.xlsx

Context

Zambia has among the world’s highest rates of maternal mortality. Although there has been a decline from 591 to 398 per 100,000 live births between 2007 and 2013/14[1], maternal mortality is associated with complications during pregnancy and childbirth, unintended pregnancies, unsafe abortions, and unsafe deliveries. Women in Zambia have a 1 in 79 lifetime risk of dying from pregnancy-related causes (compared to 1 in 5,800 in the United Kingdom)[2]. Historically limited knowledge about and low uptake of modern family planning methods result in high proportions of unintended pregnancies which have not only socio-economic implications on families and communities, but also on maternal and newborn morbidity and mortality. This is compounded by high rates of early marriage and teenage pregnancy. The 2013/14 Zambia Demographic and Health Survey (ZDHS) estimates that over 30% of women have given birth by age 18 (compared to 28% in 2007) and more than 50% by age 20; 29% of adolescent women age 15-19 are already mothers or pregnant with their first child[3].
[1] Zambia Demographic and Health Survey (ZDHS) 2007, and ZDHS 2013/14
[2] www.data.worlbank.org/indicator/SH.MMR.RISK The World Bank. Data. Lifetime Risk of Maternal Death, 2011-2015
[3] World Health Organisation (WHO) www.aho.afro.who.int/profiles_information/index.php/Zambia:Teenage_pregnancy

However, the 2013/14 DHS records progress in total fertility, which dropped from 6.2 to 5.3 between 2007 and 2013/14[4], and an increase in the demand for and uptake of modern family planning methods in rural areas, as demonstrated in Table 1. Over the same period, the contraceptive prevalence rate rose from 32.7% to 45%, and the unmet need for family planning among married women (or women in a union) declined from 27% to 21%[5].
[4] ZDHS 2007, and ZDHS 2013/14
[5] ibid.

Table 1: Current use of contraception (%) by background characteristics (ZDHS 2007 and 2013/14)
Background characteristic	Any modern / method		Pill		IUD		Injectables		Implants		Not currently using
Age / 15 – 19 / 20 – 24 / 25 – 29 / 30 – 34 / 35 – 39 / 40 – 44 / 45 – 49 / Residence / Urban / Rural	2007 / 8.4 / 27.9 / 33.9 / 31.6 / 29.6 / 25.1 / 17.6 / 42.0 / 27.6	2013 / 35.8 / 44.1 / 48.6 / 48.7 / 47.1 / 44.2 / 27.5 / 56.6 / 43.9	2007 / 1.5 / 8.2 / 12.1 / 11.0 / 8.9 / 5.5 / 3.0 / 18.2 / 7.0	2013 / 6.4 / 9.4 / 12.5 / 15.1 / 13.1 / 11.5 / 7.9 / 15.9 / 9.0	2007 / 0.0 / 0.0 / 0.0 / 0.2 / 0.0 / 0.2 / 0.2 / 0.1 / 0.1	2013 / 0.0 / 0.2 / 1.0 / 1.7 / 2.0 / 1.5 / 1.3 / 2.0 / 0.6	2007 / 1.9 / 8.2 / 9.0 / 7.8 / 6.0 / 6.1 / 3.1 / 10.5 / 7.3	2013 / 20.9 / 25.3 / 24.1 / 19.8 / 16.4 / 13.2 / 4.3 / 19.0 / 19.6	2007 / 0.0 / 0.0 / 0.4 / 0.6 / 0.5 / 0.8 / 0.2 / 0.9 / 0.1	2013 / 2.6 / 5.3 / 5.7 / 6.0 / 7.0 / 5.7 / 3.2 / 7.6 / 4.1	2007 / 90.3 / 66.7 / 59.7 / 62.4 / 62.8 / 66.5 / 75.7 / 51.6 / 63.3	2013 / 62.5 / 53.2 / 47.5 / 47.5 / 48.0 / 48.0 / 67.1 / 51.6 / 43.4

Outline of the programme and what it has achieved

DFID is contributing £14,800,000 to the four-year Scaling Up Family Planning (SUFP) programme, designed to address family planning needs through the rapid scale up of services for hard-to-reach, poor and vulnerable populations in 26 districts throughout Zambia. By strengthening the capacity of the public sector to manage family planning services at both facility and community level, building up the supply chain management of family planning commodities, and increasing the availability of goods and services, the SUFP programme has been instrumental in turning around outcomes for family planning and reproductive health.

Through a consortium agreement, the programme was led by Abt Associates in partnership with the Planned Parenthood Association of Zambia (PPAZ), Imperial Health Sciences (IHS), and the American College of Nurse Midwives (ACNM). It has also collaborated strategically with the Zambian Ministry of Health (MoH) and the Ministry of Community Development, Mother, and Child Health (MCDMCH), at all levels of the health system (national, provincial, district and community).

The programme had four main objectives:

1. Expand availability of family planning methods
2. Increase access to family planning services for underserved areas and populations
3. Increase community support for family planning
4. Increase public sector capacity to provide comprehensive family planning services

The SUFP programme is fully aligned with the national eight-year integrated family planning scale up Plan (2013-2020). It has received strong support and political will, and there is recognition that addressing family planning extends to better health outcomes for mothers, their families and their communities.

The programme has realized several of its key targets. For example, between March 2012 and July 2015, 286,456 additional women and girls had started using FP. At the time, this translated to 571,522 total couple years of protection (CYP), 326,582 unintended pregnancies averted, 888 maternal deaths averted, and an estimated 80,966 unsafe abortions averted. This increased even further over the remainder of the programme, and the following achievements have been made over the programme’s four-year life cycle from March 2012 to February 2016:

- 295,104 additional women and girls using modern family planning methods (147% above the programme’s target of 200,000)
- 578,241 total Couple Years of Protection generated (175% above the programme’s target of 330,000)
- 1,896 and Safe Motherhood Action Groups (SMAGs) trained as Community-Based Distributors (CBDs), increasing access to family planning methods
- 752 health workers and 65 family planning mentors trained to provide comprehensive family planning services, including long-acting and reversible contraceptives (LARCs)
- training of over 370 personnel in supply chain management
- <1% of SUFP-supported facilities experienced a stock-out of commodities
- Procurement of family planning commodities carried out transparently and in collaboration with Medical Stores Limited (MSL) and other key partners
- Family planning activities integrated into district health plans
- Centres of Excellence (CoEs) providing a full package of couple counselling for family planning and HIV testing and counselling.

As the programme progressed, two specific areas were intensified:

1. Couple family planning (CFP) and couple voluntary testing and counselling for HIV (CVCT). were originally designed and implemented as two separate DFID-funded programmes under SUFP and the ‘Intensifying HIV Prevention in Zambia’ project (implemented by Zambia HIV Emory Research Project, ZEHRP), respectively. However, they have since been integrated and implemented closely together to address Zambia’s high fertility rate and high levels of new HIV infections, both of which are a burden to the country’s health and social system. The Centres of Excellence established throughout the country provide the full package of HIV and family planning counselling and services, and focus on mobilising couples on the importance of uptake of long-acting and reversible contraceptives (LARCs) if they on ART. Integrating family planning and HIV testing and counselling (HTC) has also: a) limited the number of repeat visits couples potentially need to make to the facility, and b) reduced waiting times while seeking services. However, this integration of couple family planning and HIV counselling services is not clearly reflected in SUFP’s log frame, and will need to be given greater prominence if a successor programme is developed.
2. A stronger emphasis on adolescent reproductive health (ARH), especially given Zambia’s alarmingly high rates of early pregnancy and/or marriage. Young people often experience prejudice when seeking sexual reproductive health services, particularly in public health facilities. By intensifying the need for equitable and quality ARH services at both policy and service level and generating demand at community level, appreciation for the importance of providing interventions for young people has increased.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The 2013/4 ZDHS data shows good progress overall on the contraceptive prevalence rate (44%) and the national unmet need for family planning has decreased by 6 percentage points from figures in the original business case. SUFP did not conduct an endline survey therefore no data is available to measure outcome progress in programme areas for the period under review. However, SUFP has made significant progress against programme outputs, which suggests that the DFID has contributed to improvements in these outcomes indicators. By scaling up information on family planning, increasing access to a comprehensive range of methods, and strengthening providers’ ability to provide quality family planning services in the intervention areas, the programme has contributed significantly to changes in sexual reproductive health-seeking behaviours as well as service delivery, particularly at community level.

Outcome Indicator	Baseline	Milestone 2016	2016 Progress
Contraceptive prevalence rate	National: 27.6% for all rural married women (DHS 2007) / SUFP Project Areas: 48.5% (SUFP survey 2012)	National: 36% for all rural married women / SUFP Project Areas: 69% / Breakdown: / 15-19 yrs: 40% / 20+: 60% / Rural: 65%, Urban 35%	Exceeded Target National: 44% (DHS 2013-2014) / for all rural married women / SUFP Project Areas: Not measurable
Percentage of women and girls with unmet need for family planning in project areas	27% (SUFP Business Case)	Project Areas: 5% / Breakdown: / 15-19yrs: 8% / 20+: 2% / Rural: 7.5%,Urban: 2.5%,	National: 21% (DHS 2013-2014) / Project Areas: Not measured

Recommendation

Conduct an endline evaluation in the programme intervention districts by December 2016.

Output Score and Description: A+ - moderately exceeded expectations

The programme output indicators are: a) expanding choice and availability of family planning methods, b) improving access to family planning services, c) increasing support at community level, and d) improving the public sector’s capacity to provide quality comprehensive family planning services.

The programme exceeded the targets for three out of four output indicators, and has used innovative approaches to generating demand for modern family planning methods, particularly LARCs, since its inception. However, it moderately failed to meet its target to increase the public sector’s capacity to provide comprehensive family planning services, which constitutes 25% of the programme. The SUFP programme, therefore, scores A+.

Lessons and how these have been shared

The MoH has expressed the need for the SUFP programme to share its findings in order to help the government improve on its coordination and management of district-level family planning programmes, and better understand how it can enhance its own programming from a national perspective.

The following recommendations are made for the SUFP programme:
1. Intensify family planning programmes targeting adolescent boys and girls, and scale up provision of services to young people and communities, including the reinvigoration of Youth Friendly Corners in schools and facilities, enhancing sensitisation and awareness in schools and faith groups, and expand family planning outreach services (integrated with HIV behaviour change communication and testing) tailored to adolescents
2. Assist MSL with an investment plan to implement an electronic data system and abolish its paper-based system
3. Facilitate dialogue with government to amend current procurement arrangements, and convert to procurement through WHO pre-qualified suppliers. DFID, SUFP, UNFPA, USAID and other partners to document evidence on the cost-effectiveness and cost-savings of this option
4. Design a scale-up plan for the roll-out of SUFP’s ‘Camping’ approach in the new phase of SUFP
5. Empower the districts to manage their own programmes and establish mechanisms for district-led performance monitoring, reporting and planning, to eliminate any potential for creating dependency on the implementing partner
6. Provide technical support for the implementation of the new Community-Based Distributor (CBD) Strategy and support the monitoring, evaluation, and supervision of this cadre for the provision of injectable family planning methods, and ensure they are affiliated to the MoH
7. Draw up a realistic time frame for roll-out and ensure that all supported districts have adequate time to benefit from the programme and demonstrate tangible impact
8. More actively target and encourage men to participate in community and facility-based couple counselling services for family planning and HIV testing and counselling during the week as well as at weekends
9. MoH to develop and implement an articulate Community Health Strategy clarifying the roles and responsibilities of community health workers, and oversight of the different cadres
10. District health management teams (DHMTs) to be involved in the development of the new CBD Strategy, and provide monitoring and supportive supervision to CBDs as they scale up to provide injectables
11. Ensure that a thorough mapping assessment has been conducted before agreeing interventions at district level, in order to avoid duplication in reporting
12. Facilitate a single reporting system at district level to minimise duplication and multiple reporting channels
13. DFID to conduct an endline evaluation in the programme intervention districts that will report on the outcome indicators in 2016. This should include
  1. a comparison study of attitudes towards family planning in SUFP operational and none operational districts to inform SUFP II programming.
  2. In collaboration with ZEHRP facilitate a thorough assessment of the usefulness of the five-day training model and its effectiveness in equipping health providers for LARC
14. Monitor the implementation of the Adolescent Strategy in collaboration with the Adolescent Health Working Group, and report on progress and identifying barriers to implementation; help family planning committees advocate for district support for community level behaviour change communication (BCC) activities.
15. DFID to work with the SUFP programme to determine the underlying cost drivers for the cost per CYP for the programme.
16. Ensure consistent and accurate capture of all costs under the appropriate categories to improve accuracy of data for value for money (VfM) calculations.

## C: DETAILED OUTPUT SCORING

Output Title	Expanded availability of choice of family planning methods
Output number per LF		1	Output Score	A++
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		Y (from High)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of additional women and girls using: i) short term methods and ii) long term reversible methods / (disaggregated by: method type; urban/rural; age 15-19, 20+; source of method)	Total: 200,000 broken down as follows: / Short-term: 117,000 / Rural: 75,000 / Age 15-19: 15,000 / Age 20+: 60,000 / Urban: 42,000 / Age 15-19: 5,000 / Age 20+: 37,000 / Long-term: 83,000 / Rural: 33,000 / Age 15-19: 5,000 / Age 20+: 28,000 / Urban: 50,000 / Age 15-19: 5,000 / Age 20+: 45,000	Substantially Exceeded: / Total: 295,104 / Short-term: 237,605 / Rural: 183,671 / Age 15-19: 51,138 / Age 20+: 132,533 / Urban: / Age 15-19: 11,456 / Age 20+: 42,478 / Long-term: 57,499 / Rural: 44,380 / Age 15-19: 8,318 / Age 20+: 36,062 / Urban: 13,119 / Age 15-19: 2,158 / Age 20+: 10,961
1.2 Percentage of public sector facilities covered by the programme that experienced a stock-out of the full comprehensive package* of FP methods during the last 12 months / (*comprehensive package of FP methods: IUDs, Jadelle, DepoProvera, OCs, condoms)	1.33%	Achieved: / 1.20%
1.3 Couple Years of Protection generated attributable to the programme / (disaggregated by: urban/rural; age 15-19 and 20+)	Total: 330,000 / Rural: 210,000 / Age 15-19: 70,000 / Age 20+: 140,000 / Urban: 120,000 / Age 15-19: 30,000 / Age 20+: 90,000	Substantially Exceeded: / Total: 578,241 / Rural: 367,972 / Age 15-19: 84,646 / Age 20+: 283,326 / Urban: 210,269 / Age 15-19: 38,647 / Age 20+: 171,623
1.4 **Percentage of national forecasted need in FP commodities met by programme (**linked to UNFPA’s commodity procurement function)	4%	Substantially Exceeded: / 26%

Key Points

Score: A++ (Output substantially exceeded expectation). All targets were met under Output 1, and some were exceeded significantly.

Indicator 1.1: 295,104 new users were reached, and the programme has substantially exceeded its target by 147.5%, with an unprecedented increase in uptake of short-term methods in rural areas (245% above target) and among rural women in the 15-19 age group (340% above target). Short-term methods are traditionally more well-known and have been provided for several years at facility level. The results further support evidence that injectables are the most commonly used contraception among women between the ages of 15 and 45[6]. As demonstrated in Table 1, young women of age 15 – 24 prefer short-term FP methods, particularly Depo-Provera and other injectables. There is still need, however, at a national level to intensify family planning programming that targets adolescents in order to address the country’s excessively high rates of teenage pregnancy, which are associated with high maternal and neonatal morbidity and mortality. Table 2 demonstrates trends in age at first sexual intercourse among young people since the 2001/02 ZDHS, which have increased significantly for both boys and girls, particularly in 2007, and efforts need to be scaled up in schools, communities, in faith communities, and in peer-to-peer counselling.
[6] ZDHS 2013-14 Preliminary Report

Table 2: Trends in first sexual intercourse (ZDHS 2013/14)[7].
[7] World Health Organisation (WHO) www.aho.afro.who.int/profiles_information/index.php/Zambia:Teenage_pregnancy

The low uptake of LARCs is largely attributable to inadequate practice by the service provider: ideally, this should be performed consistently, in-service and on available clients. However, the nature of the intervention (which requires woman to partially undress), the need for a separate, confidential space, and myths about intrauterine devices (IUDs), such as pain during sex and spontaneous abortion, makes it challenging to encourage uptake. There have also been incidences of provider bias where women are encouraged to use non-invasive methods, or the facility is unable to provide IUDs because they do not have the relevant skills to provide the service. However, the SUFP programme has commendably a) increased awareness at community level about LARCs, b) scaled up their availability and provision, and c) trained health workers to ably provide information and services for the full package of family planning methods.

Although high uptake and demand for family planning at facility level is the main objective of this programme, they present several challenges: a) overcrowding in the facilities resulting in long waiting times, b) inability to provide services that require separate space and privacy, c) an additional burden on an already limited and overstretched human resource. These are all compounded by high rates of staff attrition where health workers are deployed to different posts, or are absent due to attendance at training programmes or workshops.

Indicator 1.2: There is a reduction in SUFP-supported facilities experiencing stock-outs, demonstrating an improvement in the FP commodities supply chain. SUFP has collaborated with MSL, UNFPA, IHS, MoH and MCDMCH (the maternal and child health functions have now been reintegrated into MoH) to strengthen the capacity of personnel responsible for supply chain management at central and district levels, 371 of whom have been trained. Following an overwhelming initial response for Jadelle (which led to stock-outs when they were first introduced), SUFP has worked with MSL, UNFPA, and MoH district teams to ensure adequate stocks of commodities, and this has been reinforced by annual quantification meetings to plan for commodity procurements. SUFP also implemented and monitored a tracking system for commodities, and carried out a district-specific mentorship programme on commodities and supply chain management; trainees provided onward training and mentorship to their peers. Through this mentorship programme, district-level stock-outs were virtually eliminated, contributing significantly to this indicator.

Indicator 1.3: There has been a substantial increase in couple years of protection (CYPs), and the programme has exceeded its target of 330,000 by 175%. The high uptake at rural level (134% above target) can be attributed to the programme’s highly innovative and successful ‘Camping’ and ‘Camping Reloaded’ approach, an evidence-based model which involves the placement of volunteers and health workers in communities to conduct outreach activities and promote couple counselling and the use of family planning methods; this model brings family planning services closer to the communities, and has played a pivotal role in the attainment of this indicator. SUFP has been instrumental in lobbying for a policy that would enable CBDs to provide injectables; this which will further increase access to an even wider range of commodities at community level. In addition, this service can be provided directly by CBDs during outreach activities and will a) minimise the need for clients to access it only at facility-level, and b) reduce the burden on already over-stretched health facilities.

Indicator 1.4: The programme achieved a substantial improvement in met need for family planning. Involving key partners, such as the Society for Family Health (SFH), USAID, and Marie Stopes International (MSI) in the national discourse on family planning has helped to minimise over-procurement or distortion to the national procurement system. Table 3 below shows forecasts and procurement between 2014 and 2016, and includes USAID projections:

Table 3: Procurement projections for family planning products (source: UNFPA)

	2014 forecast	2015 forecast	2016 forecast
IUDs	27,000	86,000	33,900
Implants	150,000 (72,000 attributable to the SUFP programme)	380,000	221,000 implants (broken down as: / 131,000 Jadelle / 45,000 Implanon from UNFPA / 45,000 Implanon from Government)
Depo vials	3.55 million	2.95 million	6.52 million (includes UNFPA, USAID and buffer stock)

As the lead procurement agent for the programme (and for national reproductive health commodities), UNFPA is working with the Government and partners to:

Develop an Investment Plan that aims to agree incremental increases in domestic financing (the government currently contributes 20% of national need) for family planning commodities. Through the SUFP, DFID has contributed 34% in 2015 of the funds required to the national pool (up from 17% in 2014)
- Conduct annual surveys on the availability of family planning commodities (and other life-saving drugs) at facility level
- Address system-specific bottlenecks, such as transport, electronic data systems for real-time reporting, warehousing and storage, and the quality of data analysis
- Encourage Medical Stores Limited (MSL) to eliminate its paper-based system, and invest in an electronic system.

It is anticipated that the regional hubs that are being established by MSL as part of Zambia’s decentralisation policy will address delivery to ‘the last mile’ by facilitating direct access by facilities to their pre-ordered stocks. In addition, the placement of the former MCDMCH family planning procurement contact point in the MoH’s Directorate of Pharmaceuticals is a welcome development, and is optimal for the continuity of the programme.

Recommendations for future programmes

- Intensify family planning programmes targeting adolescent boys and girls, and scale up provision of services to young people and communities, including the reinvigoration of Youth Friendly Corners in schools and facilities, enhancing sensitisation and awareness in schools and faith groups, and expand family planning outreach services (integrated with HIV awareness and testing) tailored to adolescents
- Assist MSL with an investment plan to implement an electronic data system and abolish its paper-based system
- Facilitate dialogue with government to amend current procurement arrangements and change to procurement through WHO pre-qualified suppliers. DFID, SUFP, UNFPA, USAID and other partners to document evidence on the cost-effectiveness and cost-savings of this option
- Design a scale-up plan for the roll-out of the Camping approach in the new phase of the SUFP programme.
- Indicator 1.4 on percentage of national forecasted need in family planning commodities met by programme should be moved to the outcome level to reflect the reliance on GRZ and partners to contribute to increasing funding for family planning commodities to meet forecasted need.

Output Title	Increased access to family planning services
Output number per LF		2	Output Score	A++
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Percentage of target communities covered by outreach services (comprising both community mobilisation and service provision) by the programme in target districts / (disaggregated by: urban/rural)	Total: 50% (target of 1,345) broken down as follows: / Rural: 80% / Urban: 20%	Exceeded: / Total: 74% (reached 2,001) / Rural: 78% / Urban: 22%

Key Points

Score: A++ (Outputs substantially exceeded expectation)

Indicator 2.1: SUFP has substantially exceeded its target by reaching 2,001 communities in its 26 focus districts through outreach communities. This has been attained through comprehensive engagement at several levels:

- The ‘Camping’ approach, which was initiated by the SUFP programme and initially piloted in Kaputa and Chama; it involved volunteers camping in a community for two weeks and engaging leaders selected by the communities themselves. This approach has been applauded for its cost-effectiveness, as it eliminates overhead costs and capitalises on being stationed within a community over a short but intense period
- District Outreach Coordinators (DOCs), positioned at district level to facilitate strengthening of monitoring and evaluation at community level. They have worked closely with health facility-based Maternal and Child Health (MCH) Coordinators and take forward issues concerning family planning, MCH and ARH, and have also provided a conduit to engaging existing District Community Assistants (DCAs). This has been a core component of the programme’s exit strategy which has helped to consolidate linkages between the facility and community
- Community-base distributors (CBDs), a cadre providing family planning information and distributing oral contraceptives and condoms during outreach. The Government has recently endorsed a policy which will permit CBDs to administer implants during outreach, and a draft CBD Strategy is being developed
- Drama groups which have helped break barriers, have addressed cultural misconceptions and myths, and have facilitated community dialogue about family planning and community health.

Adolescent Reproductive Health was not included as a separate component of the SUFP programme in DFID’s original design. Over the lifetime of the programme, however, SUFP has invested increasingly in the inclusion of adolescent sexual and reproductive health, particularly at policy level through the Family Planning TWG and at community level through the Ministries of Youth and Education. However, it is a more political and sensitive issue than originally anticipated; a conservative culture, seen mostly in rural communities, can make it challenging to address these issues in a non-health setting (e.g. in churches and schools). There is also a disconnect between the legal age of consent (16) and the age recognised in national policy at which service provision of SRH services and commodities is classified (15). As discussed under Output 1, Zambia has high levels of teenage pregnancy, early marriage and low uptake of modern family planning methods; these issues are being taken forward in the Family Planning TWG as a national priority.

The following challenges were experienced under this output:
- The staggered approach in which the programme was implemented in the 26 districts resulted in the final six districts (brought on at the end of 2014) not experiencing the benefits of the programme as comprehensively as the 20 districts engaged earlier
- Limited funding from Government resulted in some districts not receiving their grants for health activities for up to 2-3 months, which affected prioritisation and implementation
- Difficult terrain and long distances between communities and villages proved to be problematic for access for the CBDs and DOCs, who often do not have reliable means of transportation
- Evidence has shown that men are more likely to accompany their partners to the facility for couple counselling during the weekends, when they report that they are less likely to be working. The programme is making efforts to encourage more men to participate in this service during the week when more personnel are likely to be available at facility level to provide additional services targeting couples, including HIV counselling and testing

Recommendations for future programmes

- Empower the districts to manage their own programmes and establish mechanisms for district-led performance monitoring, reporting and planning, to eliminate any potential for creating dependency on the implementing partner
- Provide technical support for the implementation of the new CBD Strategy and support the monitoring, evaluation, and supervision of this cadre for the provision of injectable FP methods, and ensure they are affiliated to the MoH
- Draw up a realistic time frame for roll-out and ensure that all supported districts have adequate time to benefit from the programme and demonstrate tangible impact
- More actively target and encourage men to participate in community and facility-based couple counselling services for family planning and HIV testing and counselling during the week as well as at weekends.

Output Title	Increased community support for family planning
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of SMAGs trained as CBDs in programme districts / (disaggregated by: urban/rural)	Total: 650 broken down as follows: / Rural: 490 / Urban: 160	Moderately exceeded / Total: 796 / Rural: 597 / Urban: 199
3.2 Number of community leaders trained as CBDs in programme districts / (disaggregated by: urban/rural)	Total: 390 broken down as follows: / Rural: 270 / Urban: 120	Substantially exceeded / Total: 1,100 / Rural: 762 / Urban: 338
3.3 Percentage of community leaders in programme districts sampled who report favourable attitudes towards family planning / (disaggregated by: urban/rural)	75% broken down as follows: / Rural: 98% / Urban: 42%	Not measured

Key Points

Score: Score: A+ (Outputs moderately exceeded expectation).

Indicator 3.1: 796 Safe Motherhood Action Group (SMAG) members were trained as CBDs through the life cycle of this programme (exceeding the target of 650 by 122%). The high uptake at rural community level demonstrates both a great need among hard-to-reach and vulnerable populations for family planning information and services, and a positive demand for and acceptance of SUFP’s programme.

Indicator 3.2: 1,896 community leaders trained as community-based distributors (significantly exceeding the target by 282%). Community leaders are comprised of both male and female ‘gatekeepers’ such as chiefs, religious leaders, trusted community members who have been directly selected by district and health facility personnel; for example, village heads in Chama have conducted door-to-door campaigns together with their community vounteers. Both SMAGs and traditional leaders have capitalized on existing outreach activities (such as during under-5 immunisation campaigns, or DFID-funded sanitisation and hygiene programmes) to advocate for and provide family planning services.

In addition, 752 health workers and 65 family planning mentors were trained to provide comprehensive services. This saturation of community and district-based personnel has facilitated dialogue around reproductive health and has helped to: dispel myths and misconceptions, particularly around LARCs; expand the range of choice (which has led to the unprecedented uptake of implants, particularly Jadelle); expansion of short-term methods, especially for young women; engagement of young people, and; encourage couples to access health facilities for family planning services as well expanded health services.

Indicator 3.3: Not measured. However, Indicator 3.2 demonstrates the level of acceptance for family planning in rural and urban communities. Discussions with CBDs at Mumbeji Rural Health Centre in Kabompo and Mushili (urban) Health Centre in Ndola district revealed that the door-to-door campaigns have been particularly successful in improving understanding about the socio-economic importance of family planning. For example, there is a better awareness of the link between smaller families and the ability to provide better opportunities for children’s education, health, and basic needs. Community leaders also confirmed that myths and misconceptions, which are a deterrent to the uptake of family planning services, are being addressed through the SUFP programme, and couples recognize the risks and benefits of different methods.

The output risk rating has been adjusted from ‘Low’ to ‘Medium’.

There is a risk of overlap between community volunteers and government-funded Community Health Assistants (CHAs). The legal framework for the involvement of neighbourhood health communities/volunteers in health activities has not been clearly articulated, and nor has a supervision structure that would oversee them within the public health system. CHAs are meant to be the link between the health posts and community, helping to deliver, coordinate and collate data on community health activities; by virtue of their training, they are also equipped to provide services. However, although MCDMCH commenced the process of thinking through a Community Health Strategy and oversight structures at this level, very little progress has been made. It is, therefore, essential that a Strategy is put in place to avoid duplication and enable proper oversight of activities at the community level.

The available number of community volunteers who provide outreach services is limited. There is a greater need that the average 40 CBDs per district, making access to communities difficult. It has also been problematic to reach all target areas within the fairly short duration of the programme; this has been particularly challenging for the last six districts where the SUFP programme was only rolled out at the end of 2014.

Many CBDs are providing outreach services without incentives or expectation of monetary rewards – this is particularly evident in the urban sites visited during the PCR. However, some CBDs are focused on incentives and recognize that these could be basic contributions from beneficiaries of the outreach. However, given the risk of overdependence on incentives, and subsequent unsustainability (where some have either minimized their engagement, or have dropped out altogether) this is a discussion to be taken forward at community level by the volunteers and DHMTs if relevant, and should not be a talking point either for DFID or the implementing partner.

Recommendations for future programmes
- MoH to develop and implement an articulate Community Health Strategy clarifying the roles and responsibilities of community health workers, and oversight of the different cadres
- District health management teams (DHMTs) to be involved in the development of the new CBD Strategy, and provide monitoring and supportive supervision to CBDs as they scale up to provide.
- Indicator 1.3 should be moved to the outcome level
- Undertake a comparison study of attitudes towards family planning in SUFP operational and none operational districts to inform SUFP II programming.

Output Title	Increased public sector capacity to provide quality comprehensive family planning services
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of public sector health facilities in programme districts with the capacity to provide Long Term Reversible Methods / (disaggregated by: urban/rural; facility level)	Total: 450 broken down as follows: / Rural: 330 / Urban: 120	Moderately underachieved / Total: 372 / Rural: 284 / Urban: 88
4.2 Number of public sector health facilities in programme districts providing Adolescent Friendly Health Services / (disaggregated by: urban/rural; facility level)	Total: 450 broken down as follows: / Rural: 330 / Urban: 120	Moderately underachieved / Total: 372 / Rural: 284 / Urban: 88
4.3 Percentage of health workers in facilities covered by the programme trained in: / i) Long Term Reversible Methods and / ii) Adolescent Friendly Health Services / (disaggregated urban/rural; cadre of health worker)	Total: 100% / Rural: 100% / Urban: 40%	Moderately Underachieved / Total: 63% / Rural: 68% / Urban: 32%

Key Points

Score: B (Outputs moderately did not meet expectation).

Indicator 4.1 and Indicator 4.2: The programme anticipated reaching 450 public health sector facilities in its project districts with skills required to provide LARCs and adolescent friendly health services (AFHS). However, only 83% of the target was achieved, and this is predominantly due to the presence of other implementers carrying out the same interventions in the SUFP project districts. While it is commendable that multiple partners have recognised that there is a gap and a pressing need to provide this capacity, it highlights the more important requirement for donors and implementers to first establish what interventions are already being supported by other implementers. This will minimise duplication in programming, as well as in reporting by recipient facilities.

Indicator 4.3: This indicator’s target was also unmet: only 63% of health workers were reached. There have been concerns about the training provided by ZEHRP on integrated family planning and HIV testing and counselling for couples: while SUFP utilises the Government-standardised schedule of 12 days, ZEHRP has reduced its training programmes to 5 days (3 didactic, 2 practical). It is recognised that this is an effort to reduce costs associated with training such as meals, allowances, and time spent away from the facility by health workers; however, trainees are dissatisfied with the reduction for three main reasons:
- Perceptions that the MoH will not accredit or recognise their training because of the abbreviated training
- Inadequate time to fully absorb the content and have the opportunity to question areas of the training that need further elaboration
- Perceptions that trainees will not be able to provide onward training as trainers of trainers (ToTs) to their peers

It is recommended that SUFP, DFID and ZEHRP facilitate a thorough assessment of the usefulness of the five-day training model and its effectiveness in equipping health providers for LARC.

In addition, the health facilities also reported a positive acceptance of the SUFP’s reporting format, which has been successful in capturing couple counselling for family planning into the main national LMIS tool. However, facilities report that donor programmes duplicate reporting efforts which they do not always have the time or resources to complete, even if the donors are providing supervisory support or quality assurance. There is need to ensure that data capturing and reporting are mainstreamed into the national system to minimise the burden on already stretched and under-resourced health facilities.

Staff attrition was a major challenge, especially in 2015, where several government personnel were shuffled and relocated to different districts. This resulted in a) the loss of skills in some SUFP-supported sites, b) some sites left with sensitised communities and trained CBDs but without a trained family planning provider to deliver or support services at facility level, and c) a temporary lull in momentum of the programme. However, SUFP has done a commendable job in ensuring as seamless a transition as possible and continuing with training of trainer (ToT) capacity building between facilities.

The reintegration of the maternal and child health department (from MCDMCH) into the MoH will now enable the MoH to have full control once again – with careful planning – of issues around community health and interventions, and will hopefully facilitate government funding to relevant priorities in family planning, mother and child health.

Recommendations for future programmes

- Ensure that a thorough mapping assessment has been conducted before agreeing interventions at district level, in order to avoid duplication in reporting
- Facilitate a single reporting system at district level to minimise duplication and multiple reporting channels
- SUFP, DFID and ZEHRP facilitate a thorough assessment of the usefulness of the five-day training model and its effectiveness in equipping health providers for LARC

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

The business case identifies three main cost drivers for SUFP: personnel costs, operational costs and commodity and supply costs. Since programme inception, personnel costs have constituted a large proportion of costs, comprising 59% (2013), 55% (2014) and 64% for the programme year ended February 2016. National long-term labour costs constituted 65.5% of the total costs incurred in the period January to December 2015. Refer to the chart below. Field costs, the majority of which are monitoring, training and mentorship related activities reduced from 24% in 2015 to 21.6% in 2016. The reduction is mainly due to the scale down of the programme in preparation for closure as initially planned.

SUFP Cost Drivers
Based on expenditure Jan 2015 - Dec 2015
Personnel and operational costs make up 91% of total cost in year 4 and thus remain the key cost drivers.

The management of the key cost drivers over the life of the programme appears effective. The split between international and national staff costs progressively indicated a pronounced reliance on national technical assistance, with more than 90% of all staff costs in the final year of the programme accruing to national consultants.

SUFP developed a VFM Strategy in 2012 and has monitored and reported key VFM indicators on an annual basis (Table 4).

Table 4: Overview of VFM indicators over the life of the programme
VFM stage	Indicator					Benchmark/Trend and analysis
Economy	Average daily fee rates for TA since inception: / Short term TA rates = £685 / Long term TA rates = £347 / Ratio of National to International TA days:					Average short term and long term daily fee rates have remained competitive throughout the project are within range of international benchmarks. / Use of national TA has exceeded internal target of 75% at mid-point and 80% by end of project.
		2012		2013		2014		2015	Ave.
	Nat.	69%		87%		93%		96%	89%
	Int.	31%		13%		7%		4%	11%

Efficiency		2012		2013		2014		2015	Ave.		Administration and management costs are high compared to external benchmarks. / The unit cost was expected to rise to £49 in Year 4 as number of new users reached tapered-off along with SUFP activities. However, the unit cost was below the expected internal trend and overall the average unit cost per additional user of family planning was £22 since inception.
	Outputs	30%		65%		66%		59%	58%
	M&E	14%		6%		8%		10%	9%
	Admin & Mgmt	56%		29%		26%		30%	33%
	Unit cost of providing services to each additional user of family planning since inception / Year 4 = £19 / Since inception = £22

Effectiveness	Cost per Couple Year Protection / Year 4 = £15 / Since inception = £20					Overall unit cost of £20 per CYP is lower than business case economic appraisal of £30. / Government contribution since inception is estimated to be equivalent to 37% of SUFP expenditure on outputs. This indicates commitment by the government to SUFP activities and potential for sustainability. It compares favourably with other DFID health projects (range 10%-44%).
			Year 2		Year 3		Year 4			Ave.
	% of SUFP spend on Outputs		32%		55%		29%			37%

The average cost per couple years of protection (CYP) (£20 since inception) is not within range of a number of benchmarks[8] for LARC (IUD) costs from Ethiopia (£3.52), Uganda (£2.86), Burkina Faso (£4.50) and Cameroon (£16.12).[9] Notwithstanding, this cost remained lower than the business case target of £30 per CYP. However, there is a vital caveat to consider when interpreting this comparison. The business case pre-empts some of the factors that would result in the intervention in Zambia more expensive than the ‘average’ case, including a high cost of fuel, vast distances of up to 100km between rural health facilities and a very sparse population density.[10]
[8] Unadjusted for 2016 prices
[9] # Disease Control Priorities, Third Edition (Volume 1): Essential Surgery
[10] 16 inhabitants/square kilometre

Population density has remained sparse in Zambia,[11] and there are still large distances between some health facilities so, largely, the same factors affect the economy of the intervention. The business case target of £30 per CYP is an economic cost estimation, while the reported performance is an accounting cost. The two costs are not directly comparable, and, as the economic cost includes the cost of the next best option, it suffices to say the intervention has generally been expensive. A clearer understanding of underlying cost drivers would be required for any follow-up or extension programme.
[11] 21 inhabitants/square kilometre

Over the programme lifecycle, the percentage of total expenditure allocated to overheads has been rather high, hovering between 25 and 36% over the programme years. Operational costs have also remained high as anticipated, making up between 25% and 27% over the programme lifecycle. It has been established that programme accounting may have inconsistently classified as expenses, with travel costs for training considered as overhead for example, and this may have masked the true representativeness of this measure. Given, it would be crucial to ensure consistent accounting of capturing of value for money (VfM) data for future programmes.

Other efficiency measures are positive, including the marginal cost per health worker trained (£75 in 2014)[12] and cost per community-based distributor trained (£79 for the same year). These compare favourably to benchmarks of between £30 and £106 for the same. An overall assessment of key cost drivers is that they have remained in line with what was anticipated in the business case and their management, as indicated by trend over the years and some benchmarks, has been good.
[12] It is important to note that his VfM analysis works on the assumption that there has not been any double counting of health workers trained under the ZEHRP programme

VfM performance compared to the original VfM proposition in the business case

The business case estimated that if the programme delivered more than 330,000 CYP at a cost of £11.9 million (excluding the procurement budget), then the cost per disability adjusted life year (DALY) averted would be approximately £116/DALY averted, making this a “highly cost effective intervention” and would likely present good value for money. Estimates drawn from the lives saved tool (LiST) analysis present indicative performance of £79/DALY including the procurement budget (or £67 excluding procurement). The programme also delivered 578,241 CYPs, nearly 75% more than projected. The programme well achieved VfM against the main business case proposition.

Assessment of whether the programme represented value for money

Overall, the SUFP programme represented good value for money. Within budget, it surpassed many of the key output targets, some significantly, such as the rapid scale up in demand for modern family planning. Compared to economy benchmarks, the programme fared favourably on key costs such as remuneration costs of technical assistance that made up more than half the total programme cost. Various measures of efficiency over the programme lifecycle are very good, and these include the marginal cost of training family planning resources to be used in supporting the system. Assessed against cost effectiveness, SUFP is highly cost effective.

The programme also targets rural women, with more than 70% of beneficiaries falling into this bracket, thus scoring well on equity. However, a mixed picture prevails with regards sustainability. On a positive note, the programme trained and used MoH staff, health facilities and outreach structures and embedded capacity and ‘know how’ within government systems. This promotes sustainability. However, it is also evident that irregular and insufficient government resources mean that intervention cannot continue in their current guise without continued external assistance by SUFP or another external funder. The initial outlay required to support the 26 districts continue with activities would however be low.

Recommendations
DFID to work with the SUFP programme to determine the underlying cost drivers for the cost per CYP for the programme.

Ensure consistent and accurate capture of all costs under the appropriate categories to improve accuracy of data for value for money (VfM) calculations.

Quality of financial management during programme

Overall the SUFP programme implementing partners demonstrated exceptionally good financial management capabilities. While there were some minimal deviations in actual expenditure against what was planned in the original business case, the overall expenditure was in line with the programme plans demonstrating robust quality of financial management. Overall programme budget utilisation reached 100% (see chart below) by the end of the programme with the Abt Associates spending the majority of the budget of £11,541,762 on programme implementation; UNFPA spent £2,526,810 on procurement of reproductive Health commodities (with a small amount committed but unspent); and Crown Agents spent £390,908 on the procurement of goods to support programme implementation.

In the year 2015/16, Abt Associates spent a budget of £1.8m to implement the final stages of SUFP I as planned. UNFPA spent £469,283 remaining with a balance of £414,069 remaining committed for completing the procurement process for RH commodities. UNFPA had requested for an MOU extension past the initial programme end date of 29th February 2016 to complete the procurement process for the final consignment of FP products. With the approval of the SUFP programme extension, DFID will extend the UNFPA SUFP MOU and balance funds will be spent as part of SUFP II.

Date of last narrative financial report	5th February 2016
Date of last audited annual statement	31st July 2015

E: RISK

Quality of risk management over the life of the programme

The overall risk rating for the programme is Moderate when judged against the risk categories of context, delivery, operational, fiduciary, safeguarding and reputational risks and top five risks outlined below. In the period under review, although outputs performance has moderately exceeded expectations, programme success has highlighted increased risks associated with continuing to ensure public sector capacity to provide quality comprehensive family planning services. This includes the implementation of the new community based distributors strategy. As such, programme risks are expected to increase under SUFP II with greater dependence on government systems for programme implementation. Mitigation actions will be incorporated into programme activities going forward and will build on lessons learnt through the first four years of programming.

		Impact
		Insignificant	Minor	Moderate	Major	Severe
Likelihood	Almost Certain
	Likely			GRZ fails to provide adequate resources to sustain Family Planning interventions resulting in loss of programme momentum
	Possible			Programme fails to reach adolescent girls, especially in rural areas	Weaknesses in supply chain affect availability of Family Planning commodities in health facilities and for outreaches
	Unlikely				Community opposition from traditional/religious leaders and men to family planning affects uptake of services
	Rare

Table 5: Assessment of 5 main risks to the SUFP programme and update on mitigation measures

Risk	Mitigation Measures	Residual Risk		Update
		Likelihood	Impact
1 Inadequate GRZ allocation of resources to Family Planning to sustain interventions	Government is being consistently encouraged to increase its domestic financing commitment to family planning	Likely	Moderate	National lobbying for increase in Government funding - Government funding increased to 20% of national FP commodity needs in the period under review. / - UNFPA and Government developing National Investment Case to increase domestic financing / Managers trained in SUFP-supported sites done in collaboration with UNFPA, MSL, MoH, / MCDMCH and expected to be ToTs / Trained personnel provide onward capacity building as ToTs; this addresses issue of attrition/staffing / District Outreach Coordinators were working with District MCH Coordinators – SUFP II to support strengthening of MCH coordinators capacity to plan and prioritize FP interventions.
2 Weaknesses in supply chain for commodities to district and facility level affect Family Planning Products	District and facility pharmacists have been trained through UNFPA and IHS to strengthen supply chain management	P	Moderate	Annual quantification meetings agree procurements for coming two years, improving quantification and planning / Annual FP commodity availability survey conducted at facility level to prevent stock-outs and over-stocking / Attempts are being made for MSL to upgrade from a paper-based to a real-time electronic system (EMLIS) for more transparent and strategic oversight of stock levels and needs / Regional hubs are being set up by MSL to facilitate commodities going to ‘the last mile’. Global Fund is supporting regional hubs strategy. Unclear as to whether there is currently full buy-in and commitment from GRZ and other partners. / FP TWG addressing challenges in supply chain, coordination, supervision
3 Limited demand for long-term reversible methods relative to short-term methods	Training being provided to providers on comprehensive FP package, including IUD insertion / Myths and misconceptions being addressed at community level by traditional leaders, DOCs and CBDs / Efforts are being made to eliminate high number of Jadelle removals	P	Moderate	Increase in annual procurements of LARCs / More robust demand creation strategies informed by planned evaluation in 2016 / Thorough training of clinical staff, community personnel (CBDs), supervision, quality assurance, and refresher trainings / When implemented, Government approval for CBDs to begin providing injectables will intensify demand at community level; a draft CBD Strategy is being developed; need to monitor the Strategy’s roll-out and CBD’s work at community level / Mentoring being done through Centres of Excellence / Need for intensified in-service training for IUD insertion to eliminate i) lack of familiarity with the service, ii) low demand, iii) provider bias, iv) myths and misconceptions
4 Programme fails to reach adolescent girls, especially in rural areas	Inclusion of young female peer counsellors / Reinvigoration of Youth Friendly Corners in schools / Provision of confidentiality and privacy during integrated outreach services	Likely	Moderate	Increase in number of adolescents accessing FP services, particularly Depo-Provera / Increase in number of young (married) couples seeking CFP / Growing acceptance by health providers at facility level to provide counselling and methods to adolescents – planned evaluation in 2016 will confirm this report / Implementation of Adolescent Strategy through SUFP’s engagement in the Family Planning TWG. To be intensified / Still large numbers of early pregnancy reported
5 Community opposition from traditional/religious leaders and men to family planning	Engagement of and collaboration with ‘gatekeepers’ (traditional and faith-based leaders, elders) community health workers, CBDs and SMAGs to sensitise communities with correct information about FP, and dispel myths and misconceptions	Unlikely	Major	Continued sensitisation with correct information / ‘Happy Clients’ working with potential clients both in communities and health facilities on benefits and personal experiences of modern FP use, particularly long-term reversible methods / Review community engagement strategy informed by lessons learned from proposed evaluation in 2016

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The programme has met its objective of delivering against the timeframe that was originally agreed of March 2012 to February 2016. SUFP has depleted its funding and has exceeded most of its targets, representing good value for money, and a good investment choice for DFID.

Performance of partnership (s)

Abt Associates worked well with other partners on the consortium, and they in turn each played a pivotal role in delivery of the programme:
- Imperial Health Sciences (IHS) provided support in coordinating procurement and supply chain activities, and technical support both to the programme and the MoH and MCDMCH. IHS also coordinated with UNFPA to train health care providers in supply chain management. IHS is now leading an initiative with the government and other partners of the government to scale up its domestic financing for family planning commodities, and is working with MSL to upgrade from a paper-based reporting system to an electronic, real-time system that would enhance overall management of the supply chain
  - Challenge: transporting commodities in a timely manner for urgent use in the sites.

- PPAZ worked closely with SUFP on issues of adolescent reproductive and sexual health, provided support in the development of the national Adolescent Strategy, and training of peer educators on family planning.
  - Challenge: budgetary constraints limited this collaboration to only three meetings per year

- ACNM provided technical support in the development of the Mentorship Program in Family Planning, and provided training for health care providers to be mentors in family planning activities
  - Challenge: limited time and budgetary constraints restricted the ability to roll out the mentorship program to all SUFP project sites

Asset disposal and value obtained by DFID

SUFP maintained an updated assets register in line with its own Operations Manual as well as DFID requirements. Physical assets were checked during annual reviews and spot checks to ensure their availability and proper usage.

Because the programme was due for closure, Abt Associates in consultation with DFID, generated an assets disposal plan in which all assets were to be donated to the Ministry of Community Development Mother and Child Health (MCDMCH) and the primary implementer of family planning programmes in the government. This plan however has been stopped because the programme is in the process of being extended to phase 2 with additional funding, meaning the programme will require the assets to deliver the next phase of the programme. Lusaka based assets including IT equipment, furniture and vehicles have been moved to DFID storerooms for storage during the programme transition period as the programme contract is being worked on.

During the 2014 spot check, DFID recommended SUFP to populate and manage a vendors’ list to facilitate procurement of goods such as programme consumables. SUFP therefore owned and updated the vendors’ list annually. This reduced risks associated with procurement of smaller goods and services for the programme locally.

G: CONDITIONALITY

Partnership principles assessment

Not applicable to the programme
H: MONITORING & EVALUATION

Evidence and evaluation

The rationale for DFID’s investment in scaling up family planning was to inject substantial investment into the health system in order to ensure equitable access for all women to family planning services and facilities.

How have the Theory of Change and the Assumptions used in the programme design working out in practice? Are modifications to the programme design required?

Figure 1: DFID Zambia Scaling Up Family Planning Services Business Case, August 2011

Improved maternal health
Increased birth spacing and healthier children
Reduced costs to health service
Slower population growth and associated environmental benefits
Increased participation of women in economic and political life
Expanded availability of choice of FP
Increased access to FP services for under-served areas and populations
Increased community support for FP
Increased public sector capacity to provide quality, comprehensive FP services
Increased use of FP
Reduced unintended pregnancy
Reduced unsafe abortion
Commodity procurement
Staff recruitment and training
Outreach services
Community sensitisation
Training public sector providers on LTRM and adolescent friendly services
Outputs
Outcome
Impact
Wider impact
SUFP Theory of Change
The evidence supporting the Theory of Change (ToC) in the programme’s original design assumed the following impact:

- Wider social benefits of family planning, including women’s participation in economic and political affairs, reduced health care costs as a result of fewer pre- and post-natal complications, including unsafe abortion
- Improved maternal and child health by enabling women to have fewer and more widely spaced births
- Effectiveness of LARCs, enabling slower population growth
- Effectiveness of outreach services, resulting in increased access to family planning and lower unmet need particularly in rural areas.

The interventions carried out over the programme’s four-year life cycle have demonstrated that the ToC was realistic in its original design and made correct assumptions about anticipated outcomes and immediate impact. As already demonstrated, the programme exceeded its target to reach 200,000 additional women and girls using short-term and long-term family planning methods, and instead accomplished 295,104. For example, enhancing personnel skills along the supply chain has had the resultant effect of more ably securing family planning commodities, ensuring that they reach intended beneficiaries (i.e. the poorest and hardest to reach, thereby ensuring equity), and demand for family planning commodities not only increases but is also met. Families are subsequently smaller and births are spaced further apart, socio-economic costs from unintended pregnancies or unsafe abortions on an already overburdened health system are reduced, and individuals’ engagement and participation in political and economic life is more substantive. The inputs in the original ToC have attained their intended outcomes and have met or continue to be in the process of meetings their long-term impacts, which will likely be more measurable in ensuing population surveys (e.g. ZDHS, Multiple Indicator Cluster Survey).

It is a concern, however, that in spite of efforts from both this programme and other interventions, Zambia still struggles with high and rising rates of teenage and early pregnancy. Although the SUFP programme has taken on a more visible focus on reaching adolescents with information and services during the course of its implementation, this key target group should have featured more distinctly at design phase. A follow on programme would need to articulate how to address this in its ToC and logframe, and will need to adopt an approach tailored towards addressing misconceptions

Another assumption of the ToC was that staff recruited and trained under the programme would subsequently facilitate an increase in access to and demand for family planning commodities in under-served areas and populations. However, based on trends of staff turnover and attrition (death, resignation, retirement, redeployment, dropping out) of both community workers and government personnel, there was evidence of the programme not necessarily running as anticipated in particular districts.

Monitoring progress throughout the programme

The SUFP programme’s monitoring and evaluation plan was established at the time of implementation to complement the log frame and annual activity plan. Reports from field visits indicated a strong monitoring element, and this was substantiated by evidence of strong quality assurance of reports and data as they were fed back to Abt Associates. Health facilities reported that data was fed back regularly using a programme-specific monitoring and evaluation (M&E) tool as well as the district-level Health Management Information Systems (HMIS) tool; SUFP has advocated with government for disaggregated data tracking and the inclusion of new family planning indicators (such as CYPs generated by facility by method) in the HMIS to support MoH’s ability to monitor progress on family planning programme at all levels in the health system.

SUFP conducted regular monitoring visits to its project districts and provided training to M&E personnel responsible for data management; where any of the facilities encountered challenges with capturing, inputting or translating data, SUFP provided technical backstopping and support. M&E orientation workshops were carried out for all SUFP District Outreach Coordinators, technical personnel, health facility staff, and CBDs to familiarise all of the relevant personnel on the programme indicators and train them on data capturing and management.

It is commendable that the programme has improved the skills of personnel at district level to capture data that is relevant to the programme as well as to the HMIS. However, personnel feel burdened by having to provide multiple levels of data from different partners which may not be relevant beyond the life cycle of a project. In addition, registers are filled out by hand and there is a very high risk of human error in data transfer; it was reported that some facilities may not fill out reports on time and consequently build up a backlog of reports; to make up for time, they then either replicate or fabricate the data. It is critical, therefore, that the SUFP programme follows up and clearly articulates the relevance and proposed utilisation of data that captures couple counselling for family planning beyond just a programme focus, and to a broader national level of significance. It Most importantly, in maintaining a national effort to have one M&E system, it is essential that all programmes and projects adhere as closely as possible to the established national monitoring system.

SUFP has instituted a Sustainability Plan which is expected to phase out programme activities, and phase in activities designed to institutionalise best practices tools and linkages, such as:

- Withdrawal of SUFP staff, financial support, and technical assistance in the development of plan and processes
- Closer collaboration between DOCs and government counterparts at district and community levels on the design of action plans to ensure uninterrupted family planning activities and commodities.
- Development of a tool that facilitates the reporting of commodity availability (by district and community rural health centres to provincial hubs and central medical stores), which has increased the visibility of stock levels and improved monitoring by MoH
- Scaling up mentorships to pharmacy technicians and district pharmacist, to improve their oversight of availability of essential medicines and medical supplies
- Integration of SUFP’s outreach programmes with other existing outreach programmes (such as under-5 immunisation days)
- Identification of community-level ‘champions’ who will advocate for the inclusion of outreach activities in district family planning activities

The main challenges, which will need close monitoring to this sustainability plan are high staff turnover, unmotivated CBDs who may require support with supplies (e.g. a bicycle) and political will by the government to take on a costly and labour-intensive programme that will deliver (and exceed) even more impressive results.

International non-governmental organisations – and local NGOs that have received strong financial backing – have often been criticised for sharing findings of their projects at international symposia and conferences, without having first disseminated their findings with their host governments. The MoH has expressed the need for the SUFP programme to share its findings in order to help the government improve on its coordination and management of district-level family planning programmes, and better understand how it can enhance its own programming from a national perspective. A key recommendation is to monitor the implementation of the Adolescent Strategy in collaboration with the Adolescent Health Working Group and report on progress and identifying barriers to implementation; in addition, help family planning committees advocate for district support for community level BCC activities.

ANNEX 1: SUFP SUSTAINABILITY PLAN SUMMARY

Impact Statement: Improved capacity of the MoH to sustain effective FP programs in targeted districts
Programme outcome: The MOH has demonstrated capacity to support key interventions to ensure continued demand for and access to FP services at the district and community level
Contributing Results
Supportive tools and systems are adopted at various levels of the MoH / FP activities are planned and budgeted by the MoH for FY 2016 / Community leaders and supportive of FP programs / District health offices fund outreach programs		MoH staff have the required skills to provide the complete FP method mix / Health providers have continued access to mentoring / Current and new health workers have access to mentoring in supply chain management		Formal structures are in place to support sustained FP activities / District FP committees are established and operational / District health partner with communities to implement FP activities		Equipment required for the provision of a full method mix is available at district facilities / COEs are established and used to deliver practicum training and mentoring
Activities
Enabling Environment	Skills		Organizational Structures		Infrastructure
Support the creation of multi-stakeholder community FP committees / Advocate for budgetary support for the national scale-up plan / Conduct traditional leaders workshops / Assist districts in developing budgets and sustainability action plans / Support policy to allow CBDs to provide injectables / Support inclusion of FP indicators in government HMIS	Advocate for inclusion of FP mentorship in district action plans / Advocate for sustained support for mentorship program / Monitor implementation of supply chain mentorship program and use of reporting tool / Support training of CBDs in injectable contraception / Help develop HMIS orientation program for new staff		Support the leveraging of MCH and Pharmacy units to manage mentorship programs / Help create TORs for multi-stakeholder committees / Link committees to district health government structures / Monitor district support for BCC activities / Monitor the implementation of the Adolescent strategy		Complete refurbishing of COEs and development of TORs / Help COES assess equipment needs and submit requests to MSL / Monitor the use for COEs for training and mentoring of health providers / Assist in the distribution of equipment of COEs in the remaining period, if procured by the government

ANNEX 2: CONSULTATIONS

#	Name/Institution	Organisation	Designation
	Dr. Christopher Mazimba	SUFP	Country Programme Manager
	Mr. Maurice Pengele	SUFP	M&E
	Ms. Elizabeth Chilunga	SUFP	Admin/Logistics Officer
	Mr. Goliath Chisupa	SUFP	Deputy Director Finance & Admin
	Dr. Masumba Masaninga	MoH	Former Director Lusaka DHMT
	Dr. Angel Mwiche	MoH
	Dr. William Kilembe	ZEHRP	Lusaka Director
	Ms. Lucy Banda	ZEHRP	Medical Manager & LARC Trainer
	Ms Annie Mwaanga	ZEHRP	CVCT/CFPC Programme Manager
	Ms. Christine Mazarire	ZEHRP	ACCPAC ERPTraining Manager/Part-time Accountant
	Ms. Tyronza Sharkey	ZEHRP	Programmes Coordinator
	Ms. Alexandra Hoagland	ZEHRP	Ndola
	Mr. Kalonde Malama	ZEHRP	Ndola
	Mushili Health Centre / Kaniki Health Centre	ZEHRP	Ndola
	George Clinic	ZEHRP	George, Lusaka
	Solwezi PMO	SUFP	Solwezi
	Kasempa DMO / Njenga Rural Health Centre		Kasempa
	Kabompo DHMT / Mumbeji Rural Health Centre	SUFP	Kabompo