IFFIm Annual Review 2019
Title: International Finance Facility for Immunisation (IFFIm)
Programme Value £ (full life): £1.63 billion		Review Date: November 2019
Programme Code: 111073 & 201185	Start Date: 2007	End Date: 2029

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A+	A	A+	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:
DevTracker Link to Log frame:	See Gavi consolidated log frame

A. Summary and Overview
Description of programme
The International Finance Facility for Immunisation (IFFIm) is an innovative financing mechanism used by Gavi, the Vaccine Alliance to frontload donor pledges to fund immunisation programmes.
IFFIm raises money for Gavi by selling 'vaccine bonds' on the international capital markets. These bonds are backed by long-term legally binding pledges from donor governments. Thus, IFFIm is a frontloading mechanism, making large volumes of future donor funding immediately available for Gavi programmes.
The diagram below illustrates how IFFIm works, showing how legally-binding donor pledges are turned into funds which are immediately available for vaccination programmes.

IFFIm has played a key role in supporting Gavi’s evolution as a global health organisation. IFFIm was originally designed to enable Gavi to scale up rapidly in order to meet immediate and urgent needs, and to accelerate progress towards Millennium Development Goal 4 (reducing child mortality). Its role in Gavi’s evolution has now moved beyond that.
- IFFIm has enabled Gavi to efficiently frontload donor resources to enable the scaling up of life saving vaccine programmes in developing countries. The frontloading has enabled countries to scale up cost-effective vaccines at a much faster rate than would have been possible, saving millions of lives.
- An additional advantage of IFFIm is that it provides Gavi with a reliable and stable source of funding. This has been particularly vital in Gavi’s market shaping work by enabling it to give clear signals to the pharmaceutical industry around the size and sustainability of vaccine markets and encourage investment and competition in vaccine production.
To date, IFFIm has received legally binding pledges from ten donors totalling approximately US$6.6 billion spanning 23 years to 2030. The UK is the largest donor to IFFIm. The existing UK commitment, made in 2006 and supplemented in 2009, is for £1.63 billion over 23 years. UK support is made up of two legally binding pledges, one made in 2006 for £1.38 billion and payable over 20 years from 2007 – 2026, and the second for £250 million, made in 2009 and payable over 20 years from 2010 – 2029. This review applies to both tranches of UK commitments to IFFIm. The UK contribution is directly attributed to results and forms £430 million of the government’s £1.44 billion 2016-2020 investment which will deliver the UK Government’s manifesto commitment to immunise 76 million children and save 1.4 million lives.
IFFIm has disbursed $2.6bn to Gavi, approximately 20% of Gavi’s funding. IFFIm is now expected to provide US$ 600 million over 2016 – 2020, representing approximately 7% of Gavi’s overall resources in the period. It was originally anticipated that IFFIm would provide approximately US$ 1.3 billion over 2016-2018 however the strategic need for all of this funding has not materialised. Disbursements of US$ 100 million and US$ 50 million were made to Gavi in 2016 and 2018 respectively.
The UK’s investments to Gavi, IFFIm and AMC investments are consolidated under the same logframe. The focus of the IFFIm review is on the efficiency of IFFIm as a funding mechanism, recognising IFFIm’s role as a financing instrument of Gavi. The Gavi results are presented separately in the Gavi Annual Review.
Summary supporting narrative for the overall score in this review
IFFIm has scored an A+ in this annual review. IFFIm continues to be a highly effective and efficient financial instrument. It continues to provide Gavi with a high level of financial flexibility for frontloading vaccines, market shaping and emergency response. Financial management of IFFIm by the World Bank remains excellent and it continues to deliver value for money.

IFFIm is taking steps to support Gavi’s mandate in new and innovative ways. For example, the ongoing development of a market shaping tool to enable Gavi to negotiate long-term supply orders by using IFFIm pledges as a guarantee should be completed in time for launch of Gavi’s new strategic period. In addition, the CEPI arrangement which was approved in 2018, and successfully administered in 2019, demonstrates the strategic value of the instrument to one of its largest donors, Norway, and builds on existing synergies between Gavi and one of its partners in CEPI. Ongoing efforts to secure new funding agreements for IFFIm (either from new or existing donors) will be especially critical as Gavi and the UK look to a successful Gavi replenishment in 2020.

IFFIm is forecast to provide US$ 1.48 billion of assured resources for the 2021-25 strategic period which reduces pressure on new fundraising. IFFIm itself is an asset which strengthens Gavi’s balance sheet, as well as providing Gavi with assurance to commit to new contracts with manufacturers extending beyond the current strategic period so that Gavi countries do not feel the impact of the 5-year funding/strategic cycle.

However, there were no new IFFIm bond issuances in 2018 and Gavi have revised downwards the estimated funding requirement for IFFIm to US$ 600 million in this strategic period. The funding that IFFIm provides to Gavi is based on need so (in the absence of frontloading) when Gavi do not need additional funds, or they achieve savings from elsewhere in the portfolio, it becomes increasingly difficult to demonstrate IFFIm’s strategic value. Gavi therefore needs to continue to take advantage of the flexibility afforded to it by IFFIm by using it as efficiently and strategically as possible in the remainder of the existing strategic period as well as the next. This will be explored further in the Gavi annual review.

Recommendations for the year ahead
1. Gavi should continue to ensure that it is taking advantage of the flexibility afforded to it by IFFIm and using it as efficiently as possible. This includes finding the optimal balance between drawing down funds and maintaining headroom in IFFIm. DFID to interrogate this in future Gavi annual reviews. [see Gavi annual review]
2. DFID should closely monitor the rollout, implementation and use of the market shaping guarantee tool currently under development. DFID to assess this as a use of IFFIm funds in future annual reviews.

3. IFFIm and Gavi to continue to explore new opportunities to drive further innovative use of the IFFIm vehicle in delivering Gavi’s mandate, including the best use of IFFIm in helping Gavi deliver its 5.0 strategy goals. Progress on the existing strategic initiatives should be reported at the 2019 IFFIm donor meeting.

4. IFFIm to continue to work with the World Bank to enable IFFIm to receive new pledges in non-USD currencies and efficiently frontload such new pledges. The timeline of this will be especially critical to enable donors to consider IFFIm as part of their overall Gavi pledge for the 2021-25 strategic period.

5. IFFIm, Gavi and the DFID to consider an independent review of the mechanism as IFFIm’s modality has shifted away from being purely a frontloading mechanism (which was reviewed in 2011) to a financial vehicle that serves Gavi more strategically in terms of providing assurance and flexibility of future funding. This should review the success of IFFIm to-date and consider the case for the future.

6. The Gavi Secretariat and IFFIm Board to continue to engage with potential new donors to develop opportunities for new partnerships. Likewise, Gavi should continue to explore the potential for new pledges from existing IFFIm donors. Together these efforts should aim to minimise the risk that IFFIm’s activities diminish in the coming strategic period.

## B: DETAILED OUTPUT SCORING
Output Title	Demonstration that IFFIm is a feasible, efficient and acceptable mechanism, and is an effective tool for development financing.
Output number per LF		6 (Gavi logframe)	Output Score	A+
Impact weighting (%):		100%	Impact weighting % revised since last AR?	No

	Indicators	Milestones for this review	2017 achieved	2018 achieved	Progress
6.1	Nominal value of cumulative past disbursements for other uses (interest cost, admin fees etc.) should not exceed 10% of cumulative value of all IFFIm outlays to date	<10%	3.9% / IFFIm administrative costs: $3.8m / Interest costs: $9.9m / Investment income: $15.0m	3.8% / IFFIm administrative costs: $3.9m / Interest costs: $15.7m / Investment income: $20.6m	Exceeded milestone
6.2	The spread (in bps per annum) between IFFIm's cumulative cost of financing and that of donors over IFFIm’s entire lifetime	IFFIm's cumulative CoF does not exceed that of its donors	IFFIm's cumulative CoF 8 bps lower than that of its donors	IFFIm's cumulative CoF 8 bps lower than that of its donors	Exceeded milestone
6.3	Cost of carry (in bps per annum) - expressed as the average investment return minus average funding cost in the past 3 years	Positive cost of carry	Positive cost of carry: average investment return 16 bps higher than average funding cost	Positive cost of carry: average investment return 11 bps higher than average funding cost	Exceeded milestone
6.4	Overall support by Gavi of IFFIm's operations and activities, as indicated by the IFFIm chair.	Satisfactory	Satisfactory	Satisfactory	Met milestone

Source: World Bank (for 6.1, 6.2, and 6.3)
6.1: Nominal value of cumulative past disbursements for other uses (interest cost, admin fees etc.) should not exceed 10% of cumulative value of all IFFIm outlays to date. Exceeded milestone.
This indicator is a measure of IFFIm’s economy as a funding mechanism. As of 2018, total IFFIm spend for non-Gavi purposes has been 3.8% of total Gavi disbursements. This demonstrates that IFFIm continues to maximise the economy of use of funds, with more than 96% of disbursements to date used for delivering vaccines through Gavi. IFFIm administration, including secretariat activities and high-quality treasury management by the World Bank as Treasury Manager, continue to be delivered at a low cost. The positive trend continued in 2018 supported by tight control on administrative costs and investment returns exceeding the interest cost for the year. Overall, IFFIm’s interest costs, governance costs and treasury management fees totalled $19.6m, a 43% increase on 2017 largely driven by an increase in interest costs. IFFIm’s interest costs are floating rate and increase with the rise in interest rates. These were however offset by the rise in its investment income which increased to $20.6m in 2018, 37% higher than 2017.

6.2: The spread (in bps per annum) between IFFIm's cumulative cost of financing and that of donors over IFFIm’s entire lifetime. Exceeded milestone.

This indicator measures IFFIm’s efficiency at converting long-term donor pledges into front-loaded support to Gavi. During 2018, IFFIm continues to have access to capital markets and is well recognized as a socially responsible issuer. A cumulative cost of capital 8bps lower than that of donors shows IFFIm’s ability to efficiently fund Gavi in accelerating immunisation at a cost lower than that of its donors since inception.

This indicator compares IFFIm’s cost of borrowing over its entire lifetime, not just the current period, to that of its donors. It therefore reflects IFFIm’s continuing ability to flexibly fund Gavi at a cost lower or similar to that of donors, while noting that the higher cost of funding due to macroeconomic factors outside its control is not a failure of IFFIm’s efficiency in itself.

While IFFIm continues to raise money more efficiently than its donors over its lifetime, short term market conditions remain challenging. The average spot-rate of IFFIm funding cost for all outstanding bond issues is US$ LIBOR + 22 bps, 12 bps higher than the weighted average spot rate of donors funding cost of US$ LIBOR + 10 bps.

This has been driven principally by the continued low interest rate environment. ECB’s quantitative easing bond purchase programme has significantly lowered the spreads of euro denominated bonds issued by some of IFFIm’s donors (particularly Spain, Italy and France). The tighter spreads have resulted in a lower weighted average cost of IFFIm’s donors compared to IFFIm’s own borrowing cost.

Despite IFFIm’s current borrowing cost being higher than the weighted average of its donors, the spread between the two has actually decreased to +12bps at present from +22bps in 2016, when the donors’ weighted average funding cost at the time was below LIBOR. This follows a tightening of spreads among European donors as a result of market recovery in 2017. Issuance cost for IFFIm has remained relatively stable during 2018.

6.3: Cost of carry (in bps per annum) - expressed as the average investment return minus average funding cost in the past 3 years. Exceeded milestone.

The funding costs that IFFIm incurs in supporting Gavi's activities are partly offset by returns from its liquidity portfolio, which is invested in high-grade fixed income instruments. IFFIm’s risk management policies require it to hold a minimum level of liquidity, but IFFIm may also hold liquid assets for other reasons, such as pre-funding under attractive market conditions. Therefore, IFFIm's relative funding cost vs. investment return, or "cost of carry", provides a good proxy for assessing financing efficiency. A positive cost of carry implies that the World Bank continues to efficiently manage IFFIm's liquidity and achieve returns that are higher than IFFIm's funding costs.

In 2018 IFFIm’s average funding cost of its outstanding bonds was $Libor + 17bps. Meanwhile, IFFIm’s investment return during the same period was $ Libor + 28bps. With IFFIm’s current AA/Aa1 credit rating and the World Bank’s prudent funding and investment management strategy, IFFIm continues to enjoy a positive carry over a three-year period. IFFIm applies three-year averaging to compare the value of investment return over its funding cost, as three years represent the maturity tenor of a typical IFFIm bond

6.4: Overall support by Gavi of IFFIm's operations and activities, as indicated by the IFFIm chair. Met milestone.

This indicator is a process indicator to measure coordination, smooth and uninterrupted operations, and good governance of a complex development finance instrument such as IFFIm. This would include, but is not limited to, IFFIm's capital market activities, IFFIm board and donor meetings, interactions with ratings agencies, IFFIm's and Gavi's interactions with other external counterparties in the context of IFFIm's business.

The IFFIm Board annually evaluates the quality and adequacy of Gavi’s support for IFFIm’s smooth and efficient operations, the outcome of which it communicates with the Gavi Secretariat. In 2018, the IFFIm Board expressed satisfaction on the overall support that Gavi provided. Gavi has maintained a satisfactory level of support historically.

Lessons identified this year, and recommendations for the year ahead linked to this output
IFFIm and World Bank to continue high-quality and efficient management of IFFIm funds that delivers value for money
Discussions with the Bank continue to explore possibilities for a change in IFFIm’s risk management profile that would result in IFFIm donors being able to make new non-USD denominated contributions

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change and any major changes in the past year
IFFIm is a multilateral development institution set up in 2006 to rapidly accelerate the availability and predictability of funds for Gavi, the Vaccine Alliance – a public-private partnership set up in 2000 to accelerate access to life-saving vaccines for children in the world’s lowest-income countries.

IFFIm issues Vaccine Bonds, backed by long-term, legally binding pledges from donor governments, on international capital markets. These bonds are bought by investors who in return receive interest over a fixed period, at the end of which they are repaid their original investment. The money raised by these bonds provides Gavi with large volumes of funds immediately available to deliver life-saving vaccination programmes. IFFIm enables donor funding to be made available to Gavi more quickly. The predictable and flexible nature of this funding means that Gavi can plan effectively while also retaining its ability to respond to new developments in disease prevention.

The process of transforming long-term donor commitments into immediate cash for Gavi is called frontloading. Put simply, it is the process of shifting financial resources from the future to the present. Frontloading is important to Gavi because there is zero value vaccinating a child in 10 years if he or she dies from a vaccine-preventable disease this year. The majority of Gavi’s vaccines need to be given to children within a few years of birth. Withholding or delaying this access can prevent children from leading healthy and productive lives. By frontloading future resources, IFFIm has helped Gavi immunise more children, more rapidly.

Furthermore, the impact of flexibility to frontload goes beyond improving the life chances of each vaccinated child. A healthy child is an asset to his or her family, the wider community and ultimately the national economy.

IFFIm’s effectiveness lies in its ability to:

Provide Gavi with flexibility either to frontload resources over a shorter term, or to draw down funds over a longer period, enabling Gavi to use funds when they are needed most.

Provide long-term, predictable funding to enable Gavi to support market shaping activities, reinforce Gavi’s financial strength, and enhance Gavi’s ability to make long-term funding commitments.

Offer donors a cost-effective way to spread contributions over future years and to have an immediate impact.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Within the consolidated logframe IFFIm contributes to the overall Gavi outcome. Gavi has made strong progress against the consolidated logframe outcome indicators in 2018:

Lives Saved: 4.3 million achieved against a milestone of 3.1 million

Children vaccinated: 198million achieved against a milestone of 170 million

Gavi transitioned countries that continue to implement Gavi-supported vaccines: 100%

Gavi continues to deliver excellent results; progressively immunising more children every year and on track to achieve and potentially to exceed its goal of supporting immunisation of a further 300 million children with three doses of pentavalent (5 in 1 vaccine) in the period 2016-2020. This is estimated to save Gavi supported countries between $80-100 billion in economic costs and will save 5-6 million future lives over the same period.
IFFIm has leveraged donor pledges of US$ 6.5 billion over a 25-year period to raise US$ 6.04 billion in cash from 34 bond issuances over the 2006 to 2018 period.
As of December 2018, IFFIm provided approximately 20% of Gavi’s funding to support its life-saving vaccination programmes. In 2018, IFFIm disbursed to Gavi a total of US$ 50 million to support Gavi’s Board approved programme. So far in this strategic period Gavi has drawn a total of US$ 150 million of proceeds from IFFIm. Gavi forecasts that it will meet the US$ 600 million draw down from IFFIm by the end of the strategic period in 2020, though this figure has already been revised downwards from US$ 1.3 billion forecast need from IFFIm at the start of the strategic period.

IFFIm’s continuing ability to generate more efficiency and more effectiveness in Gavi’s funding has helped Gavi immunise close to 760 million children, avert 13 million future deaths and accelerated the delivery of vaccines by making the money from long-term pledges available immediately. IFFIm’s frontloading mechanism in support of routine immunisation has allowed more than 80 million children to be vaccinated ahead of receiving donors’ grants. Gavi has been responsible for more than 300 vaccine introductions and campaigns, including those protecting against the leading causes of diarrhoea and pneumonia, two of the biggest child killers.

Further, IFFIm’s long term, predictable funding, as well as volume, contribute to continued improvement in the affordability of immunisation programmes and enable Gavi to engage in market shaping activities.

Explain major changes to the logframe in the past year (1/2 page)
The progress of IFFIm in delivering results is consolidated under a combined Gavi logframe. There has been no change in the IFFIm logframe in the past year. The 2017 annual review documented an extensive re-evaluation of the logframe was conducted, updating the IFFIm-related indicators to better reflect IFFIm’s activities and to fairly capture progress towards delivering results clearly attributable to IFFIm.

Describe any planned changes to the logframe as a result of this review
No changes to the log frame are recommended. However, it would be beneficial for DFID, Gavi and IFFIm teams to reconsider including an indicator to capture the benefit IFFIm brings to Gavi’s market shaping activities, or more broadly, the efficient and strategic drawdown of IFFIm funds by Gavi.

## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year
Economy: In 2018, total costs, including governance, WB fees and interest was US$ 19.6 million. Total costs of running IFFIm were still offset by high investment income in 2018. However, these costs have increased in the last few years from US$ 8.4 million in 2016, largely driven by increasing interest costs. Table 1 presents the actual IFFIm governance costs, Treasury Manager fees, and the investment income from IFFIm’s inception in 2006 until the end of 2018.
	2006	2007	2008	2009	2010	2011	2012	2013	2014	2015	2016	2017	2018
Governance Costs	1.6	2.2	2.8	3.0	2.9	2.7	3.0	2.7	2.8	1.9	2.0	1.8	2.0
Interest Cost	-	53.0	37.1	11.7	4.0	1.6	4.7	1.3	-0.6	2.5	4.4	9.9	15.7
Treasury Manager Fees	1.9	1.3	1.8	2.0	2.2	2.6	2.4	2.3	2.3	2.3	2.0	2.0	1.9
Investment Income	3.5	14.4	4.5	10.8	5.7	8.0	6.3	3.8	3.0	4.8	8.2	15.0	20.6
Surplus/deficit	N/A	-42.1	-37.2	-5.9	-3.4	1.1	-3.8	-2.5	-1.5	-1.9	-0.2	1.3	0.9

Table 1: Overview of governance costs, Treasury Manager fees, interest costs and investment income, 2006 – 2018 (US$ millions)
Source: IFFIm’s Financial Statements
In 2018, the treasury management fees remained largely stable at 1.9 million as there have been no significant changes in the nature of the treasury operations from 2016. Treasury manager fee comprises of two broad categories:

1. a) Financial Service Cost including bond issuance design and execution costs, investment management and swap fees; and
2. b) Support Costs which include fund and relationship management, rating maintenance, legal services, and accounting and reporting costs. Following its peak in 2011 when it reached US$2.6 million, the fees have decreased over the last several years due to lesser capital markets activity and optimisation of support costs.

In 2018, the governance costs increased to US$ 2.0 million, 11% higher than the previous year. This result was mainly driven by the incremental consultancy fees and related administrative support in relation to the recruitment of two new IFFIm directors replacing two directors rotating out of the Board and the increase in IFFIm’s media and communications activities (which among other expenditure, reflects additional communications around Gavi’s MTR) and external legal services performed in 2018 compared to 2017. Gavi administrative support fees, part of IFFIm’s governance costs, remained stable at US$ 0.9 million in 2018.

IFFIm’s investment income is generated from its investible assets under the same prudent risk-return framework mandated for IBRD-TRUST pool, namely its cash holdings. Despite decrease in liquidity due to bond maturities and disbursement during 2018 (from $912m in December 2017 to $817m in December 2018), the investment income increased from US$ 15.0 million to US$ 20.6 million, an increase of 37%. This increase is driven by allocating to sectors with limited sensitivity to rising short-end rates for CY2018, primarily expressed through tactical duration and curve positioning that effectively profited from the steepening of the front-end of the LIBOR curve. Security selection also positively enhanced performance, efficiently capturing cheap risk-adjusted carry across regionally diversified high-quality liquid asset classes (sovereigns, supranational, agencies, emerging markets, covered bonds and securitized products).

The increase in investment income ensured that the investment income exceeded all the administrative costs of IFFIm. With the World Bank’s prudent liquidity management and low operating costs, IFFIm continue to generate operational efficiency through a positive cost of carry.

The World Bank, as Treasury Manager, continues to be a vital and effective financial partner. It has continued to fulfill its roles and responsibilities exceptionally well, managed liquidity well, and used its conservative risk management approaches to reassure investors’ and rating agencies’ confidence in IFFIm. This has allowed IFFIm to raise funds on favorable terms and operate with a positive cost of carry.

With the World Bank’s prudent liquidity management and low operating costs, IFFIm continues to generate operational efficiency.

IFFIm continues to deliver efficient frontloading of donor resources and has been able to borrow from the financial markets, on average, at a cost of funding below that of its donors over its lifetime. In 2018, IFFIm made no bond issuances, therefore its lifetime cost of funding remained the same. As of December 2018, the weighted average cost of all bond issues by IFFIm since inception was US$ Libor +2 bps, 8bps lower than the weighted average cost of funding of IFFIm’s donors over the same period. IFFIm has maintained its funding efficiency in frontloading funds for Gavi to deliver on in its life saving mission.

In 2018, IFFIm made no new issuance, as it had adequate liquidity to fulfill IFFIm’s funding requirements for the year.

IFFIm is not a frequent issuer, and the timing and size of its issuances is first and foremost driven by the funding need of IFFIm for a given funding year, whether that need is for refinancing of IFFIm bonds or disbursement for Gavi’s immunisation programmes. Once the funding need is determined, its overall funding strategy is premised on the intention to optimise the following three objectives:
1. funding cost;
2. diversification; and
3. raising the profiles of IFFIm and Gavi and increasing awareness of Gavi’s immunisation mission.

IFFIm continues to achieve this strategy by issuing bonds in different currencies and regions, attracting new investors and broadening its geographical reach.

IFFIm continues to effectively provide Gavi with financial flexibility by allowing it to target the timing and amount of drawdown from IFFIm based on its needs. Gavi decides the size, timing and sources of funding required from IFFIm based on its long-term projections for expenditures, incomes and cash flow plan (including new programme budget needs). In making this determination, Gavi takes into account the relative financial efficiencies between IFFIm disbursements and all other sources of funding available to it.

Once Gavi makes a funding request to the IFFIm Board, the Board - in consultation with the Treasury Manager – considers the request in line with IFFIm’s various operational and financial criteria as set out in its Finance Framework Agreement, its funding strategy, its liquidity policy, its risk management policy and the IFFIm Gearing Ratio Limit.

IFFIm has provided close to 20 % of Gavi’s funding since 2006. In 2018, IFFIm disbursed to Gavi US$ 50 million to support Gavi’s Board approved programmes, with an additional US$ 450 million of proceeds expected to be disbursed in 2019 and 2020. In this strategic period, Gavi has drawn down US$ 150 million from IFFIm, with another US$ 250 million forecasted to be drawn down in 2019 and a further US$ 200 million in 2020. The combined past and future disbursements would represent approximately 7% of Gavi’s overall resources in this strategic period.

The drawdown from IFFIm by Gavi in the 2016-20 strategic period originally was intended to be US$ 1.3 billion which would have moved to its gearing ratio limit. The original drawdown has been revised over time to reflect Gavi’s changing resource needs due to programme changes in Gavi countries. This reduction is due to the positive effects of Gavi’s market shaping activities (i.e. reduced vaccine prices) and better stock management along with the impact of supply constraints for several vaccines (e.g. Rotavirus and HPV) and an updated schedule for the roll out of some new routine and campaign programmes. In 2018, Gavi adjusted this amount to US$ 600 million (in addition to US$ 66 to the CEPI arrangement) from US$ 950 million forecasted previously for the current strategic period (2016-2020). This is in line with the amount IFFIm provided Gavi during the previous strategic period (2011-2015). Disbursement from IFFIm is significantly backloaded as Gavi has found it more efficient to prioritise direct pledges for direct use and maintain IFFIm as a source of financial flexibility.

IFFIm’s gearing ratio remained largely unchanged in 2018. The gearing ratio finished 2018 at 8.7% from the 18.7% of December 2017. The gearing ratio is a function of net debt (outstanding debt net of liquidity) and present value of outstanding donor pledges. A downward trend indicates that the net debt is reducing as a percentage of the PV of pledges. As of December 2018, IFFIm’s recommended gearing ratio was 58.3 percent (70.3% Gearing Ratio Limit (GRL) less 12% for the Risk Management Buffer), which leaves significant funding capacity available to fund Gavi. The GRL was set so that the value of outstanding borrowings, less cash held by IFFIm, does not exceed 70.3% of the present value of outstanding pledges. IFFIm is currently projected to disburse US$ 600 million during the remaining 2 years of the current funding cycle, leaving an estimated US$1.48 billion in available assured funding for the next funding cycle 2021-2025 (about 15% of the forecasted need for that period). This would take IFFIm to the gearing ratio limit.
[note] IBRD applies a Risk Management Buffer of 12% in addition to the GRL as a result of its exposure on IFFIm’s swap position.
In reducing the required funds from IFFIm for the 2016-20 strategic period, Gavi has re-programmed the receipt of some of IFFIm’s funding to post 2020. This would not have been possible without the benefit of IFFIm’s flexible funding model. IFFIm has enabled Gavi to maintain the optimal balance between drawing down funds for vaccine delivery while at the same time keeping its headroom for contingency and other Gavi purposes such as market shaping. Gavi has therefore found it more efficient to prioritise direct pledges for use in the current period and maintain IFFIm as a source of long-term flexible funding source. However, the decline in gearing ratio and the low level of disbursements so far this strategic period raises the question of whether Gavi is using IFFIm as strategically as it could be.
Looking forward, the assured resources from IFFIm provide tremendous credibility to Gavi’s programme commitments through the confidence it provides vaccine manufacturers, safeguarding production capacity to meet the vaccine demand, and to implementing countries to pursue ambitious immunisation objectives even with rising co-financing obligations.

In order to further maximise IFFIm’s efficiency and increase its effectiveness for Gavi to deliver vaccines beyond simply frontloading, four strategic initiatives were presented to donors in 2015/16. Of these, the initiative that is currently in active development and could be of immediate value to Gavi is the creation of a new facility that would issue guarantees in support of Gavi’s market shaping commitments. Currently at an advanced stage of development, this tool will be launched and ready for Gavi to utilise at the start of the next strategic period when it will help strengthen Gavi’s ability to secure long-term manufacturer contracts by using IFFIm’s unused long-term assets to support financial guarantees. The tool was originally intended to be launched in early 2019 but its timeline has been revised to be operational over the course of next year, in time for the start of the next strategic period. This is due to the fact that Gavi currently does not foresee a use for this mechanism before that time. At this stage, Gavi has received proposals that meet its criteria and is working with UNICEF to finalise a structure that will work for all parties and to be deployed for use in Gavi 5.0.

This is an efficient use of IFFIm funds as the donor pledges will be put to use, underpinning long-term purchase commitments even before drawdown. This tool is on track for operationalisation under Gavi 5.0 (2021-2025) and could activate up to US$ 150 million of IFFIm’s assets in the form of guarantees with the potential to scale the instrument significantly and rapidly should Gavi market shaping efforts require it. The immediate need for a standby facility has been reduced from $400m to $150m in line with the anticipated need and so as not to tie up unnecessary capital in an idle facility. However, the facility could easily and rapidly be increased should greater demand materialise.

Two other initiatives - financing Gavi’s Cold Chain Equipment Optimization Platform (CCEOP), and providing a funding tool to respond to disease outbreaks – continue to be on standby in 2018 per IFFIm donors’ guidance until Gavi clarifies its role on funding support for these areas. Progress on the fourth initiative is outlined below:

Initiative	Description	Progress in 2018
Supporting vaccine scale-up as part of the current Gavi Vaccine Investment Strategy	This is an uncontroversial approach which has been a feature of IFFIm’s funding to Gavi e.g. the frontloading of funding for the hugely successful global scale up of the pentavalent vaccine.	As part of Vaccine Investment Strategy 2018, Gavi Board approved future investments in six new and extended vaccine programmes in November 2018. No special application of IFFIm funding was identified, however IFFIm will continue to be considered as a potential source when determining funding sources for these vaccines. In addition, IFFIm’s frontloading could apply if there is an unexpected development of new vaccines that require accelerated scale-up.

In December 2018, the UK supported Gavi approval for support for the Coalition for Epidemic Preparedness Innovations (CEPI) using funds made available by the Government of Norway (a AAA credit rated donor), which were frontloaded through IFFIm. CEPI is a public private initiative that accelerates development of vaccines against emerging infectious diseases and enables equitable access to these vaccines during outbreaks. This arrangement was an opportunity for Gavi and IFFIm to collaborate with and make available the IFFIm structure to a global public health organisation whose mission aligns with Gavi’s broader mission. The CEPI arrangement provided additional resources to IFFIm’s capital base and a clear statement of IFFIm’s relevance to one of its strongest rated donors. The rating agencies took note of the CEPI arrangement appreciating the fact that a AAA rated donor chose IFFIm as the innovative financing solution to support CEPI and its impact to global health. In September 2019 Fitch wrote in their rating opinion: “Earlier in the year, the boards of IFFIm and Gavi approved a proposal from Norway (AAA/Stable) to support a Gavi programme for the Coalition for Epidemic Preparedness Innovation through IFFIm bond issuances.”
Gavi is a core member of CEPI’s Joint Coordination Group (JCG), which provides predictability to vaccine R&D and delivery all the way through to registration, manufacturing and stockpiling. The use of IFFIm to help Norway frontload its commitment to CEPI is therefore an arrangement that also helps create organisational synergies beyond those that exist through Gavi and CEPI’s existing areas of work. The arrangement had neither any impact on IFFIm’s operations and the financial flexibility that it afforded to Gavi nor any additional cost to Gavi and IFFIm.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
IFFIm has been highly successful at delivering its objectives and increasing Gavi’s effectiveness at delivering vaccines despite challenging financial market conditions. If the steps being taken by IFFIm to move it from being purely a frontloading vehicle to expanding into other purposes to support Gavi’s delivery are successful, this will further increase its value for money proposition in the coming years.

E: RISK
Overview of programme risk
The risk rating for IFFIm is assessed to be moderate, unchanged from the previous annual review. The main programme risks and mitigation strategies are outlined below:
Risk	Description	Mitigation strategy
Credit rating risk	IFFIm has lost its original triple-A rating. S&P and Fitch both rate IFFIm as AA (negative), and Moody’s rates IFFIm as Aa1 (stable). IFFIm’s rating is primarily based on the rating of its two largest donors, the UK and France; if their ratings deteriorate then further downgrades to IFFIm are possible. Credit rating downgrades will lead to a higher cost of funding for IFFIm issuances and higher proportion of funds going towards interest payments.	The strength of donor support and commitment, and the credibility of the World Bank as Treasury Manager, are both cited as positive aspects supporting IFFIm’s current credit rating. Maintaining these supporting factors is crucial to maintaining a stable credit rating. This is only a partial mitigating strategy since further downgrades to donors are outside IFFIm's control.
Currency and interest rate swap exposure	A key risk for IFFIm continues to be around managing currency swap exposure and its impact on attracting new pledges. Exchange rate and interest rate volatility and credit rating downgrades have led to high levels of exposure imposed on the Treasury Manager.	In 2018 and 2019 IFFIm and IBRD are exploring ways to enable IFFIm to receive new pledges in non-USD currencies and efficiently frontload such pledges, which could include finding new counterparties able and willing to offer swap line to IFFIm cost-effectively or potential bond issuances in donor currencies (such as GBP and EUR). If successful, this would reduce the risk of IFFIm not attracting new pledges by transferring the FX risk away from donors.
Investment risk	IFFIm’s investment income is generated from its investible assets, namely its cash holdings as mandated by its liquidity policy. Investment income earned from assets ideally should more than offset the cost of governance and management of the IFFIm portfolio. However, investment performance of IFFIm's portfolio is subject to market risk.	Continued high quality treasury management by the IBRD should mitigate this risk to an extent.
Interest rate risk	Recent IFFIm bond issues have had a higher cost of funding than that of the weighted average donor. Factors such as the significant change in the economic environment (principally the historically low interest rate environment) and the effect of the downgrade of IFFIm’s credit rating on its cost of borrowing have led to this difference in performance. Higher cost of funding for IFFIm issuances is risky because a higher proportion of funds will go towards interest payments.	Continued high quality treasury management by the IBRD and measures to prevent further credit rating downgrades are required to mitigate this risk. This is only a partial mitigating strategy since further downgrades to donors are a major determinant on borrowing costs and lie outside IFFIm's control. Important to highlight, that since inception, the weighted average costs of IFFIm borrowing has been lower than the weighted average cost of IFFIm donors’ borrowing.
Risk that IFFIm is used for purposes beyond its core mandate	The key risk associated with this is to the effectiveness and efficiency of IFFIm as a financing instrument to enable Gavi to achieve its core immunisation mandate.	IFFIm financial management is governed by the IFFIm legal agreements, including the Finance Framework Agreement. These set out how donor payments are made and how funds are managed by the World Bank as Treasury Manager and transferred to Gavi. These also require that all funds disbursed by IFFIm are used for Gavi Board approved programmes and the 2016-2020 strategy. Gavi is responsible for monitoring the risk of misuse of IFFIm funds and regularly reports back to IFFIm on the outcomes. Gavi, the sole beneficiary of IFFIm’s funds, has zero tolerance for misuse. IFFIm has been in compliance with all applicable regulatory requirements and industry norms.
Risk that IFFIm will cease to operate in providing flexible funding to Gavi	IFFIm’s ability to raise funds efficiently depend on it being able to go out to the market and issue bonds frequently. As some donor pledges to IFFIm come to an end over the coming years, if IFFIm does not receive new donor pledges, it will have decreasing capacity to make new issuances. This creates a risk that IFFIm will cease to operate in a way that it has to Gavi, providing flexible and frontloading funding for future investments.	The UK is hosting the 2020 Gavi Replenishment which will include an ‘ask’ to top up IFFIm to ensure it retains its usefulness to Gavi as a flexible funding instrument. As hosts for the replenishment, the UK will support Gavi in these fundraising efforts to ensure the replenishment is a success. The existing UK commitment continues to support IFFIm until 2029.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and DFID, notably on commercial and financial issues
Delivery against planned timeframe

IFFIm has provided US$2.6 billion to Gavi as of December 2018, representing 19% of Gavi’s total resources since 2000 (US$13.5 billion), and 20% since its inception in 2006. This is below its original target of providing US$3.3 billion by the end of 2015, due to Gavi exceeding its replenishment targets for the 2011 to 2015 period and not requiring additional frontloading of IFFIm funds at the scale originally envisaged. In its first five years of operation, IFFIm provided more than half of Gavi’s total funding (53%); this is evidence of its ability to frontload resources.

Over the 2016 – 2020 strategic period, IFFIm is expected to disburse US$ 600 million, representing approximately 7% of Gavi’s overall forecasted resources in the period. As of December 2018, IFFIm has disbursed a total of US$ 150 million to Gavi to date.

The current IFFIm logframe includes indicators updated in last year’s Annual Review which provide more comprehensive perspectives on the efficiency and effectiveness of IFFIm’s operating model. IFFIm has consistently delivered on these targets.

Performance of partnership (s)

Partnerships continue to perform well, with the World Bank acting as a highly engaged, efficient and credible Treasury Manager. The World Bank and the IFFIm Board continue to engage to find options that could alleviate the pressures presented by the swap exposure. The IFFIm donors and the World Bank are closely engaged with the IFFIm Board and the Gavi Secretariat in furthering the development of IFFIm’s strategic initiatives.

Quality of financial management

IFFIm’s financial reporting is in line with international best practice. Financial forecasts for IFFIm disbursement are aligned with Gavi’s needs and are reported to the IFFIm Board on a quarterly basis. The IFFIm financial statements are audited by Deloitte LLP, an external independent auditor, who also issues unqualified audit opinions.

The World Bank is IFFIm’s Treasury Manager; it manages IFFIm’s finances to the same prudent standards that it manages its own finances. With its strong institutional reputation and financial market expertise, the World Bank enables IFFIm to leverage donor pledges for Gavi’s vaccination programmes through the issuance of vaccine bonds on international capital markets.

IFFIm and the World Bank carefully review and negotiate treasury management fees every year to ensure cost optimisation.

IFFIm and the World Bank actively manage IFFIm’s funding cost to maximise its overall efficiency while also taking into account the opportunity that any new market provides to Gavi in increasing its profile and visibility.

Date of last narrative financial report(s)	31 December 2018 (published June 2019)
Date of last audited annual statement (s)	31 December 2018 (published June 2019)

G: MONITORING, EVIDENCE & LEARNING
Monitoring
DFID monitors IFFIm’s progress via quarterly reports issued by the World Bank, annual IFFIm donor meeting , and regular dialogue with the Gavi Secretariat. The last IFFIm donor meeting was June 2018 and the UK will attend the upcoming donor meeting which will be held at the Gavi Board in December 2019.

This IFFIm Annual Review involved discussions with Gavi staff in Geneva, the IFFIm team in Washington DC by videoconference and further desk based analysis carried out in consultation with the Gavi Secretariat. Sources of information included: previous IFFIm annual reviews, the 2019 Gavi Annual Review, and data from the Gavi Secretariat, World Bank and IFFIm website. Scoring was conducted internally by the DFID Global Funds Department team based on the evidence provided.

In the coming year, IFFIm’s second largest donor, France will conduct a review of IFFIm’s performance as a financing mechanism. Next year’s annual review should consider the findings of this report and examine how IFFIm and Gavi have responded to and implemented any critical lessons learnt for the future.

Evidence
IFFIm was independently evaluated in 2011. This evaluation assessed “whether the IFF concept is proven and whether the IFFIm pilot has worked”. A number of key strengths and weaknesses were identified, including that it had successfully demonstrated a proof of concept but that it had not fully utilised the potential the model offers in terms of frontloading and predictability.
[note] http://www.gavi.org/results/evaluations/IFFIm-evaluation/

Of four strategic initiatives that were identified in 2015/16 to support Gavi’s broader strategy, the initiative on the creation of a new facility that would issue guarantees in support of Gavi’s market shaping commitments is at an advanced stage of development. The timeline for this tool has been revised to be operational over the course of next year, in time for the start of the next strategic period. While the vaccine scale-up initiatives will look for opportunity for IFFIm’s application as it arises, the other two initiatives - supporting CCEOP and providing a funding tool to respond to disease outbreaks – continue to be on standby per IFFIm donors’ guidance until Gavi clarifies its role on funding support for these areas.

In addition, the World Bank and the IFFIm Board are engaged in exploring potential options to alleviate the pressures presented by the swap exposure and to enable IFFIm to receive new pledges in non-USD currencies.

Learning
In line with a developing donor dialogue, IFFIm’s recent activities demonstrate IFFIm’s continued efforts to supporting Gavi in new ways.

IFFIm’s successful bond issuance to support the work of CEPI demonstrated its ability to expand its frontloading capacity to support important global health initiatives that are aligned with Gavi’s mission. CEPI is a public private initiative that accelerates development of vaccines against emerging infectious diseases and enables equitable access to these vaccines during outbreaks. In November 2018, Gavi approved support for the CEPI using funds made available by the Government of Norway, which were frontloaded through IFFIm. Following the approval, IFFIm raised NOK 600 million in immediate funding for funding CEPI in June 2019. Norway and CEPI cited IFFIm’s simplicity, speed of execution, cost, compliance and strong reputation among investors as compelling features for utilising the IFFIm model. Looking to the future, IFFIm’s support for CEPI is expected to yield dividends in the form of new vaccines for deadly epidemics and diseases.
Social bonds are an emerging trend in the capital markets attracting interests from the growing set of SRI investors. Over the past decade, IFFIm’s vaccine bonds have earned the reputation for being one of the best managed and most ethical and impactful socially responsible investments (SRIs) in the market place. The success of these bonds has been instrumental in influencing the financial markets to develop a set of common Social Bond Principles in 2017, which now underpin the SRI market. In view of this growing market interest, IFFIm has implemented organised, sustained communication activities to reinforce its reputation and leadership in the social bond space. As a pioneer in socially responsible investments (SRI), IFFIm’s Vaccine Bonds continue to fuel the interest of the growing community of socially responsible investors globally. Not only do these bonds provide strategic market access for IFFIm but they also increase the visibility and awareness about Gavi’s life-saving mission and the global health agenda.

At Gavi’s mid-term review (MTR) held in Abu Dhabi in December 2018, IFFIm’s contributions to world immunisation were recognised highlighting the productive partnership between Gavi and IFFIm to build alliances with investment and development sectors to help create transformative solutions to global immunisation challenges.

Progress on recommendations from 2018 review
	DFID Recommendation	Progress update
1	Gavi should ensure that it is taking advantage of the flexibility afforded to it by IFFIm and using it as efficiently as possible. This includes finding the optimal balance between drawing down funds and maintaining headroom in IFFIm.	Ongoing. / Refer to Section D.
2	Gavi and IFFIm to ensure that IFFIm is not stretched to uses beyond its purpose of enabling Gavi to deliver its core mandate, and thus risk the effectiveness of the use of IFFIm as a funding mechanism. DFID to work with IFFIm, Gavi and other donors on this	Ongoing. / IFFIm applies a donor consultative process to consider new potential strategic options. In supporting the Coalition for Epidemic Preparedness Innovations (CEPI) through the issuance of bonds backed by a new Norwegian pledge to IFFIm, IFFIm and Gavi in consultation with IFFIm donors and other Gavi’s partners made sure that the opportunity was aligned with broader Gavi’s mission and had no adverse financial implications for Gavi nor IFFIm. For further details, please refer to Section D.
3	IFFIm to continue to ensure that shortlisted strategic initiatives are scaled up and implemented to drive further innovative use of the IFFIm vehicle in delivering Gavi’s mandate. Progress on these should continue to be reported on annually through Board meetings	Ongoing. / Please refer to Sections B and D for progress updates on IFFIm’s strategic initiatives.
4	DFID should closely monitor the rollout, implementation and use of the market shaping guarantee tool currently under development. DFID to assess this as a use of IFFIm funds in future annual reviews.	Ongoing / Please refer to Section D.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided