Business Case

Asia Regional Human Trafficking Programme

December 2012

Contents	Page

I Intervention Summary	2

II Strategic Case	4

III Appraisal Case	16

- Economic Appraisal	23
- Theory of Change	31
- Climate and Environment Assessment	32

IV Commercial Case	34

V Management Case	40

Appendix 1: Migration and trafficking corridors	45
Appendix 2: Legislation and policy context in
Bangladesh, India and Nepal	48
Appendix 3: Climate & Environment Assurance Note	52

Logframe: Attached separately

Business Case
## Asia Regional Human Trafficking Programme

I	INTERVENTION SUMMARY

What support will the UK provide?
The UK will provide £9.75m over five years from 2012/13 – 2016/17 to help prevent trafficking of women and girls from South Asia in the domestic and garment sectors. Over 100,000 women and girls will be direct beneficiaries of the programme.

Why is UK support required?
This programme will help deliver DFID’s Strategic Vision for Girls and Women in two priority areas - Preventing Violence against Women and Girls; and increasing Direct Assets for Girls and Women through better wages, working conditions and remittances from safe labour migration.

It will also help deliver DFID’s public commitments as part of the UK Government Strategy on Human Trafficking, by delivering against both Action Points identified: to continue to work with source countries to raise awareness among those who may be at risk of becoming a trafficking victim; and to raise awareness in source countries of the risk of child trafficking.

The UK will take forward anti-trafficking prevention work globally by taking a ‘whole trafficking chain approach’. This means we will identify women and girls in their villages and follow their migration journey, identifying and providing support during the critical points at which they are most vulnerable to being trafficked. We will help improve their workplace conditions and support them to return home safely. Most of the international effort on human trafficking has focused on sexual exploitation. However labour trafficking, which is far more prevalent, has been neglected. DFID will also make a contribution to global public knowledge goods through improving the evidence on what works.

Human trafficking is a crime and a human rights violation. It causes significant financial, physical and psychological harm to victims and their families. It restricts the ability of people to lift themselves and their families and communities out of poverty. The UN definition of trafficking includes the recruitment, transportation or harbouring of human beings by threat, use of force, coercion, abduction, fraud, deception and/or abuse of power for the purpose of exploitation. This programme focuses on the worst forms of child and labour trafficking affecting women and girls.

Asia has the highest number of trafficking victims. According to the ILO’s most recent count in 2012, there are about 21 million men, women and children trafficked and in forced labour worldwide, the majority of whom are in Asia (11.7 million). Approximately 4 million victims of forced labour are from Bangladesh, India and Nepal - involving migration across borders or between states within countries – to exploitative jobs, debt bondage and extremely low wages.

Expected Results
The programme will help to prevent women and girls from India, Nepal & Bangladesh from being trafficked within South Asia and to the Middle East for garment and domestic work. Within five years, the programme will help 100,000 women and girls to protect themselves from being trafficked and will contribute to an overall reduction in the incidence of trafficking in South Asia.

Activities and results will include:
- 8,000 domestic workers will receive skills training aimed at supporting them to secure a legal contract and decent wage.
- 9,000 girls under 16 will be supported to stay in school so that they are not compelled to migrate for domestic work.
- Over 100 private sector recruitment agencies will sign up to ethical principles and practices for recruitment, benefiting up to 200,000 women workers.
- 12,000 women will benefit from pre-departure information to help protect themselves from being trafficked or otherwise exploited.
- 6,000 vulnerable women will receive mobile phones so that they can access helplines and support services and remit money safely and cheaply.
- At least 8,000 women and girls will be prevented from being trafficked.
  [note] This is a conservative estimate based on the only survey data available from Eastern Europe, which shows around 8% of poor people who migrate are likely to end up trafficked. South Asia’s poverty levels and vulnerability to trafficking are much greater
- We will help governments implement laws and policies to tackle human trafficking.
- A rigorous evidence base will be developed for the first time on what trafficking interventions work in South Asia.

How will we do this?
The key implementing agency will be the International Labour Organisation working in partnership with the UN Office on Drugs and Crime, the International Federation of Private Employment Agencies and its affiliates, domestic and garment workers organisations and NGOs.

The London School of Hygiene and Tropical Medicine will lead and manage two large impact evaluations, deliver new evidence papers and support overall monitoring and evaluation.

An external advisory group of experts, other donors and global leaders on trafficking will be established to provide oversight and advice. The programme will be managed by a Steering Committee that includes DFID and all key implementing partners. DFID country offices will be closely involved in the programme to ensure that it complements and supports existing programmes and partnerships. Regular updates will be given to a UK government and stakeholder group that has been set up and consulted throughout the design phase.

This programme has been designed on the basis of new evidence and data developed as part of the inception phase, which included five pilot programmes, two evidence papers and consultation with trafficking experts.

How will we determine whether the expected results have been achieved?
We will support two rigorous and independent impact evaluations for the first time in South Asia. These will focus on:
- The impact of this programme’s comprehensive package of support, information, vocational training and financial literacy before women migrate, to reduce the risks of trafficking; and
- The impact of mobile phones to help women access help and services if trafficked, reduce social isolation and use ‘mobile money’ channels to remit wages safely and cheaply.

Results will be tracked through baseline surveys, continuous monitoring of migrant workers, measuring changes in private sector attitudes and practices, changes in government policy and practice and progress in cooperation between sending and receiving countries – over the five year period. An independent evaluation to review progress will be conducted at the mid-point of the programme, and changes made to ensure it is on track to deliver expected results. At the end of the programme, another independent evaluation will be conducted on achieved outcomes and impacts.
II	STRATEGIC CASE

Context and need for a DFID intervention

Human trafficking is a significant problem in Asia

Asia has the highest number of trafficking victims. According to the International Labour Organisation’s (ILO’s) most recent count in 2012, there are about 21 million men, women and children trafficked and in forced labour worldwide, the majority of which – 11.7 million – are in Asia. Approximately four million victims are from Bangladesh, India and Nepal. Human trafficking is a human rights violation that causes significant financial, physical and psychological harm to victims and their families.
[note] 1 This figure was derived from the ILO Global Estimate on Forced Labour, 2012 using regional level data. Three different methodologies were used to calculate the figure: two based on a repartition estimates for the region Asia and the Pacific, and the third based on the country of origin.

There are an estimated 600,000 trafficking victims in the Gulf States and Middle East, where a significant proportion of workers migrate from South Asia working in mainly in textile sector, domestic and care work and the construction industry. Because of poor data and under-reporting, the actual numbers are likely to be much higher.
[note] IOM country based reports “Distribution of migrants by region of destination”, 2009
[note] Amnesty International’s 2011 report on trafficking and migration in Nepal 2011 found official figures indicating only 3% women migrant workers, but unofficial records show this is more likely to be 30% of Nepalese migrant workers abroad. In 2011, Indonesian officials estimated that around 70% of the 1.2 million Indonesians working in Saudi Arabia are domestic workers.

Figure 1: ILO Estimates of Forced Labour, 2012
[note] 4 http://www.ilo.org/global/about-the-ilo/press-and-media-centre/news/WCMS_181961/lang--en/index.htm

Human trafficking often starts at the point of recruitment, with families accepting huge fees charged by local agents or labour recruitment agencies to facilitate their journey and secure jobs abroad. These fees are to be repaid from future earnings, tying workers and their families in debt bondage even before they migrate or start to work. These agents regularly operate through informal channels, paying off corrupt officials at each stage of the process and condemning migrants to vulnerable practices.
[note] ILO Global Estimate on Forced Labour, 2012.

Women and girls from South Asia face particular vulnerabilities to forced labour and trafficking. They are often poorly educated and unskilled and as a result can only access jobs at the lowest end of the labour market – precarious, unskilled and badly paid. Once working, they are often subjected to sexual and other forms of abuse.
[note] World Bank, ‘Gender, Poverty Reduction and Migration’, Irena Omelaniuk,

The definition of trafficking used for this programme is the internationally agreed UN Protocol to Prevent, Suppress and Punish Trafficking in Persons, Especially Women and Children. The term includes recruitment, transportation, harbouring human beings by threat, use of force, coercion, abduction, fraud, deception or abuse of power for the purpose of exploitation.
[note] The term “trafficking” refers to the recruitment, transportation, transfer, harbouring or receipt of persons, by means of the threat or use of force or other forms of coercion, of abduction, of fraud, of deception, of the abuse of power or of a position of vulnerability or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purpose of exploitation. Exploitation shall include, at a minimum, the exploitation of the prostitution of others or other forms of sexual exploitation, forced labour or services, slavery or practices similar to slavery, servitude or the removal of organs. Source: Protocol to Prevent, Suppress and Punish Trafficking in Persons, Especially Women and Children, supplementing the United Nations Convention against Transnational Organized Crime (article 3 (a). Key references & guiding principles for the programme will be based on Internationally or regionally ratified instruments & agreements, including ILO & Human Rights Conventions and the Colombo Process.

This programme will focus on the worst cases, in which coercion (removal of choice or agency) and threat (related to harm, withholding payment etc.) will be the defining indicators. These are based on the ILO Convention on Forced Labour (No.29) which provides the most comprehensive set of indicators to measure labour-related trafficking. By using these tight definitions and indicators, we will avoid relative measures of abuse and exploitation, such as long hours and low pay, which workers may decide is better than no job at all.
[note] The ILO Forced Labour Convention 1930 defines forced or compulsory labour as “all work or service that is exacted from any person under the menace of any penalty and for which the said person has not offered himself voluntarily.”

     The economic drivers of human trafficking

Large differences in wages, resulting from differences in wealth and the pace of economic growth, create incentives for people to relocate in order to pursue higher incomes and standards of living. People commonly migrate between regions within countries, from rural to urban locations and between countries. Poor people often suffer from a lack of accurate knowledge about the process of migration and the true nature of employment opportunities available to them. They are unlikely to have the resources to address these knowledge gaps, making them vulnerable to dishonest recruitment agents who seek to exploit them. Evidence shows that despite the risks, as long as large wage differences exist, people will move to obtain the opportunity of a better standard of living.

South Asia is home to 40% of the people who are living on less than $1.25 a day (some 600m). Though the region has recently experienced high growth rates, increasing inequality mean that high levels of under-employment and low wages persist. Millions attempt to escape this poverty through voluntary migration, looking for work in richer countries or areas. Some economists consider greater freedom in labour mobility to be the single greatest weapon for development - it has been estimated that the gains from a lifetime of micro-credit is equivalent to spending eight weeks working in the U.S.A..
[note] DFID Bilateral Aid Review
[note] There is an estimated 214million current international migrants worldwide, with women accounting for just under half of the total (IOM, ‘World Migration Report’ 2010)
[note] Many Indian migrants move from poorer states to richer states within India
[note] Lant Pritchett (2009). ‘Is Migration good for development? How could you even ask?’ Presentation delivered at Columbia University.

Labour migration is an increasingly important vehicle for governments and the private sector world-wide to generate growth and manage employment in both sending and receiving countries. Migrants are able to assist family members, who remain at home, by sending remittances. Though these cash-flows are notoriously hard to quantify, the remittances sent to developing countries in 2010 were estimated to be $325bn and are likely to be significantly higher as many transfers go unrecorded through informal channels. These flows are very significant in many of the regions poorest countries. As can be seen in Figure 2, remittances sent to Bangladesh in 2010 equated to 12% annual economic output and those sent to Nepal, 21% of the country’s economic output.
[note] World Bank's Migration and Remittances Fact Book 2011
[note] The Economist: ‘An unexpected downside’, (April 20th, 2011)

Figure 2: Remittances as a percentage of annual economic output

Family members who receive remittances are able to feed, clothe and invest in the family unit, paying school or training fees, purchasing assets or providing seed capital for businesses. In the poorest countries, remittances can often be received as foreign currencies, such as US dollars, that have a stable value, providing important protection against domestic inflation that can be catastrophic for poor people. As well as this, remittances are primarily spent in local areas, increasing the demand for local goods and services. This increase in demand stimulates local economic growth and can have a multiplier effect that provides local employment opportunities into the future. There is some indication that women remit more of their earnings then men, and are able to exercise greater control of their household income by ensuring the remittances are spent on family needs back home.
[note] IOM Report (2002), A Study on Remittance Inflows and Utilization
[note] IOM Report on vulnerability of women in migration, 2005 and D. Acemoglu et al.: ‘Finding Eldorado: Slavery and Long-run Development in Colombia’, June 2012, MIT Working Paper

Though the benefits from successful migration can be very large, they are mirrored by the costs that are incurred when migration is unsuccessful and an individual becomes a victim of trafficking, entering into forced labour. Economic research has demonstrated that trafficking-related exploitation has a long-term negative effect on the development of entire communities, especially if they depend on industries that are prone to exploitation.

According to ILO research, the “opportunity costs” of forced labour amount to over US$21 billion annually, measured in the principle monetary costs of unpaid wages and illegal recruitment fees. These lost incomes represent lost development gains – both at the household and community level. At the household level, lost income means lower remittances and fewer choices because of mounting debts. These lead to a vicious cycle of poverty and dependence. Addressing forced labour from a broader labour market perspective, and not solely from a narrow criminal perspective, will therefore increase development gains for individuals as well as communities. For communities, lower remittances and high debt burdens mean depressed local spending, lower economic activity and increased social costs from lower spending on food, health care and schooling.
[note] The figure is currently being updated in light of new global estimates. It is most likely to be significantly higher. See ‘ILO: The cost of coercion, Global Report’, 2009. See forthcoming ILO report on the economics of forced labour and trafficking.

Asia is both an important sending and receiving region for female migrant workers, who move along numerous migration ‘corridors’ as shown in Figure 3. A full outline of the specific dynamics of laws, policies, risks and entry points along these migration routes is set out in Appendix 1.

International migration flows from South Asia are primarily to the Middle East, primarily Gulf Cooperation Council (GCC) countries, as can be seen for flows from Bangladesh and Nepal. Of the 214 million international migrant workers in 2010, half were women and more than 61 million were from Asia. Of this 61 million, 14.3 million migrated to countries of South Asia, whereas 28.8 million to countries in Western Asia and the GCC.
[note] IOM country based reports “Distribution of migrants by region of destination”, 2009
[note] United Nations, Department of Economic and Social Affairs, Population Division, International Migration 2009-2010
[note] Afghanistan, Bangladesh, Bhutan, India, Iran, Maldives, Nepal, Pakistan and Sri Lanka (op. cit.)
[note] GCC countries, Middle East and South Caucasus (op. cit.)

There are few reliable figures for internal migration flows in Asia, however evidence suggests there is a great deal of movement between states or provinces, and from rural to urban centres. This includes movement by children under the age of 18. Broad estimates put the number of children involved in seasonal migration in India alone at 4 to 6 million.
[note] Understanding Children’s Work Programme: Joining forces against child labour: interagency report for The Hague Global Child Labour Conference 2010, Geneva, ILO, 2010.

Figure 3: Asian migration ‘corridors’

Migrants, recruiters and employers

Migrant domestic workers

In most patriarchal societies domestic work has little value. Most domestic workers enter the job unskilled and receive no training or access to other employment opportunities. Many domestic workers, especially live-in workers face sub-standard conditions and usually have no defined working hours. Live-in workers are often ‘on call’ for the family 24 hours a day, with virtually no paid weekly time-off or any defined period of rest. Numerous micro-studies and media reports reveal a range of punishments such as slapping, hitting, pulling hair, verbal abuse, threats, detention in the house, sexual harassment and abuse. Most domestic workers migrate from rural and isolated areas and have little or no contact with their families. They suffer loneliness, stress and mental health issues, especially as many have left small children behind in the care of others and worry about their welfare.

Because domestic work is in private homes behind walls, there is no public scrutiny, protection or recourse to help for domestic workers. Many have their passports and personal items taken away from them on arrival, and may not be allowed to leave the house. Even if they are, they may not be able to get to their national embassy, contact the labour attaché or know who else to turn to for help. In any event, migrant domestic workers are often reluctant to report abuse or leave their jobs because their families have incurred enormous debts and are dependent on them to send remittances. If they are sexually abused at work, they may be stigmatised when they return home and regarded as prostitutes or not suitable for marriage.

Migrant domestic workers tend to be underpaid and sometimes not paid at all. There are often delays in paying wages, or ‘additional costs’ are deducted without justification. Although labour inspection is required in all employment situations, in practice the private home is usually out of bounds for labour inspectors. As a result migrant domestic workers are most at risk from forced labour. Only 19 out of 67 countries studied by ILO have specific laws or regulations dealing with domestic work, and these laws often afford lower protection to domestic workers than to other categories of workers. For example, India has a Domestic Workers Act and social security schemes for informal sector workers that also apply to domestic workers. But so far, there have been very few convictions of abusive employers or intermediaries involved in the trafficking of domestic workers.
[note] A. D’Souza, ILO - ‘Moving Towards Decent Work for Domestic Workers: An Overview of the ILO’s Work’, Working Paper 2010

According to the latest ILO estimates, domestic workers represent 4 to 10 per cent of the total workforce in developing countries and 1 to 2.5 per cent of the total workforce in developed countries.

Migrant workers in the garment sector

The garment industry is especially susceptible to the abuse and exploitation of labour. Garment production is labour intensive and the industry highly competitive, so labour costs are a critical concern for businesses, creating the pressure for labour exploitation to occur.

For many years, high levels of exploitation and abuse in ‘sweatshops’ have been exposed in the textile sector. Most of the evidence is qualitative using case studies and stories. Governments are often reluctant to acknowledge cases of forced labour in the textile sector as this could jeopardise trade relationships with partners that monitor trafficking. The clearest cases of forced labour in the textile sector in India are reported under the Sumangali Scheme. This binds workers in bonded labour because their wages are held back for three or more years until the contract has ended. There are an estimated 35,000 female migrants working under the Sumangali Scheme in one district of India alone (Puddukottai).
[note] The Sumangali Scheme remains a sensitive political issue in India. In 2011, In May 2011 SOMO (Centre for Research on Multinational Corporations) and the India Committee in Netherlands published the report ‘Captured by Cotton – Exploited Dalit girls produce garments in India for European and US markets’ , 2011, Overeem & P.M. Theuws. The report exposed a number of large garment brands and retailers were using girls from Dalit and low caste background under this system. See also ITG baseline report which was submitted to ILO in 2012.

Whilst some of the well-known textile brands have started to tackle fairer labour practices in factories as a result of sweat-shop and child labour scandals, very little has been done to take account of the particular vulnerabilities faced by migrant workers. There is also little evidence of multi-stakeholder approaches involving governments, employers and workers to tackle this. Despite continued action on the part of governments, social partners, NGOs and large corporations to eradicate forced labour from garment and textile supply chains, verifiable impact has remained minimal.

Child labour – girls trafficked in domestic and garment sector jobs

Due to the criminal and clandestine nature of trafficking, the numbers of victims are difficult to measure. Despite these challenges, in 2005 the ILO estimated that 40-50% of the global 2.45 million victims of trafficking originate from Asia-Pacific and there are indications that trafficking of children is on the rise. They are trafficked both within and between countries, for example from Bangladesh and Nepal to India or from South Asia to South-East Asia or the Middle East. Asia is a regional hot spot for trafficking in children. The ILO estimated that in 2005, 40-50% of the global 2.45 million child trafficking victims originate from the Asia-Pacific region.
[note] Asian Development Bank (2003) Combating Trafficking of Women and Children in South Asia: Regional

It is thought that most child trafficking victims from Nepal end up in India. In 2001, an ILO study estimated that 12,000 girls were trafficked annually from Nepal to India in prostitution alone. Another study in 2003 found some 55,000 girl children working as domestic workers, migrating from rural to urban areas inside Nepal.
[note] ILO rapid assessment and baseline survey 2003 on child trafficking in Nepal.

Bangladesh is a source and transit country for child trafficking, both internally and across borders. Official records found 13,220 cases of child trafficking between 1998 and 2004.. Early marriage and dowry practices contribute to the vulnerability of young girls to trafficking. A little less than ten percent of the country’s 65.3 million children are without birth certificates, which makes it more difficult to trace and rescue trafficked girls.
[note] Bangladesh Ministries of Home, Social Welfare and Women & Children’s Affairs records 2004: they have responsibility for monitoring statistics for cross-border trafficking.

A UNIFEM study in 2006 indicated that in India data for trafficking of children is mainly found on commercial sexual exploitation. The US State Department Trafficking in Persons Report however, finds evidence that both girls and boys are being trafficked into a wide range of other economic activities, such as factory work, domestic work, begging or agriculture.
[note] US State Department (2012) Trafficking in Person Report 2012. Washington D.C.

Employers and recruiters of migrant workers

Almost all Gulf Cooperation Council (GCC) countries follow the system of sponsorship or ‘kafala’ whereby employers sponsor a worker within agreed laws as temporary workers, often paying recruitment and transport costs. The worker’s contract and leave to stay in a country is linked directly to a single employer, which commonly has the effect that employers assume an expectation that they ‘own’ their worker’s time and services, are unaccountable, and have the right to terminate contracts at any time if they’re dissatisfied.

Legal and policy responses to trafficking in South Asia

Anti-trafficking policies involve a complex array of laws, different government departments and authorities at national, state and local levels, often with little clarity about which law applies to a particular situation. For example, each country may have anti-trafficking legislation relating to crime, but also laws on forced labour, domestic work, child labour, violence against women and labour migration, poor guidance about which is more relevant or protective. When there is migration from one country to another, this problem is exacerbated as each country will have its own laws and policies. This complexity has contributed to a very low rate of prosecution of labour trafficking cases in South Asia.

Of the three focus countries of this programme, only India has ratified the UN Protocol on Trafficking in Persons in 2011. In South Asia, the SAARC Convention on Preventing and Combating Trafficking of Women and Children for Prostitution falls short of international standards by excluding the labour dimension of trafficking. It focuses largely on return and reintegration of sex workers and many international organisations have called for its revision. A more detailed outline of government legal, policy and programme responses to trafficking for India, Nepal and Bangladesh is set out in Annex 3.

Significant progress – at least at the level of law and policy - has been achieved in the Middle East (including GCC countries) as policy makers have taken action against trafficking in human beings. With the exception of Kuwait, all countries in the region have now criminalized trafficking and/or forced labour. In 2011, UAE and Oman issued new regulations on private employment agencies to avoid fee charging and contract substitution. In 2010, Member States of the Arab League launched the Arab Initiative to Build Capacity to Fight Trafficking. The initiative is aimed at: strengthening the institutional and human capacities of the criminal justice systems; improving mechanisms for the appropriate identification, referral, support, and protection of trafficked victims; and raising the awareness about the crime and its devastating consequences on individuals and societies at large. It is as yet too early to assess the impact of these initiatives and policy changes but there are still gaps in protection. For example, domestic workers are not covered by labour law and the sponsorship system (kafala) has yet to be reformed. Ratification of the ILO Convention, 2011 (No. 189) could offer an opportunity to regulate domestic work.
[note] See forthcoming ILO report on Trafficking in the Middle East

Anti-trafficking programmes to date have tended to focus only on supply-side measures, such as raising awareness of departing migrants in source countries, prosecuting traffickers at the recruitment stage and ensuring safe return and reintegration of trafficked victims, but not enough on the ‘demand side’. Demand-side interventions create opportunities to work with recruiters, employers, workers, NGOs and governments on global value chains. Without tackling both supply and demand, it is difficult to identify entry points and incentives for safe migration and decent work, nor identify critical risks and enablers of trafficking.

Gender dimensions of migration and trafficking policies

To date, there has been a lack of gender sensitive approaches to migration and trafficking. Bilateral migration agreements between South Asia and countries in the Middle East / GCC do not mention women workers nor take account of the specific vulnerabilities they face. Many policies within countries intended to protect women and girls, often by imposing restrictions on migration, have had unintended negative consequences as they push those determined to migrate towards unofficial routes with higher risks from informal recruiters and traffickers. Rather than reduce the overall incidence of trafficking, these policies are likely to displace it.
[note] On the questions of age limits see ‘GAATW: Collateral Damage. The Impact of Anti-Trafficking Measures on Human Rights around the World’, Thailand 2007

India, Bangladesh and Nepal have imposed age limits or conditions on emigration of women for certain categories of work. For example the Indian government stipulates that only women of 30 years old can go abroad for unskilled work. Nepal has a ban on women migrating to Lebanon for domestic work. A similar “protectionist” approach, driven by patriarchal attitudes and concern for the security for women migrant workers, is also evident in destination countries. In Jordan, for example, migrant workers (men and women) stay in dormitories which are usually managed by the garment factory that employs them. Factories are located in “Qualified Industrialized Zones” in often isolated areas. Factory managers restrict the freedom of movement of women on grounds that they feel responsible for their security. The same practice can be found in the garment factories of India and Bangladesh.

Weak inter-state coordination

Most regulations in destination countries (Middle East/GCC) require employers to pay recruitment fees while regulations in source countries of South Asia generally permit fees to be charged to workers, albeit within certain limits. It has been widely documented that the problems of over-charging and deception (indicative of trafficking) start in the source areas where migrant workers are recruited through a web of agents and informal sub-agents. Debts gradually increase with each step in the migration process. Low skilled migrant workers are often left with little choice but to pay these excessively high recruitment fees and most experts acknowledge the need for pro-active government intervention and inter-government coordination.
[note] Rita Afsar: Unravelling the Vicious Cycle of Recruitment: Labour Migration from Bangladesh to the Gulf States, ILO 2009
[note] See for example Philip Martin & Dovelyn Agunias: Guiding the Invisible Hand : Making Migration Intermediaries Work for Development, Human Development Research Paper 2009/22, and ILO: Merchants of Labour, ed.Christian Kuptsch, 2006

There is also a role for international organisations to work with governments on building consensus for a legally binding multilateral framework in line with international standards and good practice that would establish a level playing field for recruitment practice in source and destination countries (as opposed to the current ‘patchwork quilt’ of bilateral MoUs).
[note] The important role of international organizations has been recognized by government themselves, as demonstrated by the following statement: “Governments participating in the workshop committed themselves to making the recruitment process fair, transparent, and free of abuse and to leverage the support and expertise of the ILO, IOM and OHCHR in achieving this goal” at: GFMD Workshop hosted by the UAE, February 2011.

The case for focusing on labour-related rather than sex trafficking

The Strategic Business Case approved in July 2011 agreed the case for a focus on domestic and garment sector labour-related trafficking rather than sex trafficking for a number of reasons:

1. Labour-related trafficking has been virtually ignored or avoided by governments and international development agencies despite emerging evidence that most trafficking cases globally are not in sex work but in forced labour.
2. There are good entry points for tackling this problem such as labour laws, standards, inspections and supply chain monitoring.
3. Sex trafficking responses have created 'collateral damage' from approaches that treat women like children and restrict their rights.
4. There is little evidence that that concerted efforts to identify and prosecute sex traffickers through the criminal justice system have helped to reduce the overall incidence of trafficking. Arguably, the high costs of prosecution of individual cases could be better spent tackling more than one link in the whole trafficking chain.
5. There has been a lack of coordination between stakeholders, resulting in a proliferation of single-focused interventions competing with one another and widely diverging views on which approach is best. This does not only apply to sex trafficking. However, the ideological differences between those wishing to protect the rights of migrant sex workers and those focused on protection, rescue, reintegration of sex trafficking victims polarised the debate on trafficking and inhibited opportunities for multi-stakeholder collaboration.
  [note] 34 The issue is far more complex than outlined here but since sex trafficking is not the focus of this programme, this is not expanded. This issue is raised merely to explain that DFID was advised early on in the design of this programme to avoid focusing on sex trafficking as it would inevitably demand that we 'take sides' in the debate, and that labour trafficking required more urgent attention.

There are, nevertheless, clear links between labour and sex trafficking: women trafficked in labour migration may end up trafficked for sex work. Conversely, interviews with trafficked women show they would be less likely to be trafficked for sex work if safe labour migration options were available.

        Learning lessons from piloting new approaches and partnerships

This Business Case is informed by a series of activities undertaken in the past year to help us understand the nature of the problem and to identify DFID’s added value. Our ambition is to contribute to an overall reduction in the incidence of human trafficking in women and girls from South Asia. This will help to reverse inter-generational cycles of gender inequality and poverty in the region.

The piloting and inception phase has drilled the evidence on what we know about labour-related trafficking and what works; has piloted new approaches which have yielded impressive results with limited funds and time; and built partnerships and learned lessons about what works elsewhere. This included listening to trafficked and migrant women themselves – understanding why they migrate, what risks they face and what help they need.
[note] Over nine months, DFID invested £400,000 in five pilot programmes with results that include: 4,000 vulnerable women and girls were engaged in in face to face dialogue on human trafficking through community workers and women’s organisations; 650 police officers and senior officials were trained to respond to labour trafficking; 82 community workers helped women and girls in vulnerable communities at risk of being trafficked; a web-based mobile platform was built to empower women and girls to find decent jobs and migrate safely; 14 instances of trafficking were identified and 4 victims were rescued and re-united with their families.

The design of this programme is based on the key findings and lessons of the pilots and inception phase that include:

Why women migrate – Two of the key drivers of migration for women are low family income (women who migrate are often the sole provider of income for their family) and a lack of local opportunities.

Victims of trafficking? - Returned migrant women, even if their experiences show clear evidence of forced labour, frequently don’t speak of themselves as trafficked. This is for a number of reasons: they decided freely to move to another country to seek work; the term trafficking carries a stigma associated with sex work; if they are ‘rescued and returned’ they are often criminalised for migrating illegally, and shunned by their families and community. Because they no longer send remittances home, their families remain poverty-stricken and crippled by the debts they incurred to help the women migrate; and if sexually abused, they are deemed un-marriageable. Whether trafficked or not, women migrants see themselves as workers and will need support to claim their rights.

Recognising labour trafficking as human trafficking – A key challenge has been to shift the conversation on human trafficking to include labour-related as well as sex trafficking. Victims of labour trafficking are not identified or recognised as being trafficked, and very few anti-trafficking services or prevention measures reach them. ‘Bonded labour’ is recognised as an abuse in India, Nepal and Pakistan, but generally regarded as unconnected to migration outside the South Asia. In India, the National Human Rights Commission is under pressure to be more pro-active and effective in tackling bonded labour. However, the term ‘trafficking’ is sensitive, particularly because of the US State Department’s Trafficking in Persons rating as Tier 1,2 or 3. These ratings have significant foreign policy and trade implications and as a result, governments in South Asia have been less willing to include labour trafficking in in their reporting or in legal definitions.

Pre-departure training at community level works - Surveys showed that women who participated in discussions within their local community felt more empowered with increased knowledge and awareness of their rights as migrants and benefited from sharing lessons on how to protect themselves from risks of trafficking. Pre-departure awareness training increased knowledge from 50% to 96%. On the other hand, most of the pre-departure training organised through labour migration official channels had been unhelpful. It is usually a standard module – often outdated, not tailored to their needs. It omitted critical information such as how to protect themselves from abuse or how to claim benefits to which they were entitled, such as the national insurance scheme in Nepal.

Use of innovative technologies - There is emerging evidence that mobile phones have huge potential to help reduce poverty, to protect workers, give them access to helplines and social networks, and can be used for remittances and wage payments. However this is still unchartered territory in anti-trafficking interventions. One of the DFID pilot programmes trialed tablet computers using Community Knowledge Workers (CKWs). The tablets generated interest and awareness with women in local meetings (e.g. via video, women’s stories and visual tips for safe travel). This approach worked especially well for women with low literacy levels.

Apparel brands working with trade unions - One pilot involved a partnership between NGOs working on improving recruitment and employment practices in global supply chains working alongside multinational apparel companies and trade unions. It showed the value of partnerships between actors that are often targets of campaigns against one another. By understanding the value of good working relationships between employers and workers in the global supply chain, some apparel brands began to see their responsibilities for ensuring ethical practices not only in the workplace but also the migration and recruitment phase too. Equally, some trade unions could identify ways to mitigate risks and maximise benefits for both workers and employers. They began to see the advantages of working together to stop unfair competition from unscrupulous and unethical employers.

The value of professionalising domestic work and changing employer attitudes - Domestic workers, normally at the lowest end of the value chain of work, provide a critical service to the middle class families and households that employ them. But changing attitudes and behaviours of employers to value and treat domestic workers with respect is challenging and will take time. Through baseline surveys and interviews with employers and migrant domestic workers, the pilot provided some insights on how this could be addressed. If domestic workers received certified vocational skills training, the sector could be 'professionalised' and treated as semi-skilled or skilled work (e.g. childcare, elder care, cooking). This would improve prospects for legal contracts with agreed hours, fair pay and the right to leave voluntarily, whilst employers could expect in return an efficient, professional and effective service.

Multi-dimension, multi-stakeholder interventions are needed - Specific projects based on single-focused activities will achieve limited long-term impact. A review of the evidence shows that anti-trafficking interventions have shown results only in relation to the specific objectives of their projects/programmes but failed to identify the key drivers and potential interrupters of trafficking. The pilots showed that catalysing partnerships, working alongside other existing initiatives and identifying additional interventions that complement one another will achieve far more than the sum of their parts and contribute to sustainable change. Strong differences between agencies that claim to have the right approach have resulted in competition and unwillingness to collaborate across sectors, constituents or country boundaries.

Building an evidence base - Identifying what works and why, as well as what doesn’t is critical to effective and efficient use of donor resources and ensures the best use of institutional expertise and experience. The evidence reviews commissioned during the inception phase revealed almost no robust independent evaluations, despite millions of dollars of investment over the past two decades of anti-trafficking interventions.

Building on what exists already

This programme will complement a range of existing initiatives, including DFID’s own programmes in Nepal, India and Bangladesh, such as:
- The Responsible and Accountable Garment Sector (RAGS) Challenge Fund in India and Bangladesh;
- UCEP (Under-privileged Children’s Education Programme) in Bangladesh providing education to poor under-age working children and skills training in garment production to enable them to work in Bangladesh or migrate abroad when older;
- Skills and Employment Programme under design, part of a participatory design phase of Better Work Bangladesh to support those migrating for employment;
- DFID’s private sector programmes in India and Nepal have vocational skills training components for women and girls, enabling them to get better jobs and skills in-country or abroad, and could potentially include skills for textile and domestic sectors.

This programme will also complement the work of the ILO as DFID’s primary partner in managing and delivering this programme. For example:
- In India, an ILO-Swedish funded project is providing support to study domestic worker recruitment and placement practices. The results of this study can be used to inform interventions under the proposed anti-trafficking initiatives. The ILO also supports a range of child labour and bonded labour projects in India
- A project in Bangladesh to promote decent work improved migration policy and its application.
- ILO has several technical cooperation projects on migration underway in South Asian receiving countries such as Lebanon and Jordan, which seek to strengthen the policies of the Government and other key stakeholders to better protect migrant workers.
- In Lebanon, the European Commission and the Swiss Agency for Development and Cooperation (SDC) fund a project, which focuses on women migrant domestic workers.
- In Jordan, the US Department of State funds a project to improve the rights of migrant workers, with an emphasis on domestic work and garment sector.
- The ILO Better Work Jordan (BWJ) project started its operations in Jordan in 2008 to improve labour standards and enterprise performance in the QIZs. The project operates in close coordination with the Ministry of Labour, the Ministry of Industry and Trade, the Foreign Investors’ Association (FIA), the General Trade Union for the Textile and Garment Industry (GTUTI), the Jordanian Garments, Accessories, and Textiles Exporters’ Association (JGATE), international buyers and the Jordan Chamber of Industries and the General Federation of Jordanian Trade Unions.

Whilst all these initiatives are important, each of them alone will not be able to show impact on the incidence of trafficking and abuse in labour migration overall. This programme will add value by ‘joining the dots’ between each stage of the process. The pilots and inception phase helped to identify the critical points in the ‘labour migration chain’ at which women and girls are most vulnerable and at risk of being trafficked. This programme will target those points and attempt to model a safe labour migration cycle with good protection and support in place. But rather than try to do everything ourselves, we will work with a range of partners to show how existing projects and programmes can add up to much more than the sum of their parts.

The programme will also build an evidence base for the first time to track what works and why.

UK links and interests

There are other relevant links for this as a UK-supported programme: both India and Bangladesh are increasingly important to multinational businesses headquartered in the United Kingdom. The UK is the largest European investor in India, and trade between the countries has been growing. Imports from India grew 27 per cent last year. Similarly, UK foreign investment (about £2 billion) has begun to filter into key growth sectors of Bangladesh’s economy, particularly in garments – it is home to around 70 British firms operating successfully, particularly in the garment sector.

The reputational risks of UK companies being associated with trafficking and forced labour are high, but good opportunities for synergy and partnership with UK-based NGOs such as the Ethical Trading Initiative and joint DFID-UKTI-supported ‘Capturing the Gains’ programme that seek to mitigate these risks.
[note] Capturing the Gains’ is an international research network exploring the role of the private sector, civil society, national governments and international organisations in securing real gains for poorer workers and producers in the global south

In October 2012 on Anti-Slavery Day, MP Michael Connerty proposed a new Transparency in UK Company Supply Chains (Eradication of Slavery) Act, following similar legislation in California. If introduced, it would commit all UK £100m public companies to report what they are doing to ensure their business is slave-free. This programme could put the UK on the front foot in response to such proposals.

III	APPRAISAL CASE

Generating Options

This business case will not assess the high-level decision ‘what are the options’ other than addressing human trafficking to tackle violence against women, promote women’s economic empowerment and reduce poverty and vulnerability’ for the following reasons:

The Bilateral Aid Review approved a proposal to prevent trafficking of women and girls under the Governance and Security pillar with direct relevance to Wealth Creation and its contribution to delivering two of DFID’s Strategic Vision for Girls and Women priorities.

Tackling Human Trafficking is a priority of the Coalition Government and this programme is the primary vehicle for delivering DFID’s commitments to a cross-Whitehall Strategy on Human Trafficking launched in July 2011. It will deliver against both of the Action Points for DFID in the Strategy: Action 15: continue to work with source countries to raise awareness among those who may be at risk of becoming a trafficking victim, and Action 36: raise awareness in source countries of the risk of child trafficking.

What are the feasible options that address the need set out in the Strategic case?

DFID’s 2011 pilots provided strong evidence that an integrated strategy, which takes a ‘whole trafficking chain’ approach, is the most effective way to contribute to strategic, long-term trafficking prevention of women and girls in South Asia. Consequently this approach will be used for each of the options, and is not being appraised. It is recommended that this programme targets and tracks progress of specific cohorts of women and girls and focuses on particular sectors and routes from one country to another. This will maximize impact and learning.

Option 1: focus on the Domestic / Care Sector only:

- Preventing trafficking and forced labour of women workers migrating from Bangladesh, India and Nepal to Lebanon and the UAE.
- Preventing trafficking of women from Nepal migrating to India as domestic workers.
- Preventing trafficking of the girls under 16 in India from migrating into domestic servitude by retaining them in school and providing alternative incomes and livelihoods for their families.

Option 2: focus on both Domestic Work and the Garment Sector:

This includes Option 1 but targets fewer numbers of domestic workers and instead also targets garment sector workers. The intervention would:
- Contribute to the prevention of female garment workers being trafficked from Bangladesh to Jordan; and
- Prevent trafficking of women workers and girls migrating for jobs from the poorest states of India (Bihar and Orissa) to richer states such as Tamil Nadu.

Option 3: Do Nothing Counter-factual

Rely on existing interventions by other actors and donors. ILO will continue to build support for ratification of ILO Convention on Domestic Work; anti-trafficking organisations continue to provide support services and strengthen laws and policies; organisations seeking to improve the enabling environment for poor people to benefit from labour migration and remittances continue with their efforts; DFID and other actors continue support for vocational skills training and working with the private sector to support poverty reduction. These are likely to continue as separate areas of activity.

Approach and key elements of the integrated strategy

The programme strategy is to model a successful migration cycle that intercepts key points of risk and vulnerability with three key elements:

1. Empowering women migrant workers: improving their financial literacy and economic independence, increasing awareness about their rights and access to support as migrants; and providing them with opportunities to exercise their voice, make decisions and informed choices;
2. Protecting women migrants and girls from being trafficked (including girls under working age from migrating for work and enabling them to attend school); and
3. Reducing the demand for cheap and exploitable labour by creating positive incentives for recruitment agencies, companies and employers.

To achieve the expected impact and outcomes, a multi-stakeholder, multi-country and multi-dimensional approach will be used to tackle the problem all the way along the trafficking chain - from household and community level prior to departure, to recruitment, transit, employment and return. This would involve multiple actors – including different government ministries in both sending and receiving countries, recruiters, direct employers, companies, private sector actors, NGOs, trade unions, multilateral agencies and regional institutions along the care and value chains of domestic and garment sectors.

There are five elements that will deliver a comprehensive, strategic approach to trafficking prevention. These should be regarded as an integrated and mutually reinforcing package – none of them alone are likely to contribute to a reduction in the overall incidence of labour-related trafficking.

- Economic empowerment of migrant women workers from South Asia in decent jobs, sending regular remittances to their families.
- Safe and successful labour migration of women workers with legal safeguards, protection from harm and coercion, and reducing the risks of trafficking before migration takes place.
- Private sector companies and employers that use ethical standards of recruitment and fair employment practices.
- Prevention of child labour and migration for girls under 16 so they can attend school
- Developing a robust evidence base on what works to prevent trafficking

Expected Results:

Within five years, the programme will, amongst other things, deliver a number of activities and results that include:

- Help 100,000 ‘at risk’ women & girls from India, Nepal & Bangladesh to protect themselves from being trafficked to the Middle East and in Asia;
- Provide 8,000 domestic workers with skills training to enable them to get a professional contract, decent wages and deliver an efficient and effective service when they migrate.
- Support 9,000 girls under 16 to stay in school and not be compelled to migrate for work, and help to provide their parents and families with alternative livelihood opportunities;
- Help over 100 private sector recruitment agencies to sign up to ethical principles and practices for recruitment, benefiting 200,000 women migrant workers who will no longer have to pay recruitment fees, which put themselves and their families in debt and more at risk of being trafficked.
- Provide 12,000 women with pre-departure information and financial literacy training to help so that they can protect themselves from being trafficked. They will also get help setting up bank accounts so they can send money home safely and save for the future when they return.
- Provide 6,000 women with mobile phones so that they can access helplines and services if they are trafficked, and will also use their mobiles to remit money safely and cheaply.
- Help to prevent at least 8,000 women and girls from being trafficked and will contribute to an overall reduction in the incidence of trafficking in South Asia;
- Develop a rigorous evidence base for the first time in South Asia on what works for labour trafficking prevention, which will help others target their resources more effectively.

Assessing the strength of the evidence base for each feasible option

The evidence for the two feasible options is largely the same as both will use the overall integrated approach. Section E sets out the advantages and disadvantages of each option.

Overall evidence of the situation is difficult to capture due to the hidden nature of trafficking. Evidence of what works has not been coordinated or adequately captured and as such remains weak. That is why a significant element of this programme will involve generating and capturing evidence of what works to inform and better target future anti-human trafficking interventions and resources.

This design of this Business Case was informed by a year-long inception and piloting phase to better understand the problem and to identify the UK’s comparative advantage:

- Five nine-month pilot projects were funded to test new approaches and partnerships that could be scaled up;
- A regional workshop involving peer scrutiny of the pilots; lesson-learning from other programmes in the region. Sixty global trafficking experts, key donors, policy makers, implementation agencies and researchers in Asia were invited to share lessons and insights and to help DFID design the Theory of Change. This was widely praised as best practice in transparency, aid effectiveness and design of a new programme - building on evidence of what has worked in other contexts, and not trying to ‘reinvent the wheel’.
- Listening to the voices and experiences of trafficked and migrant women workers about interventions that have been helpful and unhelpful to them;
- Experimenting with innovative information and communication technologies to help prevent trafficking of women and girls;
- Working with private sector companies on supply chains, recruitment practices and ethical business models that deliver better outcomes for migrant workers and employers, and have the support of governments and enabling policies;
- Using new ILO Global Estimates on forced labour and trafficking for the first time. These provide a robust, verified set of indicators to measure incidence that can measure change and impact;
- Feasibility assessments for tackling trafficking in both domestic and garment sectors, and identifying critical trafficking / migration corridors;
- A commissioned Evidence Paper; two Literature Reviews and several baseline surveys.

Supporting evidence for this approach:

Findings from a systematically conducted review of literature on trafficking prevention interventions and results of DFID-supported pilot projects strongly indicate that combining the five proposed intervention elements comprises the strongest approach to prevent trafficking of women and girls and foster safe migration. Specific evidence for each component includes:
[note] Kiss, L., Zimmerman, et al., Systematically conducted review of the literature on interventions to prevent trafficking for labour exploitation. Paper prepared for the DfID ARTP Meeting in Bangkok. 2012, London School of Hygiene & Tropical Medicine: London.
[note] Various DfID pilot project authors, Reports from the DfID pilot projects in India, Nepal and Bangladesh. 2012: London.

Economic empowerment of migrants and of women has been demonstrated to foster greater control over individual finances and remittances. Local rights-based vocational training and educational support leads to potentially better employment situations. The combination of these two targeted approaches has significant potential to prevent trafficking.
[note] Ashraf, N., et al., Remittances and the Problem of Control: A Field Experiment Among Migrants from El Salvador. Journal of Economic Perspectives, 2011; Pocock, N., Immigrants. Entrepreneurs. Global is Asian, 2012. Jan-Mar.
[note] Chemonics International, USAID Anti-Trafficking in Persons Programs in Asia: A Synthesis. 2009, USAID; Evans, C. and P. Bhattarani, Trafficking In Nepal: Intervention Models: A Comparative Analysis of Anti-Trafficking Intervention Approaches in Nepal. 2000, Population Council: New York.
[note] Kiss, L., Zimmerman, et al., Systematically conducted review of the literature on interventions to prevent trafficking for labour exploitation. Paper prepared for the DfID ARTP Meeting in Bangkok. 2012, London School of Hygiene & Tropical Medicine: London.

A range of evidence indicates that women’s poor pre-migration knowledge of safe migration options, employment opportunities, the dangers of trafficking and their rights and legal remedies is associated with being trafficked. Preventing trafficking will depend on improvements in women’s financial literacy, awareness of safe migration opportunities alongside stronger legal protection mechanisms and women’s knowledge of their rights under relevant legislative frameworks.
[note] Zimmerman, C., et al., , The Health Risks and Consequences of Trafficking in Women and Adolescents: Findings from a European Study. 2003, London School of Hygiene & Tropical Medicine: London; Shinkle, W., Preventing Human Trafficking: An evaluation of current efforts. Transatlantic Perspectives on Migration, 2007. Policy Brief; Pramod, V. and S. Liberalato, Preventing and combating the trafficking of girls in India using legal empowerment strategies: Evaluation report. 2011, IDLO Monitoring & Evaluation Unit.
[note] Thakali, H. and T.R. Nepal, Evaluation of the “Empowering Girls and Women for Prevention and Protection from Trafficking” project, in Review Report of Shakti Samuha. 2008: Norway; Ruiz, Neil G.. 2008. Managing Migration : Lessons from the Philippines. World Bank, Washington, DC.; Pocock, N., Immigrants. Entrepreneurs.Global is Asian, 2012. Jan-Mar.

Unscrupulous recruitment tactics, usurious employment contracts and women’s limited resources to leave hazardous or unfair work conditions have been identified as core trafficking risk factors. Emerging evidence from initiatives to establish and monitor protection mechanisms through ethical recruitment, private industry and employment regulations (e.g. working conditions) suggests these are essential anti-trafficking approaches that work best in synergy.
[note] Zimmerman, C., et al., , The Health Risks and Consequences of Trafficking in Women and Adolescents: Findings from a European Study. 2003, London School of Hygiene & Tropical Medicine: London; Mital, A., Compendium of best practices on anti human trafficking by non governmental organizations. 2008
[note] Oonk, G., P. Overeem, and M. Peepercamp, Maid in India Young Dalit Women Continue to Suffer Exploitative Conditions in India’s Garment Industry. 2012, ICN/SOMO; International Labour Organization, Demand Side of Human Trafficking in Asia: Empirical Findings. 2006, International Labour Organization: Geneva.

Increasing evidence shows that child labourers do not go to school, suffer abuse, do not develop useful vocational skills and experience significant health and social problems. Strategies to keep girls in school appear to have great potential to prevent child trafficking for domestic work.
[note] Ager, A., Zimmerman, C., et. Al. 2013, in press. What strategies are appropriate for monitoring children outside of family care and evaluating the impact of the programs intended to serve them? Journal of Child Abuse and Neglect; Bond, G., et. al., 2012 Sweeping the Bedroom: Child domestic workers in Zambia. Report for Unicef, Zambia. Hesketh, TM, Gamlin, J., Ong, M., Cambacho, AZV. 2012. The psychosocial impact of child domestic work in India and the Philippines. Archives of Disease in Childhood2012;97:773-77. Thorson, D. 2012 Child Domestic Workers. Evidence from West and Central Africa.
[note] Chemonics International, USAID Anti-Trafficking in Persons Programs in Asia: A Synthesis. 2009, USAID; Evans, C. and P. Bhattarani, Trafficking In Nepal: Intervention Models: A Comparative Analysis of Anti-Trafficking Intervention Approaches in Nepal. 2000, Population Council: New York.

A systematically conducted review showed there is extremely limited reliable evaluation research-based evidence on the effectiveness of trafficking prevention interventions to inform policy or donor investment and indicates the necessity of future evidence on the potential for replication, scale-up and value for money.
[note] Kiss, L., Zimmerman, et al., Systematically conducted review of the literature on interventions to prevent trafficking for labour exploitation. Paper prepared for the DfID ARTP Meeting in Bangkok. 2012, London School of Hygiene & Tropical Medicine: London.

E. The advantages and disadvantages of each feasible option

This section looks at the advantages and disadvantages of the two feasible options, as well as an analysis of the counter-factual. Section F takes this a step further by seeking to outline the economic costs and benefits of each of the options.

Option 1: focus on the Domestic Sector only:

Advantages:
- The clearest cases of trafficking and forced labour are to be found in the domestic and care sectors, for all the reasons set out in the Strategic Case above.
- This is an opportunity for DFID to focus on the most excluded, vulnerable, isolated and exploited workers doing difficult jobs in isolated working conditions, on precarious contracts, and worst paid.
- The focus on one sector will enable DFID to be more targeted about the way we work in each country and across borders.
- There is strong momentum and advocacy behind ratification of the new ILO Domestic Workers Convention 189, agreed in 2011. It will create the opportunity to extend legal protection to domestic workers, improve their working conditions and pay, recognise the value of their work. Domestic worker trade unions and NGO advocates are stronger now than ever before, and have organised and mobilised effectively in South Asia. There are good opportunities for partnership to deal with the particular vulnerabilities of migrant domestic workers.
- Governments in South Asia are keen to ratify the Convention, recognise the widespread abuse and exploitation of domestic workers and will be more willing to address trafficking in this sector. Governments of Arab States have also endorsed adoption of Convention 189.

Challenges:
- This is a relatively new and uncharted territory in the anti-trafficking field.
- There is no robust evidence of successful anti-trafficking prevention efforts in the domestic sector in South Asia and the Middle East.
- It will be challenging to develop an effective business model to effect change, in the absence of clear incentives for the private sector and employers to ‘do the right thing’. Collective bargaining to improve working conditions will be challenging because there are so many different employers. In some countries, such as Saudi Arabia, the Government sets the wage rates, not individual employers. It will be particularly important to influence host governments and employment recruitment agencies.
- Changing norms and attitudes about the status and value of domestic workers is an uncertain initiative and will take time.
- Domestic workers are difficult to find as they are behind closed doors in their places of employment. (However, there are strategies proposed to overcome this, such as identifying them before they migrate, at border crossing points, airports, and through labour migration and recruitment agents, embassies, NGOs, migrant worker associations and trade unions).
- Despite the positive momentum around the Domestic Work Convention, there are limited entry points and actors with whom to engage.

Option 2: focus on both Domestic Work and the Garment Sector:

Advantages of working on the garment sector:
- There are many entry points and actors – particularly on the 'demand-side' of trafficking.
- The programme could capitalise on an increasing focus on global value chains – particularly in the textile sector – with opportunities to engage governments, the private sector and the public. There is growing interest through social networking and consumer actions to effect change.
- It is easier to work with established legal and regulatory systems and strengthen monitoring.
- The pilot programme developed a new code of practice for companies and recruitment agents – the Dhaka Principles, based on the UN Guiding Principles on Business and Human Rights. It had strong interest from some apparel brands, governments and recruitment agents in South Asia. This would be a useful building block for further work.
- Garment workers can organise and address their grievances with employers and recruiters collectively if they are empowered to act as agents of change.
- This would contribute to rising global support for eliminating trafficking in supply chains. There is already some progress in this area, including work with multinational companies and other private sector actors to develop voluntary codes of practice for tackling recruitment fees and improving workplace, living conditions and services for garment factory workers.

Challenges:
- The textile sector is politically and economically sensitive as it impacts on bilateral and multilateral trade agreements. Governments are unwilling to talk about trafficking in this sector as it carries negative reputational risks and inhibits trade preference agreements etc.
- It is more difficult to establish clear cases of trafficking linked to coercion and threat, although not difficult to identify widespread exploitation and abuse. This is particularly the case for women workers migrating to the Gulf States.
- It is often the better off women and girls who work in this sector and migrate abroad, especially in semi-skilled jobs where they are paid better and usually treated better than they would be ‘back home’ in a garment factory.
- It is difficult to identify or get buy-in from unregistered private sector garment factories; corruption and deceit is rife, with few levers or incentives to change the practice if they do not operate within global supply or value chains.
- Countries in South Asia, particularly Bangladesh, are reliant on remittances from garment work abroad, and reluctant to change existing practices, however unregulated and unethical.

The value of covering both sectors:
- Efficiencies of scale – using the same interventions to cover both sectors, such as cross-border agreements, working with recruitment agencies on ethical hiring practices and fee payments, legal & policy change.
- There is a far stronger case to be made on the transferability of approaches, models and lessons if the programme covers more than one sector of labour-related trafficking. The approach could apply to other sectors that are more susceptible to labour trafficking, such as construction, agriculture and fishing.
- The textile sector offers opportunities to work with apparel brands on global supply chains – capitalising on their aversion to reputational risk associated with trafficking and sweat shops. It would encourage them to take greater account of migration dynamics and help them see the added value of changing their recruitment practices and payment systems.
- There is strong synergy with DFID programmes in South Asia in the textile sector – particularly in Bangladesh and India - where engagement with the private sector on skills and jobs are relevant and could be complementary.
- In economic terms, workers in the textile sector will earn more money than those in domestic work, so economic gains are higher from improving remittances and increasing family incomes.
- The political and economic environment in South Asia is becoming more conducive to tackling forced labour in both domestic and textile sectors.

Option 3: Do Nothing Counterfactual

The counter-factual sets out an economic scenario in the absence of this programme. Financially, no costs are incurred as the pilots have ended. No further funds would be committed so the incremental financial costs to DFID would be zero.

Failure to support this programme however risks incurring wider economic costs.

The evidence presented in the strategic case shows that the trafficking this programme seeks to address is driven by people seeking voluntary labour migration. Poor understanding around migration laws and labour markets in destination countries make these individuals vulnerable to exploitation by dishonest agents and employers. This migration is driven by the desire to find employment – possibly at higher rates of pay – in economies such as India and the Middle East that are growing faster, leading to higher rates of pay, as well as promising potential stability away from the fragility of some regions of Nepal and Bangladesh. These conditions, which drive the incentive to migrate, are unlikely to subside over the period of this intervention.

At current growth rates, India will continue to diverge away from the economies of Nepal and Bangladesh. If India’s growth was to fall dramatically, to average 2% per year, whilst Nepal’s increased to an average 3% per year, it would still take 109 years for average incomes per person in Nepal to match those in India. Incomes per person in Bangladesh, given such a slowdown India, would not equalise for 77 years. Though these scenarios are hypothetical, it is clear that strong incentives for low income workers to migrate will remain for many years to come. With growing populations of young workers the absolute numbers of women and girls seeking to migrate are very likely to increase. This situation will continue to provide opportunities for the dishonest to exploit poor people.
[note] Based on data from the World Bank World Development Indicators dataset updated quarterly - last Sept 2012.

A failure to support this programme will mean that the 100,000 women and girls that would be have benefitted will be more likely to be trafficked and exploited. The additional, but un-quantified benefits, of these individuals spreading their understanding of how to migrate safely will also be missed. The UK will miss the opportunity to work with the ILO, London School of Hygiene & Tropical Medicine and a large number of other key partners. This is also likely to mean that partners do not build a systematic understanding and evidence base of how to intervene to protect the poor who migrate for better employment opportunities. In turn, this will reduce the ability of development organisations to ensure maximum value for money for all future interventions.

Trafficking prevention would rely on existing interventions by other actors and donors (as set out above). But these activities will continue, as they have done previously, to be delivered as separate streams of work. While as individual initiatives they are likely to mitigate trafficking to some extent, none set out the challenge of reducing the incidence of labour-related trafficking in the region or globally.

F. What are the costs and benefits of each feasible options?

The total costs for both of the Options are the same at £9.75 million over five calendar years.

A cost-benefit analysis was conducted for the three options. A monetary value has been put on the benefits where it is possible. There are however a large number of benefits where it is harder to place a monetary value. The economic annex sets out the approach to the analysis and key findings.

ECONOMIC APPRAISAL

G. Approach to the economic analysis

This intervention, whether focused solely on domestic workers as in Option 1 or both domestic and garment workers as in Option 2, seeks to prevent individuals and societies from incurring the costs that result from trafficking. This is analogous to insurance, and in essence the prevention of these costs forms the most significant expected benefits from the programme. To demonstrate these we estimate and compare three scenarios, a counterfactual and the two proposed interventions. We then subtract the costs of the intervention to estimate the potential net benefits. Insufficient evidence exists to credibly quantify or monetize some benefits. Nonetheless these are important programme considerations and have been discussed where appropriate.

Approach

1. The three scenarios involve monetary estimates of two factors, earnings and recruitment fees. Any individual, whether trafficked or a successful migrant, pays a recruitment fee to cover migration costs and secure employment to access higher wages than are available to them at their point of origin. When trafficked however, as in the counterfactual, individuals incur excessively high recruitment fees and very low earnings. If they migrate successfully, as assumed in both Options, they receive greatly improved earnings and pay lower recruitment fees. The differences between these factors are the principle monetary benefits to individuals.
2. This is clearly an incomplete description of the full effects in each case, but insufficient information exists to be able to be able to quantify or monetise other effects with any confidence. Despite this, such other effects are important considerations and are discussed accordingly. Of particular importance is the value of the interventions in strengthening the evidence base on how to tackle the issue of human trafficking and the contribution to a more sustainable system of migration management by both sending and recipient countries – outcomes that are extremely hard to predict.

In either of the two Options for the intervention, the programme seeks to reduce the probability that an individual who is voluntarily migrating for employment will become a victim of trafficking. This is to be achieved through a number of strategies, mainly incorporating the distribution of information, skills and equipment. The ILO estimates that the intervention, in either Option 1 or 2, will directly reach 100,000 women and girls. We have assumed that all 100,000 go on to migrate. There will be ‘spill-over effects’ when information is distributed - where individuals communicate their new understanding to their friends, family and co-workers increasing the number of people who are prevented from being trafficked by the programme. We have made no attempt to estimate these spill-over effects due to insufficient information to make such an estimate credible.

It is not feasible for the interventions to target women and girls who have been trafficked since it is a criminal act and consequently concealed and we cannot identify which migrants will become victims of trafficking. As a result we cannot assume that all 100,000 women and girls will become trafficking victims in the absence of the programme, since many individuals migrate successfully each year. We use data on the incidence of forced labour to estimate the number of the 100,000 women and girls who may go on to be trafficked. As a result of concealment, however, victims are extremely hard to identify in order to count their number, so estimates of this incidence vary widely. The volume of migration and incidence of trafficking will also vary widely along different migration corridors and over time. Given the high degree of uncertainty, the ILO suggest a very conservative estimate of the average proportion of migrants who may become victims of forced labour of approximately 8% based on the only credible surveys available from Eastern Europe. For South Asia, this is likely to be much higher. If 100,000 women and girls are reached by the programme, this implies 8000 are likely to be at risk of trafficking. If the interventions are completely successful, they will be prevented from doing so. Though the interventions are unlikely to be completely successful, given the spill-over effects and anticipated underestimate of the probability of becoming a victim of trafficking, we have simplified the analysis by retaining the 8000 figure throughout.
[note] ILO Survey data – trafficking in Eastern Europe, 2011

Using data from the ILO Global Estimate of Forced Labour on the estimated numbers of women and girls who have been trafficked, we split this population of 8000 into numbers of adults and children. The children remain in their country of origin and complete a year of education, the monetary value of which we have not estimated. Adults will migrate and go on to work overseas for an average of three years. Migrants regularly remit wages back to their country of origin where they act as a source of income to the country. In this sense migration can be thought of as one country exporting labour to another. As with all export revenue this income will have additional benefits to the recipient economy, principally through a ‘multiplier effect’ by which a higher level of demand for goods and services is induced when the income is spent. We also have not attempted to value this additional benefit.
[note] ILO Global estimate of Forced Labour: Results and Methodology, 2012.
[note] Rita Afsar 'Unravelling the Vicious Cycle of Recruitment: Labour Migration from Bangladesh to the Gulf States'

The wages that a migrant receives will vary depending on their sector of employment and destination. Data about these wages vary widely in quality. Due to this uncertainty, we have made a simplifying assumption and used a single estimate for region in each of the domestic and garment sectors. This estimate is taken from a single source and has been uprated to a 2013 value using a 1% rate of real wage growth. We have assumed that if an individual becomes a victim of forced labour they will receive a wage that is 40% of that in the domestic sector. This may be considered a very conservative assumption for the programme analysis, as many victims are forced to work for no pay and the effect of lower wages in the counterfactual would be to increase the programmes overall benefit.

There is also a large variation in the recruitment fees that a migrant will pay to an agent. We have used the Bangladesh Association of International Recruiting (BAIRA) figure as an estimate of the fee if an individual migrates successfully. If trafficked, these women and girls will typically pay excessive recruitment fees, entering a situation known as ‘debt bondage’. Again, the reality of these amounts is both concealed due to the criminality of the behaviour and will vary across the region and sectors. Surveys of migrants have attempted to establish what these fees are and following a survey of these we have used a figure of US$ 6000 as our estimate of the recruitment fee paid by a trafficked migrant. Figure 4 provides a summary of the data used in this appraisal.
[note] 54 RRMRU - Bangladesh Migration Update Report, 2012.
[note] US Trafficking in Persons Report 2011

Figure 4: Summary of Appraisal Assumptions

The 8000 individuals assumed to be prevented from being trafficked were allocated across the programme lifetime in proportion to the annual programme budget allocation, provided by the implementers, the ILO. This allocation was completed for both of the programme Options and the counterfactual. Using these five ‘cohorts’ of workers, we calculated the aggregate wages earned in each of the migration periods and the aggregate fee paid by each cohort. All costs and benefits were discounted using a 10% rate. This is a process that adjusts values over time in order to account for the preference to receive a benefit immediately rather than in the future, with values falling through time due to increasing uncertainty. 10% is an accepted rate for regional programmes in low income countries.

Costs

A breakdown of the ILO, the programme implementers, budget is provided on page 37. Their costs are not evenly distributed, but have the following factor distribution away from an equal assignment of funds.

Figure 5: ILO Programme implementation cost factor uplift

Added to these are evaluation costs from the London School of Hygiene and Tropical Medicine to conduct a thorough evaluation of the programmes interventions and establish a rigorous baseline for comparison. These costs amount to an additional £1.4million, approximately 15% of the total budget. Though this may seem high, it is a reflection of the ambitious experimental nature of this programme, which aims to inform future policies and legal changes to maximise their effectiveness and value for money.

Benefits

Annually the following numbers of women and girls will be prevented from being trafficked:

Figure 6: Annual numbers prevented from being trafficked

Using these numbers, we applied our assumptions about wages and recruitment fees to calculate the aggregate net income for each group. For Option 2, targeting both domestic and garment workers, we have assumed 20% of workers are employed in the garment sector. The following results are obtained, from which it is clear that the high ratio of debt to income is the crippling factor for those individuals who are trafficked. The income flow converges to zero at the end of 2020 as this is the final year of migration for the last cohort of workers.
[note] ILO programme documents

Figure 7: Option Net Income Comparison

This chart illustrates that the principle benefits to the migrants are the differences in wages and recruitment fees. The net present value of the total estimated benefits accruing to these individuals, in £UK and using a 10% discount rate, is as follows:

Figure 8: Aggregate benefits to individuals in each option

This gives a net present value for the options, again in £UK and calculated using a 10% discount rate, as follows:

Figure 9: Present values of benefit and cost streams

Summary

This shows that the Net Present Value, NPV, of Option 1 is £15.6 million, with a benefit cost ratio, BCR, of 3.21. The NPV of Option 2 is £20 million, with a BCR of 3.83. This improvement is driven by the higher wages earned by semi-skilled workers in the garment sector.
[note] Where the BCR is the ratio of the present value of total benefits, B, to that of total costs, C => BCR = B/C

Whilst there is a great deal of uncertainty around the data in this programme due to the illegality and concealed nature of the issue of forced labour, we have been conservative with our estimates of both benefit streams and especially with regard to the potential numbers prevented from becoming trafficked. Sensitivity analysis has not been conducted as the programme produces strong returns despite this conservatism and the uncertainties work in opposition, some increasing the benefits significantly, some lowering them. Keeping all variable values constant, a minimum of approximately 2500 people need to be prevented from being trafficked in order for the programme to break-even in Option 1 and 2090 in Option 2.

Added to these are the benefits upon which this appraisal has not attempted to place a monetary value. These include 9000 girls who will remain in school for an additional year; the avoidance of the cost of mental, physical and sexual violence that is often endured by women and girls in forced labour; the multiplier effect of increased remittances; the demonstration effect of the programme interventions; and the value of the evidence that is produced following the programmes monitoring and evaluation.

Some costs may occur that have not been estimated, if the efforts of traffickers are displaced to other areas. Due to the weak data available we have no information on which to make an assessment of this risk and have taken the view that the appraisal estimates are so conservative as to have accounted for them.

H. What measures can be used to assess Value for Money for the intervention?

An assessment of value for money must be made by considering the estimated financial returns of the programme, balanced against the costs of achieving them. We must also consider the financial costs of the implementer, whether their administration costs are reasonable and what the implications are for DFID’s relationship with them. Finally, we must consider whether the potential, but more uncertain, benefits of the programme, make a compelling case for approval.

The economic appraisal of this programme monetised two simple benefits to the individuals prevented from being trafficked – their increased wages and reduced debts compared to their situation were they to become trafficking victims. Given these simple flows and despite the ILO providing what they regard as a very conservative estimate of the likelihood of becoming a trafficking victim both options have positive net present values. Option 2, targeting both domestic and garment workers, has the highest net present value, with a benefit cost ratio of 3.83 and is the recommended option.

Numerous other benefits would also be realised, most significantly in economic terms, the multiplier effects of the remittance flows. These support migrant’s families and induce demand in their local economies, providing the possibility of further jobs and prosperity. This money also improves the health, education and resilience of poor families. These benefits are potentially very significant, but have not been estimated due to a lack of sufficient information. The most significant potential cost is of a displacement of trafficking activity that reduces the overall impact of the programme. Again, this has not been estimated.

This programme will be implemented by the ILO, an approved partner in DFID’s Multilateral Aid Review. Although their administration fee is normally 13%, they have proposed a waiver to their Board to charge 11% instead, which compares favourably to other partners such as the World Bank, IFC and German GIZ, who charge fees ranging from 9 to 15%. As explained in the Commercial Case below, the ILO is the ideal partner to implement this programme, being the world leaders in this field and consequently having the greatest expertise and widest range of contacts. By partnering with the ILO, DFID will be building a positive relationship and network of partners to continue to tackle the problem of trafficking in the future.

Added to these considerations must be the detailed evaluation to be conducted by the London School of Hygiene and Tropical Medicine. This separate evaluation represents approximately 15% of the programme’s total budget. However, this reflects the ambitious, quasi-experimental nature of the analysis of the range individual interventions, which provides the potential to greatly advance understanding of this issue and have a transformative potential for future programmes and policies.

Summary Value for Money Statement for the preferred option

This programme represents value for money as:
- It has a large positive value when evaluated in a cost-benefit analysis, despite cautious assumptions.
- There are many potential indirect benefits to poor communities that may receive remittances, which have not been estimated as part of the cost-benefit analysis.
- The implementing partner, the ILO, is the best organization to conduct a programme of this nature, with significant expertise and contacts.
- An administration fee of 11% compares favourably to that charged by other partner organisations, such as the World Bank, IFC and German GIZ.
- The ambitious evaluation has the potential to greatly improve our understanding of anti-trafficking policy, leading to transformative change in the future.

Theory of Change – see below
Figure 10: Theory of Change: Asia Regional Human Trafficking Programme

(Double click to view full size)

Climate and Environment Assessment

Environmental degradation and climate change can have an impact on human trafficking. There are indications that growing numbers of migrants today are those who've experienced economic and livelihood shocks as a result of natural disasters or environmental degradation. When poor families are desperate to migrate abroad for jobs quickly, they are more vulnerable and at risk of using traffickers as intermediaries. There is some qualitative evidence that children are being 'offered' to traffickers as they are cheaper and easier to move 'under the radar'.

The UN Institute of Environment and Human Security’s report on ‘Human Security, Climate Change and Environmentally Induced Migration’ states that environmentally induced migration has the potential to increase significantly over the next few decades. According to climate change modelling estimates, 125 million people are likely to migrate in the Indian sub-continent in the coming century. Of these, 75 million will be from Bangladesh, who will most likely migrate to India. In India too it is estimated that 50 to 60 million people who will be displaced due to sea-level rise and resulting water source scarcities.

Climate related impacts often disrupt the functioning of local economies. The ability of enterprise to maintain or rescue economic activity and people to earn an income will be crucial after an extreme weather event. Employers’ organisations need to identify local climate and environment induced risks (e.g. floods, droughts, severe storms) for businesses that may have consequences on the enterprise and its employees. Possible actions need to be assessed and identified to reduce these risks. According to Conclusions concerning promotion of sustainable enterprises, International Labour Conference (June 2007), for an enterprise to be sustainable, it needs to be responsible towards environment and should follow environmentally friendly practices.
[note] The social and decent work dimensions of a new Agreement on Climate Change, A Technical Brief, Ana Belén Sanchez and Peter Poschen, International Labour Office

As stresses of climate change impact on livelihood systems of vulnerable people, families are more likely to try to ensure at least one member of the family migrates temporarily to send remittances home. This provides a 'safety net' of support, particularly during times of stress. Some may migrate permanently because their livelihoods have been destroyed or because it is no longer viable for them to remain in climate-affected areas.

Option 1: focus on the Domestic / Care Sector only:

Risk to project objectives due to climate change and environment

Financial inclusion: the programme aims to support economic empowerment of migrant women workers by helping them to send regular remittances to their families. However, there may be instances of climate change / disaster induced displacement of families back home in vulnerable regions. In such cases, there is a risk that remittances might not reach the intended families of migrant women and girls.

Mitigation strategy: The programme plans to provide financial literacy training, help families set up bank accounts and remit money through mobile phones. This should mitigate the risks of remittances not reaching families. Regular monitoring of migrants and their families should also help to manage this risk.

Risk to climate change and environment due to project objectives

Increased pressure on natural resources: If migration continues to increase there is likely to be an increased burden on natural resources (energy for transport, impact in urban areas on water, food etc) in the long term. However, since this programme is not promoting migration per se, but merely seeking to ensure it is safe and free of trafficking, this impact risk cannot be attributed to this programme.

Travel undertaken for programme activities may lead to increased carbon emissions. Adequate checks need to be put in place to curtail unnecessary travel.

Positive impacts of programme on climate change and environment

a) Financial security of vulnerable families: the programme seeks to enable women and girls to send regular remittance to their families. This would enhance financial security to families of the migrants living in the vulnerable areas (i.e. areas which are drought/flood prone), and thereby could reduce their vulnerability.
b) Improving working conditions: the environmental health and safety of migrant workers would be improved if they were able to have decent working conditions and safe migration. This would include improved environmental health and hygiene standards such as clean drinking water, sanitation facilities etc.

Option 2: focus on both Domestic Work and the Garment Sector

This option considers the focus on both garment and domestic sectors. Accordingly, in addition to the above risks and positive impacts on the domestic sector, additional points relevant to the garment sector are highlighted below.

Risk to project objectives due to climate change and environment

Vulnerable supply chains in the garment sector: Supply chains (for raw materials e.g. cotton) are subject to the impacts of climate change and environmental degradation. Also producing crops such as cotton for the textile sector may impact livelihoods of rural communities if the land is degraded or if such crops are cultivated at the expense of families' ability to feed themselves. Extreme weather events like floods and droughts may impact sustained supply of raw materials to the industry. This may impact employability of migrant women as they tend to be the first ones to be laid off and would affect their families back home if wages and remittances were lost.

Such events are however, outside the influence of the programme. However, financial literacy, vocational training and empowerment interventions will help build savings and increase the resilience of women, girls and their families to withstand such shocks.

Travel undertaken for programme activities may lead to increased carbon emissions. Adequate checks need to be put in place to curtail unnecessary travel.

Option 3: Do Nothing Counterfactual

In the event this option is chosen, opportunity to address the issue of financial inclusion and financial security would not be addressed. Additionally, opportunity to prevent trafficking of migrant women whose families may be impacted by climate change and environmental disaster may be missed.

Rating

Categorise as: A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.

Option	Climate change and environment risks and impacts, Category (A, B, C, D)	Climate change and environment opportunities, Category (A, B, C, D)
1	C	C
2	C	C
3	C	C

Climate and Environment Assurance Note is attached - Appendix 3.

IV	COMMERCIAL CASE

Why is the proposed funding mechanism / form of arrangement the right one for this intervention, with this development partner?

The proposal is for the International Labour Organisation (ILO) to be DFID's major implementing partner for this programme. The ILO would lead and manage strategic partnerships with other agencies and sub-contracted implementing partners. In addition, the London School of Hygiene and Tropical Medicine will be an additional partner leading the Evaluation and Evidence component of this programme.

The ILO has been chosen for several reasons: it is the only multilateral agency with a tripartite structure and mandate to work equally with governments, employer and worker organisations on labour issues. ILO has existing positive relationships with governments on these issues that have demonstrated proven programming and policy impact. For example, recent consultations with the Government of India and Government of Nepal have secured strong support and a willingness to lead efforts nationally and regionally to tackle migration-related forced labour.

The relevant ILO Convention 29 on Forced Labour that addresses labour-related trafficking has been in place since 1930. It is one of eight Core Labour Conventions and is binding for all ILO member states – including India, Bangladesh and Nepal as well as countries in the Middle East and Gulf States.

For the past eleven years, the Special Action Programme to Combat Forced Labour (SAP-FL) has managed over fifty programmes and has built a strong reputation for its technical expertise, partnerships and results in building capacity and prosecuting cases of forced labour and trafficking. It has created a ‘Global Alliance against Forced Labour’ to provide a convening space for key labour market institutions to effectively address forced labour, and involves, inter alia, strategic partnerships with the International Trade Union Confederation (ITUC) and International Organization of Employers (IOE).

The ILO is uniquely placed also to address forced labour in domestic work. The International Labour Conference in 2011 adopted by consensus the ILO Domestic Workers Convention (No. 189) represents a new international standard for decent work and legal protection of domestic workers. There is now strong momentum behind ratification of this Convention and this programme will ‘piggy-back’ on these efforts, bringing a stronger focus on the specific vulnerabilities that migrant domestic workers face.

The ILO also has a comparative advantage in addressing the child labour element of the programme through years of experience generated its International Programme on the Elimination of Child Labour (IPEC). IPEC provides technical assistance to countries with the goal of eliminating the worst forms of child labor by 2016, including trafficking of children/young women. It is the largest single programme that focuses on the elimination of child labor world-wide, having worked in more than 90 countries over the past 20 years, working with all levels of government, employers’ and workers’ organizations, international and local NGOs, education providers, microfinance institutions and universities. Since 2004 alone, IPEC’s work has directly led to the withdrawal or prevention of over 1.1 million children in or at risk of child labor and indirectly benefited over 80 million children worldwide.

ILO’s partnership with the IFC in the Better Work Programme has demonstrated success in improving working conditions in the textile manufacturing in a number of countries, including Jordan, where many Bangladeshi woman migrants work. The partnerships, impact assessments and lessons of Better Work Jordan will be used in this programme. Recent impact assessments found that evidence that skills shortages are a constraint to labour compliance, factories that have good quality training are more productive, and retention of staff is likely to be greater.

The potential benefits of working with the ILO in the Ready Made Garment sector have already been recognised by DFID through its funding of the Better Work feasibility study for Bangladesh through the IFC. This work will complement the DFID Responsible and Accountable Garment Sector (RAGS) initiative, building skills and productivity gains to improve trade opportunities and reduce the incidence of labour unrest and strikes.

It is proposed that DFID engage the ILO through a Memorandum of Understanding (MoU). DFID uses this model with the ILO for its funding of its programmes elsewhere in the world. In the absence of a framework agreement in place between DFID and the ILO, an MoU is the most appropriate funding mechanism as it is not legally binding and provides flexibility should any amendments be necessary at any stage of DFID’s commitment. Using an MoU provides less risk for both DFID and the ILO than entering into a complex legally binding relationship. DFID has worked successfully with the ILO for the pilot phase of the trafficking programme using the same funding mechanism.

DFID’s Multi-lateral Aid Review (MAR) highlighted a number of concerns with the ILO both in terms of its contribution to UK development objectives and as an effective organisation. This review was primarily based on the management of DFID’s core contributions (rather than providing specific programme support that this Business Case proposes) but nevertheless these findings were carefully considered in the process of selecting the ILO as a potential implementing partner for this programme, as follows.

Noting some of the key negative points raised, the MAR found the ILO not critical in efforts to meet the MDGs. This is not the case in the context of the proposed trafficking programme since decent work is one of the indicators of MDG 1. The programme will also support MDG 3 by mainstreaming gender concerns through the promotion of equality of opportunity in access to jobs, income earning activities, assets, education and training, the promotion of social dialogue and the promotion and realisation of rights at work. The programme will also contribute to the achievement of MDG 4 by promoting workplace education, good working conditions and safety and health standards and the elimination of child labour. In addition to MDGs 1, 3 and 4 the programme will also contribute to MDG 8 by promoting decent work as a goal in fair globalisation.

Internal processes and cost controls were also highlighted as being weak within the organisation. The ILO has taken the MAR extremely seriously and has put in place systems to address these concerns. We have discussed DFID's concerns in detail with the ILO, and are satisfied that a well-defined process of audit exists with regular reporting to governments and oversight bodies. The Asia Regional Team has consulted closely with UNCD on the implications of the MAR for funding this programme. We have received assurance that supporting the ILO for this programme is fully in line with DFID’s assurance to the ILO that we will continue to support specific programmes as and where the ILO has a proven track record and demonstrated compliance with DFID’s institutional and delivery requirements.

Effective financial systems are present with satisfactory levels of cost control in place, transparent cost effective procurement processes are used which offer value for money through competitive competition. The Asia Regional Team has engaged FCPD from early stages and throughout the design of this programme, and has received assurance that the ILO’s financial, administration, management proposals fully meet DFID’s expectations.

The other criticisms raised through the MAR process are not directly relevant to this programme and are assessed not to be a cause for concern in the implementation and management of this programme.

Implementing partnership arrangements:

Three procurement arrangements will be used for different types of partnerships:

        Implementation agreements
Partnerships with international implementing partners will likely be formalized through implementation agreements. In accordance with the Office Procedure, Implementation Agreements, IGDS No. 270 (version 1) of 6 March 2012, the ILO may enter into a written agreement (Implementation Agreement) with a legally recognized non-profit making entity (e.g., NGO’s, educational and research institutions), an international organisation, and a constituent of the ILO and/or an affiliated member of such a constituent. These agreements provide for the delivery of services as an integral part of ILO technical cooperation programmes and projects, irrespective of the source of funding.

Grant Agreements
A “grant” is a mechanism for providing financial support to a national authority or organization, an international organization or to a legally recognized non-governmental entity. It is made in order to provide support for activities that are directly related to the mandate of the ILO. Grants may be awarded individually or as part of a grant scheme. An individual grant is funded for specific activities or a specific purpose. A grant scheme is a formalised structure for review and awarding of individual grants under a project, with a specific set of technical aims. The award of a grant is based on an agreed amount for which the ILO does not necessarily expect a commercial return or the delivery of a specific service. It is expected the grant modality will be used to formalise agreements with key partners such as UNODC.

        Service Contracts
1. The ILO standard contracting instrument for the purchase of services is a Purchase Order for Services and associated contractual terms and conditions. The method of solicitation the Office would use to seek offers from potential vendors will depend on the nature, complexity and value of the services being sought. Where a single purchase of services is likely to exceed $US 30,000, a formal competitive bidding process is required. Proposals from at least three vendors should be sought through an advertising process which is directed at achieving broad participation from qualified vendors. Where a single purchase of goods or services is valued under $US 30,000, a formal competitive bidding process is not required. For such purchases, an evaluation of quotations received from at least three vendors must be undertaken (informal competitive bidding). It is expected that service contracts will be used to formalise agreements with local implementing partners.
2. It should also be noted that, in exceptional circumstances, a waiver of the procedural requirements in relation to the competitive bidding may be sought. For example, where there is no competitive market able to satisfy the requirement or where the proposed contract is the result of cooperation with other organisations of the United Nations system.

Procurement lead

The Decent Work Technical Support Team for South Asia and Country Office for India (DWT/CO-New Delhi) based in New Delhi will provide the bulk of procurement support for the program. The Decent Work Technical Support Team for South Asia provides technical support to ILO constituents in countries in South Asia (Afghanistan, Bangladesh, India, Maldives, Nepal, Pakistan and Sri Lanka including Bhutan which is a non-member country) and has substantial experience in implementing sub-regional projects. Where additional procurement support is needed this will be provided by professional staff in ILO Headquarters and the ILO regional office in Bangkok in accordance with established internal procurement procedures.

London School of Hygiene and Tropical Medicine – Impact Evaluation partner

The London School of Hygiene and Tropical Medicine (LSHTM) will lead and manage two Impact Evaluation studies which will contribute a credible, robust evidence base to work on trafficking prevention (this has not been done before). It will work in partnership with the ILO on baseline surveys and Logframe indicators for the programme overall, with advice from Human Rights Watch for their expertise on trafficking and human rights in Asia – in a no-cost contribution arrangement.

The Gender Violence and Health Centre at LSHTM is a multi-disciplinary, cross-departmental research group. It is a global leader in research on gender-based violence and health, with specific expertise on trafficking in women. Working with local partners in a range of developing countries and extensive engagement with DFID on health issues globally, the LSHTM undertakes rigorous, inter-disciplinary impact evaluations and develops robust evidence on the extent, cause and consequences of various forms of gender-based violence. It uses, for example, cluster-randomised control trials to evaluate social interventions to prevent violence. It has a proven track record on providing gold standard intervention evaluation approaches and tools, and policy-oriented evidence. It operates with a network of experts in the field, and is currently evaluating DFID-funded domestic violence interventions in Bihar by the Population Council and GVHC, and is the lead Monitoring and Evaluation partner for the Asia Regional ‘Preventing Maternal Deaths from Unwanted Pregnancy’ programme.

Value for Money through procurement

As the management agent for the Asia Regional Human Trafficking Programme the ILO would be responsible for procuring a range of implementation partners and managing those on behalf of DFID.

The ILO operates an efficient and accountable procurement model covering both goods and services. All procurement is undertaken in accordance with established ILO policies, rules and procedures and under the principles of: best value for money; economy and efficiency to achieve quality and cost effectiveness; fair and open competition, giving all qualified suppliers the opportunity to participate; transparency and accountability in the procurement process. The proposed work will require the procurement of services, largely from non-commercial providers, which the ILO are well equipped to manage through Implementation Agreements and where appropriate commercial/service contracts.

In terms of capacity, the ILO managed nearly 10,000 contracts in 2011 amounting to over $93 million. Procurement personnel at HQ are certified through the Chartered Institute for Purchasing and Supply, UK (CHIPS) and internal training is provided at HQ and in the regions for managers and operation staff. Procurement personnel have their competency levels periodically assessed as part of the staff review process.

ILO’s formal competitive bidding threshold in relation to a single purchase of goods and/or service is $30,000. When this is likely to be exceeded proposals from at least three vendors are considered. Below $30,000 informal competitive bidding is carried out to demonstrate value for money. Contracts in excess of $150,000 are also referred to an internal contracts committee with decisions made by the ILO Treasurer and Financial Controller. In regional and country offices, contracts exceeding $30,000 and up to $150,000 are reviewed by an appointed local contracts committee with funding decisions taken by the relevant regional director. Local contracts above $150,000 are considered by headquarters.

What are the costs, how are they profiled and how will you ensure accurate forecasting?

The total cost of the programme over 5 years is estimated to be £9.75 million. The table below shows the budget broken down by financial year starting in 12/13 and ending financial year 17/18.
ILO Costs	2012/13	2013/14	2014/15	2015/16	2016/17	2017/18
Management costs	35,408	212,448	212,448	212,448	212,448	141,634
Output 1. Women Migrant Workers Empowerment	125,786	1,084,402	84,403	902,013	210,189	84,403
Output 2. Recruitment Agencies Adopt Ethical Practices	283,019	62,893	283,019	283,019	251,572	153,459
Output 3. Decent Working conditions and rights	144,654	157,233	188,679	220,126	188,679	89,308
Output 4. Laws, Policies and Enforcement	323,271	94,340	157,233	157,233	314,465	62,893
Impact Evaluation and Monitoring	-	12,076	36,228	36,228	36,228	206,542
Programme Support Costs	122,675	231,630	172,839	252,275	186,551	97,960
Total	1,034,813	1,855,022	1,134,849	2,063,342	1,400,132	836,199
ILO Grand Total	8,324,357
LSHTM Costs	2012/13	2013/14	2014/15	2015/16	2016/17	2017/18
Staff management costs		214,914	214,914	214,914	214,914	214,914
Data collection/fieldwork		61,960	61,960	61,960	61,960	61,960
Travel/Site Visits		10,021	10,021	10,021	10,021	10,021
Total		286,895	286,895	286,895	286,895	286,895
LSHTM Grand Total	1,434,475

	2012/13	2013/14	2014/15	2015/16	2016/17	2017/18
Programme total:	1,034,813	2,141,917	1,421,744	2,350,237	1,687,027	1,123,094
Programme Grand Total: 9,758,832

Programme fund allocations for the outer years (13/14-14/15) have yet to be approved by Finance and Corporate Performance Department. On the assumption bids are approved an increase in funding would still be needed to cover all costs in 13/14. Bids for funds were required before the final budget for this programme had been calculated. An increase of £400,000 to the current 13/14 bid would be necessary, managed either within Asia Division or through a bid for contingency funds.

The final three years of the programme fall outside of the current spending review (approximately £5.1m), for which HMT have confirmed additional approval is not needed.

How will it be funded: capital/programme/admin?

The required resources (£9.75m) will come from programme funding. As stated above a small increase against the current resource bid would be required to meet the costs in year two (£400,000).

How will funds be paid out?

DFID will transfer funds to the ILO in instalments upon written request for payment based on an agreed payment schedule (tbc) set out in a Memorandum of Understanding. Payments to the ILO will necessarily be made in advance as ILO financial regulations do not allow any expenditure to occur until funds have been transferred. Payments to LSHTM will also be made in instalments and against agreed milestones in arrears. Payments will be made subject to proof of need and to the DFID lead adviser and programme manager’s satisfaction.

DFID’s green procurement policies will be followed (for details refer to C&E assessment).

What is the assessment of financial risk and fraud?

The risk of fraud is assessed as low for this programme. The ILO will manage most of the funding under this programme and have provided DFID with a good degree of assurance that effective procurement and financial management systems, as detailed in the commercial case, are in place. The ILO will assume the risk and responsibilities of its subcontracting arrangements through its own internal systems. The funding agreement between DFID and the ILO will clearly set out the purposes for which DFID’s funds should be used and regular financial reporting and monitoring of progress against objectives will form part of our agreement to enable any problems to be identified. As part of our agreement with the ILO if at any stage DFID believes that its funds have not been used for the intended purposes, DFID will have the right to terminate the agreement and seek to recover costs.

The OJEU international tendering process through which LSHTM were appointed included the necessary background and due diligence checks - ensuring LSHTM had robust financial management and accounting procedures and the commercial capacity and the capability to administer the programme.

How will expenditure be monitored, reported and accounted for?

Monitoring, reporting and accounting will follow ILO standard procedures. As such, the ILO will be responsible for the execution of activities for each of their respective partnerships. Both the ILO and LSHTM will submit annual audited reports, the format of which will be consistent with their accounting systems and will include progress against logframe indicators. Expenditure statements will be required from both organisations showing funds spent to date prior to the disbursement of funds.

The ILO and LSHTM will provide DFID with annual audit report within six months following the end of each fiscal year.

V	MANAGEMENT CASE

What are the Management Arrangements for implementing the intervention?

The organogram below is the proposed management structure for the programme:

Figure 11: Management structure for the Asia Regional Human Trafficking Programme

The implementation of the programme will largely be managed by the ILO in South Asia. The proposed ILO staffing structure proposes a dedicated Chief Professional Officer based in Delhi, with three national coordinators in India, Nepal and Bangladesh, supported by finance and administration assistants in each office. At HQ level in Geneva, the ILO will have a Programme Manager to act as DFID’s key point of contact for all programme related matters.

DFID is content that Management Costs for this programme are justified and necessary. Aside from relevant staff in Geneva at HQ level, a Regional Programme Manager and three Country Programme Managers with Administration staff will be needed to deliver the programme. The multi-stakeholder comprehensive approach will require strong partnerships with a range of actors – both directly delivering the programme as well as others that complement this work. There are a significant number of workstreams with different cohorts of women migrants, employers, recruiters, NGOs and governments as well as liaison with other donors and key stakeholders already operating in the region.

The DFID programme will not be able to support all elements of intervention along the migration / trafficking chain, but programme staff will need to work closely with others to ensure that we complement and align our work with what is planned or exists already. In so doing, we can identify a role for these stakeholders in contributing to the impact of this programme.

Key international partners working with the ILO in this programme:

United Nations Office on Drugs and Crime (UNODC)
UNODC represented by the Regional Office for South Asia (ROSA), was established to implement the Organisation’s drug programme and crime programme in an integrated manner, addressing the interrelated issues of drug control, crime prevention and international terrorism in the context of sustainable development and human security. UNODC has expertise in area of law enforcement (police, border guards etc.), which is especially critical in the case of reducing trafficking of women and girls for domestic work. Whilst DFID will not support this work directly, the partnership with UNODC will ensure that its own initiatives and programmes contribute to the overall impact of the programme. The collaboration means the project will also benefit from UNODC’s extensive networks, established contacts on the ground, including in India with the Ministry of Women and Children and The Ministry of Home Affairs.

The International Federation of Private Employment Agencies (CIETT)

The recruitment industry has been at the forefront of combating human trafficking and forced labour. CIETT adopted both a Charter of Private Employment Agencies and a CIETT Code of Conduct in November 2006. Many private employment agencies support concrete anti-trafficking initiatives, such as Manpower, FSI Worldwide (Dubai-based) and Second Chance Employment (US-based). The UN Guiding Principles on Human Rights and Business adopted in 2011 by all member states and with agreement from key employer bodies and trade unions sets out a helpful framework of responsibilities to prevent human rights abuses: governments have a duty to 'protect', employers have a responsibility to 'respect' and workers have the ability to seek 'remedy' if their rights are violated. This is in line with OECD and IFC's compliance standards for human rights and business and will be relevant for this partnership.

International Trade Union Confederation (ITUC) and affiliates

ITUC is the main international trade union organisation, representing 175 million workers in 151 countries and territories and has 305 national affiliates. The ITUC, founded in November 2006, groups together the former affiliates of the International Confederation of Free Trade Unions (ICFTU) and the World Confederation of Labour (WCL), along with trade union organisations which had no global affiliation. The international trade union movement has had a historic role in combating forced labour through abolitionist legislation and international law, organising, social dialogue, and direct assistance. Together with the ILO, the ITUC, the Global Union Federations and their affiliates are working to eradicate forced labour once and for all. The ITUC is currently working with affiliates in South and South East Asia on several ambitious to prevent force labour trafficking both within the region and to the Gulf States through legislative reform, enforcement and, importantly and uniquely, organizing migrant workers, and has published a series of manual and tools. Sector-specific activities will be implemented and coordinated through the International Domestic Workers Network (IDWN), Asia Section, and the newly established IndustriaALL.
[note] ITUC, “How to Combat Forced Labour and Trafficking, Best Practices Manual for Trade Unions”, 2010 http://www.ituc-csi.org/IMG/pdf/TU_Guide_Forced_labour_EN.pdf

Figure 12: Key partners working with the ILO

DFID Management

The programme will ultimately be accountable to the DFID Asia Regional Board, consisting of directors and deputy directors from both Asia and West Asia Divisions. The Board currently meets on a quarterly basis to discuss the progress against the Asia Regional Team project portfolio.

The Asia Regional Senior Social Development Adviser will be lead adviser, and has established an internal DFID Working Group that includes country office advisers in India, Bangladesh and Nepal, Results and Evaluation Advisers, the DFID cross-Whitehall lead on trafficking and organised crime, the Asia Regional Team Head, Policy and Partnerships Manager and Programme Manager.

An external Advisory Board will be created on approval, made up of external trafficking experts, donors and key stakeholders to provide independent advice and direction of the programme and will annually assess progress, results and lessons.

A Steering Committee will be convened involving all key implementing partners, and will meet twice a year in the region or virtually to discuss progress, resolve problems, learn lessons and continually build synergy and ensure complementarity of efforts to ensure each part contributes effectively to the outcomes and expected impact of the programme overall.

What are the risks and how will these be managed?

The key risks to successful completion of the intervention are set out within the project logframe, and are captured in the matrix below.

Risk	Impact	Probability	Mitigation
It is difficult to identify an appropriate cohort of beneficiaries for programme interventions – women who have decided to migrate and who risk being trafficked, and girls at risk of trafficking in domestic work	High	Medium	Baseline survey data and adequate time for planning will be critical
Key stakeholders identified are not able to deliver expected outcomes and impacts	High	Medium	Contracts, annual reviews, monitoring and independent mid-term evaluation will enable change of partners if needed
Accurate baseline to measure impact is not developed	Medium	Low	Considerable investment in survey data is planned; some baselines started in pilot phase.
Mobile phone technology does not allow reliable tracking of control and intervention groups	High	Low
Governments of India, Bangladesh and Nepal unwilling to address forced labour in domestic and garment sectors	Medium	Medium-Low	Some interventions do not rely on short-term legal & policy change and evidence base is intended to build political will
Beneficiary organisations unable to deliver high quality training	Medium	Low
Women unable to use destination mobile phone and SIM card	High	Medium	Addressed through pre-departure training
Governments of India, Bangladesh and Nepal not willing to enforce recruitment fee legislation within timespan of programme	Medium	Higher-risk
Political instability in source and destination countries threatens programme interventions	Medium	Medium
Employers and agencies unwilling to enforce ethical recruitment principles or support monitoring arrangements	Medium	Medium
Trade Unions unwilling to cooperate with domestic worker organisations	Low	Low
Financial Services for remitting mobile money from destination to source countries not available to migrant workers	High	Medium	Detailed scoping will be done and private sector interest & investment sought

Risks will be monitored by both DFID and the ILO and will be discussed during regular programme meetings. The Steering committee will be engaged with risk management where appropriate and reported to the Asia Regional Board if key risks cannot be mitigated.

What conditions apply for financial aid only? N/A

How will progress and results be monitored, measured and evaluated?

There are significant challenges in establishing clear baselines for this programme to demonstrate impact. However, a range of strategies for triangulating baseline information using mixed qualitative and quantitative measures will be used.

DFID will conduct annual reviews of the programme to monitor progress against the log-frame milestones. This will include a review of the theory of change, and the log-frame indicators at output level, which will be updated if necessary in response to changes in circumstances as the programme progresses. The indicators and milestones set out in the log-frame have been agreed with the London School of Hygiene and Tropical Medicine, providing oversight of the M&E Framework.

The ILO and DFID will contract independent evaluations at the mid-point (2015) and end point (2018) of the programme. These will use a multi-methods approach including qualitative interviews, rapid assessment surveys and customised monitoring systems to identify how the intervention elements influenced the outcomes. The mid-point evaluation will be focused to provide practical suggestions for improvements to the project design for the remainder of the programme duration. DFID's Evaluation Department will have oversight of the Terms of Reference and will assess the quality of the evaluations. Upon completion, a Project Completion Report for the programme will be completed, in line with current DFID guidance.

DFID has contracted the London School of Hygiene and Tropical Medicine (LSHTM) through an OJEU Competitive Tendering Process to lead two large impact evaluations to build a robust evidence base. These are intended to not only monitor and assess impact of the DFID programme, but to contribute to global knowledge goods on trafficking.

Using a clustered randomised trials (CRT) methodology the impact evaluations will be designed in consultation with the implementation partner (the ILO), independent Monitoring and Evaluation Experts at the LSHTM, and DFID’s Evaluation Department. They will assess impact on reducing the risk of trafficking among women and girls focusing on two interventions:
- Pre-departure information, vocational skills training and financial literacy to build economic independence and self-esteem to mitigate risks of trafficking.
- Use of mobile technology to protect women workers from abusive situations and remit money safely and cheaply.

The LSHTM will conduct a detailed face-to-face baseline interview with women when they first receive the phone. This initial contact will help engage women in the research may help with the collection of further data via the mobile phone. Throughout the duration of the project, the LSHTM will conduct brief phone surveys with each participant at pre-defined intervals to measure outcomes at different points in time and explore trends in the data. This will allow for amendments to be made in the implementation of the programme to increase effectiveness and impact.

A qualitative component will be implemented as part of the Impact Evaluation and process evaluation; the LSHTM will conduct semi-structured interviews pre- and post- financial literacy training to explore participants’ experience of the activities, and whether and how they used training-related knowledge and skills in their migration plans. Rapid assessment surveys will also be conducted to measure change at the community level. In-depth interviews with women and girls who were exposed to the intervention will be used to explore the process of change and understand which aspects of the intervention worked and how.

DFID’s Evaluations Department has been involved in the design of this programme from the start. They are content that the results are evaluable for this programme, and that these Impact Evaluations will contribute significantly to global evidence on trafficking.

Logframe (attached)

APPENDIX 1

Migration and Trafficking Corridors

Corridor 1:	Women workers from Bangladesh, India & Nepal travelling to Lebanon and UAE fordomestic work, from Bangladesh to Jordan and tackling forced labour within India

Nepal: According to Nepal’s most recent census, women migrants comprise 10.8 per cent of the total population of the country, and 68 per cent of migrants are women. The Nepal Migration Year Book 2009 reports that 57 per cent of Nepalese female migrants migrate to the Gulf region. Past and current restrictions on female migration, in particular to the Gulf, have often resulted in large irregular migration flows through India, placing migrants in particularly vulnerable situations.
[note] According to recent estimates by UN DESA (2011)
[note] More recently, the government of Nepal has taken measures to protect migrant workers by enacting the Foreign Employment Regulation 2064 (2008), which created a mechanism for enhanced protection of migrant workers, including through the appointment of labour attachés in the UAE. The government of Nepal also operates emergency safe houses in several countries in the region, including the UAE. Unfortunately none of these efforts have been implemented in Lebanon.

India: The exact number of Indian women in Lebanon and the UAE is difficult to ascertain owing to the large irregular migration flows for domestic work. Unconfirmed sources, however, indicate at least one million, out of the 15 million Indians in the UAE are women and that every year more than 30,000 female workers migrate to UAE (including undocumented migrants). Most workers come from the Indian state of Kerala and the majority depend on agents to facilitate the process and pay them significant sums of money as service charges. The large majority of women are unaware of official emigration requirements and many unwittingly become undocumented or illegal migrants.
[note] Zachariah and Rajan (2009)
[note] ILO Baseline Survey

Bangladesh: Two decades of export-oriented industrialisation in Bangladesh has led to a notable increase in the country’s foreign investment and employment creation, especially for women, in the garment sector. However, this sector is also characterised by low wages, irregular wage payment, and job insecurity.

Bangladesh’s manufacturing garment production operates on some of the lowest labour costs in the world, with the minimum wage for garment workers set at roughly $37 a month. While the minimum wage was lifted in 2010, workers have seen their meagre earnings eroded by double-digit inflation, resulting in widespread protests and violent clashes in factories. Union and NGO reports show that the industry’s mainly female workforce (80%) suffer from various illnesses after starting work, many relating to overwork and uncongenial working conditions. In the absence of workers’ organisations, there is no collective voice for workers and it is difficult for the mainly female and low educated garment workers to improve employment conditions. As a result of these conditions, many female workers in Bangladesh seek employment abroad, either to work in foreign garment factories, such as Jordan or to the Middle East as domestic workers. A total of 30,579 Bangladeshi female workers secured overseas employment in 2011, up by 2,873 or 24.67 per cent from 27,706 in 2010. The growth in women employment recorded highest in Jordan, Lebanon and UAE.

Lebanon: In Lebanon, abuse has been so prevalent in recent years that Ethiopia, the Philippines, Madagascar and Nepal — all major sources of domestic workers for the country — have set bans on their citizens traveling to the country for employment. At present there are an estimated 200,000 domestic workers in the country.

UAE: In the UAE, household staff can outnumber family members. An estimated 150,000 Emirati families employ about 300,000 domestic workers, while about 150,000 expatriate families employ about 150,000. Domestic workers represent between 5 and 10% of the UAE’s 4.6 million population, depending on the source of information.
[note] The Middle East Institute, Viewpoints: Migration and the Gulf (Washington, DC: The Middle East Institute, 2010).

Jordan: During the past few years, Jordan has also been undergoing a period of reform, economic openness and global integration, including rapid growth in the apparel industry. Apparel exports, exceeded $1.1 billion in 2011 representing an increase of almost 8% over 2010. The industry employs approximately 42,000 workers, well over two thirds of whom are migrant workers from South and South-East Asia. The majority of migrant workers originate from India, Sri Lanka, and Bangladesh. Women represent approximately 60% of the labour force. Since Jordan lifted its ban on Bangladeshi migrant workers, 13,903 Bangladeshi female workers have been recruited.
[note] Better Work Jordan: ‘Garment Industry 3rd Compliance Synthesis Report’, 5 March 2012

Corridor 2: Inter-state trafficking in India and from Nepal to India for domestic work

Domestic work absorbs a significant proportion of the workforce in India. According to the Report of the Employment and Unemployment Survey (2009-2010), there are some 10.5 million workers (urban and rural combined) employed in private households classified as maid-servant, watchman, cook, private tutor etc. comprising around 2.7 per cent of employed Indians. The sector has registered a phenomenal growth: between 1999-2000 & 2004-2005 it grew by almost 222 per cent.

While the sector employs a significant number of men as guards, gardeners, cooks and drivers, women make up an overwhelming majority of the workforce in the sector. As per the 2004-2005 National Sample Survey (NSS) data, the sector is among the most prominent in female employment in urban areas (3.05 million of the total of 4.25 million). Even though the sector is dominated by women there is gender-based stratification in paid domestic work, with men occupying better-paying jobs such as cooking and driving, and the low-paying jobs of cleaning, washing and caring left to females.

Demographically, a large number of domestic workers comprise of scheduled caste or ethnic minority communities and a sizable number of domestic workers include children. The socio-economic characteristics of domestic workers reveal that they are largely married women, illiterate or without any formal schooling and mainly in the age group 21-40 years.

Inter-state migrant women account for a majority of domestic workers. Women migrate because of push factors, such as declining agricultural produce and rural livelihood insecurity and pull factors, including an increasing demand for domestic workers in urban areas. This demand is rising because of increasing care needs for an ageing population, more women getting jobs and needing someone to help with family and domestic responsibilities, girls attending school for longer, and few, if any, state-provided services in child care, chronic health or ageing.

Many Nepali women cross the porous border to India for work as domestic workers in search of jobs that are hard to come by at home, and some fleeing political instability and civil unrest. While the exact numbers of this movement is unknown, it is estimated that 10,000-15,000 Nepali women and girls are trafficked to India each year. There is little capacity or resources from national and local government to monitor trafficking.
[note] 8th annual Trafficking in Persons Report of the US State Department

In India, whilst there is a Domestic Workers Act, domestic workers are excluded from most labour legislation such as maternity benefits. Most are underpaid and they have little or no bargaining power. Most don’t receive the minimum wages proscribed by law and women’s wages are lower than men’s in the domestic sector – often less than the minimum wage of 80 rupees per day, both in rural and urban areas.
[note] Such as the Minimum Wages Act 1948, Maternity Benefit Act 1961, Workmen's Compensation Act 1926, Inter State Migrant Workers Act 1976, Payment of Wages Act 1936, Equal Remuneration Act 1976, Employee's State Insurance Act, Employees Provident Fund Act, Payment of Gratuity Act, 1972.
[note] Source: NSS

Corridor 3: Trafficking of girls under 16 in domestic work from the poorest states to richer states in India

Children in South Asia are predominately affected by internal trafficking. Children who are not in school, come from poor families and are employed in low-skilled occupations are especially vulnerable. Studies show these factors are compounded if the children belong to marginalized and excluded groups, such as Dalits, religious or ethnic minorities.

The child labour dimension of this corridor will focus on trafficking of children and specifically young girls from India and Bangladesh’s poorest states. While there is little reliable data on child trafficking for labour, a State Labour Commissioner from Orissa recently stated that around 1.8 million people migrate from Orissa every year but only 50,000 of them are registered. Much of this movement follows conflict or disaster-prone periods when marginalized communities with low savings, few skills and limited mobility become easy prey for traffickers who prefer children as the cheapest, most exploitable source of labour. For example, in 1999 after a severe cyclone in Orissa, there was a marked increase in trafficking, especially of children, since basic needs like shelter and food were non-existent in the affected areas. Bihar’s floods have also contributed to the increase in trafficking.
[note] http://www.deccanherald.com/content/278687/migration-woes-amp-bricked-lives.html

Domestic work is an area which is especially vulnerable to child trafficking. Girls come with other girls from the village, through private recruiting agents, or other organisations to be employed as ‘maids’ in urban households. Girls are often abused physically, psychologically and sexually by employers and agents, tend to work long hours and in conditions similar to bonded labour--isolated and solely dependent on employers. Many employers opt for child domestic workers because they are considered uncomplaining, easily controlled, naïve and more vulnerable. Most children aren’t aware that they are in a forced labour situation and many remain because they have a roof over their head and don’t want to displease their parents nor their employers by returning home. Traffickers rely on these factors of vulnerability to recruit and maintain control over their victims.
APPENDIX 2:

Background legislation and policy context on labour trafficking in Bangladesh, India and Nepal:

Bangladesh
[note] Excerpts from 2011 US State Department Trafficking in Persons Report

Bangladesh is a source and transit country for men, women, and children subjected to forced labour and sex trafficking. A significant share of Bangladesh’s trafficking victims consists of men recruited for work overseas with fraudulent employment offers who are subsequently exploited under conditions of forced labor or debt bondage. Bangladeshi children and adults also are trafficked internally for commercial sexual exploitation, domestic servitude, and forced and bonded labour. Some children are sold into bondage by their parents, while others are induced into labour or commercial sexual exploitation through fraud and physical coercion. Internal trafficking often occurs from poorer, more rural regions, to locations with more commercial activity including Dhaka and Chittagong, the country’s two largest cities. Women and children from Bangladesh are trafficked to India and Pakistan for commercial sexual exploitation or forced labor. Many Rohingya refugees from Burma transit through Bangladesh using unofficial methods, leaving them vulnerable to traffickers inside Bangladesh and in destination countries. In 2010, some Rohingya girls were forced into prostitution.
Bangladeshi men and women migrate willingly to Saudi Arabia, Bahrain, Kuwait, the United Arab Emirates (UAE), Qatar, the Maldives, Iraq, Iran, Lebanon, Malaysia, Singapore, Libya, Europe, and other countries for work, often under legal and contractual terms. Most Bangladeshis who seek overseas employment through legal channels rely on the over 1,000 recruiting agencies belonging to the Bangladesh Association of International Recruiting Agencies (BAIRA). These agencies are legally permitted to charge workers up to $1,235 and place workers in low-skilled jobs typically paying between $100 and $150 per month, but workers are sometimes charged $6,000 or more for these services. Many Bangladeshi migrant labourers are victims of recruitment fraud, including exorbitant recruitment fees often accompanied by fraudulent representation of terms of employment; high recruitment fees increase vulnerability to debt bondage and forced labor among transnational migrant workers. Women typically work as domestic servants; some find themselves in situations of forced labour or debt bondage where they face restrictions on their movements, non-payment of wages, threats, and physical or sexual abuse. Some Bangladeshi women working abroad are subsequently forced into prostitution. Some Bangladeshis have been convicted by foreign governments for their human trafficking crimes abroad. There are reports of an increased number of Bangladeshis transiting through Nepal to obtain Nepalese visas and work permits for employment in the Gulf, and many of them are likely trafficking victims.
Bangladesh does not fully comply with the minimum standards for the elimination of trafficking, and in 2011 was placed on US Trafficking in Persons Tier 2 Watch List for a third consecutive year. However, the Government of Bangladesh demonstrated increased attention to the issue of human trafficking. The government continued to address the sex trafficking of women and children, drafted and submitted a comprehensive anti-trafficking law to the cabinet, and created an inter-agency task force mandated to monitor recruiting agencies and address high recruitment fees.
The complicity in human trafficking crimes of Bangladeshi government officials remains a serious problem, though the government made no discernible efforts to address it. During the year, there were allegations that a Bangladeshi diplomat facilitated human trafficking of Bangladeshi migrants. Several NGOs reported a nexus among members of parliament and corrupt recruiting agencies and village level brokers and indicated that politicians and regional gangs were involved in human trafficking. NGOs and press reports indicate official recruitment agencies in Dhaka have linkages with employers and brokers in destination countries and help facilitate fraudulent recruitment. In addition, some of these employers put their migrant workers in situations of servitude. The Government of Bangladesh did not provide data on investigations, prosecutions, convictions, and sentencing of public employees complicit in human trafficking.
While workers ostensibly have several options to address complaints of labour and recruitment violations and to get compensation, the process most often used – arbitration by Bangladesh Association of International Recruiting Agencies (BAIRA) – did not provide sufficient financial compensation and rarely addressed the illegal activities of some BAIRA-affiliated recruitment agents. Workers are expected to seek resolution for their complaints directly from BAIRA, rather than file cases against the company, by both BAIRA and the Bureau of Manpower Employment and Training. This resolution generally led to cash-payouts much less than the wages they were denied and the recruitment fees paid. If there are “major” disputes, recruitment agencies may lose their licenses. NGOs and news reports alleged instances of officials working at some Bangladeshi embassies abroad were mostly unresponsive to complaints and attempts to seek restitution abroad were rare. Bangladeshi officials noted that embassies in destination countries do not have enough staff to combat labour exploitation.
India
[note] Excerpts from US State Department Trafficking in Person Report 2011
India is a source, destination, and transit country for men, women, and children subjected to forced labor and sex trafficking. The forced labor of millions of its citizens constitutes India’s largest trafficking problem; men, women, and children in debt bondage are forced to work in industries such as brick kilns, rice mills, agriculture, and embroidery factories. A common characteristic of bonded labor is the use of physical and, in many instances, sexual violence – including rape – as coercive tools, in addition to debt, to maintain these victims’ labor. Ninety percent of trafficking in India is internal, and those from India’s most disadvantaged social economic strata including the lowest castes are particularly vulnerable to forced or bonded labour and sex trafficking. Children are also subjected to forced labour as factory workers, domestic servants, beggars, agricultural workers, and, to a lesser extent, in some areas of rural Uttar Pradesh, as carpet weavers.
There are victims of labour trafficking among the hundreds of thousands of Indians who migrate willingly every year to the Middle East and, to a lesser extent, the United States, Europe, and other countries, for work as domestic servants and low-skilled labourers. In some cases, such workers are lured from their communities through fraudulent recruitment, leading them directly to situations of forced labour, including debt bondage; in other cases, high debts incurred to pay recruitment fees leave them vulnerable to exploitation, conditions of involuntary servitude, and physical and sexual abuse by unscrupulous employers in the destination countries. Nationals from Bangladesh and Nepal are trafficked through India for forced labour and commercial sexual exploitation in the Middle East. Some Indians have been investigated and convicted by foreign governments for human trafficking. Over 500 guest workers from India filed a class action lawsuit in a U.S. court alleging that they were held in forced labour in Texas and Mississippi.
The Government of India does not fully comply with the minimum standards for the elimination of trafficking; however, it is making significant efforts to do so. The Ministry of Home Affairs’ launched the government’s “Comprehensive Scheme for Strengthening Law Enforcement Response in India,” which seeks to improve India’s overall law enforcement response to all forms of trafficking, including bonded labor, and established at least 87 new Anti Human Trafficking Units (AHTUs). The government also ratified the 2000 UN TIP Protocol. The government took important law enforcement steps by convicting several bonded labor offenders with sentences between five and 14 years and improved rescue and rehabilitation efforts for bonded laborers. Overall law enforcement efforts against bonded labor, however, remained inadequate, and the complicity of public officials in human trafficking remained a serious problem, which impeded progress.
The government made progress in law enforcement efforts to combat human trafficking in 2010, but concerns remain. India prohibits and punishes most, but not all, forms of human trafficking under a number of laws. The Government of India’s “Comprehensive Scheme for Strengthening Law Enforcement Response in India” saw state governments establishing at least 87 new Anti-Human Trafficking Units (AHTU) in police departments covering 17 of India’s 28 states. These focus more on sex trafficking than the more significant problem of labour trafficking, including bonded labour. Each AHTU is designed to be tailored to local conditions to effectively confront the forms of human trafficking found in the particular district.
The involvement of some public officials in human trafficking, and the pervasiveness of corruption in India, remained significant and largely unaddressed hurdles to greater progress against trafficking. Corrupt law enforcement officers reportedly continued to facilitate the movement of sex trafficking victims and protected suspected traffickers and brothel keepers from the law. Some police continued to tip-off locations of sex and labour trafficking to impede rescue efforts.
India made uneven progress in its efforts to protect victims of human trafficking. Indian law enforcement and immigration officials lack formal procedures for pro-actively identifying victims of trafficking among vulnerable populations, such as children at work sites, females in prostitution, or members from the disadvantaged social economic strata in rural industries. However a number of Indian diplomatic missions in destination countries, especially those in the Middle East, provide services, including temporary shelters, to Indian migrant labourers, some of whom were victims of trafficking.
The Government of India made progress in its efforts to prevent human trafficking. Central and state governments conducted several initiatives to raise awareness about sex trafficking, especially during the run-up to the October Commonwealth Games, but made little progress in increasing awareness about adult forced labour.
The government does not permit women under the age of 30 to emigrate to 17 countries due to the high incidence of physical abuse. Evidence suggests such restrictions on migration do not have a positive effect on preventing human trafficking. The Migrant Resource Centre in Cochin counselled 2,985 potential migrants between January and October 2010, compared to 2,633 in 2009.
Indian embassies in the Middle East house Indian Worker Resource Centres, including a new centre publicly launched by the Indian president in the United Arab Emirates in 2011.

Nepal 87
Nepal is mainly a source country for men, women, and children who are subjected to forced labour and sex trafficking. Some Nepali women and girls are subjected to sex trafficking in Nepal, India, and the Middle East, and also are subjected to forced labour in Nepal and India as domestic servants, beggars, factory workers, mine workers, and in the entertainment industry. They are subjected to sex trafficking and forced labour in other Asian destinations, including Malaysia, Hong Kong, and South Korea. Nepali boys also are exploited in domestic servitude and – in addition to some Indian boys – are subjected to forced labour in Nepal, especially in brick kilns and the embroidered textiles industry.
There is some indication that China is an emerging trafficking hub for Nepali girls in sex work as well as to become brides because women of marriageable age are increasingly scarce due to sex selection practices. There are some reports of traffickers in the remote Karnali region who deceive families into sending their children to urban areas with false promises of schooling. Many of these children, however, are never sent to schools and some end up in forced labour, including forced begging.
Bonded labour is often based on caste lines, where traditional landlord castes use debt bondage to secure unpaid labour from Dalit workers. Traffickers generally target uneducated people, especially from socially marginalized and traditionally excluded groups. However, a growing number of victims are relatively well-educated and from traditionally privileged groups.
Many Nepali migrants seek work in domestic service, construction, or other low-skilled sectors in Gulf countries, Malaysia, Israel, South Korea, Afghanistan, and Libya with the help of Nepal-based labour brokers and manpower agencies. They travel willingly but some subsequently face conditions indicative of forced labour such as withholding of passports, restrictions on movement, non-payment of wages, threats, deprivation of food and sleep, and physical or sexual abuse. Some are deceived about their destination country, the terms of their contract, or are subjected to debt bondage, which can in some cases be facilitated by fraud and high recruitment fees charged by unscrupulous agents.
Many workers migrate via India; this is illegal, due to the 2007 Foreign Employment Act that requires all workers to leave for overseas work via the Kathmandu airport. Many migrants leave by land because it is easier and cheaper than travelling by air, and to avoid legal migration registration requirements, the scrutiny of a labour migration desk in the airport, and bribes that some officials reportedly require at the airport to secure migration documents.
A recent survey of returned migrants served by the NGO Maiti Nepal assessed that 67 percent of female Nepali workers who returned from the Gulf were unhealthy; most disorders were psychological illnesses. Nepali officials have reported a large increase of Bangladeshis transiting through Nepal in recent years due to increasing migration restrictions of Bangladeshis by foreign countries. Officials believe many Bangladeshis illegitimately obtain Nepali visas and work permits for employment in the Gulf, and noted, because these Nepali documents are often produced fraudulently, the Bangladeshis are at risk of being trafficked.
The Government of Nepal does not fully comply with the minimum standards for the elimination of trafficking; however, it is making significant efforts to do so, despite limited resources. During 2011, the government established the Central Crime Investigative Bureau’s special unit to investigate trafficking and increased its direct financial support for protective services in Nepal and abroad. Incidents of trafficking-related complicity by government officials were not documented by the government, but reported by civil society. The lack of proactive victim identification remained a serious problem in Nepal.
The incidence of trafficking-related complicity by government officials is a problem. Anecdotal evidence suggests that traffickers use ties to politicians, business persons, state officials, police, customs officials, and border police to facilitate trafficking. Some Nepali officials may work with traffickers in providing false information in genuine Nepali passports. Politically-connected perpetrators enjoy impunity from punishment. There were no trafficking related investigations, prosecutions, or convictions of government officials for complicity in trafficking during 2011.
Limited protection for victims negatively affected law enforcement efforts. Victims were often intimidated in their communities not to pursue a case, and they did not want to prosecute due to concerns for personal and family safety, particularly as their traffickers may have been family members. Many victims were unaware that legal recourse was available against traffickers. The government did not encourage trafficking victims to participate in investigations against their traffickers. Judges reportedly often took an adversarial, rather than impartial, stance when dealing with trafficking victims.

APPENDIX 3: Climate & Environment Assurance Note

Intervention Details
Title	Home Department		Budget
Asia Regional Trafficking Programme	DFID
Responsible Officers
Title	Name		Department
Project Owner
Climate Change and Environment Advisor	Ritu Bharadwaj / Nidhi Sarin		DFID-India
Appraisal
Success Criteria		Sensitivity Analysis
No separate C&E success criteria were identified		C&E sensitivity analysis was carried out in detail for all options
Climate & Environment Category
Risks & impacts Category C		Opportunities / Category C
Management
Risks and opportunities defined	Climate & Environment Measures agreed		Climate & Environment Measures in log-frame
Describe briefly what are the risk and opportunities that were identified in the BC C&E assurance note / Opportunities / Programme activities seek - to enable women and girls to send regular remittance to increase financial security of vulnerable families. / - to improve working conditions, by promoting improved environmental health and hygiene, clean drinking water and sanitation facilities. / Risk to project objectives due to climate change and environment / - Extreme weather events and other environmental factors may lead to displacement of families of the migrant’s in vulnerable regions risking transfer of remittance / - Extreme weather events like floods and droughts may impact sustained supply of raw materials to the industry. This may impact employability of migrant women as they tend to be the first ones to be laid off. / Risk to climate change and environment due to project objectives / - Travel undertaken for programme activities may lead to increased carbon emissions. / - As an indirect impact, in long term, if migration continues to increase there is likely to be an increased burden on natural resources (e.g. energy for transport, impact in urban areas on water, food).	Describe briefly what actions were decided upon to mitigate any environmental impacts / - The programme plans to provide financial literacy training, help families set up bank accounts and remit money through mobile phones. This should mitigate the risks of remittances not reaching families and increase resilience of women, girls and their families to withstand shocks. / - Adequate checks need to be put in place to curtail unnecessary travel undertaken by project teams.		Answer whether any actions were included in the logframe to mitigate C&E impact or maximise opportunities and, if yes, describe what these are / Yes. Following actions are included in the log frame / - empowering women migrants by providing pre migration training on climate resilient livelihood options / - Revision in laws and policies of private employment agencies to be monitored to assess the impact in terms of improved environmental health, sanitation and hygiene to ensure that recruitment agencies follow ethical practices / - Baseline and endline surveys with employers on rights and obligations to include environmental health, sanitation and hygiene to ensure decent working conditions with protection of rights for women migrant workers.

Evidence
Relevant documents
Foresight Report: Migration and Global Environmental Change, 2011 / The social and decent work dimensions of a new Agreement on Climate Change, Technical Brief, Ana Belén Sanchez and Peter Poschen, International Labour Office, 2012

SIGNED OFF BY:	Ritu Bharadwaj

DATE:	30 November 2012