## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
Development and Implementation of a Education Minimum Services Package (MSP) for Mental Health and Psychosocial Support (MHPSS) in Humanitarian Settings
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
Girls and boys affected by crisis have improved MHPSS wellbeing, learning capacity and learning outcomes. | % of improvement in subjective wellbeing of girls, boys, women and men benefiting from MHPSS services implemented through MSP-recommended activities | Planned |  |  |  | Will not be measured during the implementation of the project
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| % of improvement in learning capacity and outcomes among girls and boys benefiting from MHPSS services implemented through MSP-recommended activities | Planned |  |  |  | Will not be measured during the implementation of the project
Achieved
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| % of improvement in reach of girls, boys, women and men who receive care for mental health problems. | Planned |  |  |  | Will not be measured during the implementation of the project
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022) | Assumptions
Girls and boys, women and men in humanitarian contexts receive effective prevention and response services/support to MHPSS problems through education response in emergencies. | Number of girls, boys, women and men who receive care for mental health problems in demonstration sites | Planned | Number of girls, boys, women and men who receive care for mental health problems in demonstration sites | TBD after demonstration sites identified | TBD after baseline is collected | To be determined based on Milestone 2 | • Organizations will be identified who are willing and able to demonstrate use of the MSP for program development and/or implementation in humanitarian settings and provide feedback
Achieved
Source
(1) Implementing partner records, attendance and participation forms (2) Site implementation quarterly activity reports with disaggregated (gender, age, locations) of individuals reached with MHPSS activities
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022) | Assumptions
Humanitarian actors have access to a MHPSS Minimum Services Package (MSP) that enables improved MHPSS programmes in education response in emergencies. | One Education Minimum Services Package for MHPSS developed and costed | Planned | 0 | 1 Structure and content of the education chapter developed in consultation with project advisory group, and peer review groups, and in alignment with health and child protection components of the MSP. | 1 Education chapter for MHPSS in MSP completed and ready for demonstration and field testing. | 1 Minimum services packaged for Education; each with an accurately costed value of budget required for population reach | • Members of the Advisory group and other relevant stakeholders involved in the development and demonstration of the MSP will collaborate and render support by providing input and feedback as well as helping dissemination. • Inter-agency and cross-sectoral ownership and collaboration with humanitarian agencies, coordination bodies, and platforms across sectors- maintained through ongoing consultations and 2-way dialogue. • A suitable and sustainable hosting site for the MSP will be identified • Additional resources will be identified in the future to make updates to the MSP (e.g. newly available tools, resources, or evidence based interventions)
Achieved
Source
(1) Project reports providing progress updates (2) Demonstration sites supported to track implementation spending to confirm package costings (3) Documented methodology for costing calculations (Education chapter contributing to a final report with methodology for costing)
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
50% | % of EiE networks that demonstrate committment to strengthened integration of MHPSS through the processess of development and implementation of the MSP for evenutal uptake. (Such as IASC MHPSS Reference Group, the Inter-Agency Network for Education in Emergencies (INEE) and Education in Emergencies cluster) | Planned | 0 | >20% Note: member organisations of IASC MHPSS Reference Group engaged through consultations for MSP demonstration and official endorsement acquired: 1st following the completiion of content development, and 2nd following the completion of field testing. | > 50% member organisations of IASC MHPSS Reference Group demonstrate commitment to strengthened integration of MHPSS through endorsement of the MSP for MHPSS. | Final publication of the MSP to include acknowledgement of endorsing organisations/ groups with >75% member organisations of IASC MHPSS Reference Group demonstrate commitment to strengthened integration of MHPSS through endorsement of the MSP for MHPSS.
Achieved
Source
(1) consultation meeting attendance. (2) Depending on type of product (IASC product, UN product), endorsement will be reflected and approved in the acknowledgements for content development, field testing & use, in the final publication. 3) recommending trainers for the ToT, 4) Feedback given to the MSP tools and final products
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022) | Assumptions
Education responses in countries affected by crisis demonstrate improved integration of MHPSS | Number of MSP Master Trainers (core group) trained from multiple humanitarian clusters (education, IASC MHPSS Reference Group) in multiple regions | Planned | 0 | 0 Member organisations of IASC MHPSS Reference Group and CP, Education and INEE groups and clusters engaged through consultations for MSP development and selection of trainees for MSP Master Training. | 15 MSP Master Trainers (core group) trained from multiple humanitarian clusters (education, IASC MHPSS Reference Group) in multiple regions | Minimum of 30 MSP Master Trainers (core group) trained from multiple humanitarian clusters (education, IASC MHPSS Reference Group) in multiple regions | • Organizations will be identified who are willing and able to demonstrate use of the MSP for program development and/or implementation in humanitarian settings and provide feedback through a monitoring and evaluation framework. • MSP implementation by partners/organizations are successful in ensuring communities are consulted and involved in the identification of problems and solutions, to allow communities to take full ownership of projects from the outset.
Achieved
Source
(1) Training reports, Trainee knowledge assessments, Trainee assessments of training programme (2) Data collected during and post training activities
| Output Indicator 2.2 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| % of MSP Master Trainers (core group) trained who have reported satisfaction with the training, demonstrate enhanced skills and knowledge, and report that they feel capable to use in their jobs. | Planned | 0 | 0 Member organisations of IASC MHPSS Reference Group and CP, Education and INEE groups and clusters engaged through consultations for MSP development and selection of trainees for MSP Master Training. | 80% MSP Master Trainers (core group) trained who have reported satisfaction with the training, demonstrate enhanced skills and knowledge, and report that they feel capable to use in their jobs. | 80% MSP Master Trainers (core group) trained who have reported satisfaction with the training, demonstrate enhanced skills and knowledge, and report that they feel capable to use in their jobs.
Achieved
Source
(1) Training reports, Trainee knowledge assessments, Trainee assessments of training programme (2) Data collected during and post training activities
| Output Indicator 2.3 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| Number of MSP Master Trainers in established sectoral surge capacity mechanisms (e.g., for MHPSS in education) | Planned | 0 | 0 | 0 Member organisations of IASC MHPSS Reference Group and CP, Education and INEE groups and clusters engaged through consultations for MSP development and selection of trainees for MHPSS sectoral surge capacity | Minimum of 15 MSP Master Trainers recognized in established sectoral surge capacity
Achieved
Source
(1) Training reports, Trainee knowledge assessments, Trainee assessments of training programme (2) Data collected during and post training activities
| Output Indicator 2.4 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| Number of field implementers per implementation site trained in MSP by Master Trainers | Planned | 0 | 0 - Implementation not yet commenced. | 0 - Implementation not yet commenced. | Minimum of 10 field implementers per implementation site trained in MSP by Master Trainers
Achieved
Source
(1) Training reports, Trainee knowledge assessments, Trainee assessments of training programme (2) Data collected during and post training activities
| Output Indicator 2.5 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| % of field implementers per implementation site trained in MSP by Master Trainers who have reported satisfaction with the training, demonstrate enhanced skills and knowledge, and report that they feel capable to use in their jobs. | Planned | 0 | 0 - Implementation not yet commenced. | 0 - Implementation not yet commenced. | 80% of field implementers per implementation site trained in MSP by Master Trainers who have reported satisfaction with the training, demonstrate enhanced skills and knowledge, and report that they feel capable to use in their jobs.
Achieved
Source
(1) Training reports, Trainee knowledge assessments, Trainee assessments of training programme (2) Data collected during and post training activities
| Output Indicator 2.6 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
| Number of country MSP implementation learning reports with recommendations for future implementation disseminated to humanitarian response stakeholders (up to 5 countries, only one funded through this grant) | Planned | 0 | 0 - Methods of M&E and reporting developed | 0 - Ongoing monitoring and evaluation at each demonstration site. | Minimum of 5 country MSP implementation learning reports with recommendations for future implementation disseminated to humanitarian response stakeholders
Achieved
Source
Implementation science methodologies. Full methodology to be completed based on consultation and consensus about key information to be extracted from the learning reports.
IMPACT WEIGHTING (%) | Output Indicator 2.7 |  | Baseline | Milestone 1 (August 2020) | Milestone 2 (August 2021) | Milestone 3 & Target (Aug 2022)
50% | % of improvement of integration of MHPSS in education sector | Planned | To be measured at each demonstration site (not yet identified) | To be determined after collection of baseline. | To be determined after collection of baseline." | Minimum 50% improved integration of MHPSS in programming where Education Chapter for MHPSS is used
Achieved
Source
(1) A measure, or checklist of integration to be established (2) Based on assessments of education sector responses in demonstration country sites
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.