Annual Review – post April 2018

Title: Modern Slavery – Supporting Global Action to End Modern Slavery
Programme Value £ (full life): £22.2m (includes funding for the Independent MEL Unit)		Review Date: December 2019
Programme Code: 300466	Start Date: September 2018 (with varied start dates for implementing sub-partners)	End Date: March 2022

Summary of Programme Performance
Year	2019
Programme Score	A
Risk Rating	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/38904967.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/49574918.xlsx

A. Summary and Overview

The UK, through DFID, is providing direct support of up to £20m to the Global Fund to End Modern Slavery (GFEMS) from 2018 – 2022 (across FY 18/19, 19/20, 20/21 and 21/22 financial years) to develop new and innovative approaches to reducing the prevalence of modern slavery and human trafficking (MSHT) in three sectors (apparel/garments; commercial sexual exploitation; and overseas labour migration) in communities in South Asia. DFID has also set aside up to £2.2 million for technical support to ensure robust independent Monitoring, Evaluation and Learning (MEL) and social development expertise.
The programme spent £1,715,639.20 during the period of this Annual Review (AR).

Global Fund to End Modern Slavery Programme

The Global Fund to End Modern Slavery (GFEMS) is an Non-Governmental Organisation (NGO) whose mission is to work with governments, the private sector and civil society to develop and coordinate a global strategy informed by rigorous measurement, owned by countries, and at the scale needed to permanently dismantle slavery systems - addressing the structural gaps which help create and maintain the environment in which modern slavery thrives. GFEMS is focused on delivering under the following interconnected themes:

1. Effective Rule of law: Tackling impunity with effective criminalization and judicial punishment for all forms of trafficking; (NB DFID’s grant will not be used for rule of law projects).
2. Business engagement: eliminating forced labor from supply chains at local, national, and international levels; and
3. Sustained freedom: Ensuring survivor freedom is sustained through recovery, reintegration and economic opportunity

GFEMS’ vision and approach is well-aligned with the UK’s, but since they aim to trial new techniques less familiar to the anti-slavery sector or the development community, GFEMS added value is in what it can potentially provide by way of new, innovative, and valuable perspectives on what works to tackle modern slavery (and to do so in what remains to date an evidence-light environment).

The DFID GFEMS Programme is focused on increasing the global evidence and resource base and working with new partners to design, test, and improve effective practice in tackling modern slavery and human-trafficking, specifically in India and Bangladesh. By the end of the programme in 2021/22, we expect to see the following four outcomes:

Improving the Evidence Base
1. Key actors have an improved understanding of the scale and prevalence of modern slavery and global knowledge gaps are reduced;
2. Increased evidence and learning on the drivers of modern slavery and learning from the pilots is available and used by key actors to design MS interventions;
Testing and scaling impactful interventions
Key beneficiary vulnerabilities (at individual or community level) that enable modern slavery are reduced in targeted communities and sectors;
Leveraging innovation
GFEMS harnesses and captures innovative ways of working to reduce modern slavery and shares with key actors; innovation shapes future investment strategies.
The further expectation is that this investment, if successful, will act as a catalyst and multiplier by attracting other governmental donors, the private sector, and the broader development community to invest in the Fund as a mechanism through which to help address modern slavery and human trafficking.

This is the first Annual Review of the GFEMS Programme. It covers the inception/design phase of the programme (September 2018-September 2019) during which time the relevant actions and measures where undertaken to place the programme on the right footing to deliver during the subsequent implementation phase. As the majority of the programmes expected results are due to be achieved during the implementation phase from 2020-2022, performance indicators for the period under review are therefore principally focused on the quality of the Design Phase Outputs (DPOs) and an assessment of the key programme management activities that form part of the inception/design phase.

Summary

The outputs set for the first year of the programme have all been met. Despite significant early challenges experienced by GFEMS in respect of establishing effective operational processes for financial and risk management, GFEMS has performed adequately and is now on track to move into full implementation phase.

Forced labour, modern slavery, and human trafficking remain sensitive issues with national governments in both target countries. There have been challenges related to the design of innovative interventions in this context with a novice organisation. Going forward, DFID will be monitoring the following challenges in particular:

Delivery partners’ ability to secure permission to operate in-country in time for proposed interventions to remain viable.

Financial and risk management processes continue to evolve as the scale and scope of the programme increases into the implementation phase.

Ensuring longer term financial sustainability. Despite GFEMS successfully securing support from Norway of up to 100 million NOK (approx. £9.1m in December 2018), longer term financial stability remains a concern. GFEMS continues to engage a range of other potential donors to the Fund, both bilateral and private.

Proportionate use of DFID staff time. Recognising the potential value of the programme to the Modern Slavery sector as a whole, DFID has invested more staff time during this phase of the programme than would normally be proportionate for a programme of this size

Recommendations for the year ahead

We encourage GFEMS to step up its resource mobilisation efforts to broaden and diversify its donor base and accelerate progress towards its strategic ambition to become a multi-donor, pooled fund. As part of this, GFEMS should produce a specific resource mobilisation strategy by 31 March 2020 and regularly review progress against it.

During the second year of the programme, GFEMS must focus on continuing to strengthen its financial management. DFID will require GFEMS to ensure expenditure against agreed budgets does not vary by more than 5% for each quarter during the life of the programme, starting from 01 April 2020.

GFEMS should revise its risk register clearly outlining the relationship between risks at all levels from project partner to higher level strategic risks. The revised risk register should be submitted to DFID by 31 March 2020 and reported against quarterly.

Based on a fuller understanding of delivery partner objectives and projects following the call for proposals, a revised Value for Money (VfM) framework based on DFID’s VfM guidance, should be submitted to DFID by 31 March 2020 and reported against quarterly. The VfM framework should be based on DFID’s VfM guidance.

Based on a fuller understanding of delivery partner objectives and projects, the theory of change and logical framework (logframe) should be revised and agreed by DFID by 31 March 2020 and reported against on a quarterly basis.

## B: DETAILED OUTPUT SCORING

The outputs relating to the period under review were:

Output Title	New/improved tools and methodologies to assess scale and prevalence of modern slavery at sector level created and shared
Output number per LF		1.1	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1.1: Number of sector/geography baseline and end-line prevalence reports and associated data produced and shared with key actors	DPO1 (Interim findings, lessons and challenges / on validity of new methodologies) - GFEMS to conduct pilot prevalence studies (in at least 2 targeted sectors) during the Inception Phase - testing and validating measurement methodologies and providing baseline data to inform sector-level theories of change.	Achieved. GFEMS conducted an internal review of prevalence pilots, produced interim findings (and reported on these in the Design Phase report submitted to the Programme Steering Committee (PSC) in April 2019.
1.1.2: Number of reports on new approaches and methodologies to measure prevalence and scale of modern slavery produced and shared with key actors	DPO1 (Interim findings, lessons and challenges on validity of new methodologies)	Achieved.

Output Title	Strengthened analysis identifies the structural drivers of modern slavery & learning from interventions is published through evaluations for use by key actors
Output number per LF		2.1	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1.1: Mid-term (1.5 years) and post-intervention (3years) analyses identifying key structural drivers of modern slavery in targeted contexts produced and shared with key actors	DPO2 (Influence strategy: key stakeholders, channels and formats for dissemination)	Achieved. GFEMS commissioned an Influence Strategy study to research and / analyse stakeholder archetypes in the global modern slavery community. They used this analysis to produce an Influence Strategy Guidebook that defines main players in the field, outlines their expectations around actionable research findings, and details a strategy to reach them.
	DPO3 (Baseline analysis of structural drivers in targeted sectors and priority intervention areas to reduce them) – GFEMS to commission studies to identify structural drivers of modern slavery in at least three targeted sectors and identify priority intervention areas to reduce them.	Achieved. GFEMS commissioned 3 Driver Analysis and Strategic Review studies – incl. analysis of drivers of modern slavery and interventions to reduce them.
	DPO4 (Stakeholder maps of targeted sectors that cover key actors in government, private sector and civil society and will/capability to address structural drivers) – GFEMS to identify key relevant actors in government, the private sector, civil society representing the most vulnerable; identify their willingness and/or capability to respond to existing structural drivers of modern slavery; and develop a stakeholder map.	Achieved. GFEMS produced stakeholder Maps (contained in the Driver Analysis and Strategic Review studies). GFEMS also commissioned 4 Industry and Competitive Analysis studies, which touched on / key stakeholders.

Output Title	Strengthened analysis identifies the drivers of key individual and community vulnerabilities & learning from interventions is published through evaluations for use by key actors
Output number per LF		2.2	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.2.1: Mid- (1.5 years) and post- (3years) analyses identifying key individual/community vulnerabilities to modern slavery in targeted contexts and mechanisms to reduce them produced and shared with key actors	DPO2 (Influence strategy: key stakeholders, channels and formats for dissemination)	Achieved.
	DPO4 (Stakeholder maps of targeted sectors that cover key actors in government, private sector and civil society and will/capability to address structural drivers)	Achieved.
	DPO5 (Sophisticated, precise targeting of beneficiaries most vulnerable to slavery in targeted communities) – GFEMS to provide: / a) detailed analysis of those most vulnerable to slavery; b) develop a beneficiary targeting strategy; and c) produce an inclusion strategy that sets out how GFEMS will ensure interventions are inclusive.	GFEMS commissioned 5 Beneficiary Vulnerability Analysis and Engagement studies in the 3 targeted sectors (apparel, / overseas labour recruitment, and commercial sexual exploitation (CSE)) and across the 2 targeted geographies.

Output Title	Beneficiary vulnerabilities effectively identified and reduced through GFEMS projects/investments.
Output number per LF		3.2	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.2.1: Number of beneficiaries (individuals) most vulnerable to slavery directly benefitting from the programme; disaggregated by gender, age, disability status and geography	DPO5 (see above) & DPO6 (Baseline analysis of priority / interventions to address targeted / individual, community vulnerabilities)	DPO5 & DPO6 - completed
3.2.2: Number of total beneficiaries (individuals), including beneficiaries most vulnerable to slavery, directly benefitting from the programme; disaggregated by gender, age, disability status and geography	DPO5 (see above) & DPO6 (Baseline analysis of priority / interventions to address targeted / individual, community vulnerabilities)	DPO5 & DPO6 - completed

Output Title	Innovative tools, models and approaches for reducing MS piloted, tested, evaluated, learnings are shared in case studies etc.
Output number per LF		4.1	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1.1: Number of innovative tools, models and approaches for reducing modern slavery (i) piloted/tested, (ii) evaluated	DPO7 (Innovative tools, approaches and models identified for testing/scaling (and corresponding partners) to reduce modern slavery drivers/ vulnerabilities) – GFEMS to identify (new and existing) innovative tools, approaches and models that could be piloted to reduce drivers of, and/or vulnerabilities to, modern slavery in target sectors. Also identify potential partners for project pilots.	DPO7 – achieved. GFEMS used the Driver Analysis and Strategic Review studies and 4 Industry and Competitive / Analysis studies to supplement its own analysis of potential innovations and determined appropriate funding mechanisms. Submitted findings as part of Design Phase Report.
	DPO8 (Proposed funding mechanisms identified (for the innovations to be tested/scaled) and linked to type of idea/partner, and partner capacity) – GFEMS to determine the most appropriate mechanisms to fund these innovations, and what steps are needed to establish them.	DPO8 – achieved. GFEMS produced analysis of potential innovations and determined appropriate funding mechanisms given the nature of partners and innovation projects identified. Submitted findings as part of Design Phase Report

Final Score: A - Outputs met expectation

Key Achievements:

The above output indicators provide a representative summary for the purposes of scoring the programme. The following section elaborates on other key achievements.

GFEMS successfully completed the Design Phase (extended from the original 6 to 9 months). The Design Phase focused on identifying innovative interventions and future research priorities. GFEMS conducted field research and commissioned twelve studies covering drivers of modern slavery, industry dynamics, and beneficiary vulnerability in these sectors. GFEMS developed plans for prevalence measurement; monitoring, evaluation and learning (including a MEL Strategy); gathering survivor/beneficiary feedback; disseminating knowledge; and processes for funding small innovation grants.

GFEMS worked to refine outputs and align programming priorities with the scope as required by DFID (guided closely by the Programme Team) – resulting in a revised sector-level theories of change (DPO9) and a revised logframe. The outputs were used to inform the programming and concept note solicitation for India and Bangladesh (issued in July 2019).

Successful concept note solicitation

In July 2019, GFEMS issued a request for concept notes (sent to nearly 2,000 stakeholders) covering 14 specific intervention or innovation opportunities for funding. The Fund received 122 eligible concept notes that were put through review, based on the six evaluation criteria defined in the July 2019 Request for Concept Notes. GFEMS conducted eligibility screening, and then a two-stage review in order to shortlist proposals and enter into a 6-week co-creation with applicants. Co-creation phase took place in October and November.

Expansion of the Research Methods and Advisory Panel

GFEMS expanded the Research Methods Advisory Panel (RMAP). The RMAP is the expert advisory group which will be responsible for quality assurance of GFEMS methodologies to improve key actors’ understanding of the scale and prevalence of modern slavery and reduce global knowledge gaps. The now 7-person panel consists of experts in the field of modern slavery who work on research and evaluation. RMAP members have diverse experience and backgrounds working for international NGOs, multilateral institutions, universities, and government institutions. GFEMS consults with, and seeks to gain consensus from, the RMAP before undertaking any prevalence measurement activity.

Prevalence Estimation Partner

GFEMS submission of their lessons learned report on prevalence estimation to date and has since then successfully contracted NORC at the University of Chicago as primary partner to implement the prevalence estimation studies under this programme.

Monitoring, Evaluation, and Learning Data Collection Partner

GFEMS launch a competitive process for identifying an external partner to complete targeted data collection and analysis, as well as support evaluation efforts across all future DFID-funded projects. The request for proposals (RFP) was issued in July 2019.

Adaptive Management and Community Feedback Mechanisms

From April-September 2019 GFEMS finalised the operational guide for MEL planning. The guide includes activities for assessing partner MEL capacity, reviewing available evidence, and developing a project theory of change, logframe, and learning agenda. The guide incorporates feedback from GLAM and includes an adaptive management module. The adaptive management module also integrated feedback from the Independent MEL Unit’s adaptive management specialists. Additionally, GFEMS developed introductory session content on Community Feedback Mechanisms (CFM) for use in co-creation workshops to complement the CFM Guidance document. The guidance will be used during co-creation and will inform programme design.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Programme Theory of Change

The Fund’s ultimate objective is to reduce the relative and absolute prevalence of modern slavery. The theory of change (TOC) for this programme is set out below and is based on the assumption that improved prevalence data + improved evidence on drivers + reductions in individual/community vulnerabilities + innovation will result in a reduction in modern slavery prevalence in targeted sectors and communities:

There have been no major changes to the programme’s Theory of Change (ToC) in the period under review. Minor amendments to the Theory of Change were made in June 2019 by GFEMS and approved by DFID in July 2019. A revised theory of change will be included and reviewed as part of the next annual review.

The independent Monitoring, Evaluation and Learning (MEL) unit will also work closely with GFEMS to advise, where appropriate, on revisions to the ToC as the programme now moves into implementation phase.

Recommendations:
The theory of change and logical framework (logframe) should be revised and agreed by DFID by 31 March 2020 and reported against on a quarterly basis.
## D: VALUE FOR MONEY

The Business Case identified the indicators which would be used to assess the Value for Money of this programme while noting that these would be subject to revision at the end of the inception phase. They are summarised as follows in the table below:

Value for Money Indicators

Measure	Indicator	Source	Purpose
Economy	GFEMS’ staff salaries and long-term consultant day rates	GFEMS’ Budget	Benchmark key costs to other institutions.
Economy	Implementation partner’s salaries and day rates	GFEMS	Benchmark key costs to other institutions.
Economy	DFID share of GFEMS’ staff salaries, consultant day rates, and operational costs	GFEMS	Ensure DFID’s share of GFEMS’ costs shared with other donors is in line with DFID’s share of donor contributions to GFEMS

Efficiency	Project score	DFID	Assess the efficiency of GFEMS as an organisation in delivering the programme.
Efficiency	Timeliness of outputs 1.1, 2.1, 2.2, 4.1 and 4.2	GFEMS	Assess how quickly GFEMS are delivering
Efficiency	Quality of studies under Outputs 1.1, 2.1, 2.2, 5.1 and 5.2	GFEMS’ Technical Review Panel	Assess the quality of GFEMS’ outputs.
Efficiency	Cost per person reached	GFEMS	Assess coverage of GFEMS’ service delivery
Efficiency	Time to develop interventions	GFEMS	Efficiency of internal mechanisms to develop projects from initial design to implementation
Efficiency	Internal resources used to deliver interventions	GFEMS	Efficiency of internal mechanisms to develop projects from initial design to implementation

Effectiveness	GFEMS’ internal project scoring system	GFEMS	Assess the quality of GFEMS’ interventions and the extent to which they are learning and improving from previous experience.

Cost-effectiveness	Cost per victim ‘saved’	GFEMS	Measure how much value we are creating per pound spent.
Cost-effectiveness	Cost per beneficiary	GFEMS	Measure how much value we are creating per pound spent.
Cost-Effectiveness	Number of new (public/private) donors making significant contributions to GFEMS	GFEMS	Monitor GFEMS’ progress towards transition to a pooled funding mechanism

In view of the length of the design phase and call for proposals made, it is too early to provide a robust assessment of the performance of this programme against all value for money measurements, and this section will focus mainly on economy and cost-effectiveness measures.
GFEMS is a new organisation with no previous track record of working with DFID or similar development organisations. During the review period DFID and GFEMS have worked closely to ensure that GFEMS’ staff salaries and the overall proportion of budget allocated to salaries was in line with other broadly comparative organisations and within parameters acceptable to DFID.
DFID’s share of GFEMS’ staff salaries, consultant day rates, and operational costs has remained in line with our share of GFEMS’ donor contributions – reducing in absolute terms during the period under review as GFEMS increased its donor base.
In terms of cost effectiveness, GFEMS increased its public/governmental donor base by 1 during the review period. During the period under review, GFEMS received a second tranche of funding totalling $21M from the US State Department (an existing donor). The significant new contribution made by the government of Norway to the fund in December 2018 has also boosted GFEMS’ total available funds but remains restricted through the single-donor fund model it has necessarily adopted. GFEMS has not secured donors (public or private) who are willing to provide it with unrestricted funding. It’s progress towards transitioning to a pooled fund mechanism has therefore been minimal (although it was not anticipated that this transition would occur during the lifetime of this programme).
From a VfM perspective, it is not possible to provide a full assessment at this stage. However, it is possible to say that on the VfM measures we are able to consider combined with the onboarding of a new donor and the relatively low spend during the inception phase, this programme should be allowed to move into full implementation.
Recommendations:

Based on GFEMS’ fuller understanding of delivery partner objectives and projects following the call for proposals, a revised Value for Money (VfM) framework based on DFID’s VfM guidance, should be submitted to DFID by 31 March 2020 and reported against quarterly. The VfM framework should be based on DFID’s VfM guidance.

E: RISK

Risk overview

The GFEMS programme overall is rated as Major risk and that remains unchanged at this review. The following are the key risks:

Monitoring, Evaluation and Learning (MEL) risks

The main risk related to effective MEL activities is the complexity of the programme and sensitivities of working on Modern Slavery issues in the target countries These include:

- The lack of prevalence data on the risk of modern slavery in specific modern slavery industries.
- The lack of evidence on what works to address modern slavery;
- We agree an adaptive approach to programming is appropriate. This will have an impact on the resources required to effectively monitor and evaluate the results.
- The ability to assess contribution and attribution in such a complex policy and programming area.

DFID will mitigate these MEL associated risks through the independent MEL Unit. The effectiveness of this approach will be assessed at the next Annual Review.

Corporate Management Processes

During the period under review, GFEMS’ internal due diligence and corporate functions required particular support from DFID. Improvements have been made and the required standards met but DFID will continue to closely monitor GFEM’s ability to demonstrate required corporate management assurances.

Recommendations:

GFEMS must revise its risk register clearly outlining the relationship between risks at all levels from project partner to higher level strategic risks. The revised risk register should be submitted to DFID by 31 March 2020 and reported against quarterly.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The project’s main delivery mechanism is an Accountable Grant between DFID and GFEMS. The grant started in September 2018 and a six- month inception phase was extended in April 2019 and was completed in July 2019. A transition between inception and implementation is being completed due to an agreed co-creation period between GFEMS and its identified downstream partners. Once GFEMS has completed this process and contracts are signed, the programme will move to full implementation by March 2020.

Financial Performance

All progress reports have been submitted as agreed.
GFEMS is a new organization.  All of its current donor funding is restricted by donors for their programs and cannot be deployed to other purposes.  GFEMS does not have resources of its own that can be used to advance funds to this project.
DFID continues to stress that requests for payments must be based on a realistic budget and forecast estimate of expenditure. As with all DFID programming, consistent failure to provide realistic budgets will be taken into consideration when assessing DFID’s ability to continue funding partners.

Financial Sustainability

GFEMS’ overall financial sustainability is dependent on securing a broad and stable donor base. The long-term impact of DFID’s investment will only be fully realised if GFEMS is able to realise its goal of becoming a multi donor fund with the reach that it offers.
Recommendations:
During the second year of the programme, GFEMS must focus on continuing to strengthen its financial management. DFID will require GFEMS to ensure expenditure against agreed budgets does not vary by more than 5% for each quarter during the life of the programme, starting from 1 April 2020.
GFEMS should also step up its resource mobilisation efforts to broaden and diversify its donor base and accelerate progress towards its strategic ambition to become a multi-donor, pooled fund. As part of this, GFEMS should produce a specific resource mobilisation strategy by 31 March 2020 and regularly review progress against it.

Date of last narrative financial report(s)	Submitted to DFID 27 November 2019 (covering period July – Sept 2019)
Date of last audited annual statement (s)	Submitted to DFID 28 June 2019 (covering period Sept-Dec 2018)

G: MONITORING, EVIDENCE & LEARNING

Independent Monitoring, Evaluation and Learning Unit

During the period under review DFID externally contracted a supplier to provide an independent monitoring, evaluation and learning unit in support of the GFEMS programme from 1 August 2019 to April 2022. IMC Worldwide is the supplier – selected through an open and transparent tendering process. At the time of review, IMC are nearing the end of the four-month inception phase and have produced the inception report, following workshops with DFID, GFEMS and Global Learning for Adaptive Management (GLAM). We expect the contract to move into implementation in late January/early February 2020. IMC will play a critical role in helping DFID to manage risk and support adaptive monitoring, evaluation and learning. We expect IMC to provide timely, high quality reports and technical assistance to support DFID and Programme Steering Committee (PSC) decision making and learning will be monitoring this through the use of key performance indicators between now and the next annual review.

The purpose of the MEL Unit is to provide an independent monitoring, evaluation and learning function on behalf of DFID that will deliver the following four outputs:

1. Independent monitoring to complement and strengthen GFEMS’ own monitoring and learning through the provision of additional monitoring mechanisms for the sectors and/ or country-specific interventions.
2. targeted technical advice to GFEMS on MEL for adaptive management on the basis of partner MEL system assessments.
3. independent performance evaluation to assess the extent to which intended outcomes have been achieved and capture key lessons from implementing an adaptive programme designed to introduce new ways of working to tackle modern slavery, and
4. Facilitate regular structured learning mechanisms between DFID and GFEMS to assess the quality of the programme’s learning and adaptive processes and to create a space for changes to programme strategy as a result of evidence and learning.

The MEL Unit is not substitute or replacement for GFEMS’ own MEL and reporting systems. Rather through it, independent monitoring is expected to provide DFID with a greater assurance of the results being achieved by GFEMS and its downstream partners operating in targeted sectors in Bangladesh and India, highlight potential risks and support programme adaptation and learning.

We expect the impact of the MEL Unit to be improved performance of the programme implemented through DFID’s investment in GFEMS, and a contribution to the evidence base on modern slavery. The expected outcomes are:

1. Strengthened programme delivery and accountability through a greater understanding of the quality of programme implementation, highlighting of potential risks, and verification and triangulation of results;
2. Appropriate programme adaptation based on evidence and learning generated across the programme; and
3. Understanding and evidence of the programme’s contribution to intended impact and outcomes.

GFEMS’ monitoring evaluation and learning approach

GFEMS and implementation partners are responsible for undertaking their own monitoring, evaluation and learning to report progress against the logframe results as well as ensuring monitoring and learning supports adaptive management. During the design phase GFEMS developed i) sector-specific theories of change, ii) a detailed MEL strategy and iii) accompanying monitoring and learning guidance for its implementation partners.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed, and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the appropriate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible e.g. categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management e.g. accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided