Project Completion Review – post April 2018

Title: Delivery of the 2018 Global Disability Summit
Final Programme Value £ (full life): £1,314,605.99	Review Date: / 31 March 2020
Programme Code: 300530	Start Date: 22 February 2018	Final End Date: 31 December 2019

Summary of Programme Performance

Year	2019	2020
Programme Score	A+	A+
Risk Rating	Low	Low

DevTracker Link to Business Case:	Found here
DevTracker Link to Log frame:	N/A

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

This programme covers funding for delivery of the Global Disability Summit (GDS18), hosted by the UK Government, the Government of Kenya and the International Disability Alliance (IDA) from 23-24 July 2018. The Summit was designed to achieve three outcomes: (1) raise global attention on a neglected issue, (2) mobilise new global and national commitments, and (3) showcase best practice and evidence of disability inclusive development.

The Summit brought together more than 1200 high-level delegates from around the world and secured significant commitments in support of the UN Convention on the Rights of Persons with Disabilities (UN CRPD) and the Sustainable Development Goals. The Summit mobilised 171 sets of ambitious commitments and over 349 signatories to our collective action plan, the Charter for Change.

The emerging long-term impact of the Summit is now becoming evident, with work underway on implementing the commitments. For example, the World Bank Group are progressing work on delivering their ten wide-reaching commitments to accelerate global action on disability-inclusive development in the areas of education, digital development, data collection, gender, post-disaster reconstruction, transport, private sector investments and social protection. The Nigerian Government has, since the Summit, passed the Discrimination Against Persons with Disabilities (Prohibition) Act following 17 years of advocacy from Nigerian-based Disabled People’s Organisations (DPOs). The UN developed a groundbreaking system-wide Disability Inclusion Strategy in the year following the Summit, with the UN Special Rapporteur on the rights of persons with disabilities crediting GDS18, reflecting that the Summit “had a major impact on the UN’s ambition to become disability inclusive.” Momentum continues post-GDS18 with the Government of Norway indicating that it intends to hold a follow-up Global Disability Summit in 2021, having been directly influenced by GDS18. It aims to build on the success of GDS18 and support continued implementation of commitments, while also seeking to engage new actors and incentivise new commitments.
[note] Global Disability Summit 2018: One Year On progress report, p.16 https://www.gov.uk/government/publications/global-disability-summit-one-year-on-accountability-report-2019

In terms of organisational level impact of the Summit, a self-reporting survey launched one year after GDS18 asked agencies to reflect on whether the Summit made any difference to the way they work. Just over 68% of all respondents reported that GDS18 had made it easier for their organisation to work in a more disability inclusive way, with the results showing a 54% increase in the number of agencies reporting they believe their organisation to be more inclusive since the Summit, in comparison to before.

The programme also covers three other components: (i) the delivery of a public disability data tool, (ii) funding to ensure disabled people’s organisations (DPOs) were central to the planning, implementation and delivery of the Summit, and (iii) the establishment of an accountability mechanism for the Global Disability Summit.

These components have all been successfully delivered and well received by stakeholders; a disability data portal has been established, DPOs were central to GDS18, and the initial accountability work for Summit commitments has been completed culminating in the publication of a GDS18: One Year On progress report. The report sets out in more detail the significant emerging impact of the Summit.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Successful delivery of the Global Disability Summit
Output number per LF		1.1	Output Score	A++
Impact weighting (%)?		60%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Summit held with high level attendance from developing country governments, UN agencies, multilateral organisations, other donor agencies, civil society and private sector	Summit to be held in London in July 2018.	The Summit was attended by over 1200 delegates from around the world, including the President of Ecuador, the Vice-President of Argentina, five heads of UN agencies and over 40 government Ministers from around the world.
Number of governments and organisations signing the Charter for Change	The original target was 100 organisations signing the Charter.	Over 345 organisations from around the world signed the Charter.
Number of commitments made by governments and organisations	The original target was 100 organisations making commitments.	Over 170 governments and organisations made commitments, with a total of 968 individual commitments being made.
All sessions at the Summit to be fully accessible	The aim was for the Summit to follow best possible practice on accessibility.	All sessions were designed to be fully accessible, resulting in positive feedback from attendees.

Provide supporting narrative for the score

The Global Disability Summit in July 2018 (GDS18) raised global attention on a long-neglected issue, mobilised new global and national commitments on disability and showcased good practice, innovation and evidence from around the world. GDS18 was instrumental in building the recent global momentum around disability inclusive development and delivering ambitious new commitment to action. There were four indicators, which achieved an A++ score overall:

Indicator 1.1a required strong, high level attendance at the Summit, from across a variety of sectors. This was achieved with high level attendance from across the global community. 67 countries were represented overall, five heads of UN agencies and leading figures from across the global disability community. (Source: GDS18: Official Readout).

Indicator 1.1b related to the Charter for Change which was a collective call to action on disability inclusion. The Charter was the principal outcome document of the Summit, designed to bring about further implementation of the UN Convention on the Rights of Persons with Disabilities (CRPD) and Global Goals. It was signed by over 345 organisations including 47 national governments, 20 multilateral organisations and 226 civil society organisations. (Source: GDS website)

Indicator 1.1c focused on the number of commitments made. Over 170 ambitious sets of commitments were made at the Summit, comprising 968 individual commitments. This included 300 by national governments, 466 by CSOs and 125 by multilaterals. (Source: GDS18 Accountability Inception Report, draft). The commitments were wide-ranging, including:
- anti-discrimination laws to gender equality reforms and commitments on humanitarian assistance.
- Nine organisations and governments, including USAID, the World Health Organisation and UNICEF, along with the UK, joined the Global Partnership on Assistive Technology, aimed at transforming access to, and the affordability of assistive technology.
- Seven UN agencies committed to make their work more inclusive for people with disabilities in various ways, and at least 15 organisations, including the World Bank, committed to promoting the use of the Washington Group questions.
(Source: GDS18 Summary of Commitments)

Indicator 1.1d required sessions on the day to be fully accessible. All sessions were fully accessible including for those with mobility issues, use of sign language interpreters and on-screen captions, facilities for guide dogs, as well as the availability of braille and easy-read for related documentation. There were occasional issues with the functioning of the technology in some sessions, but overall feedback from attendees was that the accessibility was excellent.

Lessons identified this year linked to this output and recommendations for future programmes

GDS18 was successfully delivered in July 2018. The Disability Inclusion team has produced a ‘Lessons Learned’ document for future summits. The document sets out a number of recommendations regarding: planning, staffing and recruitment, governance, partner engagement, country and stakeholder engagement, cross-HMG working, comms work, policy and commitments, costs, delegate management and post-Summit accountability work. The lessons learned document is now used by the Head of Events and will continue to be shared with teams across DFID as a resource for future summits. Subsequent DFID summits are now more accessible and inclusive to people with disabilities as a direct result of GDS18.

Post-Summit we have also created a wider package of GDS-specific materials, including guidance for using the GDS brand and information on how the core themes were developed, which can be shared with other countries looking to host a follow-up Summit. This will ensure that future Global Disability Summits build on the success of the 2018 Summit as far as possible.

Output Title	Successful delivery of a public disability data portal
Output number per LF		2.1	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of countries for which disability disaggregated data have been collected	The original target was 40 countries, including the Summit countries.	Data have been collected for 40 countries across 16 separate indicators. (Source: Disability Data Review)
A website is developed, tested and launched that disseminates disability data	The aim was to launch the website at the Summit.	Website containing the data launched at the Global Disability Summit.
Number of countries for which disability disaggregated data have been collected	The original target was 40 countries, including the Summit countries.	Data have been collected for 40 countries across 16 separate indicators. (Source: Disability Data Review)

Provide supporting narrative for the score
Until recently there was no central online portal for data disaggregated by disability status. The Disability Data Portal was created to provide a snapshot of the data globally available on people with disabilities in 40 countries and identifies where there are gaps in the current body of data. The portal focusses on data relating to the four thematic areas of the Summit: inclusive education, stigma and discrimination, technology and innovation, and economic empowerment. The portal presents key development indicators relevant to the Summit themes, mostly drawn from the Sustainable Development Goals (SDGs), along with others relevant to the UN CRPD.

There were two key parts of this output. Indicator 2.1a required investigating what disability disaggregated data already exists across the world and collecting these figures into a central place. Indicator 2.1b then required a website which could be used to disseminate the data collected under indicator 2.1a.

Both of these tasks were completed in line with expectations and on time. The Data Portal had 34,557 unique users and almost 66,000 page views during 2019. We have received positive feedback from users - for instance, it was highlighted as good practice by independent users at the Washington Group annual meeting in November 2018. It is regularly sourced on social media, and Leonard Cheshire continue to publicise it.

The GDS budget only provided funding for the initial development, initial data collection and a short period of refinement (up to two months). As stated in the business case, the portal was intended to raise the profile of the scale of need at the summit and fill a gap until the UN Statistics Division (UNSD) Disability Team were able to develop their own portal. Leonard Cheshire are now planning to develop it with data from more sources.

Since the summit and the launch of the GDS Data Portal, UNSD has further developed its own repository and dissemination of disability data (https://unstats.un.org/unsd/demographic-social/sconcerns/disability/statistics/#/countries). Although the UNSD portal does not explicitly refer to the GDS portal, it does draw upon some of the same data sources. However, neither portal provides global coverage, and each portal contains data for some countries that the other does not.

The GDS18 Data Portal offers some advantages over the UNSD one (for instance, the user interface components are easier to use). Given that the UNSD will be better resourced to ensure that a data repository continues to be maintained and updated there is little value for money in DFID providing more funding to develop the GDS18 Data Portal.

Lessons identified this year linked to this output and recommendations for future programmes

The 2019 Annual Review identified some suggestions which could result in improvements to the Portal. For instance, there is currently no way of downloading data from the Portal, making it harder for users to carry out analysis. There is also scope to link the site in with related and emerging data activities.

Following discussions about potential improvements, Leonard Cheshire has committed to restarting the development of the Data Portal. They have some specific plans to align it with the SDGs, add new quantative data from additional surveys (including the possibility of including citizen-generated data), and introduce qualitative data.

We will work with Leonard Cheshire to provide technical advice on development plans and additional improvements. Specific things that we will recommend including is a data download facility, addition of overall country disability prevalence data, and creating better linkages to the underlying data, as identified in the 2019 Annual Review.

We had a discussion with the Washington Group about whether they would be able to take over the Data Portal and continue to maintain it in 2018. However, although they showed interest in maintaining a potal, their preferences were for one that hosted only data that have been derived from the Washington Group Questions. It is not yet clear if the Washington Group will develop a portal and, if so, what this would look like or when it will happen.

The UNSD seem to have resource to continue to maintain and update their repository. We will continue to engage with all organisations maintaining disability data portals to help them develop their data platforms to be as useful and accessible as possible.

Output Title	Disabled People’s Organisations are central to the planning and delivery of the Global Disability Summit
Output number per LF		3.1	Output Score	A+
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of DPOs from developing countries participating in GDS18	The original target was for 50 DPOs from developing countries to attend the Summit.	IDA facilitated a reference group to ensure that CSOs contributed to design and planning of the summit. 450 applications were made in response to IDA's open call to DPOs to attend the Summit. 55 DPOs were selected to attend. (Source: IDA Report to DFID)
All sessions led by people with disabilities	The target was for all sessions at the Summit to be led by people with disabilities.	Successfully achieved, with all sessions led by people with disabilities. All panel sessions had at least two people with disabilities on the panel.

Provide supporting narrative for the score

The principle of “nothing about us without us” is central to the disability movement. It was therefore vital that the Summit reflected this and that people with disabilities were at the heart of the event. DFID and the Government of Kenya worked closely with the co-host, IDA, to ensure people with disabilities and their representative organisations were embedded in the planning and delivery of the Summit. More broadly, the success of the Summit was built around partnership, with civil society organisations actively working alongside governments, private sector and multilateral organisations to achieve a common goal to leave no one behind and bring disability front and centre of international development and humanitarian assistance.

This output was a key success of the Summit, and scored A+.

Indicator 3.1a was based on the number of DPOs from developing countries participating in the Summit. This was a huge success and critical to achieving the Summit’s objectives. This process was led by IDA, who undertook a set of actions ahead of the Summit, including:
The establishment of a Civil Society Reference Group to the Summit. This ensured that people with disabilities were involved in planning the summit and creating commitments from civil society.
- An open call to DPOs to attend and participate in the Summit. They received over 450 applications. 55 DPOs were selected to participate and supported, as necessary, to meaningfully engage in the Summit’s design and delivery.
- The Civil Society Forum was held on 23rd July 2018. Over 400 participants attended the forum. On average, 50% of each panel session were representatives of organisations of persons with disabilities.
(Source: IDA Report to DFID).

Indicator 3.1b required people with disabilities to lead the sessions at the Summit. This was achieved, with all sessions being led by people with disabilities. All panel sessions were also balanced, with at least two people with disabilities on each panel, and at least one woman.

Lessons identified this year linked to this output and recommendations for future programmes

The level of engagement, representation and leadership from people with disabilities, received significant praise across the international community. GDS18 was praised by high-level attendees as an important influence to change the way international conferences are designed and delivered. In amplifying voices of people with disabilities and bringing together a range of DPOs along with other organisations and governments, the Summit provided an opportunity for people with disabilities and their representative organisations to build ties with each other and strengthen wider connections. Through ensuring there was a diversity of presenters and co-chairs from across the disability community, including women with disabilities and co-chairs with intellectual disabilities, marginalised groups were able to extend their capacities and networks, ultimately leading to better inclusion.At all stages, the summit aimed to comply with and promote the CRPD. There are some lessons learnt on the process for selecting DPO attendees and ensuring the process for selection is as open and clear as possible. We also need to further ensure that excluded groups within the international disability community, such as mental health groups, feature even more strongly. The Disability Inclusion Team should work with IDA and Norway to ensure that DPOs are central to the planning and delivery of the next Global Disability Summit, sharing our collective learning and experience on this issue, as it was key to the success and legacy of GDS18. It will also be important to invest in the capacity building of DPOs, in order that they may continue to play a key role in furthering the disability movement globally. This will be an action taken forward in the Disability Inclusion Team’s new programme for 2020 onwards.

Output Title	An accountability mechanism for the Global Disability Summit
Output number per LF		4.1	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of commitments published online in an accessible way	The original target was to have all commitments on the DFID website immediately following the Summit, with a searchable commitment portal built on the IDA website by December 2018.	All commitments were made available on the DFID website immediately following the Summit. / A searchable portal on the IDA website was developed which houses all the GDS18 commitments, although this was delayed by two months.
First stage of accountability process put in place	Delivery of a one year on progress report showcasing initial analysis and monitoring of commitments.	Consultants undertook analysis of the commitments made and a self-reporting survey was successfully launched in April 2019. Findings were published in a one year on progress report in September 2019, which was launched at a disability inclusion event at UNGA. The report is published online.

Provide supporting narrative for the score

To help ensure the long-term success of GDS18, DFID has designed and developed an accountability approach in consultation with partners to encourage full implementation of the commitments, monitor progress and to maintain the momentum that GDS18 has generated. This output relates to the early stages of that process, including visibility of commitments and initial analysis and monitoring. This has been successfully delivered and scored an A overall. Longer term monitoring will be carried out by an independent secretariat, funded by DFID from 2020 onwards.

Indicator 1.1a required the commitments to be made available in an accessible format. This task has been completed, with the commitments available in an accessible format on the DFID website as well as on a searchable portal on the IDA website, available at: www.internationaldisabilityalliance.org/commitments. The commitments are searchable by stakeholder, theme or region, and the portal includes an easy-to-read summary of all commitments. The launch of the IDA portal was delayed by two months as the process for uploading, verifying and quality assuring commitments took longer than was previously anticipated.

Indicator 1.1b relates to the first stage of the accountability process being put in place. This work has been successfully completed and an independent secretariat will pick up where this initial work ends. Consultants were contracted to undertake analysis and monitoring of all commitments made; almost 1000 in total. An analysis of all commitments by theme, stakeholder and region was carried out, a self-reporting survey was designed and launched in April 2019, and case studies were undertaken by DPOs in three focus countries (Jordan, Nepal and Kenya). The findings of all of this analysis and monitoring were summarised in a ‘GDS: One Year On’ progress report, available here: https://www.gov.uk/government/publications/global-disability-summit-one-year-on-accountability-report-2019. The report was launched at a disability inclusion event at the UN General Assembly (UNGA) in September 2019, co-sponsored by the UK. The report indicated good progress against commitments with 74% on track and 10% already completed. The report and its findings were welcomed by stakeholders. We consider progress reports such as this one to be important for creating accountability and momentum for meeting the commitments, and envisage similar reports to be regularly produced in future.

Lessons identified this year linked to this output and recommendations for future programmes

An independent secretariat will manage the longer-term accountability work going forward, picking up where this work leaves off. The longer-term approach was designed by a Key Stakeholder Group comprising representative organisations from across the disability sector, in consultation with CRPD committee members. The secretariat will be initially funded by DFID and in place from summer 2020, housed within IDA. A high level advisory group of key stakeholders will also be convened to advise on and guide the secretariat’s activities.The approach taken by the secretariat should link in with existing reporting mechanisms as far as possible, such as those associated with the UN CRPD and the 2030 Agenda. It should also build on the initial accountability work which has been undertaken so far, producing further progress reports starting with a ‘two years on’ report, and incentivizing continued delivery of commitments. It is envisioned that other donors will come on board in due course to share the burden of funding.
The accountability process also relies on organisations and governments holding themselves and each other to account for their commitments. Continuing informal dialogues will be a key part of this activity, through the GDS Parternship Forum as well as in-country monitoring activities led by DPOs. For future summits where commitments are gathered, we would recommend further emphasis on the importance of self-accountability from the beginning, and encourage organisations to set up their own internal accountability systems to strengthen and complement the wider accountability process.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The programme has delivered on all of its intended outcomes: catalysing political will through high-level attendance and ambitious commitments, generating rigorous new disaggregated data for the Global Data Portal and sharing new emerging evidence, and also through providing essential leadership and representation opportunities on the global stage. The Government of Norway has indicated that it intends to hold a follow-up Global Disability Summit in 2021, having been directly influenced by GDS18. This demonstrates the success of GDS18 in catalysing political engagement on the issue of disability inclusion, and the strong momentum which continues post-Summit.

Through 2019 the accountability process for GDS commitments was developed, with initial analysis and monitoring successfully undertaken and published. The one-year-on report summarises the good progress which is being made against commitments, and a longer-term accountability process will build on this work from 2020 onwards.

The objectives have therefore been achieved, and there are no formal outstanding actions. DFID’s focus will now be on sustaining momentum for GDS commitments and ensuring that the legacy of the summit continues. We will do this by working closely with the accountability secretariat and hosts of future Global Disability Summits to build on progress. We will also seek to maintain the GDS Partnership Forum to ensure wide engagement with GDS partners on relevant issues going forward.

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

The Summit theory of change was designed in collaboration with stakeholders and co-hosts in the run-up to the Summit. The Summit theory of change provided a rationale for why the Global Disability Summit would make a difference and where it would fit in the overall process of transforming the lives of people with disabilities.

Impact Statement: The lives of people with disabilities are transformed and disability inclusive development is realised.

Outcome 1. Political will: Catalysing political and institutional will for inclusion in order to mobilise new global and national action. This includes creating opportunities to assess progress and promote accountability for the promises of the SDGs and UN CRPD processes, and to build on those with new commitments. The Global Disability Summit provided fora in which governments could make specific pledges and foster collective action for decision makers and global, national and local actors. The initial accountability work which has been undertaken, as well as the longer-term monitoring which will continue going forward, is essential for success to hold leaders to account for their promises. The follow-up Summit which is in the early stages of being planned by Norway for 2021 indicates the increased global political will on this agenda, and will build on GDS18 to engage new actors and seek further commitments to implement the UN CRPD.

Outcome 2. Data and evidence: It is critical to raise awareness and the profile of issues faced by people with disabilities. The Global Disability Summit provided essential opportunities to share data and evidence to demonstrate ‘what works’ and presenting and furthering the imperative for disability disaggregated data.

Outcome 3. Leadership and representation: Providing high profile and diverse opportunities for leadership and representation of people with disabilities themselves to provide a global platform for people with disabilities to reduce stigma and discrimination. Leadership and representation is needed for effective change in challenging stigma and increasing voice and opportunities for partnership at a variety of levels; the global, national and local level, and the Global Disability Summit was a unique platform for ensuring this representation.

Explain major changes to the logframe in the past year (1/2 page)

There was no accompanying logframe for this programme.

N/A

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

Economy: A critical success criterion in design of the business case for GDS18 was securing private sector funding to offset the cost of the Summit. Through the development of partnerships with Microsoft and the Open Societies Foundation (OSF), the team secured £200,000 in funding from the private sector. This covered the following: travel, transport, accommodation for high-level attendees; catering and hospitality; moderator and VIP costs; and supporting technology on the day.

Several Summit outputs were purchased at the appropriate quantity and price. For example, the team negotiated robustly with the venue, event production company and other suppliers on costs. A number of these contracts were secured for reduced rates, and the venue was secured free of charge and for a number of extra days. The team drafted and agreed funding criteria for travel, accommodation and visa expenses in conjunction with the initial budgeting, modelling cost implications of different scenarios and principles for what could and could not be funded. Delegations from least developing countries and DPO representatives were identified as funding priorities.

For the first stage of the accountability work, the Disability Inclusion Team negotiated robustly with consultants Equal International to reduce the costs of undertaking the commitments analysis work and compiling a progress report, resulting in a significantly reduced contract value of £89,760 which represented excellent value for money for work by experts in the field of disability and development.

One lesson learnt is that costs for Summits can be difficult to forecast given the evolving nature of delegate numbers. Teams should look to secure higher levels of funding than estimated to build contingency for this.

Efficiency: We monitored delivery of outputs by the production company and related sub-contractors through regular project-level meetings. We agreed delivery objectives, responsibilities and timelines with the production company and developed TOR between the co-hosts and the production company. We also worked closely with delivery partners and developed feedback loops, such as with Leonard Cheshire, on the global data portal, to ensure the outputs were to the highest possible quality and could have most impact.

Effectiveness: The Summit generated 171 sets of commitments from actors around the world – these have the potential to create positive and lasting change for people with disabilities and therefore implementation of these commitments is key. The initial accountability work summarised in the GDS18 One Year On progress report shows that 74% of commitments are on track and 10% are already completed, indicating that significant progress has been made so far which is essential to the long term impact of the Summit. Continuing to support a robust accountability approach will be vital to ensuring that the Summit continues to deliver lasting change. The independent secretariat funded by DFID from 2020 will pick up from the initial monitoring work, and is a key part of ensuring this long term accountability.

The funding to IDA to secure meaningful participation of people with disabilities and their representative organisations was extremely productive and was a particular success of the Summit – it set the tone for the Summit, and ensured GDS18 truly ‘lived’ the motto of ‘nothing about us, without us’.

Equity: The range and balance of attendees and country commitments was broad and equitable – and we paid particular attention to the involvement of women with disabilities. Every session was chaired by someone with a disability and each speaker panel included at least one person with a disability and one woman. There was more to do to ensure the involvement and participation of mental health groups and those with intellectual disabilities. The Summit was, however, cohosted by two people with intellectual disabilities which was groundbreaking for an event of this kind and strongly welcomed by civil society.

The global data portal will allow us to understand which developmental areas and regions show the greatest inequalities and help DFID and the wider sector reach and target the most vulnerable.

The programme was granted a no-cost extension of nine months to allow for the accountability component to be effectively implemented. The original business case provided for an accountability process to be set up by March 2019. However, with the high number of commitments made at the Summit across a wide variety of stakeholder sectors, we decided it would be useful to factor in time for a preparatory phase of work to be carried out including thorough analysis of the commitments. Additional research and shared learning from other accountability processes also highlighted that the longer-term accountability work would benefit from a longer lead-in time with increased stakeholder engagement in the design stage, which this time extension allowed for.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Reputational risks:
- Credibility and risk of protest at GDS18
  - This was identified as a risk due to previous civil society criticism of domestic policy on disability inclusion. Whilst there was a small protest outside the venue, IDA were on hand to meet with the protestors and hear their concerns. DFID have since met with the relevant organisations for further conversations.
- ICAI’s report on DFID’s approach to disability in development (published in May 2018)
  - ICAI’s report had potential to undermine DFID’s reputation and credibility on disability and therefore impact on the Summit itself. A comprehensive fact check was undertaken on this review, and the review was broadly positive. It provided valuable recommendations for our future approach.

Delivery risks:
- Momentum post-Summit
  - The risk of momentum post-Summit not being maintained has largely been mitigated. We set up a Key Stakeholder Group and Partnership Forum to build momentum and partnership related to delivery of commitments, and had a high rate of engagement in the self-reporting survey launched to monitor implmementation of commitments. DFID are now funding an independent secretariat from 2020 to take forward a long-term approach to accountability. Going forward, the Government of Norway has indicated it will host a follow-up Global Disability Summit in 2021, which will build on the success of GDS18 and ensure continued global momentum on disability inclusion.
- Ambition of commitments
  - There was a risk that a limited number of commitments would be made at the Summit, or that commitments would not be ambitious enough. This did not come into fruition and the Summit exceeded expectations with 171 governments and organisations making a total of 968 individual commitments, many of which were analysed to be very significant.
- Data Portal
  - There was a risk that the plans for a data portal would not deliver a rigorous platform, with insufficient data being collected. This was mitigated through strong engagement and collaboration with the delivery partner.
  - Following discussions about the scope for improving the data portal post-launch, Leonard Cheshire has identified funding to allow them to undertake further development. We will engage with them in this process and provide technical advice on the plans, and suggestions for areas that could be improved / added. These developments should ensure that the portal remains a valuable and relevant resource for users.
  - In addition, we will also engage with the UNSD to influence them to maintain the development of their new disability statistics site, including adding countries and data that are currently missing from the UNSD portal, but are included in the GDS18 portal.
- Support from NGOs and Persons with Disabilities
  - There was a risk that certain NGOs and persons with disabilities would not support GDS18 because they felt it did not address a particular impairment type. To mitigate this, we consulted IDA/IDDC at every stage on tone and content and took policy advice on contentious issues whilst advancing disability rights and ensuring visibility of different kinds of disability. We recognised the likelihood that despite efforts to represent all, some groups may have felt it was not enough.

Operational risks:
- Communications
  - There was a risk that communications activities in relation to the event, deliverables or high-profile figures would not get sufficient traction. However, we worked up a strong comms strategy and worked with a range of third-party actors to amplify our messages and GDS18 outcomes.
- Delegate management process
  - If the delegate management process was not adequately efficient, it could have had severe consequences on Summit outcomes. To mitigate this risk, we appointed a senior member of staff with decision-making powers for, and oversight of, delegate management. We also dedicated sufficient resource and time to this area of work. VIPs needed tailored invitations much earlier to secure the date in diaries.
- Accessibility concerns and logistical issues
  - We ensured all hotel accommodation was fully disability inclusive/accessible and suitable for high level delegates e.g. close to venue, with transport connections etc. It was important to manage expectations of delegates to avoid disappointment/misunderstanding e.g. unable to book top hotels due to finite budgets.
- Visas
  - There was a risk that delegates would be prevented from attending if their visas were delayed or applications made too late. This would have led to poor representation at the Summit, especially from fragile states, with knock-on effect on reputation. To mitigate this risk we liaised early with UKVA regional representatives and Home Office to avoid visa delays. We escalated issues quickly to avoid reputational implications, and we drafted guidance for delegates to avoid delays.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The initial budget for the programme was based on a best assessment of likely costs, taking into account previous summit budgets, actual quotes received and consultation with procurement and commercial department. This also included consultation with disability experts on costs to ensure the Summit was fully accessible and costs of reasonable accommodations for people with disabilities were met.

The majority of the budget was disbursed via formal agreements with the following delivery partners:
- A contract with Calders Conferences and their downstream suppliers to manage direct Summit production costs;
- An accountable grant with Leonard Cheshire Disability to produce an Open Source Disability Data Portal and Data Analysis;
- An accountable grant with The International Disability Alliance (IDA) to manage the attendance, involvement and participation of Disabled People’s Organisations (DPOs) and delivery of the Civil Society Forum

The remaining budget was disbursed post-Summit through a contract with Equal International, who are leading experts in the field of disability and development. The consultants led the initial analysis and monitoring work for accountability of Summit commitments, including delivering the One Year On progress report. The Disability Inclusion Team negotiated a contract with Equal International representing excellent value for money, and worked closely with the consultants throughout the year to ensure milestones were met on time, while retaining final sign off of all outputs.

To help reduce DFID costs for the Summit itself, the team secured co-financing from the private sector. Travel and accommodation costs for government representatives from developing countries were covered by contributions by Microsoft and the Open Societies Foundation.

Calders Conferences were selected through a standing call-down contract to manage the production of the Global Disability Summit. Due to specific venue requirements and the value for money that the Here East venue offered, Calders were required to sub-contract SMART Live to deliver the majority of the works related to production of the event.

The team worked closely with delivery partners to ensure that delivery was consistently on track, on budget, delivered to a high standard and represented a high level of value for money. A budget lead was appointed, all budget items accounted for and regular meetings held both internally and with suppliers to review actual spend against projections. Where third party suppliers were necessary for delivery of specific services, these were sourced in consultation with the team to ensure that the services provided fulfilled the requirements and supported the delivery of Summit objectives.

Budget
Component	Lifetime Budget	Actual Spend
Management of direct summit costs (300530-101)	£726,341.41	£726,341.41
Open Source Disability Data Portal and Data Analysis (300530-102)	£105,838.00	£105,838.00
Establishing an accountability mechanism (300530-103)	£112,772.00	£112,772.00
Representation of Disabled Peoples Organisations (300530-104)	£369,654.58	£369,654.58
TOTAL	£1,314,605.99	£1,314,605.99

Lessons and Recommendations
- In managing a contract with a production company on an event of this nature, it is necessary to plan for flexibility, as budgets regularly shift and need to adapt to meet emerging needs.
- VAT must be factored into all budget calculations – whilst most Summit costs will be VAT exempt there are elements which are not, for example spend on catering. These were not full considered at the initial budgeting of the programme which led to reallocations of funding.
- Also, clear rules and expectations on detailed financial reporting should be communicated to accountable grant delivery partners. Some payments were made later than expected due to delays in detailed financial reporting.

Date of last narrative financial report	NA
Date of last audited annual statement	NA

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

There was light-touch monitoring processes in place throughout delivery of the Summit. The team met regularly to assess the efficiency and effectiveness of the team’s outputs, and to change and modify structures and systems accordingly. Feedback was sought from Summit attendees, with substantial praise being received from across the disability community and from international actors. For example, GDS18 was described as creating “a new wave in the disability rights movement”, and is credited with helping to “galvanise momentum, prioritisation and action” on the issue of disability inclusion.
[note] GDS18: One Year On progress report p.5 (https://www.gov.uk/government/publications/global-disability-summit-one-year-on-accountability-report-2019)
[note] GDS18: One Year On progress report p.16

The accountability process has been developed through consultation with a Key Stakeholder Group and a wider Partnership Forum, enabling inputs and feedback to be collected throughout the design and development of the accountability work. The 2019 self-reporting survey collected information from Summit stakeholders as to the progress made so far against commitments, as well as the wider impact of GDS18 on the way their organisations work. DPOs in three target countries (Jordan, Nepal and Kenya) also carried out more detailed case studies on the impact of the Summit in their countries. Findings are set out in the GDS18: One Year On progress report, along with analysis of the commitments.

The PCR was undertaken by building on the contributions from different leads (policy, finance, logistics) involved in the 2019 Annual Review, and taking into account the inputs received through the GDS18 lessons learned document and the 2019 self-reporting survey on Summit commitments.

Evidence (1/2 page)

Analysis of the commitments, as well as self-reported progress through an online survey, provides good evidence of the emerging impact of the Summit and the commitments made. As well as evidence of the the progress made against commitments, the One Year On report reflects wider feedback from stakeholders on the impact of the Summit which was collected through the self-reporting survey. Just over 68% of respondents to the survey reported that GDS18 had made it easier for their organisation to work in a more disability inclusive way, and the data demonstrates that there was a 54% increase in the number of agencies reporting they believe their organisation to be more inclusive since the Summit, in comparison to before the Summit.

Through engagement with a Key Stakeholder Group and wider Partnership Forum, we have also worked to gather evidence from experts working across the disability inclusion field, including DPOs and the CRPD Committee, to shape the accountability approach.
Learning (1/2 page)

A comprehensive lessons learned document was drafted through consultation with team members and feedback from GDS18 co-hosts. We have also developed a package of plans and guidance relating to GDS18 specifically to help inform official follow-up disability summits, which can be shared with future host countries and organisations.

Progress on recommendations from annual reviews for this programme (1/2 page)

In terms of the accountability component, the 2019 Annual Review recommended that the Disability Inclusion Team ensure successful delivery of the accountability work by December 2019, with particular attention to publishing a one-year-on progress report by UNGA 2019, designing a long-term accountability approach for delivery of Summit commitments, and continuing to disseminate and raise awareness of Summit learning and successes.

These recommendations have been fully and successfully implemented; the GDS: One Year On report was launched at UNGA in September 2019, the independent secretariat focused on long-term monitoring will be funded by DFID from 2020 onwards and will be housed within IDA; and the Disability Inclusion Team continue to regularly engage with external partners to promote the legacy of the Summit, including through support to Norway on their proposed Global Disability Summit 2021. Further progress reports will be published by the secretariat, including a ‘two years on’ report in 2020. We will work closely with future hosts to ensure that gaps and recommendations from this report inform the policy aims of the next summit.

As further recommended, DFID’s Head of Events also continues to share learning from GDS18 with other Summit teams, including the lessons learned document.Subsequent DFID summits are now more accessible and inclusive to people with disabilities as a direct result of GDS18. Venues chosen are fully accessible and consideration is given to transport options both travelling to and around the venue(s); all major DFID events since GDS have had sign interpretation and captioning in the plenary sessions, with facilities provided in other sessions where required. Events also continue to use apps and other digital solutions eg Slido for asking questions, to enable all delegates, including those with accessibility requirements, to participate in the event.

The final recommendations related to the global data portal. One recommendation was to work with Leonard Cheshire and others on improvements for the data portal such as creating a data download, adding more countries or indicators, or further validation of the underlying data. Another was to discuss with the Washington Group whether there is scope for the Group to take ownership of the site and use it as a dissemination tool for Washington Group data. Despite initial discussions, as yet the Disability Inclusion Team have been unable to identify an organisation to continue funding and/or hosting the platform in the long term. We will continue to seek to work with external partners on finding a long term host for the portal, linking in with other initiatives where possible.
Smart Guide
The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Signifcant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.