Project Completion Review – post April 2018

Title: PITCAIRN FINANCIAL AID 2019-2020
Final Programme Value £4.205M	Review Date:	April 2020
Programme Code: / 300235	Start Date / 01/04/2019	Final End Date: / 31/03/2020

Summary of Programme Performance

Year	2020
Programme Score
Risk Rating

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300235
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300235/documents

A. Summary and Overview

A1. The International Development Act 2002 specifically exempts aid to the UK’s Overseas Territories (OTs) from the poverty reduction criteria that apply to the rest of the DFID aid budget. The UK’s obligation to the OTs derives from the fact they are British Citizens and the UN Charter: “to promote to the utmost, within the system of international peace and security established by the present Charter, the well-being of the inhabitants of these territories [whose peoples have not yet attained a full measure of self-government]. Accordingly DFID’s responsibilities for the OTs continue to be framed by UN Charter obligations, UK legislation and long-standing Government policy reaffirmed in the 2016 National Security Council Strategy. The UK Government is therefore responsible for meeting Pitcairn’s reasonable assistance needs.

A2. The UK Government (HMG) recognises that the prospect of economic self-sufficiency for Pitcairn is very low, given its small population (in December 2018 there were 46 resident islanders - of whom 7 are off island long term), its small size (47 sq km/18.1 sq miles covering Pitcairn and 3 uninhabited islands) and extremely remote location. . Previously revenue was generated by trade with passing ships and the production and marketing of stamps and commemorative coins, through agents in New Zealand. However changes to trade routes in the last three decades have seen a marked reduction in the number of ships passing Pitcairn. Similarly sales of stamps and commemorative coins have been declining steadily since the 1990s. As a consequence, the accumulated reserves of the island were consumed by 2004, requiring the island to seek financial assistance from HMG in order to meet its reasonable assistance needs. Pitcairn has received development assistance in the region of 90-95% of it’s budget since then; it received £4.205m in 2019/20, against an original budget of [£3.6m (of which £100,000 was allocated for some small capital expenditure)]. We expect it will remain dependent on financial aid from HMG for the foreseeable future.

A3. As defined in the Business Case, the project supported the provision of public services to meet the reasonable assistance needs of the people of Pitcairn (including health, education and securing sea access), given self-sufficiency is currently not a viable option. UK funding was used to promote accountability, transparency and overall good governance of the Territory. It also ensured the island had high standards of child safeguarding.

A4. Financial aid to Pitcairn is in line with the 2012 Overseas Territories White Paper. It is consistent with relevant elements of the UK’s Aid Strategy and DFID’s 2015-2020 Single Departmental Plan, in particular on :
- Strengthening global peace, security and governance
- Tackling extreme poverty and helping the world’s most vulnerable
- Delivering Value for Money

A5. The project supported the Pitcairn Islanders by meeting their reasonable assistance needs through:
- maintenance of essential public service provision; and
- maintenance of regular and reliable sea access to Pitcairn.

A6. The context, in which Pitcairn remains reliant on financial assistance from the UK’ will not change in the near–medium term. Without financial aid from the UK, the Pitcairn Island government would be unable to provide essential public services and the islanders would either have to return to basic subsistence or consider leaving the island.

A7. The UK is the only source of significant external financing available to Pitcairn. Pitcairn does receive a very modest amount of support from the European Development Fund (less than £500,000): Pitcairn is currently implementing EDF10 and EDF11 project activities to improve tourism facilities each with a financial envelope of €2.4m. As the UK has left the European Union, discussions with Pitcairn will be required on how to progress initiatives previously funded through EDF.

A8. Maintenance of effective child safeguarding continues to be at the forefront of HMG’s mind and we have put in place interventions to create a substantial child safeguarding framework and a series of bi-annual independent reviews have taken place since 2009. There is now increased engagement by the Pitcairn Island Council (the Council) and most members of the community on child safeguarding. Following a facilitated reconciliation process in 2018, most Islanders acknowledge that what happened in the past was wrong and what needs to happen to keep children safe in the future. The current measures are regarded as effective, having been reaffirmed in all Child Safeguarding Reviews (CSRs), including the last review in 2017. The next CSR is scheduled to take place during 2020, although COVID-19 restrictions may affect the timing.
A9. With an ageing population and a steady decline in the economically active proportion of that population, there is very little prospect of the island attaining self-sufficiency. HMG remains engaged with the islanders in a concerted, meaningful, and frank discussion to understand their ideas and concerns about the future, which will inform any medium-long term vision for the future of the Island. The the Council continues to lead work, with external facilitation and supported by HMG, to determine what the future holds for the island. In parallel, there is ongoing consideration (led by the FCO) of HMGs longer term options for Pitcairn should the status quo prevail. Even with an increase in population by 40/50% this might not reduce the liabilities for HMG (and may actually increase them) or Pitcairn’s dependency on aid. There would be an increase in health and education costs for the island in addition to the need for increased public services, all of which are funded from financial aid. Pitcairn faces a very uncertain future with continuing HMG financial aid required.

A10. Following the World Health Organisation declaration that COVID-19 be classified as a global pandemic on 11 March, the French authorities introduced stringent quarantine measures, with all passenger ships being refused entry to French Polynesia (FP) and it is not clear at this stage (April 2020) when these restrictions will be lifted. This will have a major impact on the shipping service to/from Pitcairn as Mangareva (part of FP) is the dedicated port of call for passengers with a 36-hour transit journey to Pitcairn. The ship can for the foreseeable future only travel between New Zealand and Pitcairn, a 14-day journey one way, so the schedule will need to be adjusted accordingly. This will mean a reduction in journeys and an increase in fuel and operating costs.

A11. Despite a good initial uptake on passengers when the new shipping service was introduced, this has reduced in the second half of the year. The Government of Pitcairn Islands’s (GPI’s) Tourism Department and the Pitcairn island Office (PIO) continue to work with existing tourism brokers to market the service. During the first half of 20/21 DFID will work with the Governor’s Office to review progress on sales and revenues, what the projections are, and what that should mean for a) the number of rotations offered between Mangareva and Pitcairn, and b) how we approach the renewal negotiations towards the end of the two year period (late 2020). We will also review whether there are alternative options for shipping and access for the island as the 2-year shipping contract comes up for renewal in 2021.

A12. Due to the COVID-19 pandemic and its effect on the shipping service, the planned review will need to take into account global projections for shipping and high-end tourism as part of these deliberations. In addition, the review will need to be conducted based on the information prior to COVID 19. The existing contract will no longer be viable if tourism numbers fall and the costs of maintaining the contract continue to rise.

A13. DFID was alerted very late in the financial year to an overspend on medical and shipping costs and this has been detailed later in this report. This was unfortunate and the higher costs do diminish the achievements identified elsewhere and reduce levels of cost effectiveness. The Pitcairn Island Office (PIO) and the Governor’s Office have committed to closer monitoriong of any future potential overspends and alerting DFID in good time

A13. A Business Case for Financial Aid for 202/21 was approved in May 2020.

## B: DETAILED OUTPUT SCORING

Output Title	Sustained budget management, in line with best practice
Output number per LF		1	Output Score	A
Impact weighting (%)?		20	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Government of Pitcairn to reflect the priority recommendations from the Fiduciary Risk Assessment (FRA)into the risk register	2018/19 Annual Statement of Progress confirmed stable situation with no new risks identified	The 2020 FRA (finalised Feb 20) concluded the risk levels remain unchanged. / There are Public Financial Management (PFM) reforms that are based substantially on the EU Assessment of PFM and the FRA. The reforms are implemented through the risk register. This is appropriate given Pitcairn’s tiny population and reasonably straight forward support. It is monitored regularly.
Implementation of audit recommendations	"Unqualified" annual audit	2019 audit report confirmed as unqualified

B1.1. A Fiduciary Risk Assessment (FRA) was carried out in early 2020 and concluded that as for the previous FRA (2016):
- The overall assessment of fiduciary risk is Low to Moderate.
- The assessment of corruption risk is Low and unchanged
- There is a credible programme of reform of PFM, strengthening domestic financial accountability and fighting corruption.

B1.2. OTD’s Governance Adviser supported the GPI in developing a mitigation strategy following the 2016 FRA. This will be updated to reflect comments made in the 2020 FRA report, with the most pressing of the risks identified mapped onto the government’s internal risk register so they can be tracked. For example GPI are encouraged to adopt a series of key performance indicators (KPIs) for its budget management. HMG will provide support to Pitcairn in implemtenting the recommendations made in the FRA.

B1.3. An annual audit, including an island visit, is carried out according to NZ and international standards by External Auditors. The 208/19 audit report and associated management letter confirmed a number of recommendations to be taken forward but again provided an unqualified audit. The Governor’s Office and PIO will work with the GPI to take forward these recommendations.

Lessons identified this year linked to this output and recommendations for future programmes
B1.4. FRA and Audit recommendations/observations will be carried into new programmes to help manage and improve financial management. An Annual Statement of Progress (ASP) of the FRA will be conducted at the end of 20/21.

Output Title	Public Service Provision Maintained.
Output number per LF		2	Output Score	A
Impact weighting (%)?		40	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
Number and range of expatriate experts deliver basic services in line with job descriptions	4 (education, health, social work and police) deliver in line with job descriptions	All 4 posts are filled
Percentage of children receiving full-time education appropriate to age and needs	100% (in school on Pitcairn and at boarding school in NZ)	All children are receiving education either on island or at boarding school in New Zealand

B2.1 All the required expatriate experts are in post on the island. They are all experienced professionals and are contributing to promotion of a safe environment. These posts are central to UKG’s responsibility to ensure child safety on the island and will continue for the foreseeable future, with recruitment from NZ/Australia or elsewhere if required.

B2.2. At March 2020 there were 3 children attending school in Pitcairn and 2 at boarding school in New Zealand.

B2.3 Medical costs - Pitcairn has an aging population, with associated medical needs. The remoteness of the island, and the limited on-island medical facilities (there is a 2-bed clinic with basic resources) means certain prolonged medical care takes place in New Zealand (or Tahiti, French Polynesia for short-medium term care). During 19/20 there have been three long-term medical cases requiring treatment in New Zealand, accounting for over 51% of the total medical budget.
[note] To access the NZ Public Health System, you must be a citizen/resident AND have lived or intend to live in New Zealand for a minimum of 2 years

Lessons identified this year linked to this output and recommendations for future programmes

B2.4 In terms of the deployment of expatriate experts to the island, consecutive child safeguarding reviews (2009, 2011, 2013, 2015 and 2017) have consistently concluded that the deployment of professionals to the island should continue. The next review, due during 2020, is expected to reconfirm this.

B2.5 HMG should continue to meet primary and secondary schooling costs and the medical budget will be kept under continuous review.

Output Title	Regular and reliable sea access to Pitcairn supports reasonable needs.
Output number per LF		3	Output Score	A
Impact weighting (%)?		40	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
Number of times supply ship runs to/from NZ/Pitcairn carrying freight.	4 / New contract in place and operational	4 runs were completed
Number of times supply ship runs to/from Mangareva/Pitcairn carrying passengers	26	22 runs completed (COVID-19 impact – lost 2 in February and again in March 20)

B3.1 The new shipping service was able to provide increased access to the island. However there were increased costs during 19/20 associated with the service, detailed below:
  1. Fixed costs – the contract between the Government of Pitcairn (GPI) and the owners of the vessel providing the service (the Silver Supporter) provides for a daily hire rate of US$7,200. Due to the volatility in the market, there has been a continuous flux in exchange rates resulting in an overspend on this budget line of NZ$244,414.

  1. Fuel costs – a number of factors have caused these costs to be higher than estimated. An overspend of NZD$609,669 resulted from the following:

    1. As the ship cannot shut down its main engine while anchored at Pitcairn or Mangareva due to safety reasons, . this resulted in higher levels of fuel fuel being consumed during the year than wwas anticipated. GPI is currently exploring the installation of a permanent buoy at Pitcairn, which will allow the engine to be switched off and lower these costs.
    2. In a bid to cut global sulphur oxide emissions, the International Maritime Organisation (IMO) introduced a directive effective from 1 January 2020 banning certain fuels. This change resulted in a 26% increase in fuel costs to operate the shipping service.
      [note] http://www.imo.org/en/MediaCentre/HotTopics/Pages/Sulphur-2020.aspx
    3. During the current COVID-19 pandemic, the French authorities introduced stringent quarantine measures, with all passenger ships being refused transit or entry to French Polynesia (FP). This had a major impact on the shipping service to/from Pitcairn; Mangareva (part of FP) is the dedicated port of call for the shipping service, with a 36-hour transit journey to Pitcairn. Until measures are released, the ship can for the foreseeable future only travel directly between New Zealand and Pitcairn, a 14-day journey each way, requiring the schedule will need to be adjusted accordingly. This will mean a reduction in journeys and an increase in fuel and operating costs over those originally budgetted.

  1. Take up of berths/tourism was lower than estimated for the purposes of the budget, with anend of year financial shortfall of NZ$765,749. GPI were planning for demand to provide 230 paying passengers during the year. Only 70 travelled to the end of January 2020 (subsequent figures not yet available). This has resulted in passenger fare income of just NZD$384,251 against projected income of $1,150,000 a shortfall of NZD$765,749. The GPI’s Tourism Department and the Pitcairn island Office (PIO) continue to work with existing tourism brokers to market the ship. It was found that one of the barriers to sales has been the commission GPI pay, which at 5% was considerably lower than the market rate. GPI has since adjusted it to 12% to bring it into line with market expectations and is looking at other ways to incentivise tourism brokers to secure higher volumes of passengers.

  1. The Tourism Department had been looking at increasing tourism numbers and had started to develop a market with China with 2 tours filled with Chinese tourists; this is obviously on hold due to the COVID-19 pandemic. An initial “Dark Skies” tour was sold out, with a tour to visit Pitcairn’s outer islands being 70% filled. These tours are charged at a special rate of $7,500/passenger and achieved overall income of NZ$204,636. However, there was still a shortfall against projections of NZD$20,364. Moving forward GPI will work with tourism brokers to better advertise these tours with a view to increasing passengers and revenues.

Lessons identified this year linked to this output and recommendations for future programmes

B3.2 The costs associated with the shipping service are a significant proportion of the annual financial aid settlement. The schedule for the service, as contracted, has proved very expensive and a significant drain on resources. During the first half of 20/21 we will work with the Governor’s Office to review progress on both sales and revenues, assess what the projections are, and determine what that should mean for a) the number of rotations offered between Mangareva and Pitcairn, and b) how we approach the contract renewal negotiations towards the end of the two year period (late 2020), including considering whether there are alternative options for shipping and access for the island as the current 2-year shipping contract comes to an end in 2021.

B3.3 In negotiating the contract, the lessons learned from the commercial process to agree the previous contract will be fully considered (these have been captured and agreed); this will require early and continued dialogue between stakeholders to ensure due process is followed and value for money considerations are fully reflected.

B3.4. Due to the COVID-19 pandemic and its effect on the shipping service, the planned review will need to take into account global projections for shipping and high-end tourism as part of these deliberations. In addition, the review will now need to be conducted based on the information prior to COVID 19. The existing contract will no longer be viable if tourism numbers fall and the costs of maintaining the contract continue to rise.

B3.5 As part of its own prevention measures the Island Council in conjunction with the Governor has agreed that tourists will not be able to travel to Pitcairn on the Silver Supporter before June 2020 (this may be extended). Those with existing bookings will be encouraged to re-book from September 2020 onwards (again this may be extended).

B3.6 These measures will have implications for the Pitcairn budget as revenue streams will be significantly reduced for some time and the 20/21 budget is expected to increase to take account of this.

.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

C1. The expected outcome “efficient and effective management and delivery of public service provision” was achieved thus ensuring the impact “HMG’s obligation to maintain Pitcairn’s reasonable assistance needs cost effectively is met” was also achieved.

C2. The first outcome indicator: Percentage of children and adults that show excess weight (overweight or obese) as per their Body Mass Index, disaggregated by adult/child and gender is being met and work continues through the Clinic with programmes and protocols in place and personal action plans agreed for each patient. The baseline is 70% and it is expected this will reduce to 40% over time. The island doctor will review whether the current indicator should be replaced and will work with DFID’s Essential Services Adviser on this during 20/21.

C3. The second indicator: Maintenance of child safeguarding oversight continues to be at the forefront of HMG’s mind. There is a substantial child safeguarding framework and a series of bi-annual independent reviews have taken place since 2009, the most recent taking place on island in late 2017. During 2017 a reconciliation process took place with the islanders, using group and one-to-one sessions led by independent child protection experts, the conclusion of which successfully brought the community to a point of reconciliation and an agreed way forward, including a commemoration on island as a symbol of apology, appreciation and forgiveness. The next CSR is scheduled to take place during 2020, although COVID-19 restrictions may have an impact on when.
C4. The third indicator: GPI headcount target numbers is being met with current posts equating to 9.8FTE.

Summarise the programme’s theory of change and major changes to it in the past year

Processes
Annual financial aid review agrees budget settlement and monitors performance against previous budget settlement, as well as mid-year reviews of financial, policy progress and review of progress against log frame targets.
PIO on behalf of PIC manages budget efficiently and effectively to deliver public services on island.
TC officers in critical posts to ensure continued child safeguarding and provision of basic services
Shipping subsidy covers annual operational costs of the supply ship

Outputs
1. Sustained budget management, in line with best practice
2. Public Service Provision maintained.
3. Regular, safe and reliable sea access to Pitcairn.

Outcome
Efficient and effective management and delivery of public services provision.
Impact
HMG's obligation to maintain Pitcairn's reasonable assistance needs cost-effectively is met.

Assumptions
The main assumptions are:
- No major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations. Evidence - medium
- No major unexpected increase in direct and associated costs pertaining to current island trial. Evidence - medium
- No more than one emergency medivac per year and/or no more than average costs of routine referrals. Evidence - medium
- Ability to attract and retain suitably qualified professionals. Evidence – medium/high
- Stability in fuel prices Evidence - medium
- Vessels able to land in poor weather. Evidence – medium/high

Inputs
Finance – DFID funding of up to £4.205m. gPI expected revenues of £0.31m
HR – DFID advisory and programme management.
TA - on island to ensure continued child safeguarding and public service provision. Other TA as required

There were no changes made to the Theory of Change, reproduced here, with the assumptions managed. DFID was alerted late in the financial year to an overspend on medical and shipping costs and this has been detailed earlier in this report. This was unfortunate and the higher costs do diminish the achievements identified elsewhere and reduce levels of cost effectiveness. There were no significant changes made to the logframe. The Pitcairn Island Office (PIO) and the Governor’s Office have committed to closer monitoriong of any future potential overspends and alerting DFID in good time

## D: VALUE FOR MONEY

D1. DFID continued to strengthen its VFM analysis around the Treasury’s and National Audit Office’s concept of the “3 Es” – Economy, Efficiency and Effectiveness and this was applied to the budget aid settlement for 19/20. Overall the VFM performance was as expected and in accordance with the original proposition made in the business case.

Economy: The “off-islander” professional posts (policeman, Family and Community Adviser, teacher and doctor) are all recruited from the New Zealand or Australia employment market by PIO on behalf of the government of Pitcairn. Provision and maintenance of a range of basic public services (e.g. electricity, telecommunications, etc.) and provision of part-time public sector employment is also based on New Zealand costs.

Efficiency: The workforce of 27 carried out 74 Government of Pitcairn posts on a part time basis (including 13 ad-hoc roles). This equates to 9.8 FTE, at a cost of around £116,658. The Administrator continues to work with the Mayor to keep this under review and no new roles should be created without consultation. The costs of PIO represent a fifth of the financial aid costs. Two staff members operate the PIO, which is responsible for all off island logistics, including for example managing and liaising with suppliers and monitoring medical and legal expenditure. PIO also acts as the Treasury for Pitcairn, supporting banking services for the island, producing monthly financial reports. Support costs provided through PIO represent around 63% of PIO’s total costs. The FCO appointed Administrator, has management oversight of all divisional managers, thus improving performance monitoring.

Effectiveness: This intervention is critical to ensure the reasonable assistance needs of Pitcairn continue to be met, including a strong and continuing focus on maintaining child safeguarding.

D2. The UK’s responsibility to Pitcairn is to meet the territory’s reasonable assistance needs for public services. Without financial assistance from HMG, the existence of residents on the island would quickly become untenable; public services would collapse and the islanders would have to return to basic subsistence living or leave the island. There was very little opportunity to reduce the amount of financial aid provided to Pitcairn without impacting on the delivery of basic services or child safeguarding measures currently in place. Although it represents the cost of providing support to such a remote location with such a small population, the spend per capita of UK Aid funds in Pitcairn is by some way the highest in the world (see below) and does occasionally attract criticism from parts of the media.

D3. HMG, through DFID, has provided 90% to 95% of Pitcairn’s budget requirements, since 2004, with a steady increase in the amount disbursed annually, with £4.205m being spent in 19/20. It is worth noting that in terms of funds expended on island (£468,321) this equates to 9% of the financial aid settlement of £3.2m, and equates to a per capita spend of £10,000. However taking the entire budget into consideration, the overall per capita spend for the financial aid settlement increases to £97,791.

D4. Access and shipping costs have risen in recent years. This will continue to become an issue for socio-economic development for the island if access can only be achieved through increasing costs and tourism is barely able to recover costs of any given journey. So there are vfm issues to consider. As highlighted in B3.32 -3.6 above, the costs of the shipping service and whether it continues to be viable will be reviewed during the latter half of 2020.

D45. Given the lack of domestic revenue, financial aid, the level of which is kept under review throughout the year, is able to deliver an effective and efficient public service to the island in a cost effective manner.

E: RISK

E1. The key risks to the success of the programme are regarded as moderate, although it was recognised these do not have an impact on the achievement of DFID’s strategic objectives. Risks were managed collectively by DFID, the Governor’s office, PIO and the Island Council throughout the year.

E2. Two risks were realised with mitigating action taken (see F4 below), both resulting in additional cost to HMG. These related to increased costs in medical provision (off island, primarily New Zealand) and the shipping contract. More details on both these risks are provided in B2 and B3 above.

E3. The most recent Fiduciary Risk Assessment (February 2020) concluded that fiduciary risk as Low to Moderate, the same trajectory as 2016. The mitigation plan will be updated during 20/21.

E4. As Pitcairn is a UK Overseas Territory, the partnership prinicples do not apply to this project.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

F1 The project was delivered within the planned timeframe under the auspices of a Memorandum of Understanding between DFID and the Governor of the Pitcairn Islands with an agreed disbursement schedule for funds. Given the limited resources available to Pitcairn, financial aid was disbursed in advance.

F2. PIO produced monthly expenditure reports as well as quarterly estimates of projected costs. Exchange rate fluctuations between sterling and NZ dollars were closely monitored throughout the year to ensure reasonable assistance needs continued to be met. Given the lateness of alerting DFID to the overspend at the end of the financial year, both PIO and the Governor’s Office have committed to more closer monitoriong of any future potential overspends and alerting DFID in good time.

F3. Additional costs have been incurred by Pitcairn during 2019/20 in relation to medical provision and the shipping service, both of which fall into the category of reasonable assistance needs. As a result, there was additional funding required of £605,000 to 31 March 2020 and a no-time, costed extension was made to the Business Case. Pitcairn has been able to offsets some of these costs by saving in other areas, namely freight income and saving from the on-island budgets (particularly from the Operations Division).

F4. As a UK Overseas Territory Pitcairn has limited access to partners. The European Union, through its European Development Fund (EDF) is the only other source of funding. The EU is supporting efforts to improve tourism development and increase landings by cruise ship passengers, and funded alternative landing facilities on the north side of the island and associated services, including refurbishment of buildings and the provision of relevant tourist transport on island. Implementation of EDF10 and 11 programmes is ongoing.

Date of last narrative financial report	Feb 2020
Date of last audited annual statement	Jan 2020 (for 18/19)

G: MONITORING, EVIDENCE & LEARNING

G1. Progress of the project was monitored regularly through monthly teleconferences with the Governor’s office including the on-island Administrator and FCO colleagues. Monthly financial accounts were produced by PIO. At mid year (September 2019) the Mayor and other stakeholders were asked to provide a more detailed update on progress, particularly against the outputs identified in the logframe.

G2. Pitcairn has a miniscule economic base, with a heavy reliance on government jobs, plus a small amount of tourism, honey and craft sales, supplemented by basic agriculture and fishing. The small resident adult population of 38 is split between men (20) and women (18). Of these 5 men and 7 women are over 65 The islanders acknowledge the importance of the funding HMG provides annually, particularly as 27 of the adult population are employed in government jobs, funded through financial aid. The islanders  are able to provide feedback in a number of ways; meetings with the Administrator, “Town Hall” meetings with the Island Council and Governor, as well as observing Council meetings
[note] At 31 December 2019

G3. The evidence supporting the project has not changed: Pitcairn remains reliant on financial assistance and the UK’s commitment to meeting the reasonable assistance needs of the islanders will not change in the near–medium term. There are no current plans for an evaluation.

G4. As outlined in the summary and overview section, Pitcairn faces a very uncertain future with continuing HMG financial aid required. HMG remains engaged with the islanders in a concerted, meaningful, and frank discussion to understand their ideas and concerns about the future, which will inform any medium-long term vision for the future viability of the Island. External facilitation work carried out in 2019 did not reveal any major new ideas for a vision for the future sustainability of the island. HMG will continue to support the Pitcairn Island Council (the Council) leading its work to determine what the future holds for the community. In parallel, there continues to be ongoing consideration (led by the FCO) of HMGs longer term options for Pitcairn should the current trajectory continue.