Annex A – ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Palestinian Market Development Programme (PMDP)
Country or region targeted	Occupied Palestinian Territories
Type of cost extension	Scale up cost extension
Original project budget	£17.3 million
Original project start and end dates	Oct 21 2013 - Nov 2019
Cost extension value	£2m
New project end date	Nov 2019
Business Case Quest Document No.	3598717

INFORMATION
What is the project’s purpose?
The Palestinian Market Development Programme (PMDP) aims to improve the competitiveness of the private sector in the Occupied Palestinian Territories (OPTs). It provides technical advice and matching grants to share the risk with Palestinian businesses in both the West Bank and Gaza to develop new products and enter new markets. This is in line with our Operational Plan commitment to increase long-term growth and employment by addressing government and market failures.
What is the objective of the cost extension?
The cost extension aims to address the negative impact of the recent conflict in Gaza through a “Gaza Back to Business (GBB)” funding window. This window will target companies which have experienced physical damage in the conflict. The GBB is designed to address the challenges faced by the companies which are preventing them from going back to operations.
What is the additional and total support the UK will provide?
An additional £2 million will be provided to support repairs to damaged businesses, bringing the total support to £19.3 million over six years of which the DFID contribution is £15 million (the EU funds the remainder).
What are the expected results?
The additional £2 million will contribute to Output 1 (Improved private sector skills and innovation): / 110 additional firms will be assisted with grants (to help in repairs or provide technical assistance. / 300 direct jobs will be secured / £7 million additional sales will be registered
What is the approach to implementation?
The GBB funding window will support companies to get back to operations by providing the following services (see Annex B): / Maintenance services / Assessment studies for maintenance/ replacement /renting / Spare parts / Machinery / Installation / training on new machines / Repair and reconstructions of facilities expenses / Covering employees costs / Space rental for relocation for certain period of time (3 to 6 months) / Transportation cost for relocating for Industrial factories / To be able to implement the new window of the programme by 2015/16, PMDP will require some extra short term resources over this period. This will be determined during the final design of this additional fund and it may include additional advisers, coordinators, and transportation. / Implementation and results will continue to be managed by a DFID Project Officer, and quality assured by the DFID Statistics and Evaluation Adviser and the DFID Private Sector Adviser in Jerusalem who is acting as the Senior Responsible Owner (SRO). DFID’s interface with the implementing partner will continue to take place through regular meetings between the Programme Officer and/or the DFID Private Sector Adviser and the implementing partner’s Team Leader, as well as through sporadic but regular visits to the implementing organisation and beneficiary firms (where possible due to the security situation). / In compliance with the Gender Equality Act 2014, the programme ensures that all activities are designed with gender mainstreaming. Under output 1 PMDP has introduced some measures that will encourage more women to apply and improves the chances of women to benefit from the programme, as a result by the end of 2015, 122 women will likely own or manage a business that have benefited from PMDP, this will represent 32% of the total number of beneficiaries. Under output 2 gender dynamics are a key consideration in the operations of the component and are incorporated into market analysis, the design of interventions, and in measuring the performance of those interventions. This means, assessing how the market for a specific good or service is working, such as the market for skills development in the Tourism sector, PMDP works to know a) how women may be participating in that sector, either as producers, consumers, and as labourers, and b) the economic and social dynamics around these roles. These insights are converted into intervention designs aimed at unlocking competitiveness and growth. As for output 3 Interventions and activities are designed carefully to ensure gender equality of men and women when possible. For example, in 2015 the programme implemented capacity building for 46 staff of the Palestinian Investment Promotion Agency. 16 were women, who will be given a higher position within the organization by the end of this training.
Describe any key changes to the original business case?
The key change to the original business case is the focus on Gaza reconstruction after the conflict. The programme has included a new Gaza Back to Business window that will help Gazan businesses which were physically damaged in the conflict to make the repairs they need to get back into business. / The recent war on Gaza has negatively affected the Gazan economy and private sector. For example, over 420 industrial sector companies suffered either partial or total damage. In the agricultural sector, over 36,000 Dunums (1Dunum = 1000m2) were damaged, and over 13,000 green houses were totally or partially destroyed. As a result, unemployment in Gaza is expected to rise even further (from an already high 45.1% in Q2 2014). Unemployment among young people, women and refugees is higher than the average; for example, 60% of young people in Gaza’s labour force were unemployed at end-June 2014. According to the private sector in Gaza, their urgent priority is to deal with the damage in order to get back to operation and restore their productive capabilities. This is in line with the Palestinian Authority’s economic development plan which aims at restoring productive capabilities in Gaza which were greatly affected by extensive damage to factories, agricultural holdings, and other productive assets. / There are high risks around implementing the PMDP in Gaza, which are continuously measured and monitored. The difficult operating environment in Gaza may impact on the delivery of PMDP activities in the following specific ways: / • The continuation of movement and access restrictions leads to a high risk that the jobs created through the programme will not be sustainable, leading to long-term employment. While the UK continues to encourage the Government of Israel to relax restrictions, we judge it is worth providing support in any case, as short-term employment will address chronic vulnerabilities and poverty in the absence of long-term growth; / • There is also a high risk that the maintenance of these restrictions will not allow construction materials to enter Gaza and support repairs to factories and businesses. DFID is attempting to mitigate this risk through our support for the Gaza Reconstruction Mechanism, which has facilitated the entry of some materials; / • The final risk is that funds are used to help businesses with links to terrorist entities (as defined under the UK and EU law). We assess this risk to be low-to-medium due to the presence of robust due diligence and compliance mechanisms in DFID’s existing contract with DAI. All grant recipients are vetted before funds are disbursed, and clauses are included in all grant agreements committing them to complying with the UK legislation.

Annex B

The Gaza Back to Business (GBB) window is designed to support companies to get back to operations. The support is expected to be in the following items:

- Maintenance Services
- Assessment studies for maintenance/ replacement /renting
- Spare Parts
- Machinery
- Installation / Training on new machines
- Repair and reconstructions of facilities expenses
- Covering employees costs
- Space Rental for relocation for certain period of time (3 to 6 months)
- Transportation cost for relocating for Industrial factories

The GBB eligibility criteria will include:
- The project is likely to show results in revitalisation of the business within the period of the PMDP implementation and show signs of sustainability after the completing the PMDP intervention
- The applicant is not trading in illicit areas
- The project does not adversely affect the environment

The PMDP grants ceiling per company will remain the same even with the new window (GBP 50,000), however, instead of the condition to being part of the group to reach that ceiling we are recommending to make the condition to be part of the GBB window. The limitation and ceiling can be summarized as follows:

- Combined ceiling per company is GBP 50,000
- Ceiling for the TA support is GBP 35,000.
- Ceiling for the Gaza Back to Operations is GBP 25,000
  - Maximum of GBP 10,000 for employment
  - Maximum of GBP 25,000 for repair and maintenance

Since this window is generated to support companies to get back to operations as soon as possible the following selection criteria will be applied in selecting the companies to support:

- Period needed to get back to work
- Production inputs availability, e.g. raw materials, labor
- Availability of resources to resume operations e.g. spare parts, replacement equipment , construction material
- Potential for employment

To be able to implement the new window of the programme by 2015/16, PMDP will require some extra short term resource over this period. This will be determined during the final design of this additional fund and it may include additional advisers, coordinators, and transportation.