Annual Review (AR) – Summary Sheet
This Summary Sheet captures the headlines on programme performance and the agreed learning over the course of the review period. It should be attached to all subsequent reviews, in order to build a complete picture of actions and learning throughout the life of the programme.

Title: Ghana Health Sector Support Programme
Programme Value: £67million		Review date: June 2016
Programme code: 203536	Start date: 2013	End date: 2018

Summary of programme performance
Year	2014	2015	2016
Programme score	B	A	A
Risk rating	Medium	High	Major (new risk framework rating used)

Summary of progress and lessons learn since the last review
Ghana’s health sector’s progress: 2015-2016 has been a challenging year for Ghana’s health sector with the deepening economic challenge facing the public sector and revelations of fraud in the central medical store. Despite this most health service outputs have improved slightly and there has been renewed vigour in addressing community level services and sustainable health financing.

At the annual health sector review, the sector programme scored a 3.2 (out of 5) i.e. moderate performance for 2015 using the stakeholder-agreed Holistic Assessment (HA) model. Overall budget allocation and expenditure in 2015 increased over 2014 (albeit as a portion of Government of Ghana budget it has declined). The per capita expenditure has increased from $32.8 in 2014 to $37.6 in 2015.

DFID’s Health Sector Support programme (HSSP) progress and lessons learnt: DFID’s programme scored an A in this annual review (AR). In July 2015 DFID approved the redesign of the lead aid instrument - from sector budget support (SBS) to financial aid (FA) – both earmarked (to community health services and planning (CHPS)) in 4 Regions and performance based FA (for health financing performance). The 2015 AR contains the reasoning for this redesign.

Performance by each of the 3 supported Agencies (National Health Insurance Agency (NHIA), Mental Health Authority (MHA), Food and Drugs Agency (FDA)), has improved over the last year as a result of better governance arrangements. Some significant deliverables this year include scaling up pharmacovigilance within the health system. The technical assistance (TA) Fund, managed by the Ministry of Health (MOH) has produced some valuable policy work but its management needs further strengthening. The resident TA adviser’s term has been completed and DFID and the MOH are currently reflecting on the nature of TA provision and means to ensure it is more high calibre and relevant. The mental health project has improved its management and recently undertaken a strategic review to shape the remaining project period.

Learning from 2015/16: (i) Redesigning aid instruments is complex as is the establishment of, in effect, a new “project” (CHPs support): (ii) addressing accountability is challenging due to different views on the nature of accountability, and varying levels of commitment to doing so: (iii) development partners (DPs) need to be more joined-up in their engagement with the Government about the scale and value of forthcoming development assistance and (iv) comprehensive institutional assessments of the capacity of the Agencies (in particular the MHA given how young it is) should have been undertaken prior support commencing,

The Logframe was revised to: include the focus on CHPs (through a new output); amendment of some milestones to better reflect a realistic, yet still ambitious, level of performance.
The Logframe – and hence this AR – reflects both the progress of Ghana’s health sector as well as progress in the particular areas that DFID supports through the HSSP.

HSSP summary: output, instrument and partner and score
Logframe Output	Instrument	Partner	Score
Advancement to Universal Health Coverage- national Weighting:25% Risk: high	DFID Policy engagement and MOU with MOH for performance based FA	MOH / GHS	A 3 of 4 milestones met
Advancement to Universal Health Coverage- Regional Weighting:25% Risk: high	MOU with MOH for CHPs and Health Financing / Earmarked FA and performance based FA	MOH / GHS	B 2 of 5 milestones met
Strengthened sector wide management and quality assurance systems Weighting:25% / Risk: high	MOU with MOH for TA Fund / TA and policy support	MOH	A 3 of 4 milestones met
Improved mental health Weighting:15% Risk: high	MOU with MOH for Mental health Authority / Accountable Grant with (i) CHAG (ii) Basic Needs	MHA / CHAG / BNs	A 4 milestones met
Improved medicine safety Weight:10% / Risk: medium	MOU with MOH for Food and Drug Agency	FDA	A 3 of 4 milestones met

Summary of recommendations for the next year: grouped in topic areas (details are found under each output). The recommendations are for DFID to deliver against however to do so DFID will negotiate with each partner on their commitment and capture that in DFID/partner agreements. DFID to:
Strengthen the three Agencies
- National Health Insurance Agency: Support the reform of the NHIA through the MOH TA Fund or direct DFID procured TA.
- Ensure the NHIS financial accounting system is operational as soon as possible.
- Monitor the outcome of the Bureau of National Investigation’s case with the Agency and take appropriate actions.
- Mental Health Authority: Continue to support the MHA to prioritise the allocation of the remaining funds due to it to ensure more effective spend on prevention and better treatment.
- Engage in how Ghana can better secure psychotropic drugs.
- Conclude, with partners, on how best to use the remaining £2 million for mental health, whether to vire more funding within HSSP to the mental health project and conclude on whether DFID engages in mental health past the conclusion of HSSP.
- Engage in how LEAP can better cater for those with mental ill-health given their extreme vulnerability.
- Food and Drug Administration: Undertake more monitoring of the range of FDA activities.
- Engage a consultant to provided strategic goverance support to the Agencies and provide DFID with stronger assurance of effective use of DFID funds.

Strengthen the management and effectiveness of the TA Fund managed by the MOH and across the health sector
Support the MOH in securing an ODI fellow and possible other fellows from UK institutions.
- Implement the new safeguards for the TA Fund in full by September.
- Agree with the MOH on new areas of policy level TA and to agree on the modalities of support to those areas. This may include commencing partnerships with UK public health institutions.
- Step up engagement in supporting greater accountability in the sector. This has not been adequately addressed in 2015/16.
- Support the Burden of Disease analysis and ensure the findings steer the planning for the next 5 year development plan and the NHIS reforms.
- Support initiatives to drive other efficiency gains – for example in relation to medicines policy and public financial management.
- Engage a consultant to provided strategic goverance support to the MOH and provide DFID with stronger assurance of effective use of DFID funds.

Strengthen the effectiveness of DFID’s support to CHPs
- Revise the probable CHPS spending schedule for the remaining two years.
- Continue to strongly advocate for better CHPS strategic and operational coordination between MOH and GHS and the DPs.
- Engage more deeply with the World Bank and GHS to harmonise management arrangements
- Accelerate progress with DFID’s management arrangements for the CHPs “hardware” support and DFID oversight arrangements.
- Undertake a light touch fiduciary risk assessment (and consider covering procurement capacity).
A. Introduction and context (1 page)

DevTracker Link to Business Case: addendum	http://devtracker.dfid.gov.uk/projects/GB-1-203536/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203536/

Outline of the programme
What support is the UK providing? The Ghana HSSP 2013-2018 provides financial assistance, goods and technical assistance to the MOH in Ghana and three Agencies. The programme aims to improve the coverage and quality of health services (in particular community level services) through stimulating a more efficient and effective use of resources in the health sector, building capacity of the MOH, and strengthening the coordination and oversight of the three Agencies, and finally addressing mental ill-health.

What are the expected results?
HSSP Impact is a sustainable and equitable health system in Ghana.
HSSP Outcome is quality and equitable health delivery.
HSSP Outputs are (i) Advancement to Universal Health Coverage- national; (ii) Advancement to Universal Health Coverage- regional; (iii) Strengthened sector wide management and quality assurance systems; (iv) Improved mental health and (iv) Improved medicine safety.

What is the context within which UK support is provided?
Current Macro environment: Since HSSP was approved in July 2013, the context has changed with deterioration in Ghana’s economic and fiscal situation. Implementation of the IMF programme is challenging but on track. A Fiduciary Risk Assessment (FRA) of the new financial aid mechanisms confirmed the fiduciary risk to be substantial. The economic situation has influenced funding to the health sector which in turn has stimulated greater profile of sustainable health financing options.

Health sector: update on status. Current status using the 2014 Demographic and Health survey (DHS) was reported in the 2015 AR. Relative to African countries with similar levels of income and health spending, Ghana performs well.

Update on performance and governance – Sector performance is measured by the annual HA. The HA of 2015 showed a moderately performing sector with an overall sector score of 3.2 (on a range of 1-5). This shows a modest improvement on the 2014 score of 3.0. Performance is also judge by delivery of the annual Aide Memoire (AM) commitments – this year 65% of the agreements made at the May 2015 Health Summit were met. The HA and the AM are the two most strategic objectively verifiable tools to measure the sector’s performance. Thus performance against both have now been added to the HSSP Logframe. However, the confirmation of fraud in the central medical stores (CMS) is of major concern, as is slow progress in addressing recommendations made by the Government.

This year saw a major outbreak of seasonal meningitis notable for having a number of causal pathogens and a wider than usual geographical coverage. There were 2,323 suspected, probable and confirmed cases including 219 deaths. The outbreak ended due to a combination of outbreak control interventions including the mass meningitis vaccination campaign and the start of the rainy season.

The Health Financing Strategy Implementation Plan (HFS-IP) is moving and will be the engine behind universal health coverage (UHC) (see output 1.3). The major activity of the IP is the reform of the National Health Insurance Scheme (NHIS). A strategic review of the NHIS was commissioned by President and is on course to report to Cabinet in July (see output 1.4) The focus on CHPS continues with the refreshed policy relaunched. DFID assisted in the development of the refreshed policy through support to the Office of the President under another DFID Ghana programme. DFID, the World Bank and USAID are supporting the major roll out of the policy. The number of functional CHPS zones has increased and CHP facilities share of service provision is gradually increasing albeit there are major concerns with the quality of care (see ouput 2).

Other notable developments include a new policy on antimicrobial resistance, revision of the supply chain master plan, drafting of a number of legislative instruments, roll out of the new-born health strategy and introduction of new vaccines and seasonal malaria chemoprophylaxis strategy.

The nature of HSSP’s support to the health sector is highly relevant (more so as a result of the redesigned instrument) to the challenges of the sector – addressing its current policy areas of need and supporting the critical institutional and governance needs.

## B: Performance and conclusions (1–2 pages)

OUTCOME:
Impact Indicators	Baseline (2011)	Milestone (2016)	Actual (2016)	Progress
Under Five mortality and neonatal mortality (Total; female; poorest quintile)	Total: 82 / Female: 75 / Poorest quintile: 106	No target	N/A (last survey 2014)	No target
Outpatient attendance per capita (National; Northern region)	National: 1.07 Northern Region: 0.62	National: 1.117 / Northern Region: 0.82	National: 1.08 / Northern Region: 0.72	Not met
Health expenditure per capita $	35	37	37.6	Met
Sustainability of NHIS funding	Prediction of 'bankruptcy' by 2013	Completion of the review of the NHIA by the Presidential Task Team by end of June 2016	On course to meeting the deadline by June 2016	Well met
Outcome Indicators
1.Percentage of births delivered by a skilled professional (total: poorest quintile) / Proxy for utilisation	Routine: 56% Survey: Total: 68.4% Poorest quintile: 38.6%	R: 57% / (No survey data available this yet)	55.1%	Modestly not met
2.Proportion of facilities achieving accreditation scores A+, A or B: (proxy for quality of care) / Proxy for quality	22%	40%	56%	Exceeded
3.Nurse population ratio – (and gap between best performing and worse performing drops) / Proxy for equity	Nurse to patient: 1:1,750	Ratio: <1.8 / (no equity ratio milestone set)	Ratio 1:739 / Best: 1: 449 Worst: 1: 946 Ratio: 2.11 (not dropping)	Met

OUTCOME:
Indicator 1: Percentage of births delivered by a skilled professional (total: poorest quintile):
Milestone:57% (health management information system (DHMIS) Progress: modestly not met. 55.1%. The concerning drop in the skilled birth attendance rate (SBR) may be due to inadequate budget provision for primary care as a result of the health budget not rising to the extent projected as well as allocative decisions made by the MOH. A decline in SBR will impact on neonatal and maternal health outcomes. There is no recent maternal mortality ratio to provide a trend although, the institutional maternal mortality rate continues to drop year on year. There has only been a marginal decline in neonatal mortality since 2008. Antenatal care rate has also dropped – although post-natal care rate increased. There has been a slight drop in family planning rate.

Indicator 2: Proportion of facilities achieving accreditation scores A+, A or B:
Milestone: 40% Progress: Exceeded 56% This indicator is a proxy for measuring the quality of care (QoC) provided by Ghana Health Services (GHS). The NHIA periodically accredits facilities to the NHIS and grades each facility’s level of quality. To date, QoC is being maintained despite a reduced goods and services budget and many contradictory anecdotal reports.

Indicator 3: Nurse population ratio - gap between best performing and worse performing
Milestone: Nurse to patient: under 1:800 Progress: Met 1:739. No milestone for equity set. There has been continued improvement in the ratio of doctors, nurses and midwives to the population. Indeed, Ghana does not need to increase midwife production as it had reached the WHO standard workload. The equitable distribution ratio has worsened since 2013 due to a greater increase in the nurse/population ratio in the best performing districts than in the worst. Good progress made on accreditation of health care institutions and scale up of e-learning.
Has the logframe been updated since the last review? Yes it was updated by DFID in April 2016 after significant consultation with partners. Changes include: (i) a new output on CHPs support at a regional level;(ii) some indicators were reassigned (from outcome to outputs); (iii) some new indicators were added and (iv) some milestones were amended to reflect a more realistic yet still ambitious level.

Recommended changes to the logframe indicators and milestone from this AR: small changes required: (i) revise the milestone for 1.3 as annual plans are not set so amend to an alternative measurement of progress; (ii) revisit output 2 milestones with GHS: (iii) amend indicator 4.2 to reflect number of visits or number of people cared for; (iv) consider adopting a new indicator to reflect reducing stigma and discrimination in relation to mental health (this is a core activity of the mental health project yet not being measured); (v) change wording in indicator 5.1 from “drugs” to “all pharmaceutical products” and (vi) renegotiate milestones for 5.3.

## C: Detailed output scoring (1 page per output)

Output title	Advancement to Universal Health Coverage- national
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Yes under new risk management rating amended from high to major	Impact weighting % revised since last AR?	Yes (added one new output so amended all output weights)

Indicator(s)	Milestones 2016	Progress
1.1 Budget execution on goods and services	Budget execution exceeds 62%	A + Exceeded
1.2 Use of new models in planning’(in relation to human resource planning, burden of disease)	staffing norms being used in the annual planning and analysis	A Met Models being used
1.3 Effective implementation of health financing strategy	50% of the annual plan delivered	A Met Good progress against planned stages
1.4 % of National Health Insurance Authority Regional and District offices have automated financial accounting system (175 sites)	30%	B Not met 0%

Indicator 1.1 Budget execution on goods and services
Milestone: Budget execution exceeds 62% Progress: Exceeded The budget for goods and services was 35.29 million cedis however 178 million cedis was spent. This was because the Treasury allocated additional funds during the year to pay for the Government’s share of vaccines as agreed with GAVI but which was not previously budgeted for. The disparity in budget and expenditure also exist for compensation and for assets (the other two budget classification groups) demonstrating the challenge in setting and adhering to priorities. The HFS-IP includes action to address budget discipline.

Indicator 1.2 Use of new models in planning (e.g. in relation to HR planning, Burden of Disease (BoD) etc.)
Milestone: staffing norms being used in the annual planning and analysis Progress: Met. A workforce planning model has been completed. It was used to compare midwife allocations across the regions which is influencing staffing decisions. Work with the UK’s  Centre for  Workforce Intelligence to  conduct a  horizon scanning  exercise is taking longer to complete than planned. Other planning models and tools developed this year include planning for public health preparedness and response. The MoH has started planning for a BoD study.

Indicator 1.3 Effective implementation of health financing strategy
Milestone: 50% of the annual plan delivered Progress: Met. No annual plan was made as the HFS-IP is set in stages, not years. Very good progress has been made against what can reasonably be expected for a year. The policy of capitation[1] has been successfully established in one Region and is now being scaled up in three more Regions. The main driver of the HFS-IP is the review of the NHIS – see 1.4 below. The HFS-IP also focuses on addressing inefficiencies – which have been again highlighted by the 2014 audit and the recent public expenditure review. The public financial management (PFM) committee has been revived and a draft plan developed, as per the HFS-IP, but limited progress made in its implementation.
[1] Capitation: payment arrangement for health care service providers such as physicians or nurse practitioners. It pays a physician or group of physicians a set amount for each enrolled person assigned to them, per period of time, whether or not that person seeks care.

Indicator 1.4 % of National Health Insurance Authority Regional and District offices have automated financial accounting system (175 sites)
Milestone: 30% Progress: 0% - Unmet The NHIS is central to the sector’s performance. The NHIA receives funding from DFID for the capacity development of the financial system, both the “hardware” (oracle financial suite and computers in each district) and the “software” (training of staff for all district and regional offices). The milestone was not met because the software has not been procured yet. This is due to some staff being interdicted as a consequence of an investigation into suspected fraud by the Bureau of Investigation (BNI). The staff managing DFID funds have been reinstated but into different roles, and new staff recruited. The pace has since picked up and the procurement and training is due to take place soon.

This support is a major contribution to accelerating the efficiency of the NHIS (the main driver of the efficiency component of the HFS-IP – see 1.3). The NHIS is broadly pro poor . The absolute amount of funding being managed by the NHIA has increased 43% annually between 2010 and 2014. 80% is spent on claims and is thus a major source of health facilities operational costs. However the current model is vulnerable to fraud and abuse. A major revision of the NHIS is underway to reform it into a real strategic purchaser driving value for money and addressing equity, sustainability and user-satisfaction. This will include a revised benefit package (including prevention services), and more cost containment measures through cost sharing and greater operational efficiencies.

Response to Recommendation for 2015: (i) Amend the Logframe – done
Recommendations for 2016, DFID to:
1. Be proactive in supporting the reform of the NHIA through engagement via the MOH TA Fund or direct DFID procured TA - ongoing
2. Support the BoD dissemination and ensure the findings steer the planning for the next 5 year development plan and the NHIS reforms – by September
3. Support initiatives to drive other efficiency gains – for example in relation to medicines policy and public financial management - ongoing
4. Ensure the NHIS financial accounting system is operational as soon as possible – by September
5. Monitor the outcome of the NHIA BNI investigation and take appropriate action- ongoing

## C: Detailed output scoring (1 page per output)

Output title	Advancement to Universal Health Coverage- at DFID supported Regions
Output number per LF		2	Output score	B
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		New output	Impact weighting % revised since last AR?	New output

Indicator(s)	Milestones 2016	Progress
2.1Number of functional CHPS Zones in the 4 regions supported by DFID	BA: 471 / ER: 484 / CR: 105 / WR: 258	BA: 495 / ER: 383 / CR: 220 / WR: 388 / A.+ Exceeded
2.2 % of births delivered by a skilled professional / (Routine: R) (Survey: S; poorest quintile) in each of the 4 regions supported by DFID.	BA: 62% / ER: 52% / CR: 57% / WR: 55%	BA: 60.8% ER: 51% CR: 55.7% WR: 54.2% / B.Not met
2.3 % of pregnant women receiving 4 Ante-natal Care 4 session in each of the 4 regions supported by DFID.	BA: 63.3% / ER: 48.7% / CR: 63% / WR: 63.3%	BA: 64.5% ER: 50.0% CR: 63.6% WR: 64.2% / A+ Exceeded
2.4 Family Planning Acceptor Rate (Total number of acceptors/women of reproductive age) in the 4 regions supported by DFID.	BA: 35.5% / ER: 32.5% / CR: 28.9% / WR: 25%	BA: 32.9% ER: 26.2% CR: 21.9% WR:20.0% / B Not met
2.5 Under 5s treatment: % of U5s receiving outpatient department treatment for diarrhoea at CHPS level (number receiving treatment divided by number cases disaggregated by the 4 regions supported by DFID)	BA: 24% / ER: 27% / CR: 25% / WR: 33%	BA: 18% / ER: 17.6% / CR: 14.7% / WR: 19.4% / B Not met

The HSSP SBS MOU was amended in November 2015[2]. DFID and the MOH also agreed a work plan for the earmarked financial aid for CHPs. This support is captured in this new output. The funding to CHPs only commenced in early 2016. The 2016 milestones were slightly increased in anticipation of DFID funding. However, given the delays in establishing this new modality and in effect a new project, it is not reasonable to expect that DFID’s support could influence the attainment of the 2016 milestones. DFID funding (like the World Bank’s sister project) will support intensive local level mentoring, supervision and training to enhance the quality of care (which will also booster the use of services).
[2] see the HSSP’s addendum and the last AR for the rationale for the changes to the MOU which reflect a change in focus and aid instruments).

CHPs remains a Government priority with the refreshed Policy being launched in January 2016 and the Government building new facilities. However, the core “good and services” budget used for operationalising primary care has been significantly reduced in 2016. A new CHPs policy steering committee, as well as an operational steering committee, is yet to be established which is a constraint to making best use of the considerable available development partner assistance.

The mixed picture on service usage in these 4 Regions levels mirrors the national picture as evidenced by the HA findings (which are largely drawn from the DHMIS). This performance level is generally attributed to insufficient funding (albeit the expenditure rose) and sub optimal allocative decision making. The poor performance appears to be at odds with the increasing number of “functioning” CHPs facilities. There is an ongoing policy dialogue on defining “functional”.

Recommendations for 2016, DFID to:
1. Continue to strongly advocate for better strategic and operational coordination between MOH and GHS and the DPs - ongoing
2. Engage more deeply with the World Bank and GHS to advance harmonisation of management procedures – financial and performance reporting standards and procedures - ongoing
3. Revisit the 2017 and 2108 milestones with GHS and MOH - by October
4. Accelerate progress with DFID’s management arrangements for the “hardware” support and oversight arrangements - ongoing
5. Revise the probable spending schedule for the remaining two years of support – by August and thereafter regularly

Output title	Strengthened internal management and quality assurance
Output number per LF		3	Output score	A
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Yes under new risk management rating amended from high to major	Impact weighting % revised since last AR?	Yes (added one new output so amended all output weights)

Indicator(s)	Milestones 2016	Progress
3.1% of all commitments made in the strategic Aide Memoire from the health summit delivered	70%	B. Not met 65%
3.2 % of DFID Funded and MOH managed Technical Assistance Plan delivered	80% of the agreed TA Plan delivered	A+ .Exceeded 90%
3.3 Improved overall performance of the sector - proxy Holistic Assessment score	Improve the score from 2015 (3)	A Met .3.2
3.3 Level of TA influence on sector policy and strategic management	100% delivery of annual work plan. Positive feedback	A Met 100%

Indicator 3.1	% of all commitments made in the strategic AM from the annual health summit being delivered
Milestone: 70% Progress: Not met 65%. This is a new indicator – an important proxy for appreciating commitment and action against policy and systems reforms (as described under Summary). The AM from each annual Summit guides strategic direction for the sector over the forthcoming year. Key deliverables from the AM include a review of Accounting and Financial Reporting rules and regulation leading to guidelines on use of internally generated funds in the sector and a strategic framework to manage and monitor antimicrobial resistance.
Indicator 3.2 % of DFID Funded and MOH managed TA Plan delivered
Milestone: 80% Progress: Exceeded 90%. There is a 4 year TA plan, from which annual plans are derived. It is clearly aligned to the 5 agreed areas of support: strengthening stewardship, advancing health financing and public financial management, strengthening human resources for health, procurement and supply arrangements and clinical issues. The plan comprises of over 20 “projects” varying in value and timeframe. Deliverables this year include the production of the public expenditure and implementation review, training of staff in internal audit, support to the CHPs policy, and improving  clinical care.

Over this reporting year, DFID has stepped up oversight given concerns over the governance of the TA Fund. New reporting templates and quarterly DFID and MOH review meetings were introduced. In March, the findings from the first audit of the Fund (2014 funds) revealed some irregularities which have been addressed and resolved. This led to new safeguards including DFID’s endorsement of the work plans and the engagement of a consultant to support the TA Fund and provide assurance to DFID.

Indicator 3.3 Improved overall performance of the sector – HA score (proxy)
Milestone: Improve the score from 2015 Progress: Met. Score 3.2 (over 3.0 in 2014). As for 3.1 this is a new indicator. Note that 2015 score pertains to calendar year 2014 (reported in May 2015) and the 2016 score pertains to 2015 (reported in May 2016). The HA framework ensures the sector is comprehensively, objectively and transparently assessed under 6 objectives each having a composite of milestones which are aggregated per objective. It is therefore the best tool to appraise the sector’s performance. On the 1-5 scale 3.2 represents a moderately performing sector.

Indicator 3.4 Level of TA influence on sector policy and strategic management
Milestone: 100% delivery of annual work plan. Positive feedback from stakeholders. Progress: Met. A UK Department of Health official was seconded to the MOH for 2 years ending in April 2016. The post was managed by the National School of Government International and initially partially funded by DFID with DFID Ghana fully funding (through the TA Fund) the second year. The overall objectives of the adviser changed overtime from providing strategic governance advice to MOH on its stewardship of the sector to a range of more technical inputs to policies. During the second year DFID Ghana took a more active role in the TA’s work. The TA’s work in this year covered some policy areas that DFID have prioritised (such as CHPs and health financing), support to the management of the TA Fund (and some support to the three Agencies) as well as policy areas that DFID is not engaged in. DFID and the MOH are now considering the nature of future TA. This will likely include support to Ghana’s nascent antimicrobial resistance policy, PFM and addressing accountability.

Responses to recommendations from 2015 AR
1. Amend the Logframe. Done. Log-frame was revised and revisions approved in April 2016
2. Conclude the management arrangement for the TA Fund by August to reduce the level of risk and ensure transparent and timely delivery of reports and annual plans. Done. More safeguards were introduced following the audit
3. Ensure the TA Fund’s management improves. Consider the use of an independent fund manager by November if there is insufficient improvement. Done – see above.
4. Ensure (via the new indicator) that DFID monitors the entire sector using the methodology designed and used by all stakeholders (the HA model), annually at the sector’s annual review in May. Done. This is now included as an indicator under this output.

Recommendations for 2016, for DFID to:
1. Implement the new safeguards for the TA Fund in full - by September.
2. Agree with the MOH on new areas of policy level TA and agree on the modalities of support, This will include commencing partnerships with UK public health institutions - ongoing
3. Step up engagement in supporting greater accountability in the sector. This has not been adequately addressed in 2015/16. DFID and MOH need to explore what level of sector accountability to focus on and the nature of DFID support. DFID will explore partnerships with other DFID programmes – current one and potential ones under the new DFID Business Plan. Ongoing
4. Support the MOH in securing an ODI fellow and possible other fellows from UK institutions- by August

## C: Detailed output scoring (1 page per output)

Output title	Improved mental health care delivery
Output number per LF		4	Output score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Yes under new risk management rating amended from high to major	Impact weighting % revised since last AR?	Yes (added one new output so amended all output weightings)

Indicator(s)	Milestones 2016	Progress
4.1 Number of district physicians, medical assistants and community health service providers able to provide mental health care (trained in mental health service) and delivering mental health services	Total 1,500 / female 700	A Met 1,828 / (F 519)
4.2 Number of persons treated in mental health outpatient and community settings	Total 64,000 / Female 36,800	A+ Met 65,438 (F37,300)
4.3 Number of district health facilities providing outpatient mental health care	160 district facilities	A + Exceeded 211
4.4 % of mentally unwell patients' overall health care provision improves (proxy is enrolment into the NHIS)	10%	A Met 10.1%

Indicator 4.1 Number of district physicians and medical assistants and community health service providers able to provide mental health care (trained in mental health service provision) and delivering mental health services. (Total; Female)
Milestone: Total 1,500 700 female Progress: Met 1,827 (F 519). The indicator covers a range of health care providers operating at all levels of the system excluding the three psychiatric hospitals. However, it may also include some community volunteers as well (who are predominantly male). Basic Needs supported the training of GHS staff in some selected Regions and CHAG covered CHAG staff in all its 173 facilities. The milestone was over achieved by 20% because CHAG front loaded trainings. Trainings were mainly for general health care providers (and some volunteers) and not those primarily engaged in mental health care (which DFID also funds).

Indicator 4.2 Number of persons treated in mental health outpatient and community settings
Milestone: 64,000 Female 36,800 Progress: Exceeded 65,438 (F37,300) The indicator and milestone actually reflects the number of visits – not patients. The health management information system now uses the ICS 10 classification of conditions related to mental health which allows for better data management however there is much room for improvement in tracking the real number of cases and the range of disorders. The quality of treatment is greatly influenced by the paucity of drugs.

Indicator 4.3 Number of district health facilities providing outpatient mental health care
Milestone: 160 district facilities (of Ghana’s 216) Progress Exceeded 211 This indicator captures the number of districts where services are now available.

Indicator 4.4 % of mentally unwell patients' overall health care provision improves (i.e. enrolment into the NHIS is the proxy)
Milestone: 10% Progress: Met 10.1%. This indicator is a proxy for measuring the extent to which mentally unwell people are catered for by the social services. The low rate of engagement with NHIS is a concern – not only is their general health not well managed but this indicates an inability to access a range of services making them increasingly more vulnerable.

DFID remains the only DP supporting mental health. This has created a huge dependency on DFID with Government barely contributing to MHA’s operational costs. This situation has been well debated. The rising profile of mental health needs is evident – in large part as a consequence of DFID’s support. The leading challenge to the national programme is the woefully inadequate availability of psychotropic drugs. Further, although (according to Law) those with mental ill-health should receive free services, this is not being realised. Thus, the case has been made to cover mental care under the revised NHIS.

Considerable progress has been made this year in the coordination of results amongst the three DFID partners – the MHA and the two NGOs: Christian Health Association of Ghana (CHAG) and Basic Needs (BNs) (who remain the leading NGOs in mental health). Quarterly collaboration meetings are held which are resulting in more efficiency planning and avoidance of duplication. The NGOs are active partners in MHA’s national mental health summit and other strategic events. The NGOs have met their annual targets. This year the partners have improved report writing however there is scope for further improvement.

DFID’s Accountable Grant with BNs was amended to incorporate an additional £600,000 for a 18 month project to address the mental health needs of the youth and women – in particular in relation to pregnancy and childbirth.

Given £4 million of the £6 million for mental health has been spent, the reality regarding prospects for domestic revenue in the short term, and the probable rise in the prevalence of mental health, DFID (and its partners) are undertaking a strategic review of the status of mental health preventive and treatment services in Ghana. This will inform decisions on how best to use the balance of funds and consider virement within HSSP to scale up mental health care.

 Responses to recommendations from 2015 AR
1. Encourage and monitor the MHA’s better strategic coordination with CHAG and BNs by September 2015. Done and a much more effective relationships now exist.
2. Revise the output milestones. Done. Milestones were revised between the partners and approved in April 2016
3. Ensure the MHA continue to better report and abide by the MOU. Done, no concerns this year.
4. Consider, by October 2015, virement of funds between the three mental health partners to better reflect their ability to deliver and better balance the range of activities across the mental health by component – probably increase the scale of the rural community level engagement. Done. More funds were provided BNs to address mental health of youth and women.
5. Continue to lobby with MHA to strengthen the rights of those with mental ill-health. Done with the MHA now presenting a clear policy on engaging with faith based and traditional healers
6. Strengthen linkages between DFID’s mental health work and other DFID programmes such as the new programme addressing gender based violence. Ongoing.

Recommendations for 2016, DFID to:
1. Continue to support the MHA to prioritise the allocation of the remaining funds due to it to ensure more effective spend on prevention and better treatment – ongoing
2. Clarify definitions of a couple of indicators to ensure complete accuracy of aggregated data
3. Engage in how Ghana can better secure psychotropic drugs - ongoing
4. Conclude, with partners, on how best to use the remaining £2 million – by September
5. Conclude on whether to vire funds within HSSP and invest further in mental health within the remainder of HSSP – by September
6. Conclude on whether DFID remains engaged in mental health past the conclusion of HSSP – by January 2017
7. Amend indicator 4.2 to reflect number of visits or number of people cared for – by August
8. Consider adopting a new indicator to reflect reducing stigma and discrimination. This is a core activity of the mental health project yet not being measured – by August
9. Engage in how LEAP can better cater for those with mental ill-health given their extreme vulnerability - ongoing

## C: Detailed output scoring (1 page per output)

Output title	Improved safety of medicines
Output number per LF		5	Output score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes under new risk management rating amended from medium to moderate	Impact weighting % revised since last AR?	Yes (added one new output so amended all output weightings)

Indicator(s)	Milestones 2016	Progress
5.1 Number of drug safety tests completed	2,000	A+ Exceeded 2,332
5.2 Number of reports submitted by health staff on drug adverse effects	450	A+ Exceeded 697
5.3 Number of local manufacturers with quality management standards in place	6	B not met 0
5.4 % of drugs tested by the FDA that are substandard	3%	A Met 2.5%

DFID’s support focuses on safety of clinical trials, drug registration and inspection and support to the local pharmaceutical industry. DFID’s support has contributed to FDA’s recent ISO accreditation[3] and the recognition that the FDA is a regional centre of regulatory excellence.
[3] ISO - International Organization for Standardization, which offers a standard for operating a firm from management through manufacturing. It is more encompassing than Good Manufacturing Practices standard

Indicator 5.1 Number of drug safety tests completed
Milestone: 2,000 Progress: Exceeded 2,332 products tested. The indicator states “drugs” but it ought to state “all pharmaceutical products”. Of the products tested 936 were imported medical drugs (therefore already meeting quality standards), with the remaining 1,396 being locally manufactured herbal medicines and food supplements (requiring more quality analysis). Excellent progress has been made with over double the number of tests being done compared to the previous year. This is as a result of the enhanced capacity of the laboratory and substantial training including Advance Laboratory Auditing systems, testing the quality of diagnostic kits (for example Blood Monitors, Glucometers), instrument management and preventive maintenance (all funded by HSSP).

Indicator 5.2 Number of reports submitted by health staff on drug adverse effects
Milestone:  450 Progress: Exceeded 697.  Improving pharmacovigilance (PV) within the health system is significantly improving. The FDA has supported PV integration into procedures at health facility level and as a routine GHS monitoring function. In all, 740 health care professionals have been trained.  A new Pharmacovigilance Assessment Tool (PAT) has been piloted in Greater Accra Region with a resulting increase in the number of reported adverse drug reactions (ADR). The PAT is being rolled out nationwide now through the GHS.  The FDA has also developed systems to process ADRs, cataloguing and storing them electronically in a database called “Safety Watch System”.

The UK Medicines and Healthcare Products Regulatory Agency (MHRA) is supporting the FDA to link up to the UK’s system on ADR to enable the MHRA to support them on complex cases of ARD.

In addition, patients and the public are being educated on ADR reporting and management through the Patient Engagement in Medicine Safety programme which includes use of a  “Blue form” (hard copies and on-line) reporting mechanism. There are also roadside billboards, TV adverts and patient information material distributed at facility level.

The pharmaceutical industry (manufacturers, importers and retailers) has been engaged in PV of all marketed products. The first training programme was managed in June 2015 and the second phase in May 2016. The latter was facilitated the UK MHRA.

Indicator 5.3 Number of local manufacturers with FDA quality management systems in place
Milestone:  6 Progress:  Not Met.  The FDA held training to help 80 local manufacturers on product validation protocols, product labelling and reporting writing to respond to FDA

Indicator 5.4 Drugs tested by FDA that are substandard
Milestone: 3% Progress: Met 2.5%.  The rate of substandard drugs in routinely tested groups has radically and positively declined from 30% in 2008 to 3% in 2014 and 2.5% in 2015. Out of the 5 therapeutic drug groups selected for testing, two groups were sent for quality testing after the Truscan preliminary analysis failed them. Of these two groups, one group containing (imported) Amlodipine failed quality testing and the product will be recalled and further importation prevented.

The FDA tested 27 herbal products registered for male vitality out of which 7 products were found to be adulterated. The market authorisation for these products has since been revoked and all those products recalled and administrative charges imposed on defaulting manufacturers and importers.

The FDA provided the evidence leading to the arrest of a Togolese suspected of importing counterfeit Coartem products into Ghana. A search of the suspect’s residence in Lome led to the retrieval of 17,064 tablets of fake Coartem and a range of other items including 120,000 grams of Neomycin sulphate.

Responses to recommendations from 2015 AR
Changes to the Logframe. Done. The log-frame was reviewed and revisions approved in April 2016

Recommendations for 2016, DFID to:
1. Undertake more monitoring of the range of FDA activities - ongoing
2. Change wording in indicator 5.1 from “drugs” to “all pharmaceutical products” – by August
3. Renegotiate milestones for 5.3.- by August
## D: Value for money (vfm) and financial performance (1 page)

 Programme spend to date
Description	Budget	Released to date	Balance
Sector budget support (SBS) – closed in 2015	£47.5m	£14m	£27.5m[1] the balance has been reprogrammed to CHPs (see last row)
Design Budget SBS Health Sector (102) –	£94,710	£93,900	£825
TA for HSSP (for consultancy work) (103) –	£250,655	£109,871	£70,365
Accountable Grant CHAG (104) – output 4	£2.413m	£1.095m	£1.317m
Accountable Grant Basic Needs (105) – output 4	£2,950,599	£1,876,961	£1,073,638
Financial Aid to 3 Agencies (106) – MHA, NHIA and FDA – outputs 1, 4, and 5	£6,400,724	£4,982,924	£1,417,800
Capital Materials (107)	£799,725	£ 95	£799,630
TA Fund – managed by the MOH (108) – output 1 and 3	£4,000,000	£2,900,000	£1,100,000
Support to the GoG cholera outbreak and mitigate the threat of Ebola (109) – now closed	£2.5m	£2.3m	£200,000
Support to CHPS and the health financing strategy (110). This commenced in 2015 – designed balance from SBS. Provided as (i) earmarked financial aid to the MOH (for CHPs) (ii) unearkmarked performance based aid (for progress in advancing sustainable health financing) and (iii) DFID managed funds for procurement and management costs. – outputs 1 and 2	£25m	£1,308,253	£23,691,747
TOTAL	£67,239,305	£30,079,793	£37,159,512
[1] Note: £6million was lost to the programme in 2014 as the performance based financial aid agreements were not met.

In 2015/16 the programme spent £7,723,575. This is less than originally planned due to the change in aid instrument and the time taken to redesign instruments and commence, in effect, a new project under HSSP.

VfM performance compared to the original vfm proposition in the Business Case
VFM of the overall sector: VfM is largely dependent on the economy, efficiency and effectiveness of the health sector’s processes, plans and expenditure. As noted earlier Ghana performs well compared to African peers with similar GNI and per capita health spending. However, there remains much scope for efficiency gains through reforming a greater allocation to primary care, enhancing staff’s accountability, adjusting capital investment to focus on primary level care, improving financial management and reforming NHIS into a real strategic purchaser of care and enhancing its operational models.

The last AR reported on the fire at the CMS in January 2015. The subsequent investigation revealed major corruption in the CMS. The Government is yet to fully conclude on the range of recommendations made including further forensic audits and investigations by the BNI and Police Criminal Investigation Department with a view to prosecutions. The fire has revitalised the national supply chain reform plan however progress has been slower than expected.

Salient points from the AG’s audit findings of the health sector for 2014:
- Budget execution: it is hard comparing expenditure incurred against budget lines. A technical team has been put in place to redesign the financial statements yet this was not shown in the audit.
- Over expenditure on Employees Compensation: The MOH initially projected GHS1.12 billion for employees’ compensation (as per 2014 programme of work) but was allocated less in the actual 2014 budget. However, the expenditure for 2014 again resulted in overspending of about 141%. Even though this was an improvement over the 2013 figures, this suggests that it still was not possible to make a realistic projection of the budget for the sector.
- Consolidated Statement of Financial Position: The amount owed to the MOH increased by 22.8% whilst the amount owed by the MOH to creditors increased by 39% (the latter is likely to be connected to NHIS reimbursements).
- A number of the recommendations from the 2012 and 2013 audits have still not been fully implemented.
DFID, at some DPs, are advocating for a revised PFM action plan. DFID has offered TA to support its implementation.

VfM of HSSP. An economic appraisal was undertaken as part of the re-.design from SBS to earmarked financial aid and performance based aid. This concluded that earmarked FA to CHPS (the lion’s share of the re-designed output) provides a better return based on potential impacts on child and maternal mortality: the benefits are four times greater than the costs. It is not possible to monetise the benefits of the performance based FA aid for HFS-IP, but a better financed and efficient sector will produce better outputs. DFID undertook a FRA of the proposed instruments. It concurred with both the sector and national FRAs that the fiduciary risk of working through Government is ‘substantial’.

TA Fund and support to the Agencies: Some of the TA directly supports the MOH’s efficiency drive such as addressing public financial management through training of internal auditor department and improving staffing norms (which influence placements). DFID is introducing new safeguards which will further the efficient allocations of the TA funding as well as improve the management of the funds. The TA Fund managers were, till recently, used Crown Agents (CA), DFID’s procurement agent, thus assuring them of efficiency and speedy delivery.

The VfM performance of the three Agencies has improved through better planning including procurement planning. Most attention has been provided to the MHA to guide its allocative decision making and operational costs. DFID needs to continue this level of engagement and this will be largely met by a consultant contracted to support the TA Fund and the three Agencies in planning and also providing DFID with assurance through spot checking implementation of activities.

VFM delivered through the two mental health NGOs: Both CHAG and Basic Needs undertake regular market surveys to guide their procurement.

Assessment of whether the programme continues to represent value for money. There is no change to the VfM of the entire health sector. With the redesign away from SBS to other aid instruments, improved management of the TA Fund and greater scrutiny of partners’ deliverables, DFID is now more assured of the value of its support to the sector.

Quality of financial management and asset management. All partners have room to improve on reporting and DFID has invested considerable time this year to guide partners – agreeing templates etc. The sub optimal reporting has influenced the payment schedules and the amounts actually paid. Although the MOUs with the Government governing funding for the 3 Agencies and for the TA Fund does not require audits, DFID requested audits be done by the sector’s auditors and this was provided for.

The MOH: Financial management remains a concern albeit that reporting standards have improved. The TA Fund was audited by the Auditor General in early 2016 (covering 2014 funds). This revealed some irregularities in spending without authorisation and not aligned to planned activities. The misused funds were returned to the Fund. Additional safeguards have been introduced – see output 3.2. No assets to check.

The MHA: DFID has seen a major improvement in MHA financial and narrative reporting during this year with the use of a new template. However, DFID continues to provide intensive support. The 2014 audit for MHA is contained within the health sector audit which identified a breach of the MOU (DFID has addressed this - as detailed in the last AR). All assets have been verified.

The NHIA: The NHIA narrative and financial reports are broadly good. Funds are spent against the intended purpose. An audit covering January 2014 to October 2015 was unqualified. Assets verification is yet to be undertaken. DFID has been assured that no DFID funds are involved in the concerns being explored by the BNI. DFID continues to follow up on the findings of the investigation.

The FDA: The quality of FDA reports needs improvement though they are largely accurate. Timeliness is an issue. An audit covering July 2014 to March 2015 raised an issue related to a breach of the MOU which has previously addressed by DFID and the FDA and raised concerns around the delayed execution of activities. Assets have been verified.

Basic Needs: BNs spent against their proposed objectives and budget, and on time. An audit covering 2014-2015 UK fiscal year was unqualified. All assets located in the Accra, Tamale and Bolgatanga offices were verified.

CHAG – CHAG’s reporting is improving but still room to improve. The 2014 Audit was unqualified. Assets were verified in sample districts.
Date of last narrative financial report MOH	31/12/2015
Date of last audited annual statement MOH i.e. sector wide audit (for 2014)	16/10/2015

E: Risk (½ page)
Output risk rating: Major
Overview of programme risk. Major
Fiduciary risk: A health FRA was completed in December 2012. The financial risk and risk of corruption were categorised as “moderate.” In May 2014, the FRA was updated and the fiduciary risk considered substantial. This mirrors the rating of the national FRA. A FRA in June 2015 of the new financial aid mechanisms confirmed the fiduciary risk to be substantial. A light touch fiduciary risk assessment (possibly including procurement) will be undertaken in 2016 to identify if any further safeguards are required.

Risks: changes and additional mitigation measures
Categories (as per Risk Management framework Jan 2016) Minor (Mi), Moderate (Mo) and Major (Ma), severe (S)	Changes to the risks and DFID actions during 2015-16	Forward projection and additional safeguards 2016 – 17	Net risk
Context
Political will to address systemic issues fades and/or gets undermined by public sector staff / Reform agenda may become politicised during this election year – opportunities and threats will present / Gross: likelihood and impact / Mo/Mo	New Minister appointed in 2015 / Increased political energy behind CHPs and HFS-IP. / The CMS fire in January 2015 offered an opportunity to revive the supply chain reform process. BNI investigation took one year and little progress to date in addressing the recommendations. / Increased interest in addressing public financial management	Continue to support CHPS and HSF. / Work harder to ensure DPs are consistent in messaging over reform priorities. / Strengthen the TA Fund to ensure it works to and for the core reforms identified in the annual programme of work.	Mo/Mo
Government revenue does not rise sufficiently to address ‘new’ priorities such as mental health thus DFID dependency continues / Gross: Ma/Mo	Macro economic situation continue thus no prospect of increasing domestic allocation. / No real change to prospects for MHA raising alternative funding sources (Legislative instrument calls for a proportion of VAT to be applied to mental health to increase revenue)	Unlikely to be any change to this situation. Continue to (i) encourage the MoH and MHA to look at ways to maximise efficiency within existing services (ii) advocate to MOH to lobby MoF to ensure full allocation provided for.	Mo/Mo
Ebola/cholera or another epidemic / Gross: Mi/Mi	Cholera abated. Unusual Meningitis epidemic this year – mixed pathogens and wider geographical spread. / Some evidence of learning from Ebola preparedness influencing emergency public health preparedness. USAID and other donors supporting One Health planning and some support to strengthening Ghana’s International health Regulation (IHR) status	IHR compliance level likely to improve. / Continue to encourage WHO to lead on preparedness and strengthen Ghana’s compliance with IHR. Step up exploring the scale and scope of DFID’s support to public health emergencies.	Mi/Mi
GOG funding for health declines due to macro-economic status – impacting on allocations and spending on G+S and compromising co-financing commitments to Global Fund and Global Vaccine Alliance / Gross: Mo/Mo	Domestic funding increased but as a % of GDP it fell. Allocation to Goods and Services dropped radically. Period of GAVI transition extended.	Support CHPs with USAID and the World Bank over 2 years as a means to support operational costs for primary care whilst also working on supporting better sector planning and costing (BoD study, sector costing with ODI, capacity development in raising domestic revenue and allocations - (via DFID’s Ghana’s Oil and Gas for Inclusive growth programme and the TA Fund)	Mo/Mo
Fiduciary
PFM reforms are not implemented thus increasing fiduciary risk / Gross: Ma/Ma	No perceived change in fiduciary risk. The 2014 audit does not demonstrate any change over 2013’s. / The PFM group was reconstituted and a draft PFM plan developed but no discernible reforms undertaken. / TA Fund used to train internal auditors	Measures for the sector – MOH and partners / Step up PFM reforms in response to the audit findings and aligned to the HSF-IP. / Measures for DFID / Undertake a FRA in 2016 and consider new safeguards / Lobby for more of the TA Fund to be assigned to PFM / Deepen engagement in the PFM group / Lobby for the TA Fund to include accountability initiatives to highlight misuse of funds	Mo/Mo
DFID funds to MOH are diverted and used inappropriately / Gross: Mo/Mo	No evidence via the audits of MOH, three agencies and the NGOs. Some degree of diversion by the TA Fund – DFID have addressed this	Consultant to support the agencies and MOH in management of the funds and assurance to DFID. DFID to step up monitoring and request 2015 audit of Agencies and the TA Fund	Mi/Mi
Programme partners financial probity deteriorates / Gross: Mi/Mi	No evidence from audits or reports. / DFID introduced audits for the Agencies and MOH (not in the MOU with MOH) / DFID has worked with all partners to improve the quality of financial and narrative reports / DFID and MOH agreed new safeguards.	See above box / DFID to follow up on the BNI investigation into NHIA and take appropriate action	Mi/Mi
Operational
MoF delayed the transference of funds from the Bank of Ghana to the MOH for the three agencies, TA Fund thus delaying progress / Gross: Mo/Ma	DFID wrote to MOF requesting direct transference of funds – and this has taken place	Monitor all transfers	Mi/Ma
TA Fund do not spend against agreed plans and in accordance with the MoU thus delaying progress / Gross: Mo/Mo	Some improvement in the quality of planning and reporting. Plan broadly complied with. Audit of 2014 showed some diversion of funds which have now been returned. / DFID and MOH agreed new safeguards	Safeguards: (i) Consultant to support the agencies and MOH in management of the funds and assurance to DFID; (ii)DFID to step up monitoring and request the 2015 audit of the TA Fund and (iii) all plans to be endorsed by DFID.	Mo/Mo
Assets management by Govt inadequate thus increasing wastage / Gross: Mo/Mo	No evidence of changes to management quality / Amended MOUs to accommodate asset responsibility	Continue to monitor annually	Mi/Mi
Government agencies do not spend against agreed plans and in accordance with the MoU thus increasing fiduciary risk / Gross: Mo/Mo	DFID has worked with the Agencies to improve the quality of financial and narrative reports. / Established 6 monthly meetings with Chief Director, Director Policy, Planning, Monitoring and Evaluation, the CEOs of the Agencies and DFID and to review progress	Continue to scrutinise all 6 monthly plans and reports and feedback on them. / Consultant to support the Agencies in their management of the funds and provide assurance to DFID / Undertake more site visits to verify activities / Ensure 2014 audits for the Agencies are delivered	Mo/Mo
Inadequate CHPs strategic and operational level coordination continues leading to wastage of aid / NEW / Gross: Mo/Mo		DFID step up advocating for better coordination , provided any support requested to establish the operational and strategic committees that the Health Minister has committed to.	Mo/Mo
Govt’s response to the Attorney General’s recommendations with respect to the CMS fire are slow and/or inadequate leading to loss of confidence in the Government and potential future fraud / NEW / Gross:Ma/Ma		DFID, with GF and USAID, to continue to advocate for full implementation of the recommendations at MOH level	Ma/Ma
Reputational – an increase in the likelihood or realisation of the above risks will expose DFID to criticism and scrutiny in addressing the mitigation measures

F: Commercial considerations (½ page)
Delivery against the planned timeframe – this is captured under Quality of financial management and asset management above.

Procurement practice: The MoH and the three Agencies have, to date, used Crown Agents to undertake most of their procurement. The three Agencies share their procurement plans with DFID. Most procurement is done on time but there have been some serious delays such as: (i) financial management software for NHIA;(ii) information education communication materials for the FDA and (iii) commissioning the Performance expenditure review for the MOH. The delays lie with the Agencies and MOH not CA. A large portion of the FDA and NHIA budgets relate to procurement of materials.

Using CA has reduced MOH and the Agencies’ staff time, and to some degree, enhanced the capacity of the partners through on-site capacity building. The Agencies and the MOH have confidence in CA and effective partnerships are now well established.

Performance of the partnerships – DFID’s relationship with the 6 partners is good. DFID has worked productively to improve the performance of all the partners through standardisation of reporting writing. Templates have been introduced and more rigour applied to reviewing progress reports. DFID has established joint Agency review meetings with the MOH and the Agencies. Finally, joint quarterly mental health project meetings have taken place. CHAG senior management team have undergone major changes over the team which impacted on progress to some degree. Changes in senior management in the MOH and in MHA may well assist in performance management over the next year.

Asset monitoring and control - see Quality of financial management and asset management above.

G: Conditionality (½ page)

Update on partnership principles
The last general assessment of DFID’s partnership principles, April 2016 concluded: Commitment to the partnership principles is fulfilled, but there continues to be deterioration in the area of public financial management (PFM) and corruption. There are questions about commitment to sound economic management which has direct implications for poverty reduction, There are serious weaknesses within PFM, and the fight against corruption is achieving little. Ghana does well in terms of democracy but this year will be challenging. Ghana performs relatively well in terms of human rights and poverty reduction. The main challenges relate to narrow vested interests and the political will to implement reforms and to follow-through.

The HSSP contributes most directly to the first Partnership Principle: commitment to poverty reduction and MDGs. As the AR demonstrates progress on health status and sector progress has been made as evidenced by the HA score. The share of MOH expenditure out of total government expenditure reached a peak of 8.5% in 2012 but has levelled to 5% in 2014. The recent resurgence in commitment to CHPS, which disproportionally benefit the poor, and the commissioning of the NHIS strategic review is further evidence of addressing poverty. There may be opportunities to galvanise the political energy this year to advance pro poor planning and policy making.

Respecting human rights and other international obligations: HSSP’s mental health project is addressing the rights of those who are mentally unwell. Progress is being made in reducing the stigma associated with mental health though improving society’s acceptance and support to those who are ill and reducing the scale of inappropriate treatment. Strengthening PFM and accountability: there has been increasing realisation on the imperative to address efficiency in the sector and a revival of the PFM working group. The 2014 Audit raises similar concerns to the 2013 audit and partners are advocating for more concerted efforts to be made in addressing these chronic weaknesses. Prospects for reform to advance efficiencies are not very encouraging. Domestic accountability: HSSP has not contributed to accountability as was intended. More work is required in the next year.

H: M&E (½ page)
Evidence and evaluation
No evaluation is planned for this programme. DFID updated the Theory of Change aligned to the revised Logframe – ( approved in April 2016) as some assumptions of how the aid instruments would work did not hold true.

Evidence:  The 2014 DHS provides robust data to measure progress of status and of health care use. Further analysis is being undertaken – some funded by other DFID health programmes. The TA Fund is producing evidence to influence planning for example the BoD study and the recent Public Expenditure and Implementation Review.

Economics:  There are a number of cost related studies underway – linked to the current review of the NHIS. DFID has funded a cost effectiveness study in relation to seasonal malaria chemoprophylaxis.

Monitoring progress throughout the review period was undertaken by the following:
- Monitoring visit to mental health project (to Upper West region in February, to Volta Region in February, to central Region in May 2016).
- Participation in all monthly multi stakeholders sector working group meetings hosted by the MoH
- Participation in the annual Health Summit (April 2016).
- Participation in all the monthly DP meetings.
- Review of all the partners’ reports and engagement in the finalisation of them.
- Participation in the quarterly meetings of the Agencies chaired by the Chief Director at which each Agency presents its work.
- Visit to Upper West Region to participate in the regional review (Feb 2016).
- Participated in the annual UNICEF and GHS review (Jan 2016).
- Head of the DFID Disability team visited the mental health project’s facilities (May 2016).

The AR conducted by the senior health adviser with the programme manager. All partners were consulted. It drew from the evidence and learning from all the monitoring measures detailed above.