ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Growth in the Rural Economy and Agriculture (GREAT)
Country or region targeted	Tajikistan
Type of cost extension	Bridge Funding
Original project budget	£ 19.5 million of which DFID is contributing £ 13.2 million
Original project start and end dates	30.10.2012 - 31.03.2015
Cost extension value	£ 5.8 million
New project end date	31.03.2016
Business Case Quest Document No.	3717368

INFORMATION
What is the project’s purpose?
The project will increase inclusive economic growth in rural Tajikistan: / GREAT contributes to reduced poverty in rural Tajikistan through private sector development and job creation. The project is helping to increase economic growth in rural areas by providing direct support to farmers and rural entrepreneurs at a time of agrarian reform. It works to improve the business environment by widening access to microfinance and increasing revenues from cross-border trade. / The project currently has the following Outputs: / Changing the business enabling environment to facilitate rural economic development; / Increased economic activities in rural areas through a private sector-led approach to providing farmers with access to agricultural inputs, technologies, agricultural machinery, advice and markets; / Improved access to finance and increasing the range of financial products in rural areas; / Enhanced revenues from cross-border economic activities and trading turnover along transport corridors; / Ensuring economic policy decisions are based on evidence and informed by discussion and public dialogue. / The programme has been particularly successful in increasing the number of individual entrepreneurs and rural businesses accessing finance with a total of 49,000 new clients reached, starting from a base of only 800 clients two years ago. The volume of trade turnover for cross-border market activities with Kyrgyzstan and Afghanistan has also more than doubled, from £164,000/month to £469,000/month. / The programme has supported fee-based agricultural extension services: these services have translated into a 20% yield increase (cotton, apricots) for farmers receiving agricultural advice compared with other farmers.
What is the objective of the cost extension?
The programme has made good progress so far, has a demonstrated track record and we plan a second phase of support, in line with the refreshed Tajikistan Operational Plan 2015/17. The objectives of the extension are as follows: / Activities under the current programme did not get underway until January 2013 and some have yet to complete. / To enable an independent programme evaluation to take place in May 2015 to inform the design of a second phase of GREAT during 2015. / A one-year extension until March 2016 will enable a smooth transition to the proposed next phase. It will allow programme activities and momentum to continue during 2015 whilst the second phase of GREAT is being designed. / There are a number of new initiatives that require testing and further development before becoming sufficiently robust to take forward to the next phase. / The GREAT programme is co-funded with the German Federal Ministry for Economic Cooperation and Development (BMZ), with the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) as the implementing partner. Our main Tajik government partner, the Ministry of Economic Development and Trade, wishes the programme to continue and is seeking a four–year successor phase. The contents and duration of this future programme will depend on the findings of the evaluation and the outcome of a programme design mission. / Since the programme’s start two annual reviews (the latest in January 2015) conducted jointly by DFID and GIZ have given the programme A ratings. / This one-year extension will: / Continue the implementation of, and modify a range of, current activities, / Phase out activities and components that have achieved their objectives, or which have led the project to explore different options, / Enable the testing of new innovations and activities in readiness for the next phase. / Given the high level of confidence in the expected results from the evaluation study, this extension is seen as a transitional year allowing for the development of a successor programme. DFID in Tajikistan has had a long standing investment in the field of rural growth. GREAT and its predecessor programmes support DFID’s economic development priorities by contributing to job creation and improving access to finance. GREAT directly contributes to DFID’s three pillars of support for Central Asia; private sector development and growth, promoting democracy and better governance; and regional trade, growth and cooperation. GREAT is working to promote private sector-led economic growth and regional trade. / Compliance with Gender Equality Act. Women play an important role in the agricultural sector as women make up 70% of farm labour with many women also dependent on off-farm income generating activities. Women’s income generating activities are constrained by social and gender norms with strict male control exerted even from a distance. Such control leads to unequal access for women to both labour markets and resources, severely hindering income generating capacities. The programme will contribute to women’s economic empowerment by supporting women-led enterprises and farms enhancing their role in establishing business enterprises and increasing women’s incomes. A gender disaggregated Monitoring and Evaluation system will monitor progress made towards women’s improved access to finance and advisory services. / Next steps for GREAT / DFID commissioned a Private Sector Analysis in 2014 to identify sub-sectors for possible future interventions under a successor programme. In addition DFID and its partners have drafted an outline programme for the next phase, based on experience gained during the implementation of GREAT. This incorporates project internal learning exercises and reviews, feedback from the Tajik government and discussions with programme beneficiaries. / An external evaluation/review will be conducted in May 2015 with a two-fold task: / To assess programme performance and impact and; / To provide lessons and recommendations to inform the design of the next phase of the programme. / .
What is the additional and total support the UK will provide?
Total cost of the first phase up to March 2015: the total cost of the programme, before this extension, is £19.5m of which DFID has contributed £13.2m and Germany the remainder. DFID expenditure to date is £12.037m, with £1.163m still to disburse for agreed activities that are not yet complete. / Cost of the extension: together with the balance of funds unspent, the cost of a one year extension is estimated at £7.9m. DFID will provide £6.963m of this sum (an additional £5.8m plus the £1.163m unspent) and Germany will provide £1m. The extension would run from April 2015 to March 2016 and would take the overall DFID programme budget from £13.2m (initial DFID contribution) to £19m (initial DFID contribution of £13.2m plus the cost of extension £5.8m). / Germany’s longer term commitment: in addition to an additional £1m for the one year extension, the German government has committed an initial £6million for the next phase of the programme after March 2016. / GREAT budget for April /2015- March 2016 – Breakdown of DFID £6.9 m contribution: / 1GBP = 1.2783 € (February 2015) / Output Output name Additional budget requested (EUR) Underspent (EUR) Total (EUR) Total (GBP) / Output 1 Business Enabling Environment 655,490 655,490 512,782 / Output 2 Rural Economic Development 1,912,477 2,857,088 4,769,565 3,731,178 / Output 3 Micro-finance & Financial instruments 765,818 765,818 599,091 / Output 4 Cross Border Economic Relations 1,234,854 1,234,854 966,012 / Output 5 Evidence Based Policy Making 280,125 280,125 219,139 / Management and Programme M&E Management, M&E (Monitoring & Evaluation) 938,914 938,914 734,502 / Sub-total 5,787,678 2,857,088 8,644,766 6,762,705 / DFID managed External evaluation and analysis 200,000 / TOTAL 6,962,705 / Overall DFID contribution for the cost extension: / EUR GBP / Estimated DFID funds remaining from current phase 1,486,287 1,162,706 / Additional DFID funds needed for extension (4/2015-3/2016) 7,158,480 5,800,000 / Total 6,962,706
What are the expected results?
The GREAT private sector study carried out in 2014 highlighted two major economic sectors in Tajikistan: agriculture (including agro-processing) and energy efficient materials and services in the construction sector. These sectors have been selected for their GDP and employment relevance, their positive growth trends, the potential to improve living standards of the rural population as well as a sound understanding of these sectors by DFID and its partners. The attached logframe sets out the milestones for the extension in detail. Key points include: / Outcome / The overall outcome is “Economic growth increases and is more inclusive”. Inclusive rural economic growth will be achieved by providing direct support to farmers and rural entrepreneurs at a time of agrarian reform, by improving the business enabling environment, by widening access to micro-finance, and through increased revenues from cross-border trade. / Outcome indicators include an increase in private investment as well as an increase in the value of supported value chains (e.g. cotton, energy saving products) : / The scope of the loan portfolio used for private investment will continue rising with loans for private investments increasing by 95% over the 2012 baseline and a further 20% up on 2014. / Sales value (in terms of real prices) of producers in two supported value chains, both agricultural and non-agricultural, is maintained at 30% above baseline despite currency depreciation. / Outputs / Output 1 Measurable changes in the business enabling environment / The current output indicators have been revised so that by April 2016 : / Some 40% of business people interviewed confirm that the business environment reforms launched by the Government during the extension year had a positive impact on the value of their business sales; / Up to 5% more licenses for business, land and construction are issued; / An additional 375 members of Business Associations receive high quality services by the Associations. / Output 2: Economic activity in rural areas increases / As described earlier, the programme extension will introduce some changes in approach to implementation in readiness for the next phase. It will continue the diversification of agricultural advisory services into crops other than apricots and cotton, moving to increased production of fruits, vegetables, nuts, cotton and food staples (potato, wheat). Agricultural extension services without any programme subsidy will continue to be offered based on a fee to farmers and their organisations. These services are modular, allowing the farmer to demand those that most meet his needs and ability to pay. This will result in the following output indicators: / Farmers receiving agricultural advice expected to have higher yields (compared to non-contact farmers). A yield increase of 30% in lowland areas and 15% in the upland areas; / The area of land covered by advisory services increases by 2,979 ha in lowlands (an additional 7,278 families) and in uplands by 698 ha (an additional 7,324 families); / The agricultural advisory cooperative, SAROB, will attract 10 new members while 105 new members will join the 26 new agricultural machinery cooperatives; / 100 ha of alternative crops to be cultivated with programme advice on areas that traditionally grew cotton, providing a more varied income source; / An additional 40 businesses in non-agricultural value chains receive sector-specific training (e.g. food processing techniques, food safety or energy-efficient production) and add innovative products to their portfolio. / Output 3: Access to financial products improves / The extension will signal a move away from increasing the number of micro-finance providers towards assisting businesses to access a wider range of products and financial packages that address more closely their needs. The extension will: / Assist 2,100 businesses to identify and access innovative, tailor-made financial products and assist the disbursement of 1,500 start-up loans; / See a total of 60,000 new credit clients (a 15% increase) resulting from programme activities; / Support an increase in individual saving accounts by 154,000 or 15%. / Output 4: Revenues from cross-border and transport corridor activities increase / The overall cross-border trade environment will be strengthened through the implementation of recommendations from an international trade conference (November 2011) and regular meetings between bilateral commissions covering the Afghan-Tajik and Kyrgyz-Tajik border regions. These are not additional results but they could not be delivered earlier due to violent border conflicts which have now ended. / The extension will also translate into increased revenues from supported roadside services and cross border market activities: / The cross-border markets and businesses will increase their turnover from £164,000/month in December 2012 to £493,000/month by March 2016. / The revenue from businesses along transport corridors increases to £27,000/month from a baseline of £15,000/month in December 2012. / Output 5: Economic policy decisions and regulations are taken based on evidence / This output was funded initially by BMZ only, but now DFID wishes to support it as well to strengthen the coherence of the BMZ/DFID collaboration on GREAT. The output aims to improve economic policy by rooting it in sound analysis and evidence: this will support the key objectives of GREAT as better economic policies in turn will help improve the overall business environment. / The two main areas of work are a) improving analytical capacities of the government and b) providing a platform for government agencies, research institutions and business associations to discuss economic analyses and prognoses. / Under this output, the programme will support an annual Dushanbe Economic Meeting in April. This meeting will focus on agricultural value chains: government agencies and research institutions will have a platform to present their “evidence” and analysis of major obstacles for strengthening food and agri-businesses. The analysis and the discussion will help the programme in further developing its approach. / The analysis undertaken can also be used to model the impact of policies and other developments such as Tajikistan joining the Eurasian Economic Union and understanding the effect of the economic slow-down in Russia on Tajikistan’s economic development plans. / Anticipated results include: / MOEDT better equipped to use economic analysis to inform policy decisions. / Five analytical reports produced, with at least one being directly influencing new policy. / External evaluation and analysis / As with the initial Business Case and budget, DFID will commission a follow-up of the external evaluation held in 2014 as well as assessments in line with Annual Review recommendations (gender analysis, household economy analysis). With the potential deterioration of the economic situation in Tajikistan, the programme will strengthen GoT’s capacity to measure and anticipate changes and shocks at household and community level.
What is the approach to implementation?
The changes envisaged under this programme extension will continue the shift away from support to sector services (such as the micro-finance sector) to a focus on selected value chains (ie supporting improved agricultural production and processing of specific items, through to their marketing and export) such as cotton, apricots or wheat. This will: / Improve the competitiveness of those businesses that have the potential to improve income and increase employment by focusing on promising value chains to strengthen production, processing and commercialisation; / Develop and strengthen business models for cross-sector services; / Increase the ability and confidence of the private sector to advocate for its interests and the need for improvements in the business environment. / Activities which are not consistent with the future focus of the proposed follow-on programme will be scaled back. This will affect mainly the supply driven development of products and other activities in the financial sector such as mobile banking. Other programme activities will be harmonised with the value chain approach. / The programme will continue to focus on ensuring that economic development is more inclusive. In addition to their contribution to economic growth, the programme will select value chains that have a clear potential to create jobs and livelihood opportunities for small farmers and entrepreneurs. Poorer households will benefit from the programme either as consumers or as producers, suppliers and employees. Selected businesses will receive support to strengthen their processing and marketing capacity: this will add value to local production (e.g. fruits and vegetables production) and create market opportunities for local farmers and smaller scale producers. The project will only provide direct support to a limited number of enterprises and farmers. Instead it will support a business environment that strengthens value chains and market based services. / Programme management / GIZ will continue as the implementing partner. With a view to the next phase, GiZ’s programme management structure will transition towards three flexible implementation teams that: / develop capacity of value chain actors directly (farmers, businesses, traders, factories) through agricultural advisory services, business development, access to loans, market access, / strengthen and build services that support actors in the value chain (such as service oriented business and farmers associations, quality improvement services) and / support the improvement of the business environment through policy analysis, monitoring, public- private sector dialogue, and regulations that support community based producer groups. / Programme Delivery / GIZ will continue to implement the programme both directly and through selected partners. The programme will also engage with lead firms in selected sub-sectors and value chains (e.g. cotton, dried apricots) to provide tailored services, technical advice and products. / Advice to farmers will continue to be provided through a grant agreement with SAROB, a cooperative of agronomists. The challenge is to achieve commercial viability while continuing the services it offers to small holder farmers. Additional market actors such as input dealers, buyers and traders who are offering relevant services and products to farmers will be identified. Having successfully increased access to finance with a strong uptake of new clients, the programme will continue working with a range of institutions, focusing on building management capacity. Outputs 4 and 5 with a higher political profile will continue to be directly implemented by GIZ staff. Transport corridors and cross border issues will work through cross-border cooperation support centres and selected NGOs at a regional level. A recent external audit of these centres has confirmed that funds are being managed effectively. / Coordination / Other development partners (the European Union, World Bank, European Bank for Reconstruction and Development and the International Finance Cooperation) are increasing their engagement in private sector development in Tajikistan. There is sufficient space for all. The programme extension offers an opportunity for more detailed interaction and an agreed way forward between partners which builds on their experience and respective strengths. / The GREAT programme will continue to be represented at relevant sector level working groups of the Donor Coordination Council where it interacts with the Tajik government. While mostly technical, these working groups also discuss the political economy aspects of agrarian reform and private sector development. Women’s Economic Empowerment / The programme has measured the number of women benefitting from better access to finance, advisory services and trade opportunities. While the overall figure of women benefitting from the programme has increased, it is now important to understand better the actual impact of the programme on women, particularly how GREAT is supporting their long term access to finance or business advice. The extension will provide an opportunity to explore this further and ensure the findings inform the design of the next phase. / Climate change / The support services being provided through the programme will also strengthen the messages and eventual practices around climate resilience, especially in agriculture but also in energy efficiency value chains. The programme will improve performance of the selected sub-sectors and value chains within these sectors by collaborating with private sector companies, entrepreneurs and other development partners.
Describe any key changes to the original business case?
The original business case remains valid but there will be a shift in focus away from support to providers and more towards farmers, (micro and small scale) entrepreneurs and traders. This will ensure that services are more demand driven and flexible in the selected value chains. / Logframe / The logframe has been updated after each review to reflect recommendations. It has been further updated to reflect the new targets expected during the extension phase and will be further revised following the external evaluation and ahead of the new business case. / Risks / The risks identified in the business case are still valid, from poor implementation of reforms to the impact of a general stagnation of remittances from Tajik migrants in Russia. The fall of the Russian rouble and the contraction of remittances have had a limited impact on the programme to date but the Russian economy remains volatile. A major reduction in remittances and higher risk of migrants returning to Tajikistan could affect the programme at both outcome and impact levels. / In addition to risk discussions at monthly programme meetings, the overall risk rating will be re-assessed in the next progress report in six months’ time. / The most recent Annual Review of GREAT identified the risk that the status of women could deteriorate with a large number of female-headed households depending on shrinking remittances from Russia. This will be addressed through the external evaluation and a gender analysis of the programme. Both will inform future programme design to ensure it pays greater attention to ensuring women and girls benefit.