Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: ZAMBIA SOCIAL PROTECTION EXPANSION PROGRAMME
Programme Value: £38m		Review Date: 24/06/2016
Programme Code: 200625	Start Date: 01/04/2010	End Date: End Date: 31/03/2020

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score	82.5	A+	A	A	B	A
Risk Rating	M	H/M	H/M	H/M	H	Major

Summary of progress and lessons learnt since last review

Social Protection is now well recognised as a key strategy to support inclusive economic growth. Social cash transfers specifically have proven to be an effective means of addressing extreme poverty. This impact continues to be seen through the Social Cash Transfer (SCT) programme which is supported through the Zambia Social Protection Expansion Programme (ZSPEP) .

The programme faced challenges during 2015. Firstly, the expected increase in the budget to allow expansion did not occur. Secondly, disbursement of funds from Ministry of Finance to Ministry of Commmunity Development were erratic, resulting in delays of transfers to recipients of over 4 months. This had a major impact on the effectiveness of the programme.

In response, cooperating partners (CPs) worked with Ministry of Community Development and Ministry of Finance to advocate for increased and more regular funding. DFID and other donors also provided additional bridge funding to protect recipients in return for continued GRZ commitment. This commitment was seen in improved funds flow to the programme in the later half of the year (with 74% of funds disbursed compared to 70% in previous year) and a return to increasing budget allocations for 2016 and beyond.

In 2016 MCDSW has continued to scale up the Social Cash Transfer Programme to reach more extremely poor households (180,000 to date with an additional 62,000 expected to be added from 28 new districts by June 2016. They have also to develop strategies to improve communication (advocacy activities) with the Ministry of Finance as well as being more proactive in making follow ups on disbursements.

The increasing scale of the programme is putting pressure on implementation and financial management systems and strengthening these will be a focus in the coming year. Forthcoming general elecations and El Nino related drought are additional risks that need to be managed.

Summary of recommendations for the next year
- MCDSW to actively implement the recommendations of the 2015 FRA
- CPs to continue support to system strengthening prioritising payments, MIS and grievance mechanism
- Clearer communication on programme objectives and implementation (targeting, transfer value) in the run up the General Elections in August
- SCT’s to response to increased humanitarian need resulting from El Nino related drought including increase of transfer value and scale up to full coverage in drought affected districts.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Programme Memorandum – not on DevTracker
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-200625/documents/

The latest Living Conditions Monitoring Survey (LCMS) shows a reduction in poverty headcount from 60.5% to 54.4%.[1] However, rural poverty remains stagnant at 76.6%, and inequality and poverty gap (depth of poverty) are on the rise. This is despite over a decade of macroeconomic stability, an economic growth rate of over 6%[2] per year and reclassification as a lower-middle income country. Economic growth has not been inclusive, as a result there has only been a marginal decline (6%) in poverty rates since 2010. It can be seen that poverty is unevenly distributed nationally with rural areas having a much higher headcount poverty rate ( 76.6)% compared to 23.4% in urban areas. Zambia did not meet the MDG 1 target to reduce by half the proportion of people living in poverty and hunger[3].
[1] Central Statistics Office (2016): Living Conditions Monitoring Survey 2015. Lusaka, Zambia
[2] Ministry of Finance Data Portal: Economic Performance: http://zambiamf.africadata.org
[3] UN Stats: MDG Indicators; Country Level Indicators - Zambia: http://mdgs.un.org/unsd/mdg/Data.aspx

Women and children are among the most affected by poverty. From the total child population 0-18 years old, 65% lived in poverty in 2010 (and 46% in extreme poverty), representing around 4.6 million children[4]. About 85% of all poor children live in rural areas. Child poverty is closely linked with chronic malnutrition. The cumulative effect of this results in stunting, at present 40% of under 5 children in Zambia are stunted, which represents a mere 5 percentage point reduction from 2007[5].
[4] Central Statistics Office (2012) Living Conditions Monitoring Survey Report 2010. Lusaka, Zambia.
[5] Central Statistics Office (2014): Zambia Demographic and Health Survey 2013 -14, Lusaka, Zambia

In 2015 Zambia’s sustained economic growth came under pressure, largely due to a fall in commodity prices which saw a reduction in the price of copper on the international market. This led to a significant depreciation of the Kwacha against the US dollar, inflation reached double digit (22.2%) [6]in the first quarter of 2016 up from 6.9% during the same period in 2015. Lack of investment in generation capacity and two consecutive poor rainy seasons have affected power supply and resulted in nationwide electricity shortages which have affected overall productivity of industries. As a result the Zambian government has been facing serious fiscal challenges and is considering an IMF programme in the near future.
[6] Central Statistics Office (2016):The March Monthly Bulletin, Lusaka , Zambia

MCDSW launched the National Social Protection Policy (NSPP) in 2014 out of recognition that social protection is a key strategy to improve the quality of life of the poor[7]and support inclusive economic growth. For Zambia, Social Cash Transfers (SCTs) have proven to be an effective means to directly tackle poverty and hunger as can be seen from the results of the impact evaluation.
[7] Ministry of Community Development Mother and Child Health (2014): National Social Protection Policy

DFID has been supporting the Government of Zambia (GRZ) to implement the SCT programme since 2005. Current support has been through a £38m programme which provides direct Financial Aid to MCDSW and Technical Assistance (TA) through UNICEF. As part of the TA, DFID funded a multi-year impact evaluation. The results have consistently shown that SCT are effective in reducing extreme poverty and ensuring household food security. Positive impacts have also been seen on a range of other areas like health, schooling, child material well-being and asset ownership.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The expected outcome of the SCT Programme is to ensure that, “Households receiving social cash transfers have improved standards of living by 2015.” Progress against the outcome has been measured through the impact evaluations for the Child Grant (CG) and Multiple Categorical Grant (MCG) which were conducted between 2010 and 2015. The results from the different surveys rounds have remained consistent over time and are summarised below.

Outcome Indicators	Baseline 2010	Milestone 2015	Achieved 2015*
Food security: % of hhs receiving SCTs having no more than 1 meal per day	21%	10%	Exceeded: 1% / (5pp programme impact)
Education: School enrolment in hhs receiving SCTs	64% of school age children enrolled	90% of school age children enrolled	No programme impact
Health: Proportion of people reporting illness in previous 2 weeks	14%	10%	No programme impact
Child wellbeing: % of children in hhs receiving SCTs with all 3 material needs (pair of shoes, change of clothing and blanket)	11%	15%	Exceeded: 71% (32pp programme impact)
Women's empowerment: % of women making sole decisions (in 4 or more out of 7 scenarios given)	61%	80%	No programme impact: (large impacts on savings rates and amounts saved)
Improved livelihoods: Proportion of hhs with livestock (chickens)	48%	No milestone	Exceeded: Improved 61% (26pp programme impact)

 * 48 Month Child Grant Impact Evaluation (2016)

Impacts on food security, child wellbeing and livelihoods have been exceeded. There was an improvement on education and health, however, there was no difference between the treatment and control group. As such this improvement cannot be attributed to the SCT programme.

Programme outcomes are closely linked to the expected impact of the programme. At impact level, the programme aims to reduce extreme poverty in districts covered by the social cash transfer. The impact is measured through the poverty gap. The results of the 48 Month survey demonstrate that the milestone for 2015 was achieved for SCT recipients.

Impact Indicator	Baseline 2010	Milestone 2015	Achieved / 2015
Extreme poverty gap index in hhs receiving SCTs	63%	43.5%	42% (10pp programme impact)

Overall output score and description: A – Outputs have met expectation.

The performance of the programme has improved steadily since the last annual review. A decision was made to carry out this annual review early to assess the extent to which the concerns raised in the last review had been addressed and to inform the development of a new programme of support. Despite challenges in implementation last year, MCDSW received 74% of the total budget allocation by end of 2015, compared to 70% in the previous year. GRZ funding, coupled with additional funding from DFID and Irish Aid enabled the ministry to normalise payments to recipients. GRZ also increased the 2016 budget allocation to K250m which has also facilitated further scale up to an additional 28 new districts. To date (first quarter) Ministry of Finance has disbursed 43.7m (17%) of the total allocation which is an improvement from where they were in the same period last year.

Key lessons
- The importance of timely disbursements from MoF now that the programme is majority GRZ funded as any delays have a large impact on programme delivery and impact
- Need for strengthened fiduciary risk management and implementation capacity given large scale of programme

Key actions
Develop and implement a joint advocacy strategy (MCDSW and CPs) to inform continued lobbying for full and timely disbursements.
Proactive implementation of FRA action plan under senior leadership by MCDSW.
Strengthen implementation systemsprioritising payment and grievance mechanism and MIS with continued work on other systems such as targeting and registration, Develop a new programme for continued support to SCTs, broader Social Protection and Humanitarian response.

Has the logframe been updated since the last review?
Yes, the logframe was revised as follows:

- Revise output 2 to ‘GRZ (as opposed to MCDMCH) implements SCT programme in an efficient and sustainable manner’ given importance of MoFNP funds disbursement. Done
- Change the weighting of output 2 from 60% to 40%. Not Done - this was meant to put more weight on Output 1 which is within DFID’s control. However, this revision will be made for the PCR because DFID Zambia is in the process of developing a new Social Protection programme which will fully take on board the suggested revisions to the logframe. In the new programme logframe, the current outputs will be shifted to the outcome level since they are more within MCDSW or government’s control.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Number of targeted recipients receiving regular Social Cash Transfers
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones ( by Dec 2016)	Target 2016
1.1 No. of recipients receiving timely and regular payments (DFID attributed); % female (on 31st December, except baseline which is pre-programme)	225,000 (18,800); 60% female	On track to be exceeded: 180,000 (69,777) (current) with an additional 62,000 enrolled bringing total to 242,000 expected by June 2016 ; / 60% female; 12% disabled
1.2 No. of beneficiaries of cash transfer programmes	1,125,000 (90,000)	On track to be exceeded: 900,000 (348,885) currently with 1.21m expected by June 2016 in line with above
1.3 Maximum delay in making transfers available to recipients	4 months	Met: transfers payments currently up to date (Jan-April)
1.4 Proportion of recipient households in extreme poverty / extreme food insecurity (targeting assessment).	Not measured	Not measured

Key Points
The programme is on track to exceed the milestone for Indicators 1.1 and 1.2. The programme currently reaches a caseload of 180,000 households and is in the process of enumeration of up to 62,000 additional households in 28 new districts to bring the total to 242,000 by June 2016. Discussions have started to increase this further in response to El Niño related drought.

Indicator 1.3 is largely determined by the availability of funds at MCDSW. The additional funds from the CPs and improved flow of disbursements from the Treasury have enabled MCDSW to normalise payments to recipients up to April and secure funds to pay transfers to the current caseload up to June 2016. To prevent delays in funding, the ministry has continued to actively engage with MoF by making regular follow ups when funds do not come through.

The last AR highlighted that there was a poor understanding of the dependency ratio and welfare criteria and that they were concerns around the inclusion of households with fit-for-work adults. MCDSW has since revised the targeting mechanism for the 2016 districts in a shift to a more categorical targeting system based on age or disability. Initial feedback from the field indicates that the new targeting criteria is better understood by the community and potential beneficiaries. However, more concrete evidence will be available once the Ministry carries out validation of selected households in June 2016.

The proportion of women recipients has remained steady at 56% following a change in the targeting mechanism from Child Grants and Multiple categorical to the Inclusive model. The percentage of households with persons living with disabilities has also remained stable at 9%.

Despite improvements in getting SCTs to needy recipients on time, food price inflation threatens to undermine the value of SCTs. The impacts of El Niño related drought has also increased need across the West and South of the country. GRZ, with possible support from CPs is considering supporting further expansion of the SCT programme and increasing the transfer value in response.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were several recommendations from last year’s Annual Review around the development of a joint advocacy strategy to build public support for the programme. Actions to date include:
- Social Potection has been identified as one of DFID Zambia’s priorities for policy influencing work
- MCDSW and other partners hosted Social Protection Week to raise awareness amongst the general public
- Radio programmes at districts level based on communication protocols to ensure dissemination of consistent messaging around the programme.
- A series of TV programmes showcasing the work of MCDMCH including the SCT programme.
- Continued engagement with MoF to lobby for timely disbursements.
- IMF recommendation on continuation of SCT

Recommendations
- MCDSW to lobby Ministry of Finance to re-classify SCT as a grant by the start of the 2017 budgeting cycle (Aug/Sept) to support more regular disbursements
- Arrange briefing for new Ministers and workshops for new MPs after the election (Dec 2016)
- Decision by GRZ on increasing transfer value and scaling up programme in drought affected districts (June 2016)

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	GRZ implements SCT programme in an efficient and sustainable manner.
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	60
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Operating costs (Total admin costs including procurement of goods, services and M&E)	12% (30%)	Partially met: 17% (26%)
2.2 % of funds reported to have been misappropriated according to final annual audit report	less than 1%	Met: 2014 audit completed, unqualified
2.3 Government funding to SCT programme in ZMW budgeted and released (% of total)	ZMW 250m budgeted	Met: ZMW 250m budgeted; / ZMW 43.4m released in first quarter (17.4%); / 82% GRZ Funded
2.4 Management systems in place	2015 FRA Action plan with agreed PS & CPs	On Track: Key actions agreed in principle, final action plan to be signed off by the PS
2.5 CP support to the programme	Timeliness and quality of cooperating partners financial, technical and procurement support to the programme.	On Track: New Joint programme of support finalised and submitted for approval. / JFA agreed, signing in progress

Key Points

As the programme expands, the need for robust systems is becoming more and more important. There have been some positive developments in the overall systems required to effectively implement the SCT programme since the last annual review and these are summarised below.

Indicator 2.1 measures the proportion of administration costs to programme costs. Administration costs for the programme are calculated on two dimensions; operational costs for the Ministry and secondly,total administration including all costs related to technical assistance and procurement. Lower admin costs signify high levels of efficiency. Operation costs currently stand at 23% and these relate to all costs incurred by the Ministry on overhead costs to run the SCT programme. This proportion is higher than targeted but considered acceptable during a period of rapid scale up. Overall, there has been a sharp sharp decline in the overall administration cost from 43% in the previous year to 26%. This is largely due to the fact that a significant portion of work (Impact Evaluation) under the Technical Assistance component came to an end in 2015. As such, current administration costs are largely driven by operational costs and cost of procurement of goods.

With regards to indicator 2.2, the SCT audit is now part of the ministerial audit. Whilst this is a positive development in terms of how the programme is integrated into the wider work of the ministry, the last report was slightly delayed and was only finalised in October 2015 instead of August as stipulated in the JFA. The final audit was unqualified.

DFID Zambia also commissioned a Fiduciary Risk Assessment (FRA) in September 2015. The report highlights that the rapid growth in the programme and growing dependence on GRZ funding makes the programme increasingly vulnerable to the risk of withdrawal of political support adding that the 2016 elections are likely to increase politically driven decisions around expenditure. Further, weak financial management and reporting arrangements create a weak framework of financial oversight and control. The report also makes the case for stronger oversight, internal audit and general governance of the programme. The findings of the FRA are summarised in the table below.

Level of Risk and Residual Risk:

Risk Components	SCT 2008	SCT 2012	SCT 2015	SCT 2015 / Residual Risks	Trajectory
Fiduciary Risk	Substantial	Moderate/ substantial	High	Substantial	↑
Corruption Risk	Moderate	Moderate	Substantial	Moderate	↑
Credibility of reforms	Not assessed	Not assessed	Partially Credible	Partially Credible	n/a

The FRA recommends some swift and simple measures which the Ministry can implement to reduce the overall fiduciary risk of the programme from high to substantial. It is expected that these actions will stimulate change within the programme to further reduce the fiduciary risk. These include improving the regularity of funding by ensuring the government reclassifies the programme as a statutory protected grant, strengthening staffing for financial management and improving reporting and monitoring tools. MCDSW will need to take a lead in the implementation of the key action points and DFID will work with the ministry and other CPs to agree timelines for the action plan..

GRZ has increased its budget allocation for 2016 to K250m which has made it possible for MCDSW to continue with the scale up of the programme to an additional 28 districts. The 2016 - 2018 Medium Term Expenditure Framework (MTEF) indicates a continuous increase to the programme budget, which guarantees further scale up if MoF maintains the proposed funding levels. The figures (Graph 1) below show the change in the proportion of GRZ funding to the programme overtime. This increase has established GRZ as the majority funder of the programme, covering up to 80% of the budget for SCTs and is a strong indication of sustainability.

This is a positive sign but it remains to be seen how the disbursements will flow in the course of the year. By the end of the first quarter, GRZ had disbursed K43.4m (17.4%) which is a good sign given that disbursements to line ministries are typically low at the beginning of the year. This much better than last year when only 33% of the total allocation had been disbursed by August 2015[8].
[8] (2015) DFID Zambia Literature Review: 2015 Zambia Social Protection Expansion Programme Annual Review Report
The graphs below show the change in the proportion of Government funding to the SCT programme between 2010 to 2016.

Graph 1: SCT Funding

2010 2016*

Source: MCDSW Funding Records & MTEF

In recognition of the importance of continued support to SCTs, the new joint programme document developed by DFID and other CPs (Irish Aid, SIDA and Finland) has been finalised and the signing of the Joint Financing Arrangement (JFA) and bilateral MoUs is underway. In view of this, the JFA has been revised to reflect more accurately the requirements of all the partners. In response to this, DFID Zambia is also in the process of developing a new programme to provide broader support to the programme.

There is further work going on within the MCDSW to strengthen its implementation systems; the contract for the Electronic Payment System has been signed by both parties. It is expected that set up will commence shortly. MCDSW has also started procurement of a supplier for Cash-in-Transit services to compliment the roll-out of the electronic system. Communication activities are underway; the ministry is currently running a series on National TV as well as conducting radio programmes at districts level. More activities to engage with Parliamentarians are planned for later in the year. The design of the Grievance Mechanism is underway, the selected service provider has finalised the guidelines and the system will be piloted in the second quarter of 2016 in selected districts. The evaluation of the Mobile Technology (M-tech) registration was finalised and a decision was made by the MCDSW to continue piloting mobile registration of beneficiaries.

Summary of responses to issues raised in previous annual reviews (where relevant)
The output on government funding was revised to include releases and well as budgeting given the importance of this to the programme implementation and impact. Advocacy activities are on-going as are system strengthening activities which have been highlighted above.

Recommendations

- Spilt indicator 2.3 between GRZ amount budgeted and actual funds released
- Implement FRA recommendation to improve cash management, prepare spending profiles and monitor cash balances –May 2017
- Monitor the roll-out of the Grievance mechanism and Electronic payment system. Track progress on other systems such as Mtech, MIS and targeting) – May 2017
- DFID to work with IMF to ensure that SCT budget is protected from cuts in expenditure
- Design new programme to extend DFID support to Social Protection and incorporate a shock-response component (Dec 2016)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The programme budget is broken down below. The ministry’s total operating costs for 2015 accounted for 23% of the budget. Overall admin costs for the programme have reduced from the previous years largely due to reduced expenditure on technical assistance through UNICEF. Spend on the procurement of goods was slow to start and the bulk of it will be expensed from the 2016 budget.

2015 Funding and spending through Government
Funding Sources (2015)	ZMW m	% age	Spent on (2015)	ZMW m	%
Government of Zambia	110.5	57	Transfers	151[9]	77
Donors (of which DFID)	85 (73)	43(37)	Operating costs	45	23
Total	196		Total	196
[9] This represents the equivalent of 180,000 households receiving K70 per month for 12 months.

Additional 2015 spending through Procurement through UNICEF and Crown Agents

Agency	ZMW m
Crown Agents Procurement	3.2
Total	3.2

Summary 2015 spending and funding levels/ ratios
Ratio/ indicator
Total Government operating costs vs transfers ratio	23%
Total admin costs (incl. TA and procurement) vs total spending ratio	26%
Government funding vs total spending	55.5%

Transfer value
Transfers account for 74% of the programme costs and are hence the largest drivers of value for money. Impact evaluations show strong impacts at 2014 transfer value. Transfer value analysis showed increased transfer size would have larger proportionally impacts. Transfer values have not been increased since 2014 due to GRZ’s focus on scaling up programme. As such the transfer value has been eroded by food price inflation. Discussions are ongoing with government to increase the transfer value, informed by impact modelling.

VfM performance compared to the original VfM proposition in the business case
Earlier cost benefit analysies have shown excellent value for money based on (1) a judgement that the poor value one extra Kwacha more highly than the non-poor, particularly given Zambia’s extremely high levels of inequality; and (2) evidence from the impact evaluations that SCTs are used to directly reduce various dimensions of poverty; and (3) modelling of indirect benefits and multiplier effects.

Administration costs
Total administration costs have come down and are now comparable to other DFID supported SCT programmes and World Bank benchmarks (see figure below). They are expected to reduce further as the programme goes to scale, systems are strengthened (e.g. targeting, grievance mechanism, MIS. Linkages to other programmes) and key activities such as payments are outsourced.

World Bank benchmark

Sustainability
DFID support to the programme has leveraged support from GRZ and CP’s. DFID original programme of £38m has resulted in £63m of additional GRZ funding.

Assessment of whether the programme continues to represent value for money
The programme continues to offer very good value for money, providing a highly efficient way to reduce extreme poverty. Impact evluations show that programme objectives are being achieved. At the same time the cost of delivering the programme is reducing and DFID funding has leveraged large amounts of GRZ funds which will support sustainabliity.

Quality of financial management

As indicated above, the 2015 FRA highlighted some gaps in the quality of financial management in MCDSW. It pointed out weaknesses in the budget structure for administration costs and accounting classifications and overall reporting of expenditure. To address this, it has been recommended that the Ministry should develop a new coding structure for administrative costs that is simple and provides the required amount of detail.

Date of last narrative financial report	12/02/2016
Date of last audited annual statement	14/10/2015

E: RISK (½ page)

Overall risk rating: Major

The risk rating or the programme has been revised from High to Major in line with latest guidance. The previous review highlighted the lack of clarity on the future budget of the programme. This risk can be said to have reduced given that the 2016-18 MTEF clearly indicates budgetary increases year on year to support the scale up of the programme. However, the security of disbursements still remains in question and will have to be monitored closely in the course of the year as it could potentially reduce the credibility of the programme. This is of particular concern given the forthcoming tripartite election in August 2016.

An overview of programme risks is given below;

Overview of programme risk

Risk	Current Description & Triggers	Current Mitigation Actions (i.e. treat or tolerate)	Risk Category	Current Net Risk Rating		Historical Trend Rating
				Likelihood	Impact	Feb-16
1. Inadequate GRZ financing of SCT programme	MF allocations insufficient for programme scale up	Treat: advocacy to increase GRZ financing; classified as institution to ensure monthly disbursement; continued CP financing in medium term on a reducing scale; support to MCDMCH to plan and request funding	Context	Possible	Major	Static
						Increased allocation to the programme in MTEF
2. Irregular Disbursements for the SCT Programme	Disbursements are irregular/ Credibility of programme brought in question	Treat: Coordinated work by CPs by setting conditions for disbursements.	Fiduciary Risk	Likely	Major	Static
						GRZ's weak fiscal position. Uncertainty around disbursements.
3. MCDSW Implementation Capacity	Transfers poorly targeted, delayed or stolen.	Treat: System strengthening support (targeting, registration, payments, grievance, MIS etc); M&E; support through PFMRP	Delivery	Possible	Moderate	Increasing
						Increasing fiduciary risk as a result of the rapid scale up. / Decentralisation.
4. Political interference / capture	Programme redirected for political ends. Credibility of programme undermined.	Treat: Communication of programme objectives and targeting; building broad political and popular support;	Context	Likely	Moderate	Increasing
						Elections in 2016. Lack of clarity around the targeting mechanism. Weak implementation of the Communication strategy.
5. Inflationary pressure	SCT recipients unable to use transfer to access basic needs and services.	Treat: SP policy and framework articulates linkages; DFID support in other sectors (e.g. health, education); DFID planned support to El Nino response	Context	Almost Certain	Major	Increasing
						Poor Harvest in 2016. El Nino. Erosion of transfer value

Zambia is currently experiencing the El Nino effect with a poor rainy season for 2016/17. Further, the depreciation of the Kwacha has pushed food prices up which could undermine the impact of the SCT programme. DFID is currently working with the Ministry and other partners to forecast funding required for a response and to determine the number of potential beneficiaries. In future there will be need for the programme to have an in-built mechanism to respond the growing risk of climate shocks.

Overview of programme risk – Major

Outstanding actions from risk assessment
Actions from last year that need further work:
The FRA action plan is yet to be agreed and actioned. One of the key recommendation is the re-coding of the SCT Programme from operations expenditure to statutory/ protected expenditure
- Public financial management capacity building: the FRA recommended strengthened DFID support in this area. DFID will lead and allocate more time for the PFM Advisor to support this
- Continued strengthening of delivery mechanisms: this is an ongoing process, significant progress on setting up the Grievance Mechanism and the M-Tech Registration process. It is expected that the pilot for the electronic payment system with also kick-start this year.
- Continued advocacy with key decision makers across parties: this remains a priority and recommendations in this annual review aim to strengthen.
- Transfer value increase being analysed and discussed with MCDSW

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Following a recommitment to increase the SCT budget by the government in late 2015, the scale up of the social cash transfers programme is back on track. MCDSW is currently enumerating new beneficiaries in an additional 28 districts. It is expected that the new districts will come on board and that the first transfers will be paid out by June 2016. DFID’s agreement with UNICEF was scheduled to end in December 2015, however, a no cost extension to March 2016 was granted to enable UNICEF provide additional support to the Ministry for the 2016 scale up.

Performance of partnership (s)

DFID stepped down as co-lead of the Social Protection Cooperating Partners Group in December 2015. This role has now been taken up by Finland for duration of one year. UNICEF continues to be co-lead and acts as the secretariat on the group.

The results of the survey on DFID’s performance in the co-lead role (carried out in December 2015) are summarised below;
- Act as interface for policy dialogue – Highly effective
- Support increased GRZ capacity in policy development, planning, implementation & monitoring - Effective
- Support GRZ management of financial and technical assistance - Effective
- Provide coordination services for other CP’s - Highly effective
- Monitor harmonisation performance - Effective

The development of the new joint programme has been finalised and has been submitted to MCDSW for approval, this has incorporated support from existing and new cooperating partners. DFID’s planned new Business Case will seek to align with joint programme.

Asset monitoring and control

DFID has continued to procure goods for the new implementing districts. Procurement of goods is currently underway with most goods having been delivered already. There continues to be concern over the safety of goods both whilst they are in transit at the ministry headquarters and once distributed to respective districts. There is a growing need to improve security particularly in the newly created districts which seem to have challenges with suitable office accommodation.

There was an incident of theft at the headquarters, the police investigations were inconclusive and the goods were not recovered. With support from Counter fraud and Whistle Blowing Unit, DFID Zambia worked with the ministry to ensure that they replaced the stolen goods. The case has since been closed by CFWU.

There have been further reports of thefts in selected districts and DFID is currently waiting for official notification from the ministry.

Further, an asset spot check will be conducted as part of the annual review process to verify that the procured goods continue to be used for the intended purpose.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

DFID financial aid is dependent on the Government of Zambia’s continued commitment to four partnership principles. These principles are assessed on an on-going basis; the last assessment was done in November 2015. It is our assessment that none have been breached.

Commitment to poverty reduction and the Sustainable Development Goals (SDGs):
Overall, policies on poverty reduction are not matched by budget allocations and financial releases. There are some positive signs for pro-poor investment in the increasing Government of Zambia support to the scale up of Social Cash Transfers. This programme is projected to reach around 10% of Zambian households by end of 2016, and domestic financing now covers 66% of the programme costs. Nevertheless, the programme still represents less than 1% of GRZ annual expenditure.

Commitment to human rights and other international obligations:
There has been a moderate commitment to human rights over the medium term but recent concerns around the freedoms of assembly and expression. Overall the human rights picture in Zambia remains static and is not declining at the aggregate level. The amended Constitution was signed into law in January 2016. It was felt that the decision to have Parliament enact elements of the draft Constitution instead of offering Zambians the chance to vote on new social and economic rights was, at best, a missed opportunity. Nonetheless, given Zambia remains one of Africa's more liberal and open democracies, we judge that, despite a mixed performance on political rights and the media, and issues in gender equality, Zambia is demonstrating a moderate level of commitment to upholding this Partnership Principle.

Commitment to strengthening public financial management:
On Public Financial Management and Anti-corruption commitment is moderate on the former and weak on the latter. PFM performance is gradually improving though serious weaknesses remain; budget credibility remains of greatest concern. There has been an increase in the government’s budget deficit, which is reducing funds for capital and social spending. Wages were frozen for 2015 but the freeze has been lifted for 2016, ahead of an election, amid a lack of clarity of the costs for that pay settlement. The risk of the misuse of Government funds remains significant with corruption a persistent challenge. However, the Government seems partly committed to tackling the issue with some cases brought to court for some officials.

Commitment to strengthening domestic accountability:
Zambia's competitive political environment does still provide some opportunities for accountability. Overall, commitment to domestic accountability is moderate; Elections largely credible, civil society operates freely but the media is a best partly free. Outside of elections there are few effective mechanisms to hold government to account.
MONITORING & EVALUATION (½ page)

Evidence and evaluation
Between 2010 and 2014, DFID co-funded an impact evaluation of social cash transfers in Zambia to generate evidence around the feasibility of a national scale up. A total of eight reports from the randomised control trials of the child grant (CG) and multiple categorical grant (MCG) targeting approach have been released. The findings of each of the targeting approaches have been summarised into two separate reports which will be released within 2016. The evaluation consisted of a randomised control trial including a baseline measurement, and repeated post-intervention measures, conducted at both lean and harvest times. Given the use of randomization and the existence of a baseline, differences between the treatment and control groups can be fully attributed to the SCT programme rather than to other differences between the two groups.

- Child Grants: SCTs provided to households with a child under 5 in the 3 poorest districts in the country. The impact evaluation included 2,515 households with a baseline in 2010 and follow up surveys at 24, 30, 36 and 48 months.
- Multiple Categorical Grants: SCTs provided to households headed by the elderly or a woman with high dependency ratio (3 or greater) of children, elderly or disabled. The study included 3,076 households from 2 districts with 24 months and 36 months follow up surveys.

The impact evaluations showed that SCT reduced poverty and increased food insecurity. They also allowed people to invest in improving their living conditions, especially for children, and invest in productive activities.

 A summary of the key findings is given below.

Decreased Poverty: SCTs show strong impacts on reducing extreme poverty and the poverty gap, ultimately reducing the depth of households below the poverty line. The effects on poverty reduction were greater for those farther below the extreme poverty line, evidence of both the highly successful targeting of the SCTs and their impact on welfare.

Figure (impacts of MCG on poverty after 3 years)

Key findings:
	CG 36 mth	MCG 24mth
Poverty headcount reduction	9pp	9pp
Poverty gap	10pp	12pp
Percentage of households eating two or more meals per day (and total %)	5pp (98%)	5(95%)
Material wellbeing of children	32pp (71%)	28pp (63%)
School enrolment	7pp for Boy 11-14yrs	11pp for Boys / 8 for Girls
Households asset ownership	46pp increase	29pp increase
Livestock ownership	14pp	26pp
Multiplier Impact	1.68	1.49

Monitoring progress throughout the review period

The FRA report recommended a shift from the Quarterly management meetings to meeting every four months. This is to align reporting to the bi-monthly payment of cash transfers. Participation in the quarterly meetings has expanded to include SIDA and Finland who will be providing support to the new joint programme. Additional technical meetings are held when needed. The programme is also visited regularly; these findings will be verified during field visits as part of the sector joint annual review which is scheduled for late June 2016.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: ZAMBIA SOCIAL PROTECTION EXPANSION PROGRAMME
Programme Value: £38m		Review Date: 21/08/2015
Programme Code: 200625	Start Date: 01/04/2010	End Date: 31/03/2020

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	82.5	A+	A	A	B
Risk Rating	M	H/M	H/M	H/M	H

Summary of progress and lessons learnt since last review

There is strong evidence that social cash transfers (SCTs) have a large impact on poverty. The impact of DFID funds on poverty alleviation remains high, but the performance of the overall programme has reduced, as GRZ has not provided the funds necessary to meet their targets set in 2014. The Ministry of Community Development, Mother and Child Health (MCDMCH) implemented an impressive scale up of the Programme in 2014 so that it now reaches 136,000 recipients in 50 districts, with a further 35,000 enrolled to be added to the programme. However the government has not lived up to its commitment to fund the scaled-up programme:
- Of the ZMW150m budgeted in 2014, only 104m (70%) was disbursed.
- The 2015 budget for the programme was ZMW150m as opposed to the ZMW200m indicated in the Medium Term Expenditure Framework (MTEF). The 2015 MTEF shows no further increase in budget.
- Two thirds of the way through the year, only one third of the allocated budget had been disbursed by MoFNP (ZMW50m by August 2015)

This has had a major impact on the programme, namely:
- Severe delays (up to 4 months) in delivering transfers to recipients, affecting programme impact and credibility.
- The overall caseload has not increased, and in fact has reduced due to removal of households no longer eligible.

The Ministry of Community Development, Mother and Child Health (MCDMCH), with support from donors continues to engage the Ministry of Finance and National Planning (MoFNP) to ensure adequate and timely funding for the programme, and to gain clarity on the future scale of the programme. This needs to be a priority in the coming year.

Further work is needed to strengthen implementation systems for a robust national programme:
- The scale up has raised questions around the targeting approach, with the dependency ratio and welfare criteria being poorly understood and concerns raised around supporting households with ‘fit for work’ adults.
- The Management Information System is to be rolled out to districts.
- A mobile technology (MTech) registration system has been piloted and should be used for future registrations.
- A payment service provider will soon be contracted, so a new payment mechanism will be rolled out in 3 of the 11 Provinces.
- The grievance mechanism is being rethought and strengthened.

Summary of recommendations for the next year
- Develop a joint advocacy strategy to inform increased lobbying for full and timely disbursements, and increasing SCT budget in the MTEF.
- Roll out a publicity campaign to raise public and political support for the programme.
- Continue to strengthen implementation systems including targeting, registration, MIS, payments, grievances.
- Strengthen link between MCDMCH and MoF public financial management reform programme.
- Finalise a new joint programme with other donors for 2016-2018, agreeing financial and technical support to SCTs and social protection policy more broadly.
- Revise logframe to give more weighting to outputs over which DFID has direct control.