Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	24 June 2016

Title: Support to National Malaria Programme
Programme Code:	Start Date / 1st April 2008	End Date: 31st March, 2016
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year	2008/09	2009/10	2010/11	2011/12	2012/13	2013/14	2014/15	2015
Programme Score	67.5	62.5	56.75	B	B	A+	A	A+
Risk Rating	M	M	M	M	M	M	M	Moderate

Financial Position

Original Programme Value	£50m
Extensions/ amendments	No-cost extension (April 2013-August 2013) / Cost extension to £89m (September 2013 – August 2015) / No-cost extension (Sep 2015 – March 2016)
Log-frame revisions (with dates)	July 2010 (to change to new DFID logframe format). / July 2012 (to update indicators and targets following change in strategy for case management and commercial sector. / September 2013 (to reflect the two-year cost extension).
Total programme spend	£86,459,393.74 (as at 24 June 2016)

Follow up actions required following closure

Conclusion of asset disposal in Abuja and the 10 supported States.

Full distribution of residual malaria commodities which were earlier procured, but delivered in country after the closure date (March 31st 2016). This is being carried out by Malaria consortium as part of closure activities for the programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3974095.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4658832.odt

Outline of programme and what it has achieved

In 2008 malaria accounted for 60 percent of outpatient visits and was responsible for 30 percent of deaths in children under five. The disease was also a major cause of absenteeism and low productivity. Despite the availability of efficacious preventive and treatment measures against malaria, inadequate funding and weak health systems limited their roll-out at scale and thereby reducing achievement of universal coverage. Modest anti-malaria initiatives being implemented were also not optimised due to lack of appropriate health seeking behaviour among the Nigerian populace.

The SuNMaP programme was originally approved in 2008 with the UK government providing £50 million to support the management, coordination and delivery of malaria control services in six Nigerian States (Anambra, Kano and Lagos Niger, Katsina and Ogun). It subsequently expanded to a further four States (Jigawa, Enugu, Kaduna and Yobe) added in 2012. The programme covered a total population of around 60 million (40% of the Nigerian population). The support is through the provision of long and short term technical assistance for systems development and training through 6 project outputs:

Output 1: Capacity development
Output 2: Harmonization
Output 3: Prevention
Output 4: Treatment
Output 5: Demand creation
Output 6: Operational research

SuNMaP’s malaria control efforts include building the capacity of NMEP, SMEPs and the LGAs to reach the general population in the programme states, especially the poorest and most vulnerable, with evidence-based interventions that would help control the disease. The programme’s support include health systems strengthening, working through the private sector, provision of antimalarial commidities and activities to increase demand for these commodities.

Since its inception in 2008, the £89 million SUNMAP project, although representing a relatively minor contribution to the total malaria funding in Nigeria, has repeatedly been recognised for its abilityto provide crucial technical assistance and for its outstanding contribution to malaria control in Nigeria. Some important achievements of the SUNMAP programme include[1]:
[1] DFID 2015. SuNMaP Seventh Annual Review report.

- Establishing a mechanism to develop a coordinated malaria response through federal and state Roll Back Malaria partners.
- Supporting the development and implementation of national and state malaria control plans which have increased partner coordination and enhanced harmonization of efforts in malaria control.
- Orchestrating and contributing to the successful nationwide distribution of LLINs to every household. About 100 million nets were distributed through mass campaigns since 2009, of which 7.5 million were DFID funded through SUNMAP.
- Developed and implemented the first large scale routine distributions of LLINs (4.1 million nets in total) through ante-natal clinics and other context relevant routine distribution channels.
- Development of training modules for management, planning and malaria case management that have been used across the health sector and training roll-out reaching close to 22,000 health workers in 13,000 different service delivery points.
- The scale-up of effective malaria diagnosis and treatment in supported States, with 7.3 million of ACTs doses and RDTS, respectively distributed.
- The development of sustainable private sector markets for malaria commodities through a facilitative approach known as Making Markets Work for the Poor (M4P)
- Generation of evidence and support to evidence based policymaking at federal and state level.

Between 2008 and 2015, the lives of 96,000 children under five are estimated to have been saved in the ten DFID SUNMAP supported states, of which around 48,200 are estimated to be directly attributable to DFID programming[2].
[2] Estimates based on modelling using the Lives Saved Tool (LiST model), DFID 2015, SuNMaP Seventh Annual Review report.

Gender and poverty
There is no evidence to suggest that people of a particular gender encounter systematic barriers to access for malaria services in Nigeria. However, it is well known that biological roles and gender norms mean women are disproportionately affected by the impact of malaria on the Nigerian population. Pregnant women and their unborn babies are particularly susceptible to the effects of malaria. In addition, women are the primary caregivers of children in Nigeria and have to sacrifice their time and stay away from work when children – who are the principal sufferers of malaria – fall ill. Being poor, with everything that goes with it (poor education, nutritional status, housing, and access to modern healthcare) also dramatically increases the risk of malaria. According to the 2015 malaria indicator survey (MIS), 43% of under-five children from the poorest families have malaria, compared to 4.3% from the richest.

A number of the interventions promoted by SUNMAP, such as intermittent preventive treatment for pregnant women, and routine LLIN distribution through ante-natal clinics, have helped protect pregnant women and their babies from the effects of malaria. Behaviour change efforts have targeted care-givers, primarily mothers, on the best ways of protecting their families from malaria and handling it when it occurs. By reducing the incidence of malaria among children and pregnant women, SUNMAP helped reduce the impact of the disease on mothers and increase the time women have to pursue income generation opportunities.

SUNMAP has also contributed to positive social impact by targeting rural primary health facilities and informal health workers used primarily by the poor. The distribution of malaria commodities has been carried out in such a manner as to ensure access by the poorest and vulnerable groups. A recent study investigating the effects of the SUNMAP 2009 net distribution campaign in Kano State[1] concluded that “The campaign had a significant impact by increasing ITN coverage and reducing inequity in ownership and use”. Between 2008 and 2015, wealth inequities in access to malaria prevention were dramatically reversed. Insecticide treated net ownership among the poorest households increased from 4% to 86%, compared to an increase from 11.2% to 58% in the richest households.
[1] Ye et al.: Can universal insecticide-treated net campaigns achieve equity in coverage and use? The case of northern Nigeria. Malaria Journal 2012 11:32

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Impact
The programme Impact is to achieve progress towards the health Millennium Development Goals (MDGs) in Nigeria. The impact target is a reduction in all cause under-five mortality from 157/1000 in 2008 to 100/1000 in 2015.

The most recent survey information on child mortality in Nigeria comes from the 2013 National Demographic and Health Survey (NDHS). The 2013 NDHS reported that the all cause under-five mortality in Nigeria was 128/1000.

Overall, child mortality is on the decline in Nigeria, and SuNMaP (as will be shown in the VFM analysis) has contributed to this decline. The prevalence of malaria among children under five has been falling over the last fifteen years, with the greatest reduction between 2010 and 2015 when it fell from 42% to 27%. It is very likely that this led to reductions in malaria related child mortality, contributing to the observed fall in child mortality between 2008 and 2013 (and most likely further reductions since then).

Outcome
The outcome of the project is to strengthen the delivery of Nigeria’s National Malaria Elimination Programme (NMEP), especially in supported States.

Outcome targets

Percentage of all children Under 5 in supported states that slept under an ITN the night before the interview in programme supported states increased from 3 percent in 2007 to 65 percent in 2015.

Currently, there is no state specific data at the moment to assess the achievement of the programme on this indicator. However on a national basis, there has been significant improvement from 3 percent in 2007 to 43 percent (national figure) in 2015. In NorthWestern Nigeria, where the programme supports 4 States (Kaduna, Kano, Jigawa and Katsina) which contain 80% of children in the zone, 62% of children were sleeping under an ITN by 2015, close to the target of 65%.

Proportion of all women with birth in last 2 years in supported states who received at least two doses of IPT in programme supported states increasing from 2 percent in 2007 to 35 percent in 2015.

As described above, at the moment, there is no state specific data on the proportion of all women with birth in last 2 years in supported states who received at least two doses of IPT. However, on a national basis, there has been significant improvement in this indicator from 2% in 2007 to 37.2% (above the target) in 2015.

Proportion of children age under 5 with a fever episode in last two weeks in supported states who received treatment with ACT in programme supported states increasing from 3 percent in 2007 to 25 percent in 2015.

This indicator is problematic, because as the prevalence of malaria has reduced in Nigeria (national malaria prevalence among underfives reduced from 42% to 27% between 2010 and 2015), it is expected that the proportion of childhood fevers caused by malaria would reduce. In addition, as usage of rapid diagnostic testing has increased during the period due to changes in national malaria treatment policy, it is expected that presumptive malaria treatment and therefore unnecessary treatment with ACT would reduce. For these reasons, this is no longer considered a useful indicator for assessing outcome performance under this programme and is generally no longer measured in malaria surveys.

However, available data shows this indicator increased from 3% in 2008 to 8.2% in 2013. It was not measured in the 2015 Malaria Indicator Survey.

Given the difficulties with obtaining state specific data for the outcome assessment, an assessment of outcome performance has been made using
1. The observed dramatic reduction (from 42% to 27%) in malaria prevalence rates nationally, and particularly in SUNMAP supported States between 2010 and 2015. Eight of the ten SuNMaP supported states are below the national average with 5 states out of the 8 (Yobe – 18.9, Anambra – 10.2, Enugu – 10.5, Ogun – 14.7 and Lagos – 0.0 percent) having malaria prevalence of less than 20 percent.
2. The achievement of outcome indicator 1 in the northwest zone, which has the largest concentration of SUNMAP supported States.
3. The achievement of outcome indicator 2 nationally.
4. Discounting outcome indicator 3, which is considered no longer useful.

On this basis, outcome performance is assessed to be A: Outcome met expectation

Output Score and Description

A+ Outputs moderately exceeded expectation

Output	Description	Score	Weighting	A+
1	National, State, and LGA capacity for policy development, planning and coordination are improved	A+	20%
2	All agencies’ support for the malaria sub-sector at federal, state and local levels are effectively harmonized	A+	15%
3	Population coverage of effective measures for the prevention of malaria is increased	A+	25%
4	Access of the population to effective treatment for malaria is improved	A	20%
5	Community awareness and demand for effective malaria treatment and prevention are improved	A	15%
6	Operational research into key areas of prevention and treatment provides the evidence base for more effective strategies	B	5%

Lessons and how these have been shared

One of the most significant lessons from the implementation of the SuNMaP programme is that one intervention can be so catalytic as to aid the transformation of an entire sector. The programme was established to help in malaria control but ended up strengthening the health sector in intervention states such that the results are helping service provision across the entire health sector.

Some of the specific challenges and lessons learnt under each of the SuNMaP outputs are outlined below.

Output 1. Capacity building
The use of group work, discussion and ‘learning by doing’ principles was seen as a benefit to the training sessions, engendering a greater sense of ownership among participants.

The approach of expanding and adapting existing materials (in the case of service delivery modules) proved to be cost-effective. By training trainers, who cascaded their learning to health workers, large numbers of people were reached at a low cost. The ‘cluster approach’, whereby training groups are organised by type or location, was found to save time and human resources.

Many partners using the same tools reduce cost. Using one tool and sharing between all partners means that they spend less on development costs and the time required for roll out. Training partners to roll out shared tools also allows for faster attainment of universal coverage. In addition, programme tools developed for malaria had wider application and could be adapted to other areas of healthcare.

Ouput 2. Harmonisation
Careful forward planning proved to be useful in creating a framework for harmonisation which takes account the progress of each partner in their annual cycle.

It is important to address the challenges of working with partners with different programme cycles. Some partners were reluctant to adapt their working practices to become more evidence-based. Others were protective of their territory and were reluctant to share resources. Simple practical issues, such as bringing large numbers of partners together for group meetings, were difficult to overcome. Practicing good planning and communication skills is, therefore, essential. It is also important to be patient and allow for practice and results over time.

Demonstrating achievements can be a challenge. The benefits of harmonisation may be difficult to demonstrate, especially as it involves a range of outputs from different partners and agencies. Progress must be measured by an increase in scope, depth and breadth, and cover large geographical areas. Performance tracking at national level is good both for reporting on progress and for engaging partners in harmonisation, because every partner wants to know what is happening within its own programme and how that fits into the national context.

In effect the programme had to provide close support to NMEP and SMEPs to lead harmonisation efforts across fronts, including linking multiyear plans with operational plans to coordinate and track performance within NMEP and across all tiers of government and the contributions of the private sector.

Output 3. Prevention
Transforming the commercial LLIN commercial sector requires a long-term, pragmatic strategy. While the Making markets work for the Poor (M4P) approach advocates for a flexible and hands-off approach, the complexity of the LLIN retail market space arising from heavy engagement of donors and government meant the programme had to adopt a much more hands-on approach at times in order to bring players together and demonstrate the business opportunity. The programme worked continuously to bring market players together, as an educator and mediator, through high level dialogue, consultative workshops, and cross-sector training and promotional events. This role can be intensive and probably required more time and resources than the programme was able to commit.

There is a need for evidence based selection of effective prevention interventions at the sub national level: the selection of the interventions should be based on ecological stratification and preparedness of the local authorities. Nigeria has five ecological transmission zones each with unique attributes. These attributes determines the choice of prevention and management of malaria.

Undoubtedly, the LLIN distribution campiagn has contributed immensely to the increase in its ownership. Between 2008 and 2015, LLIN ownership increased from 8% to 68% nationally. Although the rate of use of LLIN lags behind rate of ownership, it ismportant to continue with replacement campaign and continuous distribution, since a recent study indicate that increase in LLIN ownership enhance access, which in turm enhance use (Koenker & Kilian 2014).

Output 4. Improved diagnosis and treatment
While gains have been recorded in logistics management system for malaria commodities and other commodities at national level, there is a need to focus on the subnational level for not only malaria but also other commodities to limit stock-outs.

Building capacity for integrated Community Case Management (iCCM) roll-out: Evidence from surveys and risk mapping has shown that malaria cases are on the decline, which poses challenges for the management of non-malaria fevers, and therefore a need to integrate the management of malaria with other childhood illnesses such as pneumonia, diarrhoea and malnutrition using existing community structures.

It is important to improve the quality and credibility of both rapid diagnostic testing (mRDT) and microscopy: The proportion of fever cases that are malaria is falling, but this apparently has not been disseminated sufficiently to clinicians who continue to suspect malaria even when rapid diagnostic testing is negative. This becomes a problem for facilities that have access to both mRDT and microscopy. A false positive result on microscopy in the face of a negative mRDT result further erodes confidence in the testing kits.

Output 5. Demand creation
The change in epidemiology of malaria in the last decade calls for doing things differently, targeting specific areas or zones based on the current malaria pattern. This requires innovative ways of engaging and motivating the key target population for impactful behavioural change. The message and channel needs to be modified to suit the characteristics and preferences of the target population.

The programme found significantly greater resistance to change in behaviour toward bed net use in urban areas relative to rural areas. This may be related to the lower mosquito density, the widespread availability of other biting control measures, as well as the general perception that nets cause heat and humidity. Some of the behaviour change communications targeted at “bed net use for malaria control” had little impact in urban areas, and the messaging had to be modified to emphasize more emotional rather than logical motivation.

Output 6. Operational research
One lesson from the programme is that to improve capacity for research requires consistent, high skilled capacity while still maintaining a collaborative approach. These two ideals are sometimes in conflict with each other.
Lesson sharing
SuNMaP used a number of special forums to disseminate its lessons to roll back malaria partners, commercial sector partners and other stakeholders. These events included two dissemination events for commercial sector quarterly monitoring surveys and end of programme dissemination events at state and national level.

The programme held end of programme dissemination events at the state level for the 10 programme states during the month of February 2016. A national dissemination event was held on the 17th and 18th of February. Knowledge management products including state exit plans, programme final reports, case studies, success stories were all shared with government, other donor partners and civil society.

In addition, the programme has disseminated its lessons globally through microsites on the Malaria Consortium websites and the SuNMaP website featuring films, publications (learning papers), and blogs. SuNMaP also engaged with the media to share lessons from the programme including citations in The Guardian, Daily Independent Nigeria, National Mirror, Radio Kapital FM, Love FM etc.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	National, State, and LGA capacity for policy development, planning and coordination are improved
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme	Latest values (Feb 2016)	Source	Performance
NMEP and SMEP annual operational planning process and review mechanism in place	0	Annual Operational Plan (AOP) developed based on new NMSP at NMEP, in 10 programme States	Annual Operational Plan developed based on the new NMSP at NMEP, in 10 programme States and multi-year plans for 10 programme states developed	NMEP, SMEP documents, Annual Review Meeting Reports	Milestone exceeded
NMEP and SMEP coordination mechanism in place	Very irregular meetings taking place	Coordination framework revised at the NMEP and 6 programme states while support to its implementation continues in 9 programme states	Coordination frameworks revised at the NMEP and 10 programme states while support to its implementation continues in 10 programme states.	Coordination frameworks, Minutes of meeting of partners, Coordination Framework Review reports and sub-committees meetings	Milestone Exceeded
Number of programme management frameworks for priority malaria control systems at state level are operationalized	0	2 frameworks each in 6 states / 1 framework each in 3 additional State	1 state with 1 frameworks, 5 states with 2 frameworks, 2 states with 3 frameworks, 2 states with 5 frameworks and 4 frameworks at the National level with 2 revised	NMEP/SMEP documents, SMTWC minutes, Framework review reports, State review meeting reports	Milestone exceeded.

Key Points
One of the most significant achievements of SuNMaP that has resonated through every review has been the development of operational Annual Operational Plans (AOPs) for NMEP as well as SuNMaP supported states. Specifically, SuNMaP developed the capacity of its stakeholders in the following areas;
- Comprehensive malaria control strategic and annual operational planning
- Supporting the development and implementation of a coordination framework for malaria control
- Development of comprehensive training modules for service delivery and programme management
- Comprehensive methodology for state led training, planning and implementation of programme management modules

The NMEP coordination framework has been developed and adapted in the programme states, and these coordination frameworks and platforms are functional at all levels. SuNMaP-supported NMEP management and planning training modules have contributed directly to the state AOP development process.

Across board, there is recognition of SuNMaP’s role in building capacity for malaria programming and planning. SuNMaP is recognised as a “listening” organisation, making it possible for training modules to be developed and delivered in response to areas of need as these were identified. In addition to conventional training activities, the project has intensively developed integrated supportive supervision, which incorporates mentoring, and coaching into institutional capacity strengthening, crucial for effective and efficient malaria control.

While this process has helped improve state ownership of malaria control, States are still a long way off from taking financial and technical responsibility for malaria control. Most malaria control commodities and activities are donor funded, and the planning process was not fully integrated into the budgeting process in some states.

Summary of responses to issues raised in previous annual reviews (where relevant)
	Recommendation(s)	Response(s)
R1	Deepen understanding of AOP process and its relationship to the timing to budget timelines in states. I.e. States should conclude the AOP process on time to feed into the budget making process of the state.	The timeliness of AOP as relates to budget is well understood by states and this has also been re-emphasized by the programme. Multiple years plans were developed for all states. This comprises full AOP for 2016 and frameworks (broadstrokes of malaria plans which are abridged AOPs that can be expanded during each year’s AOP process) for 2017 and 2018. This head start for the planning of subsequent years will enable early AOP and opportunity for alignment with state budgeting
R2	Each state should initiate a sustainability process for all the activities the programme is supporting in the states so that programme’s closure has a minimal impact on malaria control activities and be sustained, safeguarding the investments of the programme over the years	The programme supported the state with technical support to develop state exit plans as well as multiyear plans. In addition, the programme has discussed with DFID programmes in some of the states like PATHS 2 on how to sustain systems built by SuNMaP and each state has developed a transition plan. These transition plans indentify institutional homes for all programme initiatives and key contact persons.

Recommendations for future programmes

1. Continue to deepen understanding of AOP processes, support NMEP to support AOP processes in all states and ensure that timing fits into to budget timelines in supported states.
2. Include a sustainability process with deliberate weaning strategies and timelines for each programme state.
3. Much progress has been made with the use of data, but more needs to be done, especially on building capacity on the use of local data for local planning
4. Re-consider co-location for future programmes with the NMEP. Although this has served the programme well through this stage, but increased distancing from the primary partners may be a better strategy for a maturing relationship.
5. Link with partners and programmes supporting health systems and governance to address wider reform issues. The burden of malaria is declining in Nigeria, and there is a need to address broader health systems issues in other to achieve the pre-elimination target of the NMEP. The current coordination platform which focuses on partners in the malaria sector also needs to be reviewed in order to identify lessons and explore how to include wider health systems partners.

Output Title	All agencies’ support for the malaria sub-sector at federal, state and local levels are effectively harmonised
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme	Latest values (Feb 2016)	Source	Performance
Cumulative number of strategic areas for which harmonised methodologies and tools are developed and used by partners	0	8 developed (cumulative)/4 revised	13 developed and 4 revised / Revised - ACSM framework and guideline, M and E plan, LLIN campaign guidelines	Annual NMEP review, meeting reports	Milestone exceeded
Mechanism in place for public-private partnership coordination	0	Forum for interaction between NMEP and SMEPs in 6 programme States, RBM partners and private sector partners meetings taking place regularly	Forum for interaction between NMEP and SMEPs in 7 programme States, RBM partners and private sector partners meetings taking place regularly’	Private sector forum meeting minutes	Milestone exceeded.

SuNMaP got off to a great start on harmonisation, by being in place just at the time the government decided on a nationwide campaign to distribute 60m LLINs. SuNMaP did an excellent job in harmonizing efforts of development partners to come together and align behind a single, clear government-led plan for LLINs.

Stakeholders widely recognise and credit SuNMaP for successfully bringing institutions/organisations and people together to secure a common approach to operational plans, intervention strategies, net campaigns, standard tools and methodologies etc over the project period. The strategic areas for which harmonised methodologies and tools have been developed include: integrated supportive supervision, quality assurance for parasite based diagnosis, continuous LLIN distribution, on-the-job capacity building, commodities logistics reporting and the National Health Management Information System. All partners are currently using these tools.

SuNMaP has played a critical role in supporting federal and state level planning processes and was particularly involved in ensuring all partners’ involvement in instituting a harmonised approach for the development of the 2014-2020 National Malaria Strategic plan. A country Monitoring and Evaluation plan 2014-2020 that aims to harmonise all partners’ inputs was developed with technical assistance and support from the programme.

Further to SuNMaP’s support, there is increasing commitment by the NMEP to achieving targets. The functioning Technical Working Groups (TWG) and subcommittees both extend the capacity of the NMEP and promote coherence among partners. SuNMaP has played an active lead role, e.g. chairing two TWGs (Programme Management; Integrated Vector Management - IVM) and co-chairing the Advocacy, Communication and Social Mobilisation (ACSM) and the M&E TWGs.

Efforts were made to develop a quality assurance (QA) framework for parasite-based diagnosis in supported States; QA is still in its infancy and needs more attention.
In the states where SuNMaP operated, where there were other DFID projects. While the programmes kept each other informed of their activities, the integration of interventions were passive and opportunities for synergy were not always fully utilised. This is similar for other donor projects in the states.

There are still areas for improvement. Many of the guidelines that have been developed are often limited mainly to paper copies, which limits their access and lifespan. Also, in Kano, SuNMaP relies on its own vertical distribution mechanisms to public sector facilities unlike in some other states like Lagos, where commodity distribution is fully integrated into the States processes.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations for future programmes

1. The NMEP should be supported in the development of a document management system on its website where all the guidelines, frameworks etc are available/searchable online etc.
2. There should be intensive documentation and sharing of learning from PPP initiatives, in order to guide potential future interventions in this area.
3. If commodities are part of next programme, distribution should be integrated fully into state structures, with central logistics mechanisms in states for all donors. If necessary, investments should be made in governance structures rather than in the development of alternate, parallel systems.
4. Better integration with other DFID supported programmes in states with clear deliverables included in log frame for all programmes, e.g. a “governance” group could be formed from all DFID programmes with agreed, common and shared deliverables
5. Tighter strategic collaboration with other malaria NGOs and tighter collaboration at state level e.g. with CHAI in supporting the management of severe malaria.
6. More aggressive advocacy to State government for increased budgetary allocation to malaria control, using tools like scorecards and infographics to show them what others are doing.

Output Title	Population coverage of effective measures for the prevention of malaria is increased
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme	Latest values (Feb 2016)	Source	Performance
Proportion of households in supported States with at least one ITN	7%	70% / 65%[3]	60.5%/77.7%	NMIS 2015	Milestone not achieved in old state but exceed in new state
Proportion of nets received from the distribution campaign still in possession of the household 4-6 months after distribution	N/A	90%	97% & 99.5%	Ogun and Kano Net Retention and Use Survey 2015 [4]	Milestone exceeded
Cumulative number of LLIN procured and distributed through campaign with DFID funds	N/A	6,740,000	7,224,700	LLIN campaign reports	Milestone exceeded
Cumulative number of LLIN procured and distributed through non-commercial continuous channels with DFID funds	N/A	4,00,000	4,568,284	Programme reports	Milestone exceeded
Cumulative number of SP doses distributed in supported States in supported health facilities	N/A	5,500,000	6,671,785	Programme reports	Milestone exceeded
Cumulative number of LLIN sold through retail channels by programme partners with DFID support	N/A	2,500,000	2,200,000	Programme Sales Report	Milestone not met
[3] Old states/Rest states (Old are Lagos, Anambra, Kano, Katsina, Ogun and Niger)
[4] Ogun and Kano net retention and use surveys done

Key points

The two main interventions supported by SuNMaP for the prevention of malaria were the distribution of LLINs and sulphadoxine-pyrimethamine (SP) as IPT (intermittent preventive therapy) in pregnant women. SuNMaP has made a major contribution to the national LLIN campaigns by supporting NMEP to coordinate campaigns and in the development of guidelines and other tools. SuNMaP directly supported campaigns with technical assistance and the provision of commodities in Kano and Anambra states. The programme has led in the mobilisation of partners to contribute over 60 million LLIN for distribution through initial mass LLIN campaigns and also led in providing technical assistance for the coordination of for the Replacement campaigns to distribute over 40 million LLINs.

As part of the strategy to keep up coverage, SuNMaP has been supporting the routine distribution of LLINs through antenatal care (ANC), immunisation programme, schools and community channels to target the most vulnerable groups; pregnant women and children under-5 years. SuNMaP is on track of meeting programme targets with regards to LLIN campaigns, and continuous distribution of LLINs in 9 programme states.

The target on distribution through retail outlets was not met. Since 2013, the commercial sector component of the programme has been implementing a revised strategy using the M4P approach to support LLIN retail market development with mixed success. A major on-going challenge is the reluctance of the private sector to engage in the marketing of bed-nets in the face of the replacement campaigns that distribute free bed-nets and leakages of nets from these campaigns into the commercial sector. SuNMaP has tried to focus on niche markets and targeted expansion of the market channels.

The programme also invested in innovative approaches such as collaborating with USAID in pioneering the design and implementation of NetCalc, a LLIN needs modelling tool, and implementing Seasonal Malaria Chemoprevention.

Collaboration with Crown Agents in the smooth and timely importation of commodities has been quite turbulent often leading to significant delays. When asked about purchasing from local manufacturing firms, Crown Agents insists that it is constrained by EU regulations on all orders over £108,000 and that local suppliers are not be able to meet the varying specifications of institutional orders or to be price competitive (in relation to international suppliers). Concerns have been raised in annual reviews about the quality of the service of the Crown Agents – in terms of quality, speed and price.

SuNMaP has been working with its partner states to develop logistics supply systems that would enable the secure transfer of malaria commodities from state central medical stores to the health facilities in the required quantities to meet demand. However until the improved systems are in place there are likely to be periodic shortages in the availability of commodities and significant numbers of potential beneficiaries will not access the services.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations for future programmes

1. Document and disseminate learning from challenges in creating a viable market for LLINs in the context of massive free distribution (which is itself a good thing). What has been learnt about what works?
2. Continue supporting the commercial sector especially in the development of local LLIN manufacturing capacity, but with clear strategy of acting as a catalyst only.
3. Continue maintenance of routine public sector commodities (ANC, IMMs clinics, SP for IPT, School programmes)
4. Increase advocacy to FGN and the public regarding the security of nets procured for public sector distribution.
5. Mass net distribution campaigns have become the corner stone of malaria elimination efforts. Public health investments in this approach was based on several assumptions around coverage, use etc. We recommend a major scientific evaluation of the campaign approach to mass net distribution, to assess if the assumptions on which the approach was based, were met in the Nigerian context, and if these campaigns have led to the anticipated results. If this is not the case, are there alternative approaches to campaigns, to achieving high coverage, such as doing this in 3-year cycles? It is important to avoid the early situation with polio of many poor campaigns. If any campaign is to continue, a lot more emphasis need to be placed on quality.

Output Title	Access of the population to effective treatment for malaria is improved
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme	Latest values (Feb 2016)	Source	Performance
Cumulative number of ACTs / RDTs procured and distributed through routine channels with DFID funds	0	ACT - 4,200,000 / RDT -4,800,000	ACT – 4534515 / RDT – 5,107,291	Programme reports	Milestone exceeded
Ratio between number of malaria tests done that are positive and the number of malaria treatments in selected health facilities (secondary / primary).	N/A	>0.8 / >0.4	0.97/1.17	Sentinel Survey report	Milestone met
Cumulative number of service delivery points with health workers trained on capacity building service delivery modules in programme states	N/A	10,500	12,977	Programme report	Milestone exceeded
Cumulative number of subsidised ACTs and RDTs sold through retail channels by programme partners with DFID support	0	ACT - 4,000,000 RDT - 1,000,000	ACT - 8,226,366 / RDTs – 300,000	Programme sales reports	Milestone for ACT exceeded / Milestone for RDT not met.

Key Points
While most indicators for this output were met, there were recurring delays in the procurement process, which caused long periods of stock outs in some states throughout the programme implementation period. These delays were caused by several factors through the life of the programme; procurement delays, clearing delays of products at the ports, testing of efficacy and reliability of the tests for RDTs upon receipt in country; an additional requirement of government to the normal factory batch testing and other quality controls.
In 2012, the procurement of ACTs was delayed for many months when it was decided to access supplies through the Affordable Medicines Facility – malaria (AMF-m) route. This required an extended period of registration with AMF-m, but resulted in ACTs being procured at around half the price of the previous procurement.
SuNMaP invested large resources in training programmes for malaria case management, microscopy, use of RDTs, malaria commodities logistics system and in monitoring and evaluation. Although the acceptance and use of RDTs has increased significantly as shown by the indicators above, there are still challenges with acceptance of RDTs as a prerequisite for ACTs. However, it is important to recognise that behaviour change does take time and effort.
Service delivery training targeted at primary health care (PHC) workers, and health staff working in secondary care facilities and in the private sector, including PMVs was delivered through the programme. Despite the efforts at training public and private sector participants, there are remaining capacity deficits, especially in diagnostics. Also, apart from in Lagos, most other states did not have a clear mechanism of monitoring and managing the distribution of people with specific skills. Quality assurance of diagnostic procedures (microscopy and RDT use) is still insufficient, despite initiatives taken.
The existence of many “fake” RDTs in the market, and the complex argument on the long term financial benefit to patients of paying for RDTs when the costs of ACTs are so low; as well as the government’s delay in changing policy on RDT use among private patent medicine vendors (PPMVs) – only finalised in October 2014 - have all contributed to the slow uptake of RDTs.
For health professionals, the “test and treat” message on RDTs contradicts some long held assumptions on the utility of good clinical “acumen” in malaria diagnosis. This is related to a poor understanding of concepts of sensitivity, specificity, positive and negative predictive values and their relationship with prevalence of a disease in making a diagnosis.
Although not initially planned or reflected in the indicators above, it is worthwhile to mention that the programme has trained over 300 health workers in the management of severe malaria with use of injectable artesunate in both public and private sector from 2014 to date. In addition, the programme has procured and distributed 68000 vails of injectable artesunate in 4 programme states. This was based on the SEQUAMAT and AQUAMAT study and demonstrates the programme’s ability to use current empirical evidence to modify programme activities and strategies.

Summary of responses to issues raised in previous annual reviews (where relevant)
	Recommendation(s)	Response(s)
R1	While PMVs in Lagos seemed well trained and able to work with RDTs in Lagos, this does not seem to have happened in Kano or Enugu, and this may be the situation in some other SuNMaP states. During the last months of the programme, it will be a great opportunity to use this time to train PMVs in Kano et al on RDTs	More trainings of PPMVs has now been done in Lagos and Kano, Anambra, Enugu, Kaduna and Niger
R2	In all the states visited, there were ongoing challenges with the quality of RDTs and microscopy. The understanding of the processes of testing as well as interpretation of findings was poor in many settings. A well-managed QA programme linked to targeted interventions where quality is poor will be a great opportunity to improve the overall quality of testing and interpretation	The programme embarked on supporting the states in development of Lab QA framework and implementation and establishment of EQA centres in the states.

Recommendations for future programme

1. Intensify training activities, especially in production streams (medical schools, nursing schools, health technology colleges). This is particularly important as previous teaching on the diagnosis and management of malaria is still very strongly adhered to.
2. Intensify capacity building regarding diagnostics and link this to well-managed QA programme for RDT and microscopy, which should itself be linked back to ISS.
3. Support states to track numbers, location and transfer of trained staff - work with other DFID programmes to support the set-up of HR management systems, including a module for tracking trained staff
4. Support states to develop “Mobile training & QA teams”, moving around states or a “hub and spoke” approach using general hospitals as a hub and PCFs as the spokes.
5. Use new evidence, e.g. MIS results, to provide a better understanding of the epidemiology of malaria in Nigeria, and use this to continue the development of training materials on training “test and treat”
6. Use “change management” approaches from other industries to continue driving change in approaches to diagnosis.
7. Irregular supplies of RDTs and ACTs really harms the malaria response in so many ways. Encourage Crown Agents to establish specialist health procurement section and explore with them or other partners options for creating buffer stocks of commodities to prevent stock outs.

Output Title	Community awareness and demand for effective malaria treatment and prevention are improved
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme	Latest values (Feb 2016)	Source	Performance
Proportion of women of child-bearing age in supported States who know the preventive benefits of LLIN	0	90%	91%	Omnibus data Feb 2015	Milestone met
Proportion of nets received from the distribution campaigns and retained by the household that were used by any household member the night before the survey	0	80%	85%/85.9%	Programme post campaign net retention and use survey (Ogun and Kano)	Milestone exceeded
Proportion of people with access to LLINs within the household compared to proportion of people using it last night (use gap) / (subject to availability of LLIN)	Gap 36%-points	Gap <5%-points	<5%	Monitoring area report 2015	Milestone met
Proportion of women of child-bearing age in supported States who know the preventive benefits of IPT	29%	80	69%	Omnibus survey Feb 2015	Milestone not met
Proportion of care givers in supported States who recognise the need for treatment of malaria within 24 hours	86%	90%	95%	Omnibus survey Feb 2015	Milestone met
Proportion of children under 5 with fever in the past 2 weeks whose care givers sought treatment within 24hrs (same day)	48%	70%	78%	Monitoring area report / (Anambra & Kano)	Milestone met

Key points
SuNMaP has expended considerable effort and resources on advocacy, communication and social mobilisation activities and the results above show a good level of understanding by the population of key malaria messages. This understanding has resulted in some behaviour change, e.g. the increase in the percentage of children under five who sought treatment within 24 hours. There is still a need to understand more clearly the determinants of IPT uptake and bed net use.
SuNMaP has also put a lot of time and effort into the demand creation strategy for the LLIN campaign, and has performed well on most indicators. However, while awareness may be high, this does not necessarily translate into 'demand', which is what the output specifies. It is also not yet clear whether people who are aware of preventive benefits of LLINs and who can afford nets will buy them when their free ones become ineffective. Programme stakeholders and partners have been trained in the skill of strategic communication and these skills are applicable for other health issues.
Communication during the programme often seemed to have been managed as “campaigns” rather than as on-going activity.
SuNMaP supported NMEP to develop a BCC plan for LLIN campaigns. NMEP was also supported by developing malaria control messages (for use in programme States). Furthermore, BCC materials were developed and distributed in all focal States. Also, radio spots and jingles were developed for all States. Culture sensitive BCC materials are now available in programme States, and SuNMaP works with State technical managers to leverage airtime with additional free airtime and free placement on popular slots.
The focus of the free distribution campaigns was on getting the nets out, and it is not surprising that use has lagged a bit. The 6-month follow-up surveys and rapid assessment of reasons for non-use led to SuNMaP doing radio & face-to-face social mobilisation, all of which was good work using Omnibus survey data.
The main driver of Indicator three will be getting pregnant women to come to ANC; getting supplies of SP into ANC clinics; and getting ANC workers to persuade women it is important.
Summary of responses raised to issues raised in previous annual reviews (where relevant)
	Recommendation(s)	Response(s)
R1	A document management system should be set up for NMEP office and website where all the guidelines, frameworks etc. are available and searchable online for the long-term.	Programme supported the revamped NMEP website to include key documents that the SuNMaP has helped developed. Also the SuNMaP microsite was revamped and linked to NMEP revamped site
R2	Intensively document and share learning from challenges in creating a viable market in the context of disseminate massive free distribution. It is clear that the context was difficult given the campaigns as well as leakages from government storage facilities, but some of these mitigating circumstances will change with time and the learning from this programme in term of how markets work for malaria products will be invaluable.	Quarterly monitoring surveys were conducted and result disseminated to partners. Data for round 2 of this survey has been collected and will be compared to round one data. Lessons learnt paper developed.
R3	Document and disseminate learning from innovative approaches, such as school-based distribution in Lagos. In contexts where school attendance is high and this approach is fully implemented, it will enable a new cohort of school children to be reached every year. It will also make the health education that they receive a lot more meaningful if it is accompanied with a net.	Technical report on school net distribution in Lagos state has been disseminated. Currently the state is using the framework developed to distrubute nets through schools using Global Fund New Funding Mechnanism.
R4	Intensify communication activities, and transfer ownership of communication to NMEP, while supporting them in developing communications capacity, especially to maintain website and to grow social media presence	Programme supported the revamp NEMP website to include key documents that the SuNMaP has helped developed. Also the SuNMaP microsite was revamped and linked to NMEP revamped site.
R5	Aggressively document what has been learnt from the programme, and disseminate the results and best practices for malaria control, especially to relevant professional groups, medical, pharmacy and nursing schools. Dissemination should go beyond an event, to include a rich website with all the relevant guidelines, research,, sessions at teaching hospitals, nursing schools, pharmacy faculties	Knowledge management products disseminated during the end of programme dissemination event that involved all stakeholders both at national and 10 supported states. In addition, lesson learnt have been shared to through professional conferences, symposim, NMEP sub committee meetings, publications and websites.
R6	Carefully analyse evaluation data on campaign related to timing of adverts and use this to optimise planning for future campaigns. There is a science to it and it should be taken seriously.	This recommendation was no longer relevant as the programme did not do another media campaign

Recommendations for future programme
1. Intensify communication activities, both locally and through media and support NMEP in developing coms capacity, especially to maintain website and grow social media presence.
2. Carefully analyse evaluation data on campaign related to timing of adverts to understand their impact.
3. Communication is a continuum, and is not effective without a long-term strategy. Plan continued engagement with public, health workers, professionals through various “on-going” mechanisms.
4. Devote more resources and prominence of communication in any future project, including a social media strategy through the life of the project, as well as innovative approaches such as insertions into local films.
5. Much stronger focus of communication and BCC – this is not as easy as it seems. The partners that deliver BCC really need to understand the science of malaria themselves. Clearer efforts need to be made in performance managing BCC partners.
6. Develop better indicators to measure the impact of communication.

Output Title	Operational research into key areas of prevention and treatment provides the evidence base for more effective strategies
Output number per LF		6	Output Score	B
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones		Progress
	Baseline 2007/08	End of Programme 2015	Latest values	Source and date	Performance
Cumulative number of OR questions answered and disseminated	0	14	14 answered / 10 disseminated	Operational Research Reports	Milestone partially achieved
Proportion of OR questions answered by research supported by SuNMaP cited or that inform current malaria strategies and practices or contributed to changes in malaria strategies or practices	0	60%	60%	Programme Reports	Milestone met

As can be seen from the table above, most of the indicators for this output were finally achieved, although it had a fairly bumpy history. In the early annual reviews in 2010 and 2012 it was noted that SuNMaP approached this task with a very cooperative approach. This approach was intended to develop a sense of ownership and to build sustainable capacity for research to support policy development in the malaria space. This approach was taken while recognising that the process by which NMEP is introduced to the process of commissioning, managing and using evidence in policy development is as important as the research outputs. This process was slower than could have been achieved by a less inclusive approach and a lot of time was spent during the early years to achieve the required buy- in, leading to significant underspend in the early years, and a loss of time. This approach also assumes an increasing value being placed by the NMEP on research to support policy development for malaria control. Although some progress was made through the life of the project in this regard (i.e. building NMEP ownership of research activities), this assumption has not fully validated and progress has been slow.
Three research priority-setting exercises were carried out, in 2010, 2012 and 2014, involving several stakeholders, in which research questions were identified and refined. After this, stakeholders carried out rigorous proritisation exercises, where they ranked the questions using a pre-agreed scoring scheme; and studies with the highest priority were commissioned. However, it was not clear what became of priorities identified in previous exercises, nor how the outcome for the new ones identified were being measured in terms of progress towards answering them.
Other work carried out included two reviews of current and recent research in Nigeria on malaria control. Although the reports were titled “Data Collection and Synthesis of Malaria Research in Nigeria”, they did more of collection and very little in synthesis. There were plans to use the information gained from the reviews to develop a virtual resource centre, but there is no evidence that this virtual resource centre was developed and it is not clear how accessible and useful the two reports are to the malaria community.
Research carried out or supported by the programme did lead to policy changes particularly on the methodology of LLIN distribution campaigns to achieve universal coverage, granting permission to PMVs to use RDTs and on the use of SP for malaria prevention.
In summary, during the life of the project, SuNMaP made progress in supporting the establishment of a national OR agenda, and the NMEP was supported with the development of an OR Unit within the M&E department. It also carried out various capacity building efforts among five local research groups and the NMEP. A large number of key research topics were identified with NMEP and partners.
One lesson from the programme is that to improve capacity for research requires consistent, high skilled capacity while still maintaining a collaborative approach. These two ideals are sometimes in conflict with each other.

Summary of responses to issues raised in previous annual reviews (where relevant)
	Recommendation(s)	Response(s)
R1	Substantially improve data collection and data analysis at all levels within the supported States. LGA teams should have a better understanding of how to use routine (HMIS) data for local decision-making	Activities for data collection and data analysis were conducted in all the states including capacity building of M&E officers and Record personnel on use of DHIS II, DQA and data analysis. The programme also focused on monthly M&E focal persons meetings to discuss data quality and use issues

Recommendations for future programme:
1. Continue to build research capacity by doing operational research. Building research capacity and carrying out operational research can be challenging in the Nigerian context, given the maturing nature of local research institutions. However, SuNMaP has identified some local institutions with capacity and has developed a strong framework at the national level, which should be built on in the future.
2. Be more deliberate about thinking through the mechanisms of how research feeds back into the policy agenda of the NMEP, this means that in addition to building research capacity, policy makers need to be educated on the value of making evidence based decisions.
3. Include some funding for innovation research – around new vaccine options and integration with other prevention options, seasonal malaria chemoprevention etc

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
SUNMAP’s key cost drivers include
1. Personnel and Consultants
2. Management
3. Travel
4. Commodities

SuNMaP shows good performance on VFM indicators assessed against the DFID framework. The key cost drivers for SuNMaP, as identified in the business case are commodity procurement and distribution costs, personnel costs, management fees and training costs. Programme data shows that the unit cost per LLIN distributed (procurement & distribution) went down by 4% to £2.49, and; the cost per ACT distributed fell by 12% to £0.52 between years six and seven.[5] These figures fall comfortably within the NAO benchmarks of £2.43-£2.92 per LLIN distributed and £0.98 per ACT distributed. SuNMaP is more directly responsible for LLIN distribution costs. The cost per LLIN distributed via continuous distribution fell by 61% between years three and seven to £0.82 per net distributed. This is good economy.
[5] However, please note that SuNMaP cannot directly influence the unit price of malaria commodities. These are procured by Crown Agents Nigeria Limited (CANL) and CANL are contracted directly by DFID.

Over the programme extension period, management fees have remained fixed at 8% of total programme spend. Staff unit costs have remained stable in year seven. While no benchmark for staff salaries was conducted in year seven (following a benchmarking exercise in year six that showed positive results[6]), an assessment of the unit cost per pound of activity expenditure shows a decline in the unit cost of Long Term Technical Assistance (LTTA) by 14% while the Short Term Technical Assistance (STTA) equivalent measure showed a modest increment of 7%. SuNMaP staff cost per input day, using evidence from the benchmark exercise conducted last year, and the trend in staff costs in year seven, remain at the lower end of the benchmark spectrum.
[6] SuNMaP benchmarked fee rates of various tiers of STTA in 2013/14 and the SuNMaP fee rates ranged from £290-£590 per day. This compared well with fee rates for international consultants in the same field and with commensurate experience from six companies (two UK consulting companies, two UK universities and two other international consultancies of between £225- £960 input per day

On efficiency, there was a sizeable decline in operating costs as a proportion of total expenditure in year seven. Expenditure on operations as a proportion of total expenditure declined from 14% in year six to only 4% in year seven. While some of this decline was due to accounting measurement, with some expenditure, specifically office rent paid up in full last year, SuNMaP achieved real declines in some cost components such as in training materials. The decline in operating costs culminated in the increase in the proportion of funding spent on activities, with activities spend making up 46% of all total expenditure in year seven – the highest the programme has yet recorded. LTTA costs remained at 14% of total costs as in year six, while STTA costs as a proportion of total expenditure increased from 11% to 14%. This; expected given the additional technical support required for campaign net distribution during the year.

The proportion of overhead expenditure dropped to 13% during the year – the lowest recorded by SuNMaP since year two. Budget performance of SuNMaP however is below average. Data available from SuNMaP shows that the programme workplan performance to date is 68% (i.e. the programme has achieved 68% of its workplan targets) but utilising more than 77% of the budget. In some cases, e.g. in output three, budget expenditure was exceeded and performance on outputs exceeded.[7]
[7] £223 000 was overspent on Output three in year seven, but, for the same output, 114 000 SP doses and 600 000 LLINs (through campaigns and non-continuous channels) more than target were distributed.

The SuNMaP intervention remains cost-effective. Cost effectiveness was assessed using two widely used international methodologies to estimate cost effectiveness of health programmes – estimating the cost per life saved using the Lives Saved Tool (LiST) and estimating the Disability Adjusted Life Years (DALY) averted.

Using the DALY method, SuNMaP is estimated to have averted 1 998 912 (approximately 2m to date) DALYs at a total cost of £89m (projected expenditure to March 2016). This equates to approximately £44.52 (or $70.6[8]) per DALY averted. There are three benchmarks to compare these results to:
[8] Using the average £/$ exchange rate of £1/$1.585 between 2009 and 2014
1. For low and middle-income countries, a health intervention can be considered cost effective if the cost per DALY averted is less than $150 per DALY averted.[9] SuNMaP costs per DALY averted more than 50% lower than this benchmark.
  [9] Investing in Health Research and Development. Report of the Ad Hoc Committee on Health Research Relating to Future Intervention Options. WHO, 1996
2. WHO proposes that an intervention is highly cost effective if the cost of saving a life for a year is less than the GNI per capita in that country. The GNI per capita of Nigeria is currently $2 950.[10] SuNMaP cost per life saved using both the LiST and the DALY methods is well below this benchmark, regardless of the LiST estimation potentially being an underestimate
  [10] http://data.worldbank.org/indicator/NY.GNP.PCAP.CD
3. A third benchmark on the cost effectiveness of malaria interventions for countries with moderate to high malaria transmission[11] (such as Nigeria) shows that the cost effectiveness of ITNs and insecticide treatment is between $19/DALY averted and $85/DALY averted. SuNMaP cost per DALY averted is below benchmark.
  [11] Hanson, K., Goodman, C., Lines, J., Meek, S., Bradley, D., & Mills, A. (2004). The Economics of Malaria Control Interventions. London School of Hygiene and Tropical Medicine

Overall, the SuNMaP intervention remains highly cost effective.

VfM performance compared to the original VfM proposition in the business case
Compared to the business case proposition, the economy and efficiency indicators are within the prescribed business case indicators. On cost-effectiveness, the cost per life saved is higher than the projected business case extension cost per DALY averted of $30/DALY, but remains within the VFM trigger points as it is below the conventional benchmarks. Overall, the programme thus remains VFM when compared to the business case.

Assessment of whether the programme represented value for money

The programme represented excellent value for money for DFID.

Quality of financial management during programme

SuNMaP’s financial management and governance resides within the MC enterprise financial systems and reporting framework. The robustness of the SuNMaP and Malaria Consortium (MC) organisational financial systems and in particular SuNMaP implementation at programme level are routinely verified by independent DFID and MC audits, as well as through regular compliance visits at HQ and state level.
In 2015, a number of audits including an asset verification audit, compliance audit, fund accountability audit and a stocks verification audit were conducted. The audit findings for all these were communicated to DFID, and did not flag any issues of serious concern

Date of last narrative financial report	21 March 2016
Date of last audited annual statement	13 August 2015

E: RISK (½ page)

Quality of risk management over the life of the programme

The risk for this programme was originally assessed as medium. In this review, the risk assessment has been updated using the new DFID risk rating system, and is now assessed as moderate.

Risk management over the life of the programme has been robust. Key risks the programme has had to manage include poor financial and poltical commitment of federal and state governments to malaria control; delays in procurement of key commodities leading to significant disruptions; difficulties with synchronising the input of other key donor partners, some of whom faced serious disruptions of their own; the risk of loss or diversion of money or commodities; security issues in the northern States, particularly Yobe; and the risk of biological resistance to insecticides and malaria medication.

These risks have been managed through risk registers at DFID and project level as well as the delivery plan. Risks and the effectiveness of mitigation have been tracked using the quarterly Programme Management Committee meetings and the annual reviews. The programme proved very adaptable to change and mitigating actions have generally been effective.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme outputs were mostly achieved or exceeded by the end of the programme.

Collaboration with Crown Agents in the smooth and timely importation of commodities has been difficult often leading to significant delays. Delays in delivery of rapid diagnostic tests affected the roll out of the Behaviour change communication as the test before treatment campaign commenced without the widespread availability of commodities. This has been cited by the programme as reducing the impact of the campaign.

Performance of partnership (s)

The programme worked exceedingly well with other partners, particularly other malaria donors and government agencies involved in malria control. The programme has been largely responsible for the significant strengthening of co-ordination arrangements for malaria control at national and state level.

Partnerships with other DFID programmes have been good but could have been better. The programme worked well with the PATHS2 and PRINN-MNCH programmes, but there could have been more effective collaboration with other DFID programmes such as MNCH2, SPARC, SAVI, and GEMS at state level.

Internal partnership within the project consortium partners (Malaria Consortium, Grid Consulting and Health Partners International) and the other implementation partners- CHAN, CHAN-MEDIPHARM, FOMWAN, HERFON, and Centre for Communications Programme Nigeria (CCPN) – has appeared excellent during the life of the programme.

Asset disposal and value obtained by DFID

The programme assets have been disposed of in line with DFID asset disposal guidance and a proposal approved by DFID Nigeria. Assets have been transferred to government malaria agencies at the state and federal level, and civil society organisations supporting the health sector or malaria control. The residual assets have been auctioned or are awaiting auction. Any value obtained after the auctions are concluded will be transferred to DFID.

G: CONDITIONALITY (½ page)

Partnership principles assessment

The programme was designed prior to the development of the Partnership Principles, so did not envisage a role for the Principles in the management and monitoring of the programme.

DFID Nigeria has now completed a Partnership Principles Assessment for Nigeria. The assessment indicates the programme approach of working with government and other partners to improve malaria control capacity and coordination, but not passing any funds through government systems, remains appropriate. Given this, the partnership principles did not form a formal basis for conditionality under this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

National household surveys such as the Demographic and health Survey (DHS), The Multiple Indicator Cluster Survey (MICS), and the Malaria Indicator Survey (MIS) etc. serve to provide evidence and evaluation measures for the SuNMaP program. To this extent some of the log frame measures are linked to these surveys. However, these surveys take place periodically and with intervals for up to 5 years. This poses a problem for the program as infrequent surveys mean lack of data to assess outcome level achievements.

To give an interim view of program impact and outcomes, the programme established four monitoring areas that represent the different strata of the malaria epidemiology in Nigeria to assess trends in transmission exposure.

The output to outcome assumptions under the theory of change have not held up as much as initially expected. Complementary input from other partners and the Nigerian government have been substantial, but significantly below the level required to fully achieve the programme outcomes to the same level as the outputs. In addition, changes in malaria epidemiology in Nigeria and malaria treatment policy during the course of the programme rendered a number of outcome indicators less relevant than initially expected. This probably counts for the greater achievement at output level relative to the outcome level.

Monitoring progress throughout the programme

The programme monitoring processes are outlined in the programme’s M&E framework. All input and process data collected based on the strategies and activity plans are contained in the Programme database.

Output monitoring captured commodities distributed, BBC materials produced and distributed, commodities sold, services provided and people reached; with monthly data collections and quarterly summaries from existing HMIS system, special data collection tools and records from implementation (training, supervision, BCC campaigns, materials and sales).

The programme workplan performance monitoring system was used to monitor the progress of activity implementation in all locations. The traffic light system” was to enable managers at a glance to detect slow progress in implementation for effective intervention.

Outcome/impact assessment: rather than undertaking population based survey specifically for the programme, a system was designed to utilizes existing nationally representative surveys such as DHS, MIS or MICS supporting their funding, implementation and analysis as necessary in combination with more decentralized or specialized surveys.including the following:

Net tracking – Net retention and Use: The programme conducted a series of LLIN retention surveys using the methodology developed by Malaria Consortium in to determine, the targeting, retention and use of LLIN approximately 6 months after campaign distributions in Niger, Lagos, Katsina, Ondo, Ogun, Anambra and Kano. This methodology is not used widely by other partners involved in LLIN distribution globally.
Nigerbus - knowledge, attitudes and practices: The programme subscribed into commercial research (Omnibus) aimed at measuring knowledge, attitudes and practices of the public. The results were useful in the focal States with regards understanding and demonstrating trends in knowledge, perception and behaviour and targeting demand creation activities by the programme and implementing partners.
Health facility assessment survey: The programme conducted two health facility surveys, using a mix of methodology and tools applied by World Bank Booster project and WHO. In addition, the programme conducted laboratory assessments in the states to inform the implementation of parasitological based diagnosis of malaria.
Market and Pricing Surveys: programme undertook retail outlet and pricing survey for LLIN, ACTs and RDTs from 2010 – 2012 to provide independent information on market penetration, actual retail prices (delivery of price support to consumer), and variety of products found as well as provider knowledge and behaviour. In addition, the programme conducted Quarterly Market Monitoring Survey (QMMS) – a quasi-experimental survey in 2015 to test a framework that could be applied by the project to assess systemic changes in the market.
Monitoring area survey: The programme conducted periodic monitoring areas surveys in Kano and Anambra from 2009 – 2015 aimed at establishing trends in morbidity in different strata of the malaria epidemiology in Nigeria and relates these to coverage. In addition, the programme has supported the establishment of Beyond Garki surveys that aimed at monitoring changes in the epidemiology of malaria within the context of the implementation of various interventions, assessing conditions for reducing transmission below its critical level where resurgence is unlikely, and make recommendations to adapt prevention and control measures to observed changes. The changes are monitored to provide an evidence base to guide policies and strategies
Sentinel sites: Recognizing the weakness in the HMIS system, the programme undertook measures to improve the quality of the HMIS special efforts with establishment of sentinel health facilities and use results from these sites as part of Data Quality Assurance (DQA).

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process