Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Uganda Accountability Programme
Programme Value: £ 100,515,548.00		Review Date: 8th June 2016
Programme Code: 200250	Start Date: 15th June 2009	End Date: 31st December 2016

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score			B	A	A	A
Risk Rating			Medium	Medium	Medium	Medium/High

Summary of progress and lessons learnt since last review

Since the 2015 annual review, progress on the remaining active components of the programme has been broadly positive. This is encouraging given both the complexity of the programme, the significant reprogramming that was required following the misappropriation of funds in 2012/13, and the complexity and rapidly evolving nature of the operating context.

The original programme period was 2009 – 2014 and whilst the overall programme timeframe has been extended to 2016, a number of the act ivies and components have ended prior to and during the period of this review. This review only reports on those components that remain active, on action against outstanding recommendations for the other components, and on lessons learned. The Project Completion Review will provide the vehicle for a full overview of the programme’s results and the contribution to its expected outcome. The status of each Output is summarised below. These were supported under two initiatives – Enterprise Uganda and the Democratic Governance Facility.

Output	Status
Output 1 - Local government capacity for equitable service delivery and management is strengthened.	Components relating to the Output were closed and inactive.
Output 2 - The most vulnerable conflict-affected communities are rebuilt and empowered.	Components relating to the Output were closed and inactive.
Output 3 - The private sector is revitalised and accessible employment opportunities are created.	Active
Output 4 - Government, civil society and communities can engage actively in peacebuilding and reconciliation.	Active

The reporting period was characterised by Presidential, Parliamentary and local government campaigns for political office. Despite the challenges created by the electoral process, a total of 15,875 Northern Ugandan youth participated in market relevant skills training, including literacy and vocational skills. The youth trained in the Business Enterprise Start up Tool (implemented by Youth Business International (YBI), in collaboration with their local delivery partner, Enterprise Uganda (EU)) resulted in the training of 13,377 youths. 161 youth were assigned to mentors and 1,555 youth were assigned to business counsellors. These results are currently being verified and assessed as part of the independent project evaluation, the results of which will be fed into the final PCDP review – the project completion review.

Under the DGF funding, Rights, Justice and Peace implementing partners delivered progress towards planned outcomes. This was despite the uncertainty faced as DGF secured an extension period, a revision of the DGF Theory of Change and logframe, and concerns that the proportion of youth and women would be lower than the targets set by PCDP. The latter concern was addressed early in the performance period by changes in beneficiary targeting activities and support services.
Under PCDP, the UK supports the RJP component of DGF to enable civil society organisations to engage in dialogue at local and national levels, on peace building, access to justice, human rights and transitional justice as well as to work with GoU on the development of policy and legislation.

Affordable legal aid service provision continues to grow both in reach and geographical coverage. Legal aid was extended to 74 districts in 2015/2016 up from 59 in 2014, then 67 in 2015 and now 74. In total 416,197 cases were handled by DGF partners during the reporting period. Furthermore, capacity of 685 Local Council III court members across 45 districts has been built. In 2011, the five year target for legal aid was set to reach 2 million men and women to benefit by 2016. This target has now been exceeded, with 4,302,093 men and women recorded as beneficiaries by March 2016. When performance for April-June 2016 Quarter is tallied, this figure will rise. Notable challenges are that, legal aid provision remains unsustainably expensive and government has delayed to approve a draft policy and legal framework to facilitate state funding and regulate legal aid provision. State-sponsored legal aid, provided through the ULS and Ministry of Justice is currently limited to capital offences, yet the poor, vulnerable and marginalized people are impacted more negatively without such services.

While progress under PCDP’s active components remains good – with some delivering beyond expectation, questions over the programme’s overall cohesion and aggregate contribution to the planned outcome, and to the Government of Uganda’s Peace, Recovery and Development Plan (PRDP), remain. These will be addressed through the PCR process. To inform the PCR, alongside results documented in annual reviews, a number of evaluations will be available. These include:

- An evaluation of the Northern Uganda Social Action Fund (NUSAF 2)
- A review of the Advisory Consortium on Conflict Sensitivity (ACCS).
- The DGF RJP thematic review and the DGF independent evaluation.
- The Youth Skills programme evaluation.
- Evaluation of the RBF approach to health care delivery.

Lessons learnt

- Independent evaluation and an emphasis on experimental or quasi-experimental evaluation methods are critical. The youth skills projects under Output 3 have been successfully concluded, with an independent evaluation due to report in July 2016. Output targets have been exceeded and positive outcomes have been generated in terms of income increases recorded. The validation of these results and the interpretation of attribution and outcome implications are critical through an independent evaluation process.
- Early access to legal aid services to prevent escalation of disputes is key. Legal aid partners (LEAP) must ensure that disputes are handled as early as possible to minimise disruptions in poor and vulnerable people’s lives. Partners use of paralegals and/or community legal volunteers who live within communities to facilitate early dispute resolution is correct, and offers a more sustainable model for the delivery of legal aid.
- There is a limited recognition of the important role legal can play in poverty reduction. If left unaddressed, legal disputes can escalate economic shock that pushes a vulnerable person into poverty. Labour abuses (such as wrongful termination and failure to pay full wages), land grabbing, eviction of widows and orphans from their homesteads, debt, and family problems (such as divorce), can all produce insurmountable financial shocks to those near the poverty line
- The legacy of the LRA insurgence continues: The impact of the conflict on traditional institutions is still felt and they remain weak.
- The need for multi-niche partnerships in delivery of legal aid services. There is a very high demand for legal aid services, which usually stretches the human and financial resources of legal aid providers. LEAP partners have attempted to have multiplier benefits through partnerships across providers, with government (especially at local levels), and with other agencies for referrals.
- Robust monitoring of quality of care should be incorporated into future RBF payment formula. A lesson learning review under PCDP shows that the quality of infrastructure, medical supplies and management processes improved in the RBF health facilities. But it appears the quality of care was poor in both sub-regions. It is therefore important to ensure robust monitoring of quality of care is incorporated into future RBF payment formula.

Summary of recommendations for the next year
- Ensure findings of the youth skills evaluation are well disseminated amongst partners and other DFID offices and interested advisers.
- Include a review of PSFU grants in the final evaluation of PCDP.
- DFID to take a decision on its future support on Rights and Access to Justice, based on the findings of the component thematic reviews and DGF Evaluation findings.
- Seek greater standardisation of legal aid service availability and quality, displaying innovation and value for money, and ensure legal aid services are responsive to the demands of poor and vulnerable people.
- Adopt the revised PCDP logframe as the monitoring tool for the PCR and adapt the legal aid indicator to cover only the PRDP districts, and update the risk register for the RJP.
- Conduct a PCR which documents lessons learned from all components of PCDP and sets recommendations on relevant future programming (ToRs drafted: Quest 5494497).
- Future DGF audits will have a risk-based remit. In addition to the audit opinion on controls (how well designed and operated), they will specifically review the effectiveness of risk management and assurance mechanisms to enable the PMU to direct its resources most effectively on areas of highest risk or where there are gaps or weaknesses in other assurance arrangements - preventative and detective controls.

A. Introduction and Context

DevTracker Link to Business Case:	4972277
DevTracker Link to Log frame:	5061544

Outline of the programme
Conflict in Northern Uganda lasted 23 years and prevented the people of Northern Uganda from enjoying the benefits of national stability and economic growth seen elsewhere in the country. As poverty steadily reduced across Uganda, levels in the north were 22% above the 2009 national average.

The UK’s Northern Uganda Post-Conflict Development Programme (PCDP) approved £100,515,548 million to support recovery in post-conflict northern Uganda. This programme, now running over six years (2009-2016), was originally designed to build on the emerging peace in greater Northern Uganda following the Cessation of Hostility Agreement between the Lord’s Resistance Army (LRA) and the Government of Uganda (GoU). It aimed to support GoU’s Peace, Recovery and Development Plan by generating growth, development and opportunities and promote peace building in a region emerging from a period of conflict and neglect.

Following the suspension of financial aid to GoU in 2012 (as a result of a corruption scandal in the Office of the Prime Minister (OPM) linked to PRDP), a number of the components under the PCDP were reprogrammed and funding was channelled through different delivery channels. While it was originally intended that PCDP should provide budget support through OPM for the Government of Uganda’s PRDP, the fiduciary risks of doing so were judged to be too high. Additionally, support through the Private Sector Foundation Uganda (PSFU) was phased out, and technical assistance to OPM ended.

The goal of PCDP is to build a peaceful, vibrant Northern Uganda with increased opportunities for the people of the north and reduced poverty for all of Uganda. The outcome is to create economic, social and political opportunities that improve the lives of people affected by conflict. The original programme period was 2009 to 2014, and while the overall programme timeframe has been extended to 2016, a number of the act ivies and components have ended prior to and during the period of this review, and the budget has been reduced to GBP 90,024,705 accordingly.

The four outputs of the programme and key results are:
1. Local government capacity for equitable service delivery and management is strengthened. This output funded the construction of 1738 homes for health workers and teachers, increased 21 target District sub-country governance conditions to a minimum standard, and installed community-level project Monitoring and Evaluation (M&E) tracking systems in 485 sub-counties. (Completed).
2. The most vulnerable conflict-affected communities are rebuilt and empowered. This output supported around 3,500 extremely vulnerable people through access to social services, shelter and livelihoods in Acholi and Lango. It also supported almost 24 million labour hours on food/cash for work projects in Karamoja and some 10,000 food transfers. Finally, it is developing an evidence base behind the use of results-based financing in healthcare, through financing 21 results-based health facilities and 10 input-based facilities across northern Uganda, targeting some 345,475 consultations and treatments. (Completed).
3. The private sector is revitalised and accessible employment opportunities are created. This output seeks to contribute to the peaceful development of northern Uganda through encouraging economic growth. The Private Sector Foundation Uganda (PSFU) programme approved grants for 426 businesses (under the target) before it was ended in 2012. However, there is evidence of strong performance from the Youth Development Programme (YDP) and the Northern Uganda Youth Employment Programme (NUYEP) in providing vocational skills and entrepreneurship training. The draft evaluations suggest that PCDP will surpass the targets of 15,400 youth trained in vocational skills and 8,400 youth trained in business start-up. Surveys conducted by International Alert have returned higher-than-targeted responses on perceived access to economic opportunity in the programme areas.
4. Government, civil society and communities can engage actively in peace building and reconciliation. This output has exceeded expectations in influencing the GoU’s Peace, Recovery and Development Plan (PRDP) interventions to make them more conflict sensitive. Through the Democratic Governance Facility (DGF) legal aid services are being provided, and satisfaction with the role of traditional institutions in traditional justice processes is currently above the target, though there are indications that these figures are declining. This annual review is recommending that the logframe indicator be revised to specify legal aid services provided just in the PRDP region with revised milestones and targets for the DGF extension period.

Two active components remained during this performance period, a youth development programme delivered by VSO and Youth Business International (YBI) through its partnership with Enterprise Uganda (EUg), and the Rights, Justice and Peace Component of the Democratic Governance Facility - a multi-donor basket fund.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

PCDP aims to increase economic, social and political opportunities, thus improving the lives of people affected by conflict in northern Uganda. It was originally designed to support and contribute to the GoU’s PRDP across a range of sectors. The outcome is to create economic, social and political opportunities that improve the lives of people affected by conflict.

The PCDP was originally firmly aligned behind GoU’s Peace Recovery and Development Programme (PRDP) and the Poverty Eradication Action Plan (PEAP) (later replaced by the National Development Plan). PRDP is a sequence of programmes that include the Northern Uganda Social Action Fund (NUSAF), The Northern Uganda Agricultural Livelihoods Recovery Programme (ALREP) and the Karamoja Livelihoods Programme (KALIP). The overall objective of these programmes is to consolidate peace and lay a foundation for recovery and development.

In relation to the overall impact of the GoU’s PRDP, the proportion of people living in poverty in northern Uganda has reduced in recent years, but only slightly - from 46.2% in 2009/10 to 41.8% in 2012/13. This is compared with the decline in the national average from 24.5% in 2009/2010 to 19.7% in 2012/13 (National Poverty Status Report, 2014). According to the Uganda Bureau of Statistics, the October 2015 Statistical Abstract reported that the incidence of poverty remains highest in the Northern region at 43.7% compared to the National average of 19.7%. Perceptions that the North is marginalised by the GoU persist, with the final Peace and Conflict Indicators Survey (PCI) showing only between 41.1% and 47.5% of respondents in affected areas reporting that post conflict development interventions in the North have helped bridge differences between the North and South. This is down from 64.2% two years ago. ’
Changes in PCDP components and delivery channels demand that its overall cohesion and aggregate contribution to the planned outcome, and to the PRDP be assessed comprehensively through the Project Completion Review. Support for and coordination and monitoring of the overall PRDP was affected by the discovery of misappropriation of funds in OPM, which amongst other things resulted in the withdrawal of DFID’s technical assistance for OPM, the decision not to provide budget support for PRDP under PCDP, and the cessation of budget support for PRDP by a number of other donors. Additionally, the PCDP Steering Committee did not continue to function after this series of events.

The revised and remaining components of the programme have delivered against their targets and milestones and having impact in their own right, in some cases delivering more direct results than when they were channelled through GoU institutions. Nevertheless, the PCR should consider their aggregate contribution to the expected outcome – while recognising that the changes in programme design were both necessary and correct.

There are significant issues that still hamper recovery in the Northern Uganda. Government is yet to formalise the transitional justice policy and legal framework, conflicts related to land ownership and land grabbing continue to rise, young men in particular lack hope and many succumb to alcoholism. This has led to an increase in sexual and gender-based violence (SGBV). The third phase of PRDP is currently under design, and through PCDP, DFID is providing strategic technical assistance to support this process and ensure the next phase learns critical lessons from PRDP 1, as well as drawing on the findings of the Economic Recovery Analysis (ERA) funded through PCDP.

Outcome Indicator 1	Milestones 2015/16 (This is a target for March 2015). The Logframe does not include milestones for 2016 as the component ended).	Progress
Number of under-fives presented with fever that are tested for malaria and appropriately treated in the 31 PNFP facilities (disaggregated by gender)	21 RBF HF = 32,965 10 IBF HF =12,197 / Total = 45,162	Lessons from the evaluation of the RBF programme were disseminated at a national event in September 2015.

Lessons from the evaluation of the RBF programme were disseminated at a national event in September 2015. These included the importance of robust monitoring of quality of care in future RBF programmes; the possible benefits of sharing monitoring data with district and health facility managers to allow for rectification of detected problems; and the challenges of sustainability beyond the life of the programme given high management and oversight costs.

Outcome Indicator 2	Milestones 2015/16 (This is a target for March 2015). The Logframe does not include milestones for 2016 or for the end of the component).	Progress
Number of YDP youth with decent jobs (employed or self-employed in the formal or informal economy) (attributable to DFID)	11,000 / (50% female)	Participation of 15,875 Northern Ugandan youth in market relevant skills training, including literacy and vocational skills. / These results are currently being verified and assessed as part of the independent project evaluation, the results of which will be fed into the overall PCDP evaluation.

- Outcomes under the youth skills components are positive, with significant income and employment benefits for participants.
- Youth Development Programme (YDP) was implemented by VSO in partnership with 36 vocational training centres in Northern Uganda, drawing on 19 long term VSO volunteers throughout the project.
- Target was exceeded by the participation of 15,875 Northern Ugandan youth in market relevant skills training, including literacy and vocational skills. The sub component closes in June 2016 and the independent evaluation is currently ongoing.
- Youth trained in Business Enterprise Start up Tool implemented by Youth Business International (YBI), in collaboration with their local delivery partner, Enterprise Uganda (EU) resulted in the training of 13,377 youths.
- 161 youth assigned to mentors and 1,555 youth assigned to business counsellors. Of particular note, targets for the establishment of savings clubs were more than doubled (60 clubs established against a target of 25).
- Early concerns that the proportion of youth and women would be lower than the targets were allayed by a change in beneficiary targeting activities, and support services, which resulted in these challenging targets being met.

Outcome Indicator 3	Milestones 2015/16 (This is a target for March 2015). The Logframe does not include milestones for 2016).	Progress
Level of satisfaction among targeted population with quality of basic socio-economic services	90%	Components linked to the outcome indicator were closed before this performance period.

Outcome Indicator 4	Milestones 2015/16 (This is a target for March 2015). The Logframe does not include milestones for 2016).	Progress
Percentage of respondents assessing that local government is responsive to community needs	Acholi 59% / Lango 59% / West Nile 62% / Karamoja 57%	Components linked to the outcome indicator were closed before this performance period.

Overall output score and description

Overall score is A reflecting that each active output has scored an A when assessed against current output indicators.

Key actions

- PCDP will be closed in December 2016. Although all components are being reviewed or evaluated in some form, a PCR will be carried out that will synthesise all lessons learned from components of PCDP and recommendations for future programming. The ToRs for the PCR have been drafted and will be actioned against between in late 2016. (Action: Governance, Security and Resilience (GSR) Team Leader– December 2016).
- In the context of the DGF independent evaluation and the design of DGF2, DFID will decide on its future support on Rights and Access to Justice work. (Action: Governance, Security and Resilience (GSR) Team Leader– April 2017).
- Findings of the youth skills evaluation should be disseminated amongst partners and other DFID offices (PSD Adviser – August 2016).

Has the logframe been updated since the last review?

Although outputs were revised up within the Youth Components in July 2015, and again in January 2016, these are not yet reflected in the overall PCDP logframe. DGF concluded the approval of changes to the logframe in December 2015. The PCDP logframe should now be updated.

## C: DETAILED OUTPUT SCORING

The table below indicates the status of the outputs for the period 2015/16. Only outputs in this performance period are scored.

Output	Status
Output 1 - Local government capacity for equitable service delivery and management is strengthened.	Components relating to the Output were closed.
Output 2 - The most vulnerable conflict-affected communities are rebuilt and empowered.	Components relating to the Output were closed.
Output 3 - The private sector is revitalised and accessible employment opportunities are created.	Active
Output 4 - Government, civil society and communities can engage actively in peacebuilding and reconciliation.	Active

Output 3	The private sector is revitalised and accessible employment opportunities are created
Output number per LF		Three	Output Score	A
Risk:		3.1 High 3.2 Low, 3.3 Low	Impact weighting (%):	25%
Risk revised since last AR?		Risk for 3.2 reduced to low	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline, Milestones, Progress
3.1 Number of applications for small grant scheme received and approved	Baseline 2009 Milestone 2011 Milestone 2012 Target 2015 / Planned 0 500 (received) 200 (approved) 1,200 (received) 800 (approved) 1,200 (received) 1,000 (approved) / Achieved 62 (received) 32 (approved) 363 (received) 273 (approved) 626 (received) / 426 (approved)
3.2 Number of YDP youth trained in a core vocational skill (s) relevant to local market opportunities	Baseline 2009 Milestone 2012 Milestone 2013 Target December 2015 / Planned 0 0 4,400 (35% female, 1,580) 15,400 (50% female) / Achieved 3,687 (49% female) 15,875 / (49.7% women) / 6% with disabilities / (Reached by April 2016)
3.3 Youth trained in Business Enterprise Start up Tool (BEST)	Baseline 2009 Milestone 2014 Milestone March 2015 Target Dec 2015 / Planned 0 2,400 6,600 10,000, revised up from 8400 in July 2015 / Achieved 3556 7,167 13,377 youth / (a total of 15,920 trained, of whom women, 6,841) / Reached by April 2016
3.4 Percentage of respondents perceiving they have access to increased economic opportunity [disaggregated age/gender]	Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2015 / Planned Acholi: 32% [M: 17%, F:15%]; Lango: 27% [M: 13%, F:14%]; West Nile: No data available; Karamoja: No data available. Acholi 42% Lango: 37% Baseline: West Nile; Karamoja Acholi 52% Lango 47% West Nile 34% Karamoja 29% Acholi 62% Lango 57% West Nile 44% Karamoja 39% / Achieved Acholi: 45% [M:24%, F:21%]; Lango: 41% [21%, 20%]; West Nile 24% [M:13%, F: 11%]; Karamoja: 19% [M:14%, F:5%] Partially achieved. Acholi 50%; Lango: 47%; West Nile: 26%; Karamoja: 33% Missed: / Acholi 38.4% Lango 38.8% West Nile 22.7% Karamoja 34.5%

A total of 15,875 Northern Ugandan youth participated in market relevant skills training, including literacy and vocational skills. The youth trained in the Business Enterprise Start up Tool (implemented by Youth Business International (YBI), in collaboration with their local delivery partner, Enterprise Uganda (EU)) resulted in the training of 13,377 youths. 161 youth were assigned to mentors and 1,555 youth were assigned to business counsellors. These results are currently being verified and assessed as part of the independent project evaluation, the results of which will be fed into the final PCDP review – the project completion review.

Tracer studies enabled the Youth Skills initiatives to track outcomes on the lives of beneficiaries. The number of youth earning an income increased from 30% at baseline to 70% by the end of the project. In addition, 97% of the youth under the Youth Development Programme (YDP) had non-agricultural earnings as compared to 50% of those in a comparison group who were not part of the project. A total of 81% of respondents said they were earning an income from a source related to the course they were trained. While earnings were somewhat lower for females than males, outcomes for people with disabilities were better than the average. 41% of youth met the double criteria for a ‘decent job’ of having a an income of 85,000 shillings per month, and having been in employment for 6 months or more, or having expectation of being in employment for the next six months. 60% met the criteria of earning 85,000 shillings or more. 86% of respondents said their standard of living had improved over the project period, while 75% attributed improvements to their participation in the programme.

The independent evaluation states an early finding that 38% of YDP youth reported better knowledge of selected life skills, compared to 8% of a non-beneficiary comparison group. A fuller assessment and validation of these claims including a basic cost-benefit analysis, and discussion of attribution and measurement issues will be included in the final independent evaluation report, and its findings fed into the overall PCDP evaluation.

Key Points

3.1 Number of applications for small grant scheme received and approved. No further activity undertaken. See 2015 PCDP Annual Review for a summary of achievements and challenges. An evaluation of this activity will be included in the PCDP overall evaluation.

3.2 Number of YDP youth trained in a core vocational skill relevant to local market opportunities.
The £7,524,643 Youth Development Programme (YDP) was implemented by VSO in partnership with 36 vocational training centres in Northern Uganda, drawing on 19 long term VSO volunteers throughout the project. The key output has been exceeded by the participation of 15,875 Northern Ugandan youth in market relevant skills training, including literacy and vocational skills. The sub component closes in June 2016 and the independent evaluation is currently ongoing.

A fuller assessment of the component will be contained in the independent evaluation report, currently being finalised. The results of this evaluation will be included in the final PCDP evaluation.

Additional results: The sub component achieved significant results[1] beyond the achievement of the PCDP output indicator. A non-exhaustive list is presented below, along with targets agreed between VSO and DFID as part of the sub-component’s separate logframe:
[1] These results are drawn from the VSO end of project report, Quest reference: 5468564

Direct benefits for youth
- Youth placed in industrial training: 2437 (or 15.4%, against a target of 5%)
- Youth receiving seed funding for business development (7237, or 46%, less than the target of 60%)
- Youth receiving mentorship support (3563, no target)
- 15,496 youth taking part in at least 2 ‘youth to youth’ activities (target 12,320)
- 11,185 youth trained in literacy and numeracy (target 10,500)
- An average of 8.6 sessions of psychosocial support, guidance or counselling received by youth (target of 7 sessions)

Benefits to the 36 partner vocational training centres[2]
[2] Originally 40 institutes were part of the project; four dropped out because of performance and/or financial management issues.
- 979 vocational centre staff trained in curriculum development (target 520)
- 368 staff vocational centre staff and board members trained or mentored on governance, strategic planning, financial and administrative management etc. (no target)
- 3.5 measures per partner institution to better include students for females and/or disabled (target of 7 per institution)
- 13 courses added or adapted as a result of market research.

In addition the project instituted innovations in relation to crèches, income generation, financial and data management systems, and partnerships with private sector companies.

The package of support provided by the project appears to have been highly appropriate in the context of post conflict Northern Uganda, and to the needs of vocational training institutes in the areas. Monitoring visits throughout the year by DFID field staff have confirmed that many innovations are likely to have a sustainable impact, although some services, such as the employment of guidance counsellors, will be reduced by the ending of the funding.[3]
[3] Although in some cases, guidance counsellors will be retained under the institution’s own funds.

The project also focused on social engagement and self-esteem. The independent evaluation has stated an early finding that 38% of YDP youth reported better knowledge of selected life skills, compared to 8% of a non-beneficiary comparison group.

A fuller assessment and validation of these claims including a basic cost-benefit analysis, and discussion of attribution and measurement issues will be included in the final independent evaluation report, and its findings fed into the overall PCDP evaluation.

The project agreement with VSO was extended (at no additional cost) to June 2015 to allow for dissemination events, and a longer period for the independent evaluators to complete their work, and for further activities aimed at embedding some of the changes to the vocational institutes.

3.3 Youth trained in Business Enterprise Start up Tool (BEST)

This sub component was delivered by Youth Business International (YBI), in collaboration with their local delivery partner, Enterprise Uganda (EU). The budget was revised from £2,280,645 to £2,738,984 in July 2015, and the project extended to December 2015. This was justified by a planned a rise in key PCDP indicator of number of youth trained from 8,400 to 10,000. YBI then proposed that exchange rate savings could be used to train further additional two cohorts (totalling 1,647 trainees) in Quarter 1 of 2016, at no cost. A no cost extension extended the project to June 30th 2016 to allow for this, as well as for further evaluation and dissemination activity. The final number of youth trained reached 13,377.

The PCDP logframe output target for delivering ‘BEST’ Entrepreneurial training to youth in Northern Uganda has thus been comfortably exceeded[4]. This is partly a result of strong performance throughout the project, as well as the addition of the two training cohorts in Q1 2016. Given the sunk costs of the project, the delivery of additional training cohorts represented good value for money.
[4] These findings and results are drawn from the YBI annual report, Quest reference 5468508

The sub-component maintained its own, more detailed logframe with five outputs, covering 14 indicators. All were achieved or exceeded, largely due to the additional numbers of students enrolling in the project. Additional outputs included specialised follow up business training (received by 6,988 youth); 161 youth assigned to mentors and 1,555 youth assigned to business counsellors. Early concerns that the proportion of youth and women would be lower than the targets were allayed by a change in beneficiary targeting activities, and support services, which resulted in these challenging targets being met. Of particular note, targets for the establishment of savings clubs were more than doubled (60 clubs established against a target of 25).

The outcomes and impacts (not included in the PCDP logframe) have been impressive, although also subject to verification and review by the on-going end of component evaluation. Self-reported data from YBI suggests that 7174 businesses were created or expanded against a target of 6000; and 1224 waged jobs were created (target: 1225). Of greatest interest is YBI’s finding that the average incomes of participants increased dramatically from 152,000 Ugandan shillings per month (approximately £35/month) to 404,700 Ugandan shillings per month (£92/month). However, these findings have yet to be verified independently. The real average income increase figure may be lower, as not all beneficiaries were followed up, and it is likely that a greater proportion of those who were available for data collection participation were amongst the more successful. Attribution of this increase is also likely to be significantly less than 100% as it may be expected that youth over the period would increase their incomes even if they were not part of the project. Both issues are being reviewed by the independent evaluation team.

3.4 Percentage of respondents perceiving they have access to increased economic opportunity: No further activities took place. See 2015 Annual Review for an assessment.

Indicator(s), Baseline, Milestones, Progress
Indicator			Baseline	Milestone		Milestone		Milestone		Target
4.1 Number of interventions and systems under PRDP modified to make them more conflict sensitive / 4.1 Number of interventions and systems under PRDP modified to make them more conflict sensitive		Planned	0	3		6		9		The component linked to the output indicator was closed before this performance period.
		Planned	0	3		6		9		The component linked to the output indicator was closed before this performance period.
			Baseline / 2010	Milestone 2011/12 (bridging period)		Milestone 2013/14		Milestone 2016		Target 2016/17 (DGF1+)

4.2 Number of men and women reached by legal aid service supported by DGF	Planned		679273 women and men reached by the Legal Aid Basket Fund partners over a five year period (and an additional 3,002,000 reached by Platform for Labour Action's mediate outreach work).		220,000 women children and men reached.		1,500,000 women, children and men reached (and an additional 6,000,000 reached by PLA's media outreach work)		2,000,000 women, children and men reached (an additional 6,000,000 reached by PLA's media outreach work)		700,000 reached directly and through community outreaches, cumulatively to reach 5million since 2012
	Achieved					1,419,548 Progress to date shows 95% of the annual target was reached in six months. Chances of reaching the annual target of 1,500,000 are high. Direct beneficiaries total up to 32,488 and indirect 1,387,060		From July 2015 to end of March 2016, 97,438 men, women and children received individual legal aid services; and 851,715 have been reached through community awareness programs including media outreach. / Cumulatively, 4,832,590 people have been reached by DGF legal aid partners (438,573 people have received individual legal aid services while 4,394,317 have been reached through community outreach programs)		-

			Baseline 2013		Milestone 2012/13		Milestone 2013/14		Milestone 2016
4.3 % of Ugandan women and men satisfied with the role of traditional institutions	Planned		Lango: 91%; Acholi: 97%; Teso: 41%; West Nile:50%		30,000 direct and indirect beneficiaries reached by DGF funded peace initiatives		100,000 direct and indirect beneficiaries reached by DGF funded peace initiatives		Lango: 65%; Acholi: 72%; Teso: 40%; West Nile: 35%
	Achieved					N/A		Latest scores are: Lango 68%; Acholi 73%; West Nile 71%, to be updated after the end of project survey

Output 4	Government, civil society and communities can engage actively in peacebuilding and reconciliation
Output number per LF	Four	Output Score	A
Risk:	Medium	Impact weighting (%):	25%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y/N

Under PCDP, the UK supports the RJP component of DGF to enable civil society organisations to engage in dialogue at local and national levels, on peace building, access to justice, human rights and transitional justice as well as to work with GoU on the development of policy and legislation. Of the total support provided through RJP, 80% is channelled to NGOs while 20% is spent through the Uganda Human Rights Commission (UHRC) and the Equal Opportunities Commission (EOC). Working through 46 implementing partners, RJP has supported initiatives organisations providing paralegal and legal aid services for poor, vulnerable and marginalized men, women, children, people with disabilities, low income workers (below US $80s a month) employees, inmates, refugees and migrants. Through Human Rights NGOs, RJP has facilitated the provision of education focusing on basic human rights knowledge as well as identifying and reporting rights violations. These efforts have led to an increase in reporting and arbitration of human rights violation cases.

RJP also prioritises Transitional Justice and Conflict Prevention in order to facilitate healing in the formerly war torn regions in the country, as well as work with stakeholders to prevent conflict in the country. By working with and training traditional cultural leaders in mediation and gender responsiveness, RJP has increased their visibility, significance and conflict resolution in the post conflict districts. Part of the support awarded by RJP is also spent on capacity building of the partner NGOs and public interest litigation of cases of national importance. As much of the RJP work is in the justice sector, coordination and synergy with state institutions in the justice sector are paramount for conclusion of issues arising from its interventions.

4.1 Number of interventions and systems under PRDP modified to make them more conflict sensitive. This was work relates to the Peace and Conflict Indicators (PCI) work delivered through ACCS which ended in 2014/15.

4.2	Number of men and women reached by legal aid service supported by DGF
Legal aid service delivery has particularly provided relief to poor and vulnerable women (especially widows and orphans), and children in 74 districts of Uganda. In addition, legal aid in the target districts has contributed to reducing the prison remand population, ensuring that men are able to engage in economic activities and look after their families. Due to the scarcity of private lawyers in many PRDP districts, legal aid partners have contributed to filling the gap through providing free legal services especially to persons accused of capital offences. Between July 2015 and March 2016, 97,438 (69,803 men and 27,635 women) accessed direct legal aid services in 74 districts. 8,056 cases have been completed through Alternative Dispute Resolution (ADR) while 3,134 cases have been concluded in Court. LEAP partners have also facilitated the release of 18,155 from police and prison including assistance to obtain police bond, ordinary and mandatory bail and assistance to get community service. On the other hand, LEAP partners have facilitated the recovery of UGX 429,188,974 on behalf of poor and vulnerable persons in terms of maintenance/child support, unpaid wages, compensation for unfair termination, terminal benefits etc.

Much of the increase in geographical coverage has been undertaken in the PRDP districts of Northern Uganda. Notably, additional support has been used by the Uganda Law Society to provide legal aid in the Karamoja sub-region, covering Moroto, Nakapiripit, Abim, Kotido and Napak districts. DGF provided additional support to Legal Aid partners and Paralegal Advisory services providers to open up clinics that provide comprehensive legal aid services to all poor and vulnerable persons, ensuring that no one, especially women and children, is left behind.

Through their umbrella organisation (Legal Aid Service Providers Network - LASPNET), legal aid partners have undertaken research to facilitate profiling of poverty and vulnerability in order to enhance the targeting of services to those who need them most. Efforts are now able to focus on meeting the needs of vulnerable people such as the disabled, prisoners, refugees, juveniles and children. LASPNET also undertook a Cost Benefit Analysis of legal aid service provision, whose findings have been used by the Justice Law and Order Sector (JLOS) to lobby and advocate for a government-funded legal aid program.

4.3	Percentage of Ugandan women and men satisfied with the role of traditional institutions.

Progress against this indicator is measured against information provided by the RJP partner reports. Progress for the final target will be measured in a DGF endline survey which is expected to be partly covered by a separately commissioned survey.

In 2011, DGF partnered with Ker Kwaro Acholi (KKA) – the traditional cultural institution comprising clan chiefs but headed by a Paramount chief in Acholiland, Northern Uganda. DGF would support training of cultural leaders in conflict mediation and dispute resolution to play a natural role as mediators, pacifiers and bastions of justice in post conflict Northern Uganda. The support also focused on gender education to increase gender and security sensitivity among the cultural leaders. However, in 2014 DGF took a decision to cease support to KKA when it failed to fully account for our funding.

DGF has redirected delivery against this output indicator by supporting NGOs to work with selected clan leaders in Northern Uganda without channelling money directly to the KKA. For example, one RJP partner, the Centre for Women in Governance (CEWIGO) has implemented a project to monitor Uganda’s UNSCR 1325 commitments and ensuring it accounts for commitments on women’s peace and security in the region. CEWIGO has worked with four district local governments to and help them develop clear strategies and Local Action Plans to promote women’s rights and women’s peace and security in traditional set-ups.

A number of other interventions have reinforced legal aid interventions to ensure efforts to promote peaceful co-existence and reconciliation are supported by traditional leaders. Through the RJP transitional justice intervention (July 2015 to March 2016), the Refugee Law Project - Beyond Juba III facilitated and scaled up provision of medical and psychosocial assistance to yet unreached areas of Uganda. It conducted eight additional dialogue sessions in West Nile, Agago and Pader. The sessions reached a total of 227 participants (128 men and 99 women) in conflict affected communities, who are now aware of available physical repair and psychosocial support services for war wounded victims. In Arua District, 95 members of the Ombachi Massacre Survivors Association were trained to provide peer counseling and can now assess and refer others for appropriate physical and psychosocial support services. In Teso sub-region, a total of 132 participants (95 men and 37 women) participated. As a result, more victims have been identified, profiled and are now accessing much needed physical and psychosocial support (21 new cases (8 men and 13 women) were identified in Teso and profiled for immediate surgery and or medical support). In total 109 clients were supported by RLP to access specialised surgical operations and medical treatment. The service providers were also trained to increase innovation in dealing with the physical and psychological impacts of war.

RJP’s other partner in transitional justice, AYINET has initiated interventions since October 2015 in medical and psychosocial support in selected district of the PRDP, working with traditional leaders to mobilise efforts in the communities.  The actual numbers of victims who received surgery were 265 (120 males and 145 females). Follow up and evaluation findings indicate that out of the patients that were offered physical repair and discharged back to the communities: 94% were recovering progressively, 43% of them had fully regained their physical functionality are currently involved in many economical activities while 51% were still recovering and visiting the nearby health centers for complete healing, though they were also partly involved in economic activities. 6% of the patients had not yet recovered and are seeking for further support towards attaining their healing.
The contribution to social cohesion by RLP and AYINET was further reinforced by the capacity building of six existing support groups and establishment of two new support groups (LugoroTute and Uketo wan Kwenein Agago and Pader Districts respectively). These groups were trained and engaged in a series of capacity building engagements which benefited 150 current members. Other activities included a leaders learning retreat in Gulu and mobile legal information sessions with survivors of the Omot massacre on rights awareness and advocacy skills.
The benefits of RJP-supported the National Memory and Peace Documentation Centre (NMPDC) which is now playing a catalytic role in promoting dialogue on peace and justice in Northern Uganda have continued to be observed during this reporting period. The Centre documents, archives and exhibits peace and conflict materials and events and attracts a growing number of visitors and high profile delegations. The Centre has supported and documented a number of local level transitional justice initiatives and led on the Martyrdom of Janani Luwum in Mucwini where 3000 Ugandans and other nationals, led by the Prime Minister and Archbishop of Uganda , marked the first national Janani Luwum Day in February 2016.

Concerns on human rights in Uganda continue to be raised by international and national actors (Human Rights Watch, Amnesty International, Human Rights Network of Uganda/HURINET). The declining human rights performance is in part to be attributed to electoral process during the reporting period. Political rights were suppressed with the blockage of political leaders from conducting consultations with the citizens, which culminated into arbitrary arrests, restrictions on civic and political rights such as expression and association. Key highlights of our support on human rights in the period are:

- An increased level of collective organisation and professionalism of civil society partners working on human rights. For example, 156 CSOs collectively inputed in to the draft National Action Plan (NAP), although it not yet clear how many recommendations Government will accept.
- Through human rights education and sensitisation of citizens on their legal rights, citizens have been gradually empowered to speak up and claim their rights. This is evidenced in the number of citizens who have claimed their rights and sought redress for rights violations by addressing their complaints to institution that are mandated to address them. In the reporting period, human rights education benefited 33,260 men and women through community outreach and trainings.
- During this period, Uganda Human Rights Commission (UHRC) received 1628 complaints, while the EOC received 51. This is attributed to the high level of trust the citizens have gained in these institutions and the quality of the free services that they are continuously receiving. It has however been noted that government institutions especially the police need to improve their customer care and respect for citizens’ rights. Evaluations have shown that without the support of DGF partners, some government institutions do not address clients’ issues effectively.
- UHRC performance did however decline as a result of delayed appointments of Commissioners. The absence of commissioners also resulted in laxity on the part of human rights violating institutions such as the Uganda Police (restrictions and violations of rights to assemblies and association), Uganda Communications Commission (restrictions on broadcast platforms) to respect or to act on previous UHRC recommendations.
- The absence of Commissioners in the UHRC was also a major setback affecting tribunal hearings of cases and annual reporting on human rights situation in the country. UHRC technical staff and the Equal Opportunities Commission were able to mediate 57 cases constituting 9.25% of the 20% cases they are expected to conclude in the financial year. With the appointment of Commissioners, it is anticipated that the UHRC Tribunals will be able to mediate more cases in the remaining Quarter of the year.

 Summary of responses to issues raised in the 2015 Annual Review
The following table sets out the 2015 Annual Review recommendations and the follow up over the last 12 months.

RECOMMENDATION (2015)	RESPONSE/PROGRESS
NUSAF
DFID will need to engage with the WB/OPM Secretariat to ensure that an evaluation of the Community Infrastructure Rehabilitation component of NUSAF 2 takes place or – more likely – commission its own separate evaluation to explore this. The evaluation should look at value for money, usage and whether the presence of the houses has led to tangible benefits to the communities (Lead: MDG Team Leader)	The lack of a baseline meant that it would be difficult to conduct a robust evaluation of the community infrastructure rehabilitation component of NUSAF 2. Following extensive discussions in 2014 between DFID and WB, it was agreed that DFID would not fund nor commission an evaluation. Nonetheless in February 2016, the WB/OPM commissioned an impact evaluation of the Transparency and Social Accountability Component. This is being implemented in collaboration with the Inspectorate of Government and external researchers. The evaluation focuses on the effectiveness of the social accountability and community monitoring intervention. A first round of follow-up data collection was completed in April 2016 in partnership with Innovations for Poverty Action and preliminary results are expected by July 2016. Another round of data collection was undertaken between May and June, and final results are expected by September 2016.
The IG’s office should undertake a proper analysis of its data on NUSAF-related complaints, providing information on how many cases have been resolved, by what method and in what time-frame, and a geographical analysis of complaints so “hot-spots” can be identified. Based on this assessment, the SRO should then consider if something along these lines should carried out under the new SUGAR project. The accountability adviser should conduct a visit to the IGG with the team responsible for TACC (Lead: MDG Team Leader and Accountability Adviser).	Raised with IGG for action.
Local Government Capacity
We need to reflect more critically on the reasons for the Gulu TA recording greater success than the Lira TA to inform future similar interventions. Accountability Adviser to do this and submit to PRDP SRO by September 2015.	Reflection taken up under the GAPP programme to inform its provision of TA.
RBF
Continue to monitor progress of the RBF mechanism here, gather lessons at the September lessons-learning exercise, and share these widely among the international community and with DFID. These lessons should include greater transparency and analysis of value for money questions, especially focused around the costs of managing the results-based financing component of the programme (Owner: MDG Team Leader)	Lessons from the evaluation of the RBF programme were disseminated at a national event in September 2015. Key stakeholders included central and district level health officials, bi-lateral partners and non-governmental organisations. Important lessons shared included: importance of robust monitoring of quality of care in future RBF programmes; possible benefits of sharing monitoring data with district and health facility managers to allow for rectification of detected problems; and challenges of sustainability beyond the life of the programme given high management and oversight costs. These have been shared widely within DFID Uganda, the evaluation cadre and with other DFID offices.
Private Sector and Youth
DFID should consider further independent review of PSFU grantees (DFID owner: Private Sector Adviser – a decision to be made as PCDP overall evaluation planning is undertaken)	It has been decided to include a further review of PSFU work in the overall PCDP evaluation, due later in 2016.
VSO vocational training and Enterprise Uganda entrepreneurial training, comparative, detailed and careful collection and interrogation of data, and a high quality evaluation are required to maximise lesson learning from the project in the remaining period.	This evaluation has been contracted and will be completed in July 2016.
DFID staff should also make every effort to attend at least one or two days of the five day training in the final project period. Given the high apparent cost/benefit and effective delivery systems, consideration should be given to maximising results through a grant increase and/or extension (DFID owner: Private Sector Adviser)	DFID staff attended BEST training in Kampala, which was not part of the project but follows the same methodology. A costed extension enabled the target to be raised from 8,400 to 10,000. Cost savings linked to exchange rate gains were used to train an additional 1,647 beneficiaries.
Although DFID should not consider continuing future funding of the PCIs, we should ensure through our advocacy around PRDP’s successor that a monitoring tool of some sort is incorporated – but not based on International Alert’s methodology due to the high costs (DFID owner: PCDP SRO).	No further support to PRDP is currently planned.
DGF RJP
DFID to consider future support to land conflict, as well as more broadly to bilateral support in the area of conflict. (DFID owner: GSH Team Leader)	Land is a cross cutting issue. The focus is on improving land administration and governance for poor, vulnerable and marginalised communities, and where necessary, seek to protect the economic and collective rights affected by compulsory land resettlement away from oil areas. DFID will promote stronger links between partners working in Natural Resource Governance (under the DGF Voice and Accountability Component) and LEAP partners, as well as ensuring legal advice and representation to communities involved in more complex public interest litigation cases. A land working group comprising partners from both RJP and V&A components has been set up within the DGF PMU to strengthen linkages and address issues on land governance and justice.
Amend the PCDP Logframe to reflect updated changes of DGF Logframe (indicators, milestones, assumptions). (DFID owner: PCDP SRO)	The logframe will be updated in July 2016 with the DGF/RJP revised indicators.
Amend DGF logframe, in particular, align indicators with the post-Juba peace process outcomes. DFID DGF Steering Committee representative to propose this work be undertaken.	The logframe was updated and approved in July 2015.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Youth: Key cost drivers in the youth skills components relate largely to the expenses of training, driven by numbers of trainees.

RJP: Key administrative (PMU) costs: office rentals, assets procurement, in-country travel for monitoring and evaluation and vehicle maintenance costs. Other cost drivers include, capacity development of partners and audit fees. DFID is one of eight partners contributing towards the administrative costs of the DGF. A total of 7% of DFID’s grant was allocated to administrative costs. These costs have been judged to be good VfM and compare favourably with other implementing partners used by DFID such as the UN or World Bank.

Key DGF Partner costs: Under RJP, legal aid work presented the highest costs. Specifically, drivers include: support for capacity building; human resource to deliver legal aid and other running costs including rent, stationery and fuel expenses. However, support to legal aid partners to increase the geographical scope of their services has contributed to bringing legal aid services nearer to beneficiaries and reduced the cost and time for accessing justice which in turn reduces the potential for escalation of disputes and attendant effects, including turning disputes into criminal cases. Whereas legal aid service delivery is expensive, the benefits related to empowerment and legal support especially for poor and vulnerable people exceeds the cost. Legal aid has enabled poor widows to retain control of their husbands’ land, thus ensuring care for their children; prevention of hunger and destitution as well as added nutritional value to prevent disease. Access to justice has contributed to reducing the rate of prison population growth. Through police and prison decongestion programs, about 30,000 people are released each year, including juveniles. However, there is increasing recognition to ensure holistic access to justice programs that also address the drivers/causes of poverty and vulnerability. There is need for social and economic empowerment programs to be run alongside access to justice programs.

Other costs include investments in research and development of regulatory framework for legal aid which are intended to enhance standards in delivery of legal aid services.

Financial Performance:

There has been regular monitoring of programme delivery by implementing partners and DFID to ensure that funds were used for intended purposes and as per approved work plans and budgets. Regular audits were conducted on the use of DFID funds by implementing partners (VSO Uganda and YBI) in accordance with the accountable grant arrangements in place.

Currently, RJP provides grants to 28 partners, however, this will reduce slightly as the peace-related work is being more closely linked to transitional justice.

The DGF reports against the GoU FY which runs from July to June the following year. The overall actual DGF expenditure was UGX 92.6 billion (€ 28.9m) compared to the budgeted UGX 97.85 billion (€ 30.6m) - registering a utilisation percentage of 95%, which is indicative of a generally high absorption rate. UK’s contribution to RJP for the FY 2015/16 was £ 2,875,000.

The depreciation of the Uganda Shilling has had a positive effect on the total exchange rate gains for the Programme Management Unit (PMU). The total exchange gain (for the PMU) for the FY 2014/15 was UGX 2.6 billion (€ 0.8m) which was re-programmed and the development partner disbursement schedule takes into consideration the exchange market gains. Implementing partners contracted in Uganda Shillings were likely to be exposed to the risks attributable to the economic environment. At the time of budget preparation, partners do not necessarily factor in depreciation challenges and miscellaneous budget lines which may expose them to shocks. Whenever a grant is denominated in a currency other than a project’s expenditure currency, foreign exchange volatility may present a risk to outcomes.

VfM performance compared to the original VfM proposition in the business case

At inception, the programme did not make an explicit value for money proposition in the economic appraisal of the Programme Memorandum. Individual components / projects under the programme have put in place Value for Money considerations to ensure that principles of economy, efficiency and effectiveness are adhered to in the project.

The original assumption in the programme memorandum was that the grant scheme would create 9,800 jobs over five years. The assessment earlier in this review questions the scale of job creation claimed by PSFU (either 58,000 or 97,000 jobs created), while not entirely discounting some success. It has been decided to include a further review of PSFU work in the overall PCDP evaluation, due later in 2016.

YDP and NUYEP have both delivered well and met the targets for numbers trained. Evaluation carried out compared VfM across the two youth skills interventions and also attempted to benchmark across similar skills projects in Uganda, and potentially worldwide. The findings were; basing on increasing the percentage of youth who had an income, the percentage of project participants that had an income at intake was about 30 percent, while the tracer studies found that 70 percent of youths had an income post-project. Using the mean monthly income from the tracer studies of 140,000 UGX, increasing from 30 to 70 percent the percentage of youth represents a net economic increase in earnings of 56,000 UGX per project participant; and that the overall benefit-cost ratio of the NUYEP project is positive.

YDP’s reported cost per beneficiary was $679, whereas NUYEP’s cost per beneficiary was $275. The difference was due to the approach as NUYEP facilitated mass trainings for up to 800 people at one time and at minimal cost. YDP, however, worked to strengthen VTIs which included high capital and training costs for both staff and students.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money. This is reflected in the different measures undertaken under components to ensure that value for money is realised in their implementation. The different components have continued to reflect value for money in the following ways:

Youth components: while representing good VfM in relation to outputs delivered, the replicability, sustainability and scalability of results represent a VfM challenge for all skills service delivery projects. This is being explicitly considered in the ongoing final evaluation of the components, and results will be fed into the overall PCDP evaluation.

Rights, Justice and Peace (RJP): PMU significantly reduced transaction costs compared to the management of similar types of grants directly by development partners[5]. As a percentage of the revised five-year budget, PMU administration costs stand at 3% (€0.9m) of the total budget (€28.9m). One of the key VfM advantages RJP enjoys under DGF that it brings to UAP is its impressive and growing reach across Uganda. In addition, many DGF interventions are explicitly targeted at the indigent and most vulnerable groups and communities and it is amongst these communities that some of the DGF’ most important outcomes are realised. In regard to partner effectiveness, DGF could consider using existing data on beneficiary outcomes and potentially undertaking more work in comparing the effectiveness of similar types of interventions across its portfolio, for instance, under local government networks, etc. The post-programme Evaluation of DGF (being undertaken from July 2016) will look at these issues in greater detail.
[5] The 2014/15 DGF external review established that the PMU which manages RJP represented good VfM compared to alternative mechanisms for managing grants of this kind and compared to similar fund management units.

In addition, many DGF interventions are explicitly targeted at the most vulnerable groups and communities and it is amongst these communities that some of the DGF’ most important outcomes are realised.

Under the RJP component, no design, management or contracting costs are incurred by DFID as DGF carries out all management activities under its existing structure. DFID also considers other measures such as the review and scrutiny of budgets and expenditures of projects to ensure that they meet value for money principles. A payment checklist which has been amended to include various levels of approval continues to be used in the programme. We hold quarter financial reviews and budgeting to ensure that all projects spend reflects VFM. In terms of the VFM of partners, no RJP partner is allowed to exceed expenditure of 7% on its own administration costs.

On effectiveness, during the period under review, the RJP partners made good progress collectively, with a few excelling and a small number who need improvement. A “light touch” assessment of all DGF Partners was undertaken by the PMU at the request of the DGF Board. A total of 82% (23 of 28) of the current RJP partnerships have exceeded or met their strategic objectives. Three partners need improvement (and are receiving support) and there is 1 serious reported case of fraud-related allegations. There is a de facto suspension of funding for the partner, pending resolution of the corruption allegations. Component reviews and a full evaluation of DGF are currently underway or planned and will go further in assessing the economy, efficiency and effectiveness of DGF and RJP partner’s work.

Quality of financial management

We have maintained a strict focus on the programme finances across PCDP. Monthly forecast meetings are held to monitor spend against forecasts. Project officers review individual finance reports and they have maintained the principle of disbursement of funds against a 75% demonstration of utilisation of funds against project activities. Different components have put in place measures to review and quality assure finance reports before they are submitted to DFID. Under RJP the external review (Jan 2015) pointed out that the PMU has a strong financial management team and the steering committee continues to play an oversight role of the financial management of the programme. All these measures have been agreed by DFID Uganda and are monitored on a quarterly basis.

Budget Performance

Project	Component	Component	Year	Budget (£)	Spend	% spend
200779	200250-108	Rights, Justice and Peace - DGF	2015/16	2,875,000	2,875,000	100%
200779	200250-117	Number of YDP youth trained in a core vocational skill(s) relevant to local market opportunities	2015/16	1,984,704	1,984,704	100%
200779	200250-128	Youth trained in Business Enterprise Start up Tool (BEST)	2015/16	1,050,090	1,050,090	100%
Total				4,964,794	4,964,794	100%

Overall, the programme spent 100% of its annual forecast.

Audit:

During the period under review, all components under PCDP underwent financial audits. RJP under DGF received an unqualified audit opinion. These audits have focused on both the managing agents of the components and the implementing partners. Overall, the audits pointed out the PMU as a managing agent for RJP has put in place an internal control environment that can enable management to prevent, detect and correct material errors in the Funds Accountability Statement, ensure compliance with the terms and conditions of the Funding Agreements and regulations and ultimately safeguard for assets and resources from loss and misappropriation.

In spite of the above, the DGF audit reported that there were some instances of non-compliance with pre-grant assessment (due diligence) procedures, unreported foreign exchange gains/losses by implementing partners and recommended strengthening internal scrutiny. DGF has addressed all these Audit issues to our satisfaction. Future audits will have a risk-based remit. In addition to the audit opinion on controls (how well designed and operated), they will specifically review the effectiveness of risk management and assurance mechanisms to enable the PMU to direct its resources most effectively on areas of highest risk or where there are gaps or weaknesses in other assurance arrangements - preventative and detective controls.

Date of last narrative financial report	RJP 29 April 2016 / (Period July 2015 to March 2016)
Date of last audited annual statement	RJP 30th June 2015

E: RISK

Overall risk rating: Medium-High

Overview of programme risk

The overall risk of the project in the original Programme Memorandum document, is medium. During the period under review, residual risk for the programme is judged as medium-high albeit with solid development return. PCDP’s risk rating has slightly changed since last year’s review, given the changes in the contextual and fiduciary risk environment as indicated below.

Contextual risks: The current risks are identified on the basis of the pre and post-election environment. During the reporting period, the tightly contested February 2016 Presidential elections provided opportunity to consolidate peace in the North. Since his 2011 victory (to the run up to 2016 elections), the President strategically designed and executed ‘war recovery’ programmes, through the NUSAF II and the PRDP II. These efforts, as NRM predicted during campaigns, entrenched the president’s hold on many parts of the North. This was also exhibited in the NRM Manifesto to which the ruling party boasted of among others, having constructed 2,693 classrooms and 1,221 teachers’ houses, distributed more than 67,000 iron sheets and constructed 54 houses for traditional chiefs in Acholi.

The political will to implement PRDP II (on which PCDP is hinged) could therefore have been influenced by personal interests of political elites, providing a gamut of political short-term solutions to long-term developmental outcomes. The major risk is that following NRM’s win in both 2016 presidential and parliamentary elections, the GoU’s political commitment to deliver PRDP may go on a down-ward trend. It remains of concern if PRDP III will not be used as a tool for the next 2021 elections, thereby focusing on ‘politicking’, with a limited focus on impact of policies and strategies on development outcomes.

There is increased clamp down on critical and dissenting voices, thus curtailing on the freedom of speech and expression. The 2014/15 Annual Review Report recommended that the DGF introduces an objective and indicator on the health and capacity of civil society to capture DGF’s positive outcomes and monitor the unintended consequences of DGF being a pooled fund. The risk rating recorded reflected the need to work with civil society and Development Partners to address the issues underpinning this risk, which are long term and systemic in nature (e.g. civil society regulation, legitimacy, accountability, professionalisation, financial sustainability etc.).

Overall the risk rating for the youth skills projects is low, as the most important outputs are on track, and have achieved the levels required for the end of project targets. The youth skills projects are now coming to an end, having successfully delivered output. However, the risk is that the independent evaluation will report lower than stated results at the outcome level due to issues to do with determining measurement and attribution.

The lack of VFM measurement was a minor risk, however, to mitigate this, a quality evaluation was undertaken to interrogate the data to assess VfM to a reasonable quality by the project.

Fiduciary risks: Uganda’s fiduciary risk environment is judged as High. A December 2015 UNDP report, the Uganda Human Development report, subtitled ‘Unlocking the Development Potential of Northern Uganda’, established that at least UGX 600 billion (~ £ 1,241,690) has been mismanaged by authorities, since government launched the PRDP for Northern Uganda in 2007. The report expressed fear that over the past nine years, poverty levels in the region have continued to rise despite increased funding by both government and development partners. Accordingly, Youth unemployment remains a serious policy challenge in the north and western regions of Acholi, West Nile, Pallisa, Budaka and Amolatar, among others. The number of residents categorised as poor according to the UNDP 2015 report rose from 4.7 million in 2005/06 to 5.1 million in 2012/13.

Under DGF/RJP, residual fiduciary risk is judged as a high likelihood but with a minor probability of failure to achieve outcomes and where failure occurs, modest drops in outcomes. Nevertheless, DGF has made significant strides to mitigate fiduciary risk. In addition to a strong financial management team, the DGF Partnership Manual and Finance and Administration Manual lays out the approach to managing fiduciary risk, including the risk of corruption. The PMU conducts (due diligence) pre-grant assessments, carries out scrutiny of quarterly or six-monthly financial reporting by partners with any irregularities reported, and followed up by an immediate monitoring visit if they persist. Partners received 137 financial oversight monitoring visits with any irregularities reported, and followed up by a special audit if they persist. All partners also undergo routine annual audits. In addition, implementing partner risk registers, regularly updated with issues are elevated and discussed within the Steering Committee. Whistle-blower reports of corrupt practices are investigated and followed up with a special (forensic) audit where it is deemed that there is sufficient evidence. DGF developed a whistle-blower mechanism with a confidential hotline and email. Where an annual or special audit indicates malpractice, a forensic audit is initiated.

Since 2012, DGF has registered 6 cases of fraud and taken action against those involved including commissioning forensic audits, reporting to police, Ministry of Finance and enforce recoveries of money and assets. In the reporting period, DGF registered one new case after a whistle-blower reported mismanagement of DGF funds. This case has been subjected to a forensic audit, which is still under way. The programme takes strong preventive measures against this behaviour and uses every opportunity including conferences, partner agreement clauses to communicate DGF’s against fraud and its policy of zero tolerance to corruption.

Although significant fiduciary risk amongst RJP’s partners was noted, a recent review of DGF’s monitoring by DFID found that: “the strongest feature was DGF’s identification and management of risk, particularly fiduciary risk, through inbuilt capacity in financial management in the Secretariat, and partner risk registers, regularly updated with issues elevated and discussed regularly within the Steering Committee”.

All active components have in place approved risk registers with the recently identified six categories of risk. Risk registers are updated on a quarterly basis and risk is part of the quarterly programme management discussions with managing partners. More detail can be found in these risk registers.

Outstanding actions from DGF risk assessment (no outstanding issues from other PCDP programmes)

- Update the risk matrix to reflect emerging issues.
- Follow-up with the DGF Steering Committee to systematically and periodically review the risk matrix and escalate, fix, record and learn from the risk identified.
- The risk of unintended consequences should be included and linked to an indicator in PMU or partner monitoring that considers the risk of doing inadvertent harm to beneficiaries.
- Update the DGF Delivery Plan with an updated 5X5 risk and development return matrix in DFID’s new standard format.

Recommendation

- RJP component to review the risk registers on a quarterly basis.
- Update the PCDP logframe.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Delivery of all components – NUSAF, RBF, Youth and DGF/RJP has been in line with the originally agreed and planned timeframe. However there were delays with some downstream RJP partners due to delays in submission and approval of partner financial reports.

The youth skills components had extensions applied in 2015-16 in order to deliver additional results and a stronger evaluation.

There is a planned extension of DGF 1 for 18 months (July 2016 to December 2017). DFID is seeking approval to support the extension with £2,000,000 under another programme (Uganda Accountability Programme). However, provision of these additional funds will be dependent on the findings of component reviews, and focused to deliver on the priorities of UAP. PCDP support will close as planned in December 2016 after a final contribution to the RJP of £ 1,015,000 in August 2016.

Performance of partnerships

PCDP projects are implemented through downstream partners. These are managed at two levels: DFID with the managing partners; then Managing partners with downstream partners. DFID has maintained close working relations with the different managing partners through monthly meetings and regular communication on email and phone calls that have helped timely resolution of emerging issues during programme implementation.

DFID cultivated a good relationship with DGF through representation on the Steering Committee and the DGF Board. DFID was able to use its influence to drive the financial management, results and VFM agendas within the multi-donor programme. Following progress made by the DGF, there was elevated confidence in the DGF by the Board. Following a series of Board meetings the Board and Steering Committee worked with the PMU to ensure implementation of the BAWAB, with the scrutiny and approval of Screening Notes and the approval of corporate reports, the Communication Strategy and Programme policy engagement proposals. The fourth Annual Partnership Conference was held in December 2015, attracting more than 150 participants from DGF’s Partners, the PMU, the Steering Committee and the Board. The conference enabled networking, synergy and building of strong linkages in the DGF Partnership, as well as enlightening partners on DGF’s plans during the extension period (DGF 1+).

Asset monitoring and control

The youth skills project has asset registers which include programme vehicles, computers and accessories, motorcycles, and a huge tent (1,000-seater). The asset register was updated in December 2016. As part of the end of project reporting requirements, both YBI and VSO were asked to report on the status of the assets that they have purchased. The Deputy Programme Manager and Programme Assistant will carry out final asset spot checks in July 2016.

Under RJP, the Programme Management Unit (PMU) maintains an asset register for both Partner and PMU Assets. Fixed assets and their value were verified during DGF’s audit for the period ending 30 June 2015. DGF/RJP submits asset registry updates to DFID and the latest Asset Register submitted was for June 2016. PMU partners, as part of the progress reporting requirements, report on the status of the assets that they have provided. DFID conducted a spot check in Western Uganda on three downstream partners in May 2015 and findings revealed that asset registers were in place and spot-checks conducted on a semi-annual basis.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The most relevant changes are deterioration in democratic governance, human rights and domestic accountability. There is restricted space for opposition voices post-election, and freedom of speech and expression has been curtailed. On other rights issues, the Sexual Offences Bill that provides for “unnatural offenses” to be prosecuted passed first reading in Parliament and is with the Legal and Parliamentary Committee for review. As currently drafted, the “unnatural offenses” clauses in question run the risk of potentially being interpreted and used as anti-homosexuality legislation, though neither the Bill (nor the Penal Code) expressly refers to homosexuality. There is also a risk that further amendments or additions will lead to a deterioration of human rights of LGBT persons in Uganda. The NGO Act 2016 was assented by the President in early 2016. However, the Act contains provisions that give the NGO Board unchecked powers to limit and end the operations of NGOs if they judge their work not to be “in the public interest”.

RJP supports the National Human Rights Institution, UHRC in carrying out its constitutional mandate of education, monitoring and reporting of human rights as well as in the adjudication of human rights cases. However, the Commission is facing a number of challenges such as delayed compensations from Government of Uganda for human rights violation cases that are awarded compensation by the Commission’s Tribunal, and challenges related to inadequate funding resulting into donor dependency. RJP also supports the NGO Board, which was created under the Ministry of Internal Affairs with a mandate to register, regulate, coordinate, monitor and advise government on the NGO sector in Uganda. Notably, all NGOs must obtain official registration from the NGO Board before they can operate in Uganda. RJP therefore supports the Board to strengthen its capacity to implement its regulatory mandate and to assist it in improving relations between NGOs and the Government of Uganda. The NGO Act 2016, in some respects may be a claw-back on the Constitution and major human rights guarantees and its intentions are largely to control rather than facilitate the NGO sector. RJP also supports the Justice Law and Order Sector (JLOS) to pilot and subsequently develop a National Legal Aid delivery mechanism for marginalised persons in Uganda. This RJP support enables GoU’s delivery on Partnership Principles 2 & 4; commitment to respecting human rights and other international obligations and strengthening domestic accountability.

The Partnership Principles are currently being updated to reflect concerns about democratic practice around the February elections. The actions of Government during the Presidential and Parliamentary elections have the potential to impact upon our relationship and further support to UHRC will be considered in that context.

H: MONITORING & EVALUATION

Evidence and Evaluation

PCDP is investing significantly in gathering evidence and undertaking evaluation.

NUSAF II (Under PCDP output I and 2): The lack of a baseline meant that it would be difficult to conduct a robust evaluation of the community infrastructure rehabilitation component of NUSAF II. Following extensive discussions in 2014 between DFID and WB, it was agreed that DFID would not fund nor commission an evaluation. Nonetheless in February 2016, the WB/OPM commissioned an impact evaluation of the Transparency and Social Accountability Component. This is being implemented in collaboration with the Inspectorate of Government and external researchers. The evaluation focuses on the effectiveness of the social accountability and community monitoring intervention. A first round of follow-up data collection was completed in April 2016 in partnership with Innovations for Poverty Action and preliminary results are expected by July 2016. Another round of data collection was undertaken between May and June, and final results are expected by September 2016.

RBF (Under PCDP output 2): Lessons from the evaluation of the RBF programme were disseminated at a national event in September 2015. Key stakeholders included central and district level health officials, bi-lateral partners and non-governmental organisations. Important lessons shared included: importance of robust monitoring of quality of care in future RBF programmes; possible benefits of sharing monitoring data with district and health facility managers to allow for rectification of detected problems; and challenges of sustainability beyond the life of the programme given high management and oversight costs. These have been shared widely within DFID Uganda, the evaluation cadre and with other DFID offices.

Youth (Under PCDP output 3): The youth skills projects for the two sub-components under Output 3 were successfully concluded, with an independent evaluation due in July 2016. Further findings will be included in the overall PCDP Project Completion Report. Output targets have been exceeded, and positive outcomes have been generated in terms of income increases recorded. The independent evaluation has stated an early finding that 38% of YDP youth reported better knowledge of selected life skills, compared to 8% of a non-beneficiary comparison group. A fuller assessment and validation of these claims including a basic cost-benefit analysis, and discussion of attribution and measurement issues will be included in the final independent evaluation report, and its findings fed into the overall PCDP evaluation. The validation of these results, and the interpretation of attribution and outcome implications will be dealt with in the independent evaluation, and the findings will be fed into the overall PCPD Project Completion Report. A key lesson has been the value of an independent evaluation, and the need for greater emphasis on experimental or quasi-experimental evaluation methods in future projects of this nature.

DGF/RJP (under PCDP output 4): DGF commissioned and concluded independent component (RJP) thematic reviews in May 2016. The findings revealed:

The absence of a robust logframe and clear baselines at the start of the programme hindered the setting of realistic targets and led to emphasis on activities rather than a greater focus on results.

A recommendation of a further streamlining of outputs and indicators to ensure a more linear relationship and greater involvement of the partners in the design of the next programme document and logframe. The need for more robust supply-side indicators as an important means of tracking and measuring the impact of the programme.

The component was largely effective in raising human rights awareness. In particular, the use of barazas, enabled the UHRC to reach tens of thousands of people cheaply. The IDF, through grassroots organisations, also reached out to tens of thousands. Radio programmes, school and university human rights clubs, drama and other forms of IEC were also effective in human rights education and awareness-raising.

The Legal Aid Programme (LEAP) appropriately responded to the need for legal assistance to poor Ugandans and has over the last 5 years, remained the major source of financing for legal aid in Uganda. Many of the government initiatives, including the Justice Centres Uganda, Pro bono Program, Law Development Centre, legal aid clinic are being implemented with support from the (donor-funded) LEAP. This poses a sustainability challenge in the absence of donor funding.

Whilst legal aid service delivery contributes to poverty reduction and empowerment; effective empowerment requires a holistic approach to legal aid client’s problems to address vulnerability which is often the underlying cause for legal problems.

The review called for caution in assessing value for money due to the diversity of partners, applying widely varying strategies. In addition, there was absence of clear criteria for choice of partners at the beginning of the programme, and therefore an unclear sense of strategic purpose amongst the partners.

The DGF has commissioned an end of Programme Evaluation due to report in October 2016 which will evaluate:

The results delivered against each component, reflecting on the evidence of attribution at both the output level and from the component level to the outcome level. This will also include: the lessons learned against comparative experience of delivering success in similar operating contexts.

The programmatic complementarity of and conceptual logic behind the five thematic DGF areas of intervention (democracy, human rights, access to justice, accountability and peace and reconciliation).

The extent to which, DGF has responded to changing demands and circumstances and how it has shaped civic and political space in Uganda, including the DGF’s theory of change.

The five thematic areas of intervention and corresponding partnerships that have provided best value for money and delivered results in DGF 1, flagging those that could be prioritised for programming in DGF 2 while suggesting what thematic areas and consequently what partnerships to disengage from under DGF 2.

This will also provide an evidence base for donors’ performance reviews of the DGF 1 and extension, and serve as a platform for the design of DGF 2. Lessons learned and recommendations for the next phase will be clearly documented.

There will be an 18 months extension phase (July 2016 to December 2017) for DGF to consolidate and closely align established component programmes to political and governance realities in Uganda, pilot innovative approaches based on lessons learnt, evaluate the impact and effectiveness of DGF1 programme strategies and partnerships, consult and consider ways to improve the “health” of civil society in Uganda in the long term and design and appraise DGF II.

Monitoring progress throughout the review period

Under Youth Skills

- An independent evaluation was contracted for the two youth skills sub components, drawing on the internal project data.
- Conducted extensive field and focus group research.
- Reviewed and updated the risk management framework.

Under Rights Justice and Peace (RJP)

The overarching ToC, adjusted logframe, risk management, monitoring programme, planned evaluations and diversification of M&E methods adopted since the 2013/14 Annual Review Report published in January 2015 all serve to strengthen the DGF M&E practices.
- In 2015 M&E framework was revised resulting into a clearer ToC which embeds lessons learned, experiences and assumptions.
- The revised DGF logframe has been aligned to partner interventions and more datasets obtained for better results monitoring and recording.
- Robust field monitoring in frequency and intensity resulting in increased compliance and partner awareness of results documentation and reporting.
- Spot checks have been broadened.
- Provided capacity development to IPs to conduct own evaluations and peer to peer evaluations.
- Semi-annual and annual reporting.
- On the whole, during the review period DGF has developed better ways of working together, continuously reviewing effectiveness and impact, and responding to emerging issues and opportunities.