Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	June 2016

Title: Statebuilding and Service Delivery Grant to the Palestinian Authority in the Occupied Palestinian Territories
Programme Code: 202564	Start Date: 2 June 2011	End Date: 31 March 2016

Summary of Programme Performance

Year	2013	2014	2015	2016
Programme Score	A	A	A	A
Risk Rating	Severe	Severe	Severe	Severe

Financial Position

Original Programme Value	A total amount of £122.21m over 4 years, comprising: / Core grant: of up to £110m to the Palestinian Authority (PA); / ‘Results compact’: funding of £12m if the PA demonstrates high value for British taxpayers money; / £200,000 for evaluation activities.
Extensions/ amendments	Extension in March 2015 for one year.
Log-frame revisions (with dates)	October 2012 – Quest 3857302 / August 2013 – Quest 4119195 / February 2014 – Quest 4380127 / March 2015- Quest 5153866
Total programme spend	£152.5 million of core funding to the PA.

The actual total amount disbursed to the PA from the UK since 2011 is £152.5 million: £30m in 2011/2012; £34.1m in 2012/13; £41.6m in 2013/14; £22m in 2014/15 and £24.8m in 2015/16.

Follow up actions required following closure

Consider recommendations set out in this PCR for future financial aid programmes to the Palestinian Authority.

Declare this Project Completion Review (PCR) as a record, upload it onto Development Tracker and ensure all project documents are saved to QUEST and linked to ARIES (DFID’s information and financial management systems).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202564/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202564/documents/

Outline of programme and what it has achieved
	Output	Score	Weighting %
1	Results Funding – Public Services bought by DFID support	A	60
2	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient	A	25
3	Development effectiveness – aid to the PA is more predictable and results-focused	A+	15

Support to the Middle East Peace Process is a high priority for the UK Government. The UK’s goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. We support the work of the Palestinian Authority (PA) which remains a vital element of efforts to achieve a two-state solution.

The Statebuilding and Service Delivery Grant (SBG) purpose is to support the PA to provide essential services to Palestinians, including vital health and education services, through the delivery of key state-building reforms and payment of salaries. Financial aid to the PA and related policy dialogue has been provided through the World Bank Palestinian Reform and Development Plan Trust Fund (PRDP-TF), with additional earmarking to vetted civil servant salaries agreed with the PA (using the EU PEGASE vetting process). Using the PRDP-TF, disbursements are automatically linked to the World Bank’s policy dialogue with the PA conducted as part of their annual Development Policy Grant (DPG). Each year in March/April the Bank and PA agree on a Policy Matrix of reforms which has traditionally focused on improving fiscal discipline, the efficiency of public spending and public financial management and accountability.

Our support has helped to address the chronic shortfall in funding for the PA resulting in part from the on-going conflict, and restrictions on movement and access in the Occupied Palestinian Territories (OPTs). These restrictions act as a brake on the Palestinian economy and the PA’s ability to raise revenues. If this funding shortfall is not addressed, the PA will not be able to pay public worker salaries and continue delivering essential services. Unemployment is high in the OPTs, and around one third of Palestinian households are dependent on a public sector wage earner.

The UK’s support has enabled the PA to continue delivering services to Palestinians and make significant fiscal and public financial management (PFM) reforms. The PA’s institutional readiness for statehood has been recognised by the international community including the UK. In 2011, the World Bank reported to the Ad Hoc Liaison Committee (AHLC) that the PA’s capacity to “fulfil state functions compares to capacity in the Middle East and other countries, and shows that it is often comparable and sometimes superior.” Subsequent reports and our own assessments continue to affirm the PA’s institutional capability but have emphasised the need to keep up the momentum on reform, in a context where the fragility of the political horizon puts these gains at risk.

An independent evaluation of this programme and the Palestinian Governance Facility (which provides technical assistance to the PA) was carried out in 2015 by the Overseas Development Institute (ODI), and its key findings have been incorporated into this PCR.[1]
[1] Evaluative review of the Statebuilding Grant and the Palestinian Governance Facility – DFID Palestinian Programme, Final report, Bryn Welham, Heidi Tavakoli, Sami Miaari and Edward Hedger, 2015.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The outcome statement is: To improve the Palestinian Authority's management of its financial systems and to provide better access to services for the Palestinian public.

Whilst DFID’s funding under this programme accounts for only a small proportion of the PA’s total revenue, DFID has complemented the funding with useful policy dialogue. The independent evaluation found that there was some evidence that the conditionality framework that was used in conjuction with this financial support had leveraged some policy reforms. Therefore this programme constributes to the following outcomes.

Progress against the outcome indicators broadly met expectations and is set out below:

#	Indicator	Target (Jan-Dec 2015)	Achieved	Comment
1	Education: Primary net enrolment rate for boys (M) and girls (F) (%)	93.7% (boys) and 96.4%(girls)	93.4% (male) and 95.2%(female)	Net enrolment rates have fallen slightly since the last AR although still significantly higher than previous years. / It should be noted however that there are no figures for Gaza, and that the Occupation restricts the ability of some children to safely attend public schools.
2	Education: Mean score obtained by students (boys and girls) in Monitoring Learning Achievements in Maths (grade 8) and Arabic (grade 7)	62.5(M) 62.5(F) Arabic 2014; / 53(M) 53(F) Maths 2014	45.5(M) 61.2(F) Arabic 2014; / 31.1(M) 41.2(F) Maths 2014	Data shows that achievement in Arabic and Maths in Grades 7 and 8 have been inconsistent throughout the life of the programme. The 2014/15 results fell short of the PA’s targets.
3	Health: Percentage of deaths caused by cancer, cardiovascular disease and diabetes	50%	53.5%	Although the target has not been fully reached, data shows improvement across the period of the programme (down from 56%)
4	Security: Rate of public satisfaction with performance of the MoJ, the PCP, the Attorney-General's Office, the HJC and the shari'a courts (%)	57%	68.7%	Data shows that overall levels of satisfaction have improved across the different security and justice institutions and the 2015 target has been exceeded.
5	Fiscal sustainability: Net present value (NPV) of money saved for the PA by reforms in DPG Matrices 2011-2014 and reforms promoted by education and health efficiency technical assistance ($m)	100	25.5	The independent evaluation conducted an analysis that revealed a higher NPV of £17.35 million (approx. $25.5m, using a discount rate of 10%) than when the project was first designed. The net present value of monetised costs and benefits are now positive, even before accounting for non-monetised benefits. Although the ambitious target has not been achieved, it still represents a significant improvement from the baseline.
6	Public financial management and accountability (PFMA): Fiduciary risk rating for PA PFMA system.	Substantial	High	Fiduciary Risk Assessment (2015) / There remains a high level of fiduciary risk. The 2015 FRA found a positive trajectory overall, due to marginal improvements.

At the impact level, the independent evaluation looked at the relationship between public spending and public employment (which the SBG has supported) and incidences of conflict. It suggests that “To the extent that collapse of the PA or Palestinian economy would increase the chances of a violent escalation, donor – and DFID – support to the PA is instrumental to avoid that outcome.”
At the outcome level, the evaluation concluded that the SBG has “clearly and directly reduced the gap between overall PA revenue and expenditure and therefore supported fiscal stability in the short term. The value of DFID’s support in this regard is arguably of increasing importance in the context of falling development assistance overall and the sporadic withholding of clearance revenues by Israel as a political tool”.

Service Delivery

The independent evaluation found that “over the past five years social sector performance has improved and surpassed DFID’s expectations, supported by strong improvements in government effectiveness”. Annual data from the Palestinian Central Bureau of Statistics illustrate performance improvements in the SBG priority sectors since 2011. This performance has been accompanied by significant improvements in overall government effectiveness between 2008 and 2014 (WGI, 2015).[2]
[2] Ibid
Human development indicators for the OPTs have broadly remained consistent over the programme period. The OPTs Human Development Index rating has remained “medium” since 2011 with little change in value, ranking at 113 out of 187 countries. By comparison, however, Israel ranks 18 and is classified as “very high”.  This contrast reflects the severe impact of the Occupation on human development in the OPTs.[[i]]
[[i]] UNDP, Human Development Report 2014: Sustaining Human Progress: Reducing Vulnerabilities and Building Resilience. Also UNDP, the 2014 Palestine Human Development Report - Development for Empowerment.

In education, there is near universal literacy in the OPTs. While primary school enrolment rates have decreased slightly from 95.2% (male) and 97.9% (female) in 2011, to 93.4% (male) and 95.2% (female) in 2015, they remain high and with good gender parity. Public health indicators are generally on a par with middle-income countries. The percentage of deaths caused by cancer, cardiovascular diseases and diabetes has reduced across the period of the programme. Maternal mortality is low at 24.1 per 100,000 live births (UNICEF/WHO 2013), although this rose in Gaza in 2014 after Operation Protective Edge. Infant mortality is also relatively low (21.7 per 1000 live births, MICS 2014), with rates declining steadily. However, in Gaza infant mortality is rising for the first time in 50 years to 22.4 per 1000 live births. This reflects the differential impact of the conflict across the OPTs, as well as the PA’s limited reach in Gaza.

### Fiscal and PFM reforms

Successive reports by the World Bank and IMF have concluded that the PA has made impressive progress on fiscal and Public Financial Management (PFM) reforms in a highly constrained and challenging political context. The PA has made very good progress in reducing the recurrent deficit over the programme period, including through key fiscal reforms such as controlling the wage bill and revenue reform, which have featured in DPG policy matrices. The PA has made notable progress on budget preparation (which DFID also supported through the Palestinian Governance Facility - PGF), and the 2016 budget was the first PA budget to be prepared against a realistic macro-fiscal framework with expenditure ceilings.

The Fiduciary Risk Assessment carried out by DFID in 2015 found that the overall level of fiduciary risk remains high, but with a positive trajectory due to marginal improvements. Priority weaknesses that need to be addressed are in the downstream areas of budget execution, reporting and accounting. This includes strengthening commitment control, payment processes and in-year financial reporting. It also includes ensuring that timely and accurate annual financial statements are published to enable effective scrutiny and oversight of public finances.

The independent evaluation looked at the link between reform momentum and the wider political context, including the impact of diminishing prospects for a two-state solution. It concluded that “the incentives and drive for challenging long-term public administration reform within the PA have weakened over the period of the programmes, making delivery of DFID objectives more difficult to achieve”. This suggests that understanding the PA’s incentives for further reform will be a key issue going forward.

Output Score and Description

The overall output score for this programme is A, outputs met expectations.

		Score				Weighting
	Output	2013	2014	2015	2016	%
1	Results Funding – Public Services bought by DFID support	A	A+	A	A	60
2	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient	A	B	B	A	25
3	Development effectiveness – aid to the PA is more predictable and results-focused	B	B	A	A+	15

Overall, the SBG programme has contributed to fiscal sustainability and in the short-term, has helped close the PA’s significant fiscal gap. In terms of induced outputs, the independent evaluation concluded that the SBG has supported the stability of the macroeconomy, primarily through public spending’s role as the main driver of growth. Spending on social sectors (health, education, social protection) has increased in nominal terms alongside overall government spending, and increased slightly as a percentage of government expenditure. The DPG conditionalities attached to DFID’s financial assistance have encouraged better fiscal management, and there is evidence that the PRDP-TF approach has had some success in pushing for reform.
Key lessons and how these have been shared

Below are some of the key lessons and recommendations from the independent evaluation. The following lessons will be considered in the design of any future programme of support to the PA.

- DFID should more rigorously define and prioritise its real political and policy objectives for budget support to the PA, and design the programme modality for financial transfers and conditionality accordingly
- DFID could consider whether the current structure of PA fiscal policy and associated financial support is sustainable in the long term, and what influence DFID could bring to bear to support a more sustainable situation, for example by increasing the share of development expenditure in the PA budget
- If DFID remains in the PRDP system, it should begin a dialogue with the World Bank and the PA regarding how to increase the predictability of the instrument, including carefully considering the added value of the performance tranche of the SBG.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Results funding - public services bought by DFID support
Output number per LF		1	Output Score	Overall: / 2016:A / 2015: A / 2014: A+ / 2013: A
Risk:		Severe	Impact weighting (%):	60
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Target (Jan-Dec 2015)	Progress
1.1	Education: Number of non-refugee children supported by DFID in primary education (grades 1 – 6) (from 2014/15)	3827; 1,906(M) 1920(F)	3765; 1881 (M) 1884 (F)
1.2	Education: Number of non-refugee children supported by DFID in lower secondary education (grades 7-8) (from 2014/15)	1285; 643(M) 642(F)	1250; 622 (M) 628 (F)
1.3	Health: Number of children under 5 years old immunised for measles.	No longer measured	n/a
1.4	Health: Average number of daily medical consultations per doctor in general Primary Health Clinics	49	45
1.5	Health: Proportion of Medicines on the essential drug list that are reported at zero stock levels in the West Bank (WB) and Gaza (G) central drug stores (%)	20% (WB), 20% (G)	24% (WB), 29% (G)
1.6	Social Protection: Number of individuals covered by DFID-supported cash transfers	6786	6827

The PA is the primary provider of basic services in the OPTs, with almost half of public expenditure allocated to the social sectors (education, health and social protection). The PA’s service delivery reach is limited by the context of the Occupation in Area C of the West Bank and East Jerusalem. There is some co-operation between the PA and the “de facto” authorities in Gaza on service delivery – for example, 50% of health sector workers are paid by the PA, while the other 50% work under the “de facto” authorities. The bulk of PA social sector spend is recurrent expenditure allocated to wages and salaries. Health and social protection have received a small proportion (2-3%) of development expenditure, while education experienced an increase to 18.8% in 2013. As mentioned above, the evaluation found that “over the past five years, social sector performance has improved and surpassed DFID’s expectations“.

Over the lifespan of the programme, the SBG has supported (per year) an average of:
- 5480 non-refugee children in primary education;
- 1857 non-refugee children in secondary education
- 50 daily medical consultations per doctor in general primary health care clinics
- 9435 non-refugeee individuals covered by cash transfers.[3]
  [3] Calculations based on total aggregated results divided by the number of years of the programme.

Key Points

Specific Results for the indicators 1.1, 1.2 and 1.6 were calculated using an attribution rate for DFID funding of the PA. This varied during the programme and in 2015/16, a 1% attribution rate was used. Across the period of the programme, the PA surpassed the majority of the milestone targets including in health, education and social protection, achieving A, A+ and A in previous years. On balance, the PA’s performance across key service delivery targets remains good..

Indicator 1.1-1.2: In education, the progress against the milestones shows that the PA has exceeded both primary and secondary education targets across the period of the programme. Although the milestones reached in school year 2014/15 were marginally under the target, this indicator is considered to have been met.

Indicator 1.3: The indicator is not measured. As stated in the previous Annual Review, the PA no longer administers measles shots separately, but instead includes them within the Measles Mumps and Rubella (MMR) vaccine to children at both 12 (MMR I) and 18 months (MMR II). In 2015, 126,164 children were given the MMR 1 vaccine and 121,294 children the MMR 2 vaccine.

Indicator 1.4-1.5: The targets were nearly met. In health, the average number of daily medical consultations per doctor in general Primary Health Clinic (1.4) is slightly below the target. The health indicator (1.5) on drug shortages shows that there was a decrease of medicine shortages in the West Bank and an increase in shortages in Gaza compared to 2014 figures. Gaza continues to suffer shortages due to the closure of the Rafah border crossing since July 2013.

Despite missing the target on stocking levels, there has been year on year improvement in stocking levels in the West Bank. Prior to this programme, 31% of medicines on the essential medicines list were reported as having zero stock levels in the West Bank (2011). Improvements have also been made in stocking levels in Gaza where 37% of essential medicines had zero stock levels in 2011.

Indicator 1.6: The target was exceeded. The PA has provided cash transfers as per their Social Protection Strategy 2014-16.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2015 AR recommended that the independent evaluation of the SBG examine the role of service delivery targets in direct financial assistance, capture lessons on what has worked well in this programme and suggest options for incorporating service delivery targets in any successor programme to the SBG. This has been incorporated into the scoping of a possible successor programme.

Recommendations for future programmes

Consider how to strengthen the links between DFID’s Technical Assistance and Financial Assistance, and explore whether there is scope to expand core systems reform to key social sector line ministries.

Output Title	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient
Output number per LF		2	Output Score	Overall: / 2016: A / 2015: B / 2014: B / 2013: A
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Target (Jan-Dec 2015)	Progress
2.1	Public finance reforms: Proportion of planned reforms in World Bank annual Development Policy Grant (DPG) Matrices that are over 50% completed (%)	70%	75%
2.2	Public service efficiency reforms: Number of Ministry of Health (MoH) Efficiency Action Plan (EAP) activities completed or being actively addressed where DFID is providing support and PGF External Inputs are envisaged.	4	4
2.3	Accountability reforms: Number of high quality reports produced by the Ministry of Development and Planning (MOPAD)	4	4

Key Points

On policy leverage, the independent evaluation found that coordinated policy dialogue through the PRDP-TF has leveraged reform in many instances. DFID (with others) has supported revenue reform efforts and the DPG policy matrices have over time paid increasing attention to revenue reform. DFID has also supported efforts to improve spending efficiency, most notably through the DPG wage control policy conditionalities as well as through support to sector efficiency action plans.

There is evidence that the conditionality system has leveraged policy reform within the PA – ie. there is a link between reform conditions included in the DPG policy matrix, and the extra effort devoted by the PA to these areas. For the first time in 2014, the World Bank withheld PRDP funding because of slower reform progress. This led to a rapid response by the PA to deliver the missing reforms, providing evidence (albeit limited to this example) of an incentive effect.

Indicator 2.1: The 2015 target was exceeded, representing a significant improvement from 56% in 2011. The PA has achieved several of the reforms within the agreed DPG policy matrix including actions focused on reducing the recurrent deficit, improving effectiveness and transparency of public finances, and improving the business climate. The main areas of reform where there have been delays were in relation to tax reform, hiring policy and institutionalisation of the public procurement law.

Indicator 2.2: The 2015 target was met for this indicator. Work focused on deepening the activities around efficiency measures, external referrals and secondments. Progress was complicated by the position of the Deputy Minister of Health remaining vacant for much of the year. Near the end of 2015 a new Deputy Minister was appointed. PGF has helped – with others, particularly the US – to address the referrals situation. Referrals spending in cardiac catheterisation fell from 2014 (from just over NIS 40m to just under NIS 36m) and in total referrals from 2015 (from around NIS 650m to around NIS 527m). Unit costs have been brought down in both categories, even as volumes have continued to rise.This indicator was updated in the 2015/16 log frame to better reflect the PA’s use of the EAPs, moving away from measuring the progress against reforms of both the education and health Ministries. In 2014, The EAPs were adopted by the Ministries at a slower pace than anticipated. Technical assistance to the MoH in implementing its EAP was however effective, and the MoH made good progress such as identifying cost drivers and developing efficiency inputs to various national health service sections. The MoE also saw progress against its EAP across the period of the programme, in areas such as adopting efficiency priorities in their new Education Strategy 2014-19 including management reform that constitutes a major efficiency intervention. The implementation of the activities improved from 2013 to 2014 by 10% overall.

Indicator 2.3: This indicator was met. MoPAD produced two progress reports in 2015. Following the merger of the ministries, the Aid Management and Coordination Directorate (AMC) at Ministry of Finance and Planning produced two AHLC reports, one in May 2015 and one in September 2015 (“Deepening Reforms, Strengthening Institutions”).

Summary of responses to issues raised in previous annual reviews

The 2015 AR recommended verifying indicator 2.1 based on the World Bank’s Implementation Completion Report and that indicator 2.2 is updated to better reflect the PA’s use of EAPs. The data was verified with regards to 2.1 and the logframe indicator 2.2 changed and aligned to the Palestinian Governance Facility output on efficiency action plans.

Recommendations for future programmes

The evaluation concluded that DFID’s own performance tranche was not found to be as effective at improving PA systems and fiscal discipline as a coordinated donor approach to results-based aid. Any future programme of financial assistance should consider carefully the most appropriate manner to incentivise reform and our approach to conditionality.

Output Title	Development effectiveness – aid to the PA is more predictable and results-focused
Output number per LF		3	Output Score	Overall: / 2016: A+ / 2015: A / 2014: B / 2013: B
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Target (Jan-Dec 2015)	Progress
3.1	Aid predictability - UK: Proportion of disbursements released by DFID according to the amount and month specified in the UK-PA Memorandum of Understanding, unless due to a breach of conditionality (%)	75%	100%
3.2	Aid predictability - international: Proportion of development aid information captured within DARP database (MoPAD lead)	60%	75%
3.3	Implementation of the EU results framework	EU results framework updated based on full implementation of pilot phase	Achieved

Overall, the ODI evaluation concluded that formal policy dialogue is well coordinated among the donors using the PRDP-TF system, and that the alignment of the new PEGASE Results-oriented framework with the PRDP-TF should continue to improve harmonisation and the impact of policy reform conditionalities.

Key Points

Indicator 3.1: The target was consistently achieved or exceeded. DFID disbursed its funds in a timely and predictable way to the PRDP, according to a schedule agreed with the PA. However, the evaluation found that the use of an intermediary body (the PRDP-TF) complicated the achievement of this goal. Although it transfers funds in a regular way (almost every quarter) to the PA, the transfers to the PA are volatile (the amount transferred varies each quarter) because of variations in other donors’ contributions.

Indicator 3.2: There was consistent progress on aid information captured by the DARP database across the life of the programme, and the 2015 target was exceeded. However, the evaluation questioned its overall value and sustainability, given the limited use that has been made of the data. In October 2015,
the Ministry of Planning and Development (MoPAD) was dissolved with its responsibilities being transferred to other ministries.

Indicator 3.3: The target was met. The EU piloted a Results-Oriented Framework in six sectors (Macro-economic, PFM, Public Administration, Health, Education and Social Protection). The pilot phase lasted from April to December 2015. Sector leads consulted with PA counterparts on progress against mutually agreed indicators and provided a quarterly progress report which assessed progress and challenges. The UK led on the Public Administration fiche and inputted regularly into the Macro-Economic and PFM fiches. Senior technical level policy dialogue took place in February 2016 between the EU, sector leads, the Prime Minister’s Office and line ministries to assess progress in 2015 as well as agree new indicators for 2016. The 2015 annual report was issued in early 2016. The EU ROF has been extended for a further year till December 2016. The EU is currently carrying out an independent external evaluation of the PEGASE mechanism and the pilot phase of the ROF. Depending on the results of the evaluation, the EU intends to continue with the ROF and potentially expand it to include other sectors.

Summary of responses to issues raised in previous annual reviews

The 2015 AR recommended ensuring that the SBG evaluation fully considers the role of results frameworks to help the PA develop a coherent reform agenda, and that indicator 3.3. be amended to reflect the development of a new EU results framework.

Recommendations for future programmes

- Continue to strengthen donor coordination and policy harmonisation on public financial management and public administration, through the LACS Sector Working Groups and close engagement with the EU, the WB and the IMF, with a view to strengthening a coordinated approach to results-based aid.
- Continue to ensure close alignment between the PRDP conditionality framework and the EU Results Oriented Framework.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Total costs for the programme have been higher than originally anticipated. Donor financing overall has increased over the period, and the calculation now covers five years of financial assistance rather than four. The calculation now also includes additional transaction costs such as exchange rate costs. The re-estimated costs now cover seven cost areas and include: 1) donor financing; 2) costs for administering the PRDP; 3) Exchange rate costs; 4) Donor staff time for implementation; 5) Reputation risk to donors; 6) Loss of donor political capital; 7) costs borne by the PA. As with the original calculation, not all costs can be fully monetised.

VfM performance compared to the original VfM proposition in the business case

The original business case used a cost-benefit analysis (CBA) to assess whether the programme would deliver VFM. The evaluation concluded that the total benefits from the SBG are larger than originally anticipated in the business case (see table on page 64 of the evaluation for a pre and post-implementation comparison of all the benefits of the SBG). A larger programme covering a longer period generates commensurately larger direct benefits in terms of fiscal stimulus and other identified macroeconomic benefits. The benefits of fiscal savings delivered during the programme are also included. Importantly, the calculation now includes an assumption of a large benefit from conflict averted as a result of the PA being able to engage in the peace process, supported by donor (and therefore DFID) financing. On the basis of various assumptions, this yields a large annual benefit. However, if this benefit is excluded from the analysis or the PA’s ability to maintain peace and security is significantly reduced, the NPV becomes negative and larger than anticipated in the original business case.

Assessment of whether the programme represented value for money

The evaluation’s revised cost-benefit analysis suggests that the programme represented a positive return on investment. The re-calculated net present value (NPV) for the SBG at a 10% discount rate suggests positive monetised benefits of £17.35 million. This means that the SBG may be a better investment than thought at the time of the original business case.

Quality of financial management during programme

World Bank
The Palestinian Reform and Development Plan Trust Fund (PRDP-TF) pools different donor funds into one administrative mechanism. This reduces the transactions costs for the PA and for the participating donors, and clearly links support to reform progress and provides regular and reliable disbursements to support priority recurrent and project expenditures in the budget

The PRDP-TF is audited by the World Bank’s external auditors following standard World Bank Trust Fund management practice. There is also an annual audit conducted by external auditors, paid for by the World Bank as part of the cost of administering the PRDP-TF. The PA produces progress reports on the National Development Plan to the World Bank at the end of each calendar quarter. The PRDP-TF then disburses after each calendar quarter upon receipt of the PA’s reform progress report. Progress reports can be delayed, and as a result, disbursement by the WB to the PA will also be delayed.

Link to PRDP-TF website:
http://web.worldbank.org/WBSITE/EXTERNAL/COUNTRIES/MENAEXT/WESTBANKGAZAEXTN/0,,contentMDK:21779811~pagePK:1497618~piPK:217854~theSitePK:294365,00.html
Link to PRDP-TF quarterly reports: http://web.worldbank.org/WBSITE/EXTERNAL/COUNTRIES/MENAEXT/WESTBANKGAZAEXTN/0,,contentMDK:21878744~pagePK:1497618~piPK:217854~theSitePK:294365,00.html

UK funds were independently audited twice a year as agreed in DFID’s MOU with the PA.

The PA has co-operated with regular Fiduciary Risk Assessments and Annual Statements of Progress carried out by DFID during the programme, as well as the Public Expenditure and Financial Accountability assessment process led by the World Bank. The Outcome Assessment provides an overview of PA progress on PFM reform.

E: RISK

Quality of risk management over the life of the programme

Our current judgement is that the overall risk rating of this programme is Severe. Throughout the programme, a risk matrix was used as an active management tool with progress reviewed on a quarterly (and then monthly in 2016) basis as part of the DFID OPTs approach to risk management. Where there was a change in direction or level of residual risk of a particular risk, it was raised in the Quarterly Challenge meeting and discussed with the DFID Head of Office in the first instance, then escalated to Head of Department, Director/Director General and Ministers as appropriate.

Stringent safeguards were in place throughout the period of the programme such as counterterrorism clauses in the MoU, earmarking and audits.. As set out in section D, the World Bank PRDP-TF, EU PEGASE mechanism and UK contribution were independently audited.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Output indicator 3.1 provides detail on the delivery against timeframe.

Performance of partnership(s)

DFID/World Bank relationship
The World Bank is assessed as having operated the PRDP Trust Fund effectively and efficiently throughout the programme. In 2012 they altered their financial procedures to enable donor funds to be transferred more quickly. The Bank has charged 1% of the contribution to administer the Trust Fund – this has recently increased to 5% (for all World Bank Trust Funds – this is supported by DFID at the corporate level). Administrative fees should be factored into the VfM appraisal of delivery mechanisms for future support to the PA. In January 2014, the World Bank began procedures to extend the Trust Fund for another three years, which resulted in the payment of an additional fee by all donors, proportional to their contribution, starting February 2014 and ending August 2017. All donors, including the UK, agreed to this amendment.

DFID/PA relationship
The UK’s relationship with the PA is governed by a Memorandum of Understanding (MoU) which centres on mutual accountability, good governance, transparency and commitment to non-violence. The most recent formal MoU Dialogue meeting took place in June 2016 where the UK reaffirmed its commitment to the Palestinian Authority and outlined the major challenges that the PA was facing. The PA affirmed the need to increase the PA’s efforts on delivering institutional reforms, where some sectors were further ahead than others.

Collaboration with other donors
The UK works closely with other donors and International Financial Institutions through a range of donor coordination mechanisms (within the EU and the Local Aid Coordination Secretariat). The UK leads on coordination of public administration reform and is actively engaged in public financial management. At EU level, the UK has been involved in setting key targets for policy reform priorities of the Results-Oriented Framework.

Asset monitoring and control

No assets have been procured under this programme.

G: CONDITIONALITY

Partnership principles assessment

We assess the Palestinian Authority’s commitment to DFID’s Partnership principles on a quarterly basis under the Statebuilding Grant Programme. The most recent assessment took place in January 2016, where it was assessed that the PA continues to deliver on the Partnership Principles, even under increasing fragile and volatile conditions.
The Partnership Principles are also discussed in the context of the annual MoU Dialogue meeting As indicated the most recent meeting took place in June 2016.

H: MONITORING & EVALUATION

Evidence and evaluation

Over the period of the programme, there have been several reviews of the programme, including the independent evaluation of the programme by the Overseas Development Institute; a comprehensive Fiduciary Risk Assessment of PA systems; and reports following visits by the International Development Committee, National Audit Office and DFID’s Internal Audit Department.

Monitoring progress throughout the programme

The programme comes under the portfolio of the OPTs Security and Governance team and is managed by a Project Manager with Governance Advisor and Senior Responsible Owner (SRO) input.

The team monitors progress through:
- Quarterly assessment of the Partnership Principles
- Regular meetings with MoF and WB
- Attending sector working groups including Public Financial Management
- Annual Reviews

Project Completion Review:
This was completed by the Project Manager with input from Governance Advisor, Economics Advisor and the SRO.
Key references: