Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Lebanon Municipal Service Programme
Programme Value: £9.3 million		Review Date: 15/06/16
Programme Code: 204397	Start Date: April 2015	End Date: February 2017

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	N/A	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress,

In 2015/16 the Municipal Action Plans identified a total of 90 projects: 29 in the Bekaa, 31 in the North and 30 in the South; 72 are basic services projects and 18 are livelihoods projects. Based on population data from the communities targeted, the total direct beneficiaries of the 90 projects will include: 253,843 Lebanese and 150,083 Syrian refugees. Originally, all projects were to be completed by March 2016. The lengthy approval process has meant that the original timetable was revised: By June 2016 59% of the 90 projects will have been completed and by September - 6 months after DFID’s expected end date - 94% will have been completed, with the remaining projects scheduled for completion by February 2016.

Aktis Strategy’s research demonstrates that LMSP is having a tangible impact on social tensions caused by service delivery in communities targeted, but also that concerns around livelihoods and competition for jobs are becoming increasingly divisive issues within communities. DFID’s assessment is that LMSP is meeting the expectations against the revised programme schedule and is having a demonstrable impact on the ground. For this reason an overall score of an A was judged appropriate. Despite performing well there are a number of lessons set out below that can be learned from this programme.

Lessons Learnt/Recommendations since last review

- DFID and UNDP should invest more time in ensuring the logframe for this intervention is kept relevant and up to date.
- UNDP are increasingly concerned about the time scales for delivering LMSP in the confines of donor financial year allocations. Real thought will need to be given to how DFID contributes to LMSP in a way that respects the community/GoL planning and approval process while also delivering within the scope of DFID’s processes.
- DFID could have been consulted more in the decision making process in December when the decision to delay updating the MRR’s was made.
- Jobs/Livelihoods continue to be an important and divisive issue in many communities across Lebanon. DFID are aware of the need to address these issues however there is a strategic question over whether LMSP is the preferred modality for addressing.
- The external evaluation by Aktis Strategy provides an invaluable insight into the perceptions of those beneficiaries in the communities targeted. The UK, through UNDP, will continue Aktis’s work over the next 12 months, and introduce a quantitative component to reinforce qualitative perception surveys.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	5450476
DevTracker Link to Log frame:	5492994

The influx of over 1m registered refugees fleeing the civil war in Syria has placed a huge strain on Lebanon’s economy and society. As of June 2016, more than one in every four people in Lebanon was a refugee (either Syrian or Palestinian). As a result Lebanon faces the real threat of domestic civil instability and violent extremism.

The UK’s objectives in Lebanon as set out by the National Security Council include strengthening resilience, stability and social cohesion, with refugees and host communities increasingly integrated and able to co-exist peacefully, and their resistance to extremism and radicalisation strengthened.

To help met these objectives the UK provided £9 million of funding in 2015/16 for the Lebanon Host Community Support Programme (LHSP) managed by the UN Development Programme (UNDP). £4 million of this funding came from DFID’s bilateral resources and £5 million from the cross-Government Conflict, Stability and Security Fund (CSSF).

The purpose of the DFID funded Lebanon Municipality Support Programme (LMSP) is to reinforce the capacities of municipalities to respond to the increased demand for services and to reduce inter communal tensions arising from the arrival of refugees which in some places have nearly doubled the population. The intervention currently targets 49 municipalities in areas of high social tensions across the Bekaa, South and North of Lebanon (including Tripoli).

The expected impact of this programme is a reduction in the level of tension between refugees and host communities in target areas. The expected outcome delivered by the programme will be enhanced basic services and livelihoods support in target municipalities. The target criterion for selection of municipalities is the ratio between inhabitants and Syrian refugees. The Outputs under this programme are:
- Output 1: Target municipalities identify service priorities through engagement with communities, taking account of preferences based on gender, confessional group, age and Lebanese/refugee status.
- Output 2: Improved and/or expanded municipal services and livelihoods initiatives are delivered in target municipalities based on community driven needs assessment.
- Output 3: Local mechanisms for social stability are established and sustained and knowledge of conflict dynamics better understood.
In March 2016, an additional £0.3 million from the CSSF was given to UNDP to fund Social Development Centres (SDCs) of the Ministry of Social Affairs, increasing the overall budget to £9.3 million. The objective of increasing funding by £300,000 is to reinforce the capacities of 15 SDCs to deliver care services to vulnerable communities affected by the Syrian crisis, based on community needs identification.

The original envisaged programme end date was March 2016. However the UNDP planning cycle, delays linked to Lebanese municipal elections and getting projects approved has meant that the programme will not end until February 2017. The original LMSP log frame included milestones up to March 2016. This log frame was later revised to reflect the February 2017 end date. Performance in this Annual Review is measured against this revised logframe.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

As part of £0.2 million funding for research and monitoring of impact of the programme Aktis Strategy was contracted to conduct field monitoring and evaluation of DFID funded interventions in six of the forty-nine municipalities targeted by DFID’s contribution to LMSP. As referenced in the logframe, the findings of these six-monthly evaluations form the basis for measuring the outcomes of the programme.

In the latest March 2016 Impact Evaluation of LMSP, Aktis concluded that:

As the municipality improves service delivery through projects under LMSP, residents feel increasingly more engaged and in control of the situation in their community, encouraging further ownership and positive interactions within and with municipalities.

Respondents who mention jobs/employment however continue to feel disempowered and unable to influence their environment. But as most respondents perceive the central government as responsible for improving the employment situation, it is however logical that they would feel less empowered.

Increased feelings of tension exist between the refugees and host communities, and are largely over competition related to employment and jobs. As service delivery improves through municipal projects, residents are turning to longer-term concerns, such as employment. Aktis suggest this competition is likely also drawn from the realisation that refugees are unlikely to return home in the near future.

The lack of stories reflecting cooperation between refugees and host communities when it comes to service delivery may, Aktis suggest, be signalling an isolation of the refugees within each municipality. This is further reinforced by the growing number of people who reported avoidance instead of cooperation. This may also play into the perception that refugees are stealing jobs from host communities, so the relationship has become one of competition for survival rather than cooperation.

Overall however municipalities are increasingly viewed as both trusted to take the right action and able to do so. The municipality continues to be seen as the source most responsible for service provision, which reflects the positive impact of the recently implemented projects through LHSP and the municipalities in boosting the legitimacy of the local authorities and their ability to meet people’s expectations.

DFID recognise that in an evolving context the drivers of social instability and tension are continuously changing. Aktis’ research demonstrates that LMSP is having a tangible impact on social tensions caused by service delivery in communities targeted, but also that concerns around livelihoods and competition for jobs are becoming increasingly divisive issues within communities. There are lessons here to be learnt, and adaptations to be made, however overall LMSP is meeting expectations in delivering ‘enhanced municipal services and improved livelihoods conditions in targeted municipalities across Lebanon’.

Overall output score and description

Overall, DFID has scored this programme an A based on the following Output scoring.

- Output 1: Target municipalities’ identified service priorities through engagement with communities: B (20%).
- Output 2: Improved and/or expanded municipal services and livelihoods initiatives are delivered in target municipalities: A (70%).
- Output 3: Local mechanisms for social stability established and sustained and knowledge of conflict dynamics better understood: A (10%).
LMSP is meeting the expectations against the revised programme schedule across and is having a demonstrable impact on the ground. For this reason an A was judged appropriate. Despite performing well there are a number of lessons set out below that can be learned from this programme.
Key lessons

- DFID and UNDP should invest more time in ensuring the logframe for this intervention is kept relevant and up to date. Better use of the programme logframe on both sides as a management tool could have ensured differences in expectations around delivery were identified earlier.
- UNDP are increasingly concerned about the time scales for delivering LMSP in the confines of donor financial year allocations. In their lessons learnt they identify ‘respecting the timeframe of one year implementation whilst ensuring quality and sustainability’ as a key challenge. Real thought will need to be given to how DFID contributes to LMSP in a way that strikes the balance between respecting the community/GoL planning and approval process while also delivering within the scope of DFID’s processes.
- DFID could have been consulted more in the decision making process in December when the decision to delay updating the MRR’s was made. DFID should reiterate to UNDP the need to be informed when decisions are made which will affect LMSP’s delivery against the logframe.
- Based on the results of Aktis Strategy, Jobs/Livelihoods continue to be an important and divisive issue in many communities across Lebanon. UNDP and DFID are aware of the need to address these issues, but there is a strategic question over whether LMSP is DFID’s preferred modality for addressing this – further internal discussion is needed.
- The external evaluation by Aktis Strategy provides an invaluable insight into the perceptions of those beneficiaries in the communities targeted. Whilst covering only 6 of 49 municipalities, Aktis’ work enables LMSP to respond flexibly to Lebanon’s changing context. The UK, through UNDP, will continue Aktis’ work over the next 12 months, and introduce a quantitative component to reinforce qualitative perception surveys.
- After a number of field visits which the team felt could have been better, the DFID Head of Office, SRO and programme manage feel a more robust strategy is needed for field visits going forward, including what the objectives of such visits are and their regularity.
- DFID have worked closely with UNDP in the development of TORs for an external evaluation of LHSP as a whole, due to start August 2016. This will look at the sustainability of the programme, the role of MoSA as a coordinating body and how the programme impacts on perceived municipal legitimacy, alongside the impact of each programming strand and areas for improvement. Lessons from this review will help shape our ongoing commitment to the programme.

Key actions

- DFID will request an updated version of UNDP’s risk register moving into the second year to ensure UNDP’s and DFID’s assessment of the risks associated with this programme are aligned.
- DFID will continue to closely monitor UNDP’s delivery of the 90 projects under Output 2 and to stress the importance of no further slippage to the timelines.
- Whilst increased GoL involvement is extremely welcome, a balance needs to be struck between GoL oversight and consultation, and timely delivery of projects. DFID should continue to talk with UNDP about this, and ensure timelines for project delivery are proportional.
- As the implementation of projects under this programme has already been agreed, as we discuss the UK’s 2016/17 contribution to LMSP with UNDP, there will need to be a strategic discussion on the split of DFID’s allocation to livelihood vs basic service delivery projects going forward (which currently stands at 20:80).
- DFID should ensure moving forward that i) UNDP are reminded that deviations from the agreed budget should be communicated during the programme, ii) budgets should be submitted in GBP and iii) more detail should be given in financial reports, with a financial narrative included.

Has the logframe been updated since the last review?

Yes - The logframe was amended to reflect the February 2017 end date, with the initial March 2016 targets moved to February 2017 and quarterly milestones included to measure performance up to the end date.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Target municipalities consolidate their community planning.
Output number per LF			Output Score	B
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones / 31st March 2016	Progress
1.1 Number of existing MRR-Multi-Sectorial Municipal Actions Plan updated by the Municipal Working Groups	49	19
1.2 Percentage of residents (who took part in the planning process) are "satisfied or very satisfied" with the process for planning the improvements (related to this project) in their municipality.	70%	80%
1.3 Percentage of budget allocated to planned activity spent or committed	100%	100%

Key Points

In 2014 UNDP introduced with the support of DFID the Methodology of Maps of Risks and Resources (MRR) for a participatory conflict-sensitive needs assessment in municipalities with the highest ratio of Lebanese population to Syrian Registered refugees. The output of the MRR is a Village Profile and a Multi-Sectorial Municipal Action Plan (MAP), for identifying short and medium-long term projects, based on an assessment of risks, problems, needs and alternative solutions. The Methodology was implemented by UNDP covering 51/242 highest ratio municipalities by June 2014, including the 20 of the 2014/15 UK-DFID intervention.

In 2015/16 MoSA agreed to extend the MRR component to:

- Update: The 49 municipalities supported by UK-DFID intervention in 2015-2016
- New: The 111 municipalities not yet assessed (242 – 131 already assessed by December 2014).
UNDP delivered 19 of the planned 49 updated MRR’s in the UK’s 49 municipalities, reaching only 45% of the proposed target for March 2016. UNDP’s performance over time:
Output Indicator 1.1 Milestones vs Performance
June 2015	Sep 2015	Dec 2015	Mar 2016
0	19	29	49
0	19	19	19

Delay in implementing the updated MRR’s was caused by Municipal elections held on the 8th of May 2016. These elections were the first Municipal elections in Lebanon for 6 years. Given that elections across Lebanon have been postponed on numerous occasions, in the planning stages of LMSP there was uncertainty about whether municipal elections would take place, and therefore the initial logframe did not take them into account.
As of February 2016, the GoL requested UNDP cease MRR activities in municipalities in order to avoid unfairly benefitting the incumbent municipal officials. In the lead up to February 2016, in order to avoid any significant delay in the finalisation of the new targeted communities, UNDP decided to prioritise these ones over updating of the old MRR.
This meant that whilst UNDP carried out new MRR’s in other (non-UK supported) municipalities, in parallel UNDP ceased updating previous MRR’s to ensure implementation of projects in those municipalities which did not previously have MRR. This is the reason why implementation was delayed from December 2015 and UNDP missed two consecutive milestones.
DFID has discussed this issue with UNDP and is content with UNDP’s reasoning. DFID is aware of the difficulties during planning in foreseeing May’s Municipal elections, and agrees with UNDP’s decision to deprioritise updating old MRR’s in favour of completing new ones elsewhere. As projects in the UK’s 49 municipalities were based on old MRR’s, delaying updating them would not have had an impact on the delivery of projects in its target communities, whereas not completing new MRR’s in other vulnerable municipalities could delay the implementation of essential projects by almost 6 months.
Assessment: B
UNDP have assured DFID that now the Municipal elections are complete, 29 MRR’s will be updated by 31 June 2016 and the full 49 by 31 September. Owing to the uncertainty around whether the municipal elections would take place, the four months freeze (February – May 2016) on implementation by the GoL in the lead up and during the elections, and the revised targets set by UNDP, the DFID CSSF team feels this target is realistic and the programme will continue to meet expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)

i) 2014/15 AR Recommendations:

For 2015/2016 we decided to strengthen the MRR process by extending the workshops to 4 days instead of 2 and ensuring close coordination and involvement from the MOSA Regional Offices.

ii) 2015/16 Progress:

UNDP identified in its 2015/16 proposal three lessons to improve the MRR methodology:
- More capacity building of MoSA staff on the MRR implementation
- Allocating more time for the implementation (from two to five days completing the assessment, data entry and Municipal Action Plan elaboration)
- Allocating more resources for the follow up and implementation in municipalities not yet covered

In support, the UK advocated that UNDP re-brand the MRR process as a MoSA tool to encourage GoL/MoSA buy-in and leadership, and provided £107,000 to build MoSA’s capacity to deliver the new MRR lead process. Part of this funding went into the recruitment of MoSA MRR support officers and training workshops. Overall, the methodology of the MRR was improved in phase 3. The assessment is now led by MoSA and is implemented over a 5 day period, ensuring an even more thorough process.

Recommendations

DFID’s recommendation is that it should have been consulted more in the decision making process in December when the decision to delay updating the MRR’s was made. DFID will communicate this to UNDP.

Output Title	Improved and/or expanded municipal services and livelihoods initiatives are delivered in target municipalities based on community-driven needs assessments.
Output number per LF			Output Score	A
Risk:		Moderate	Impact weighting (%):	70%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Proportion of municipal service projects identified in community plans which are fully completed.	N/A / (See below)	N/A / (See below)
2.2 Number of direct beneficiaries of completed municipal service projects.	100,000	107,418
2.3 Proportion of livelihoods projects identified in community plans which are fully completed.	N/A / (See below)	N/A / (See below)
2.4 Number of direct beneficiaries of completed livelihoods projects	2,250	1,645
2.5 Percentage of budget allocated to projects spent or committed	100%	100%

Key Points

The intervention continued in the 19 municipalities assisted during 2014 and was expanded to 30 new municipalities in the Bekaa, South and North of Lebanon, including the city of Tripoli. The criterion for UNDP’s selection of the most vulnerable municipalities is the ratio between the Lebanese inhabitants and displaced Syrians. In selection its 49 municipalities however, the UK also looked at geographical location, confessional balance and conflict vulnerability, to ensure the best strategic fit with UK policy and objectives.

In 2015/16 the Municipal Action Plans showed a total of 90 projects were identified: 29 in the Bekaa, 31 in the North and 30 in the South; 72 are basic services projects and 18 are livelihoods projects.
Based on population data from the communities targeted, the total direct beneficiaries of the 90 projects will include: 253,843 Lebanese and 150,083 Syrian refugees.

Of these:

- Basic Services: direct beneficiaries 245,947 Lebanese and 148,866 Syrian refugees
- Livelihoods: direct beneficiaries 7,896 Lebanese and 1,217 Syrian

Delivery of the 90 projects initially involves identification through the “MRR” process. However, proposals for projects then go through a process of being drawn up collaboratively with the relevant GoL line ministry and then are submitted to the ministries for pre-approval before presented to a Technical Group for final sign off. This process takes time, however it does ensure a programme which has the full backing of the GoL and encourages increased GoL ownership of the response inside Lebanon.

Originally all projects were to be completed by March 2016. The lengthy approval process has meant that the original timetable was revised: By June 2016 59% of the 90 projects will have been completed and by September - 6 months after DFID’s expected end date - 94% will have been completed, with the remaining projects scheduled for completion by February 2016.

Project Completion Dates
Month	Mar-16	Apr-16	May-16	Jun-16	Jul-16	Aug-16	Sep-16	Oct-16	Dec-16	Jan- 17	Feb- 17	Total
Projects	18	-	-	17	-	-	32	-	3	-	2	90
Cumulative	29	-	36	53	-	-	85	-	88	-	90	-
Percentage	32%	-	40%	59%	-	-	94%	-	98%	-	100%	-

Assessment: A

Whilst there has been some delay in delivery caused by the increased involvement of MoSA in the early approval phases of the programme and the Municipal elections in May 2016, DFID are content with the schedule outlined above and UNDP’s progress against the revised logframe targets.

As described above, DFID welcome the GoL’s increased involvement in the planning and implementation of this programme and judge this to be an integral part of the programme’s success. It should also be noted that the target for ‘beneficiaries of completed municipal service projects’ has also been raised during the logframe revisions, rising from 250,000 to 390,000 direct beneficiaries, representing a 156% increase.

As DFID’s MOU with UNDP ends in February 2017 and all projects are on track to be completed by this date, with a realistic timeline in place, DFID’s assessment is that the programme is still meeting expectations and therefore deserves an A.

Summary of responses to issues raised in previous annual reviews (where relevant)

We should continue regular field visits to monitor progress, the quality and the impact of the projects implemented.

Recommendations

- DFID and UNDP need to invest more time in ensuring the logframe for this intervention is kept relevant and up to date. Better use of the programme logframe on both sides as a management tool could have ensured differences in expectations around delivery were identified earlier.
- Similarly, whilst increased GoL involvement is extremely welcome, a balance needs to be struck between GoL oversight and consultation, and timely delivery of projects. DFID should continue to talk with UNDP about this, and ensure timelines for project delivery are proportional.
- DFID will continue to closely monitor UNDP’s delivery of the 90 projects under Output 2 and stress the importance of no further slippage to the timelines.

Output Title	Local mechanisms for social stability (MSS) established and sustained and knowledge of conflict dynamics better understood.
Output number per LF			Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
3.1 # of committees established in target municipalities	49	49
3.2 # of activities organized by the committees	49	49
3.3 # of informative sessions organized with the committees around CMA	49	49
3.4 # of interventions by the committees in conflict situations	20	20
3.5 Percentage of usage of CMA by Social Cohesion Working Group partners at central and local level	70%	80%
3.6 Percentage of usage of CMA by MoIM and MoSA at central and local level	70%	70%
3.6 Percentage of budget allocated to projects spent or committed	100%	100%

Key Points

Under Output 3, UNDP has been simultaneously following up on the mechanisms for social stability implemented under previous DFID funding to LMSP and launching new MSS’s in new villages selected in the same three areas.
- Follow up on established MSS in the 16 targeted communities: 8 communities of Wadi Khaled; 4 in Central Bekaa: Bar Elias, Saadnayel, Majdel Anjar, Terbol; 4 in South: Sarafand, Cheba’a, Bissariyeh, Borj Chemali.
- Launching of new Mechanisms for Social Stability (MSS) in 27 newly selected communities in Central Bekaa, South and Akkar.

The Conflict Mapping and Analysis (CMA) page continues to provide a resource for local and international NGOs, the international community and relevant ministries. The CMA website is being updated on a daily basis with new conflict analysis bulletins and summary analysis of key data trends in 2015. (http://cskc.daleel-madani.org/article/conflict-analysis-bulletin-issue-2-april-2016)

In addition, three new infographics reviewing 2015 data were produced, highlighting: 1) all incidents by categories, showing that airspace violations are first, arrests are second and collective actions, shooting and raids are third; 2) armed conflicts which were restricted to a number of hotspots such as: Arsal, Ras Baalbeck, Chebaa, Ain el Helweh, Tripoli and Beirut; 3) analysis of illicit activities showing how the different security forces deal with illicit activities.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

DFID will continue to work with UNDP to share conflict analysis findings widely with stakeholders, including MoSA, mayors and municipality members, as well as other donors and NGOs. This will include establishing how best to collate and build on analyses to date.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Cost Type	Description	Expenditure 2015-2016	Commitments 2016	Total
Project Deliverable	Project implementation	£1,419,257.20	£5,148,553.76	£6,567,809.96
	Perception impact studies	-	101,896	£101,896
	MRR	£22,178.96	£118,000.00	£140,178.96
	Strengthening capacities of MOSA	£59,981.48	£106,666.66	£166,648.14
Support Costs	Salaries	£427,475	£73,813.33	£501,293.33
	Local Consultants Support	£228,269.19	£29,824.66	£258,093.85
	Grant Agreements	£185,527.30	£13,096.50	£198,623.80
	Transportation expenses	£16,407.15	£20,055.36	£36,462.51
	Miscellaneous	£259,659.53	£13,333	£272,992.53
	Office Rent	£36,098.03	£69,500	£105,598.03
General Management Support (7.5%):		£212,384.59	£455,579.22	£667,963.81
Programme Total:		£2,867,238.43	£6,150,318.49	£9,017,560.92

Approximately £7 million of the UK’s initial £9 million has been allocated to project deliverable costs, representing 77.25% of the total budget. Of the £7 million, approximately 80% (£5.6 million) has been allocated to Service Delivery projects and 20% (£1.4 million) to Livelihood Projects. A further £1,373,000 has been allocated to Project support costs, representing 15.25% of the total budget and another £670,000 to a mandatory General Management support contribution, making up 7.5%.

VfM performance compared to the original VfM proposition in the business case

In the LMSP proposal, £626,666 in support costs were initially allocated to the programme. This figure however almost doubled throughout the course of the year to £1,373,000. Whilst this increase does demonstrate a deviation from the original business case, 15.25% in support costs does represent a decrease in the previous year’s support cost budget allocation of 19%.

At only 7%, UNDP’s doubling of support costs seems a response to an underestimation in their initial forecasting rather than a decrease in the value for money of the programme. Overall, the programme still delivered the agreed outputs described in the original project proposal and business case within the overall programme allocation.

The UK should however reiterate to UNDP that any reallocations of funding should be communicated to DFID during the programme.

Assessment of whether the programme continues to represent value for money

DFID still assess this programme as representing good VfM. Over the past two years LMSP has grown from a £7 million multi-donor programme (of which the UK contributed approximately £5 million), to almost £36.5 million, with the UK contributing £9 million. DFID’s initial funding has leveraged approximately £25 million from other international donors such as the United States and Germany, all contributing to the UK’s objective for a resilient, stable and socially cohesive Lebanon. LMSP presents an opportunity to multiply and maximise the impact of the UK aid.

Moreover, through our continued support and by improving the capacities of MoSA, LMSP continues to play a crucial role in strengthening our relationship with the GoL. Good relationships with MoSA, as the principal ministry responsible for the management of the humanitarian situation inside Lebanon, has a net benefit beyond the confines of LMSP and helps programming, policy and advocacy work across DFID Lebanon’s portfolio and in delivering the UK’s wider objectives in Lebanon.

Quality of financial management

Aside from the deviation set out above and the delays to implementation/spend caused by increased GoL involvement and Municipal elections, UNDP’s financial management of the programme has been good. DFID would recommend that a key lesson from this review however is that i) UNDP should be reminded that deviations from the agreed budget should be communicated during the programme, ii) budgets should be submitted in GBP and iii) more detail should be given in financial reports, with a financial narrative included.

Date of last narrative financial report	25/04/2016
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

Moderate/Medium.

Overview of programme risk
UNDP has delivered LMSP in Lebanon’s challenging context for almost two years. Whilst the challenging regional and domestic context mean the risks associated with this programme were high, accordingly, social and political dynamics that are key risk factors for violence in Lebanon were included in the design of LMSP to treat and mitigate some of these risks, lowering the overall risk rating.
UNDP programmes and projects are all managed through a Results Based Management (RBM) system, a customised version of PRINCE-2. The RBM approach clearly specifies that any major deviation from the approved work plan will be presented to the committee for approval. A Risk Log and an Issues Log will be maintained for the project. There were no significant changes to the Programme Risk Register as presented in the original programme proposal.
DFID will however request an updated version of UNDP’s risk register moving into the second year to ensure UNDP’s and DFID’s assessment of the risks associated to this programme are aligned.
Outstanding actions from risk assessment

N/A

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

As explained above, the expected timeframe for delivery of this programme has needed to be revised in light of discrepancies between the logframe targets and the end date in DFID’s MOU with UNDP. Despite these revisions, the programme has suffered from some delays caused by the increased involvement of the GoL in the approval process of projects and the holding of Municipal elections in May 2016. These delays have been explained in detail under the scoring for Outputs 1 and 2 (Section B). Looking forward, DFID has had lengthy discussions with UNDP to ensure expectations are aligned on the timeframe for the rest of the delivery of this programme, and DFID is confident in the timelines and assurances given by UNDP.

Performance of partnership (s)

DFID and UNDP have developed a strong working relationship throughout the lifetime of LMSP which ensures, even as the multi donor funded programme grows, the UK has a strong voice in the direction of the programme. As the programme has grown however, there has been a breakdown in communication regarding expectations around delivery and this has meant the logframe has needed to be revised.

UNDP have however demonstrated a commitment to ensuring LMSP is continued to be evaluated and the lessons learnt implemented to improve the impact of the programme. In their March 2016 report under ‘Section VI: Challenge, Lessons Learned and Next Steps’ UNDP captures numerous lessons and recommendations to inform the programme going forward. Moreover, UNDP have also demonstrated commitment to ensuring lessons are learnt through the expansion of the MRR process (detailed above) and the commissioning of an external evaluation of the programme, beginning August 2016. As recommended above, DFID could improve its partnership with UNDP through a stronger focus on the logframe as a management tool to ensure expectations are aligned.

Asset monitoring and control
N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The evidence base for the LMSP is based on a number of studies that continue to show the importance of municipalities as the frontline of coping with the rapid influx of the large number of Syrian refugees into Lebanon. Aktis Strategy evaluation continues to show that service delivery issues remain the top consideration of people asked, while increasingly when refugees are mentioned, so is perceived competition over jobs and economic opportunities. The most recent round of Aktis data has been disaggregated further to explore trends across age groups, socio-economic differences and gender. We will also continue to work with UNDP and Aktis to survey both Lebanese and Syrians regarding their perceptions around impact of programming.

DFID have worked closely with UNDP in the development of TORs for an external evaluation of LHSP as a whole, due to start August 2016. This will look at the sustainability of the programme, the role of MoSA as a coordinating body and how the programme impacts on perceived municipal legitimacy, alongside the impact of each programming strand and areas for improvement. This lessons of this review will shape our ongoing commitment to the programme and any lessons will be implemented.

Monitoring progress throughout the review period

Alongside formal quarterly reports, the programme team has conducted a number of visits alongside other Embassy colleagues to municipalities across the country to see first-hand work across service provision, livelihoods and mechanisms for social stability. In the South (Sarafand) the municipality and beneficiaries talked about the impact of the newly refurbished fish market as providing much needed economic opportunities for Lebanese and Syrians, while boosting the local area. In Tripoli, the municipality showed the positive changes brought about by infrastructure programming in vulnerable, dangerous areas. In the Bekaa, the newly elected mayors of Barr Elias and of Zahle both reiterated the need for programming at municipal level to tackle the issues faced by host communities of a large number of Syrian refugees and thanked the UK for their support to the programme.

In July 2016 the MRR results will be available through the MoSA website and the Prime Minister’s Office website. The programme team will accompany the UK Ambassador to Lebanon to attend a launch event of this, hosted by the Prime Minister. The Ambassador has been invited to give a speech and UK support praised in enabling this huge step forward.

Update - Upon reviewing this annual review, the DFID Head of Office felt that there needed to be a more systematic approach to field visits. After a number of field visits which the team felt could have been better, the SRO and programme tend to agree with this point and will design a strategy for field visits going forward, including what the objectives of such visits are and their regularity. This will be discussed with UNDP in due course.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process