Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Supporting Effective Democratic Governance
Programme Value: / £9.3 m (DFID contribution), £10.5 m (FCO contribution)		Review Date: / June 2016
Programme Code: / 204757	Start Date: / 1 April 2015	End Date: / 31 March 2018

Summary of Programme Performance
Year	2016	2017	2018
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learnt since last review
In response to the 2015 Triennial Review, the Westminster Foundation for Democracy (WFD) set out a new strategy in early 2015 and revised its board and management structure, monitoring and reporting framework, financial, communications systems and programming.
In summary, institutionally WFD is playing an important UK role in communicating about the value of parliaments. Areas of work such as regional networks and the new research programme are performing above expectations. Work with women MPs on gender issues is a strength and exceeding expectations. There were fewer than expected instances of parliamentary and party staff sharing their general expertise with partners in developing countries. Links between parliamentary and party work and civil society stakeholders should be reviewed as this is currently a relatively weaker are of work. In line with its theory of change, WFD could look to scale up its efforts to bring its constituent programmes together to create coalitions between parties, parliamentary staff and civil society to broker change.
UK Parliamentary personnel see WFD as an effective partner, and commented that relations have become more pro-active, co-operative and ‘outward-looking’ since the changes to WFD’s management structure.
On Output 1, parliaments and parties have sought to apply learning in the areas of gender, financial management, research, anti-corruption and tax, social media outreach and legislating. On the party side, the focus has been on gender, policy making, leadership, communications and negotiations. The gender work for example work with women’s MPs and caucuses or on quotas was well captured, and parliamentary and party interventions were less able to capture how the interventions achieved changes.. Moderately did not meet expectation.
On Output 2, peer-to-peer networks have covered issues including police accountability and parliamentary budget oversight. Moderately exceeded expectation.
On Output 3, brokered relationships and political space, progress is being made in a range of activities ranging from domestic violence to anti-corruption to women’s empowerment to research to transparency in oil and gas. The review did not see sufficient evidence of the WFD leveraging its different parliamentary and party expertise to enhance its ability to broker or enhancing civil society organisations’ access to Parliament. Moderately did not meet expectation.
On Output 4, context analysis, WFD produced a large volume of good quality country parliamentary technical assessments, which exceeded numeric expectation. There is a need for further discussion about the scope of future context analysis and their potential use in identifying political priorities and feasibility of interventions.. Moderately did not meet expectation.
On Output 5, the policy-oriented research agenda has produced a great deal of research material, and excellent engagement with DFID and FCO officials in its distribution. Substantially exceeded expectation.
The impact of the UK Elections in May 2015 meant that overall implementation was initially slower than anticipated. However, by the year-end, many of the planned programme milestones had been achieved, and actual expenditure was just five per cent below budget profile.
Summary of recommendations for the next year
R1. If DFID’s annual outcome scoring pilot is implemented in future years, the WFD M&E team should work with programme teams to begin annual outcome scoring across the full range of WFD programmes.
R2. The citizen participation outcome should be a focus of assessment at the mid-term evaluation and next annual review.
R3. WFD’s parliamentary and party expertise should attempt to address issues around decision making and political negotiation as well as technical skills around legislative drafting.
R4. The sustainability of peer-to-peer networks should be incorporated in their design and explicitly covered in reporting. Sustainability indicators could be considered as part of this.
R5. WFD could make much more of its ability to leverage its different parliamentary and party expertise to enhance its ability to broker relationships and space for policy change.
R6. WFD should review its focus on civil society organisations’ access to Parliament, which is currently underdeveloped given its importance in the theory of change.
R7. WFD should take forward its primarily technical parliamentary context analyses to in future include political context assessment of parliaments, parties and the political system to support politically informed programming decisions.
R8. WFD should further develop in consultation with DFID its concept of VFM, ensuring it is operationalised across the organisation by October 2016, with suitable indicators and means for assessing, particularly in terms of efficiency and effectiveness.
R9. WFD should encourage its country staff to consider how their daily relationships and interactions contribute to programme logframe outputs and to record this influencing work. Indicator 1.3 should be revised to reflect the greater number of activities following annual review. Indicator 5.2 should be revised to reflect the extent to which WFD is promoting its research and coverage within the democracy assistance community.
R10. Good progress should continue, and internal dissemination of lessons should be further enhanced across WFD.

This Annual Review was produced by the external consultants Moore Stephens in response to commission by the WFD Monitoring and Evaluation Steering Committee. There was feedback and detailed engagement from Westminster Foundation for Democracy including a party representative, the Foreign and Commonwealth Office and Department for International Development. Final edits and responsibility for the scoring and the overall review is held by the Department for International Development.

## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5080269.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5080297.xlsx

The purpose of this programme is to build democratic culture and practice in parliaments and political parties that will support inclusive and effective governance.
The Department for International Development (DFID) will provide up to £9.3 million over three years and the Foreign and Commonwealth Office will provide up to £10.5 million over three years from April 2015 to March 2018. The programme aims to cover at least 22 countries and six regional programmes.
The programme helps deliver Strategic Objective 1, Strengthening Global Peace, Security and Governance. It reflects and responds to recommendations of the International Development Committee (IDC) on the importance of context-specific, politically informed approaches;  the need for long-term engagement with flexibility built in to allow for continuous improvements; the need to combine parliamentary strengthening with support for other complementary elements of political and social accountability; and the significance of party politics in the design and execution of programmes.
WFD aims to achieve its intended outcome via five outputs:
1. Parliaments / parties where WFD works apply relevant lessons, including from British democratic experience;
2. Creation of dynamic regional peer-to-peer networks that address thematic priorities;
3. Brokered relationships and political space for policy change amongst civil society, parties and parliament;
4. Effective use of political context analysis by WFD; and
5. High-quality research and evidence informs support to democratic governance internationally.[1]
  [1] NB - responsibility for Output 5 is shared between WFD and DFID.
The main programme activities are as follows:
Parliamentary Strengthening - Through technical assistance and mentoring by British MPs or parliamentary officers, local research bodies and WFD staff, WFD assists parliaments to assess themselves and produce strategic development plans; set up parliamentary research centres; enhance leadership on policy issues; support women’s caucuses; and strengthen legislative / oversight capabilities, particularly public accounts committees and parliamentary budget offices.
Parties in Parliament - WFD HQ and British political parties work together to develop the capacity of parliamentary groups and party caucuses to deliver election promises and govern effectively, following specific policies through the legislative cycle from inception to implementation. WFD also works with parties to address obstacles to effective opposition politics, and support parties to operate within parliamentary institutions and structures.
Political Party Assistance - The major British political parties conduct ‘sister party’ / cross-party assistance in over 25 countries, providing technical assistance including mentoring, strategic planning support, practical learning and networking, and skills development of elected representatives. Parties also support organisational development, including internal democratisation, campaigning / external communications, and policy manifesto development.
Research - WFD contributes to public knowledge about effective democracy strengthening through research for political parties and parliaments in developing and transition countries. This research is conducted jointly with UK academic institutions. £0.3m is allocated to DFID to produce research and analysis and produce policy briefs to support innovation and the international community’s understanding of how best to support effective democratic governance.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment
The intended outcome of the programme is: “Democratic culture and practice in parliaments and political parties that will support inclusive and effective governance.” WFD has selected four outcome indicators to contribute to this overall measure:
1. Policy. The extent to which public policies are formulated or drafted or scrutinised by parliaments or political parties based on evidence and an open, transparent and consultative process. This measures outcomes accomplished by parliament or within parties. The scoring is assessed based on criteria related to evidence and the process.
2. Accountability. The extent to which parliaments or political parties hold other government institutions or actors to account or enhance their own accountability to their constituents and stakeholders. This measures outcomes achieved by parliament or within parties. The scoring is assessed based on criteria related to degree of accountability and the process through which it was achieved.
3. Representation. The extent to which parliaments or political parties represent effectively their specific constituencies and are representative of the interests and needs of their citizens as a whole. This measures outcomes observed by parliament or within parties. The scoring is assessed based on criteria related to MP performance and representativeness of parliament and party membership.
4. Citizen participation. The extent to which citizens, particularly women, youth or other marginalised groups, have greater access to and a more active role in parliamentary and political processes. This measures outcomes observed by parliament or within parties. The scoring is assessed based on criteria related to access and activity.
DFID has recently requested programmes to undertake an informal annual outcome assessment as part of a pilot project to determine whether this is possible. This would replace the current approach which is to wait for the end of the programme to assess outcome performance.
WFD is piloting outcome assessment in its programmes by assessing specific programmes against the four higher level outcome components. This is being rolled out slowly and according to plan.
This Annual Review made its own outcome assessments for the country programmes it specifically reviewed in the Western Balkans, Tunisia, MENA and Bosnia. This is not therefore a representative sample and results must be treated with caution.

Outcome Indicator	Milestone 1 / (average achievement / across programme, 0-4)	Actual 1 / (average achievement / across programme, a0-4)
1. Policy	0.75	0.75
2. Accountability	0.75	1.29
3. Representation	0.75	0.75
4. Citizen Participation	0.75	0.94
Overall score	0.75	1.04

Preliminary Outcome assessment: While the figures should be treated with extreme caution owing to the sampling approach, pilot methodology and early stage in implementation, the parts of the programme analysed have achieved on average 139% (1.04 / 0.75) of their intended milestones, meaning that the programme as a whole is on track to achieve its outcome. Note that the 0.94 citizen participation score is considered by WFD to be unrepresentative of the portfolio as a whole.

R1. If DFID’s annual outcome scoring pilot is implemented in future years, the WFD M&E team should work with programme teams to begin annual outcome scoring across the full range of WFD programmes.
R2. The citizen participation outcome should be a focus of assessment at the mid-term evaluation and next annual review. From initial figures and WFD’s self-assessment, citizen participation is currently the weakest of the four outcomes.

Overall Output score and description
Overall Output score is A. Outputs met expectation.
Key lessons
1. Take into consideration the longer lead in time needed for programme design, particularly given UK political cycle and WFD’s more robust new systems analysis and monitoring and evaluation.
2. Ensure that the corporate logframe is understood and relevant to the programme teams, and is used to channel reporting by programme teams, including the new requirement for ongoing monitoring progress on the policy, accountability and representation outcomes.
3. Communication about results requires skills and experience in story-telling so that processes of change are better understood across the organisation and can be shared with DFID and FCO.
Key actions
N/A
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Parliaments and parties where WFD works apply relevant lessons, including from British democratic experience
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of instances where MPs or staff apply relevant principles to parliamentary practice	15 instances	Moderately did not meet expectation. 13 instances including Gender Action Plan in Bosnia, research in Jordan, financial scrutiny and tax in Tunisia, Western Balkans and Indonesia, anti-corruption in Iraq an legislative reform and rules of procedure in Pakistan and DRC.
1.2 Number of instances where political parties apply skills or lessons learned from interactions with UK sister party representatives	10 instances	Moderately did not meet expectation. 6 instances. The Labour Party, Liberal Democrats and Multi-Party Offices have supported gender advocacy in Bosnia, opportunities for women farmers in Serbia, policy-making and leadership in Bosnia/Herzegovina, Serbia and leadership in Jordan.
1.3 Number of instances where parties or parliaments develop policies or processes for increasing women's participation in politics	1 instance	Substantially exceeded expectation. 4 instances, all substantive and well evidenced. Amongst other support, in Jordan, the WFD programme provided women’s caucus support via a political mentor to advise it and provide support to enhance its interventions and oversight. The decentralisation bill was amended to specify that 10% of governorate council seats should be allocated to women who obtain the highest number of votes, on the condition that no more than one seat is to be allocated for women in each electoral district.

Key Points
Output moderately did not meet expectations.
The high number of instances relating to gender equality had clear-cut examples underpinning reported performance. The Labour Party, Liberal Democrats and Multi-Party Offices have supported gender advocacy in Bosnia, opportunities for women farmers in Serbia, policy-making and leadership in Bosnia/Herzegovina, Serbia and leadership in Jordan.
However, the ‘sister party’ interventions struggled in places to demonstrate a clear causal link between the WFD-related activity and the subsequent action, behaviour or benefit attributed to it. Parliamentary support was only marginally under expectations in terms of number of instances of skills being applied.
Given the number of WFD activities with a focus on gender equality, for example in Bosnia, Jordan, Pakistan and the MENA region, a more ambitious set of milestones and trajectory may been suitable for this indicator.
Summary of responses to issues raised in previous annual reviews (where relevant) N/A
Recommendations
R3. WFD’s parliamentary and party expertise should attempt to capture how it addresses issues around decision making and political negotiation as well as technical skills around legislative drafting.
Output Title	Support to or creation of dynamic regional peer-to-peer networks that address thematic priorities
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of networks provided new or additional support to advance thematic priorities or strengthen regional cooperation.	3 networks provided with new or additional support	Substantially exceeded expectation. 5 networks (or participants therein) provided with new or additional support. For example, MENA Women, Morocco women MPs and the Liberal Democrats network in Africa.
2.2 Number of instances where issues championed by networks translate into policy proposals advocated at the national level	2	Moderately exceeded expectation. 3 instances. The MENA Women coalition has influenced national initiatives in Lebanon and Iraq to improve women’s rights in Arab legislations and called on Arab Parliaments to abolish the provisions of marital rape from their penal codes.

Key Points
Output moderately exceeded expectations, including the progress milestones for peer support and translation the support to policy advocacy.
Five networks (or participants therein) were provided with new or additional support. For example, MENA Women has supported calls for women’s leadership in Kuwait. Women MPs from Morocco joined the coalition and voiced interest in support to tackle the bill on domestic violence. The Liberal Democrats network in Africa has expanded, further establishing it as the largest liberal network outside Europe.
The case study visit the external evaluation team to the Western Balkan region allowed the review to see the type of structures and activities feeding into both indicators – for 2.1, the Network of Parliamentary Committees for Economy Finance and European integration of Western Balkans (NPC), and for 2.2 Montenegro’s development of a Parliamentary Budget Office based on the Serbian model shared with them via the NPC.
The Network of Parliamentary Committees dates from the previous grant to WFD (when it was the main implementation project of the regional programme), but has continued to operate in the 2015-18 grant period. It continues to receive a small amount of WFD funding (and hence is eligible to contribute to WFD’s performance against Indicator 2.1 above), but is increasingly reliant on the good will, facilities and resources of its members’ home parliaments across the region.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A - This is the first annual review of the current funding cycle.
Recommendation
R4. The sustainability of peer-to-peer networks should be incorporated in their design and explicitly covered in reporting. Sustainability indicators could be considered as part of this. This is happening in some places (for example, the Network of Parliamentary Committees) but not systematically. WFD might also consider producing a think piece on this issue to appraise options.

Output Title	Brokered relationships and political space for policy change amongst civil society, parties and parliament in or across countries
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Establish an active network of UK-based democracy assistance providers	Community of practice on parliamentary strengthening established and MOUs for formal network partnership agreed	Outputs met expectation. Community of Practice established, Steering Group formed, plus 3 community events held (October 2015 – Community of Practice Launch; December 2015 – Women’s Caucus and Committees; March 2016 – Corruption)
3.2 Number of instances where civil society organisations indicate that they have improved access to parliament	5 instances	Substantially did not meet expectation – 2 instances. These were engagement between civil society and local government in Serbia.
3.3 Number of instances of substantive cross-party/cross-institutional dialogue on policy issues	10	Moderately did not meet expectation – 7 instances, although all of them substantive and well evidenced

Key Points
Output moderately did not meet expectations.
In line with its theory of change, WFD must do more to bring its constituent programmes together to create coalitions between parties, parliamentary staff and civil society to broker change.
Where relationships have been brokered, this appears to have borne results. Cross-party and cross-institutional dialogues have taken place on engaging and giving exposure to women politicians in Bosnia and on LGBT rights in Serbia. Support in Tunisia has facilitated relations between the Tunisian Supreme Audit Institution and Public Accounts Committee. In Iraq WFD has facilitated collaboration between the national and regional level anti-corruption commissions. In Lebanon support has facilitated a more constructive dialogue between governmental bodies and the parliament when discussing oil and gas transparency. Research collaborations have been supported between parliamentary departments in Ghana.
Several of the external review team’s interviewees noted that much of WFD’s activity around relationship-building and ‘soft’ influencing is not captured by its existing monitoring and reporting regime
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
R5. WFD could make much more of its ability to leverage its different parliamentary and party expertise to enhance its ability to broker relationships and space for policy change, including making use of its skills supporting more cross-party dialogue
R6. WFD should review its focus on civil society organisations’ access to Parliament, which is currently underdeveloped given its importance in the theory of change. This could involve partnering with other organisations who work specifically on civic demand, or rebalancing some of its programmatic focus. The civil society output component and outcome may usefully be the subject of further discussion including WFD Board engagement given this is a strategic issue for the organisation.

Output Title	Effective use of political context analysis by WFD
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of countries with a completed context analysis	10 political context analyses that analyse the environment in order to inform strategic plan	Moderately did not meet expectation – 16 analyses produced (above expectation) but political context limited in scope. Internally: Tunisia, Jordan, Sierra Leone, Uganda, Sri Lanka. Externally conducted: Mozambique, Kyrgyzstan, Kenya, Ghana. Externally: Indonesia, Pakistan, Bahrain, Armenia, Georgia, Serbia, Azerbaijan
4.2 The extent to which parliamentary, political party and integrated project objectives align and respond to analysis, as judged by WFD internal review processes and independent external evaluation	WFD has procedures in place to assess programme design against completed context analyses	Moderately did not meet expectation - WFD has developed an inception phase. The Scoping Report from the identification phase feeds into the Context Analysis (inception phase), which is used to inform programme design and country strategies, however these focus on technical rather than political issues.

Key Points
Output moderately did not meet expectations.

WFD’s parliamentary context analysis template appraises the intuitional structure and dynamics of the parliaments. WFD produced a large volume of good quality country parliamentary technical assessments, which exceeded numeric expectation. Strengths in the context analyses include that they are: strong on covering the formal legislative processes, role of committees; good where there is coverage of engagement with civil society and media and they reflect on past reform successes and failures or informal rules/incentives.

There is a need for further discussion about the scope of future context analysis and their potential use in identifying political priorities and feasibilities of interventions. For future analyses, it would be good to consider further incorporating greater political analysis of parliaments. This might be facilitated either by making use of WFD’s long-standing knowledge from previous engagement in the country, or other implementers’ analysis. For countries where there is a WFD integrated programme in particular, but maybe more broadly, assessments could cover both the parliamentary and party system so that decisions around priorities could be based on an assessment of party and parliamentary dynamics together.

It is recommended that technical analysis and political analysis are conducted together and in an ongoing manner as the politics should be part of the decision about technical prioritisation. Some broad indicators of trajectories on accountability, representation, freedoms could be incorporated as knowing whether governance environment is getting better or worse might suggest where focus or risk management is needed.
Summary of responses to issues raised in previous annual reviews (where relevant) N/A
Recommendations
R7. WFD should take forward its primarily technical parliamentary context analyses to in future include political context assessment of parliaments, parties and the political system to support politically informed programming decisions.

Output Title	High-quality research and evidence informs support to democratic governance internationally
Output number per LF		5	Output Score	A++
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of research outputs [papers, briefs, etc.] that generate findings on agreed topics.	5	Substantially exceeded expectation. 26 outputs. 1 synthesis report, 1 policy brief, 12 background papers, 12 open democracy articles. Following discussion, blogs have been removed from the list of ‘research outputs’.
5.2 Number of instances where research is used by international and donor community	4 references	Met expectation. 4 ‘references’ (including public events, newspapers and an academic citation). / DFID has produced a draft Guide on Working with Parliaments and Parties for Sustainable Development under this output. (This is independent from DFID’s support to WFD.) This will influence internal and external partners on how to provide effective support in this area.

Key Points
Output exceeded expectations on research products and research engagement.

WFD has formed a partnership with the University of Oxford's Department of Politics and International Relations. Since January 2016, WFD has funded a post-doctoral fellow who produced 1 policy brief on 'Navigating the Trade-offs in Parliamentary Strengthening'. 2 further briefs are planned followed by longer in-depth studies.

WFD also entered into a year-long partnership with opendemocracy.net. Based around the theme "How do parliaments shape democracy? And do democracies shape parliaments?" the project has produced and commissioned 12 articles from prominent academics, practitioners and WFD staff, addressing key issues across a number of countries. WFD pursued two research themes on its own: parliaments and human rights and the cost of parliamentary politics.
The number of research outputs - 5.1 - has greatly exceeded the required number. The use of ‘references’ in 5.2 as the unit of measurement is problematic, since it implies academic (or at least published) citation of WFD research and WFD should work with DFID and FCO to consider revision.
WFD have recently upgraded its computer systems, and hence does not have historic data on downloads. However, it would be a helpful metric to pursue, since it would provide complete and comparable data over time, as well as reflecting a key means by which the ‘international and donor community’ are likely to access such research materials in practice.
WFD engaged in the PM’s Anti-Corruption Summit and DFID’s evidence programme on Anti-Corruption.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
None for WFD. DFID and FCO should continue to look for ways to incorporate WFD’s research work in their own policy making processes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
Expenditure from 1 April 2015 – 31 March 2016

	Agreed Budget for Period	Actual Expenditure by WFD for Period	Balance Held by WFD	Variance %
Year 1	£2,500,000	£2,364,218	£-135,782	-5.4%
Year 2	£3,250,000	N/A	N/A	N/A
Year 3	£3,250,000	N/A	N/A	N/A
Total	£9,000,000

April 2015 marked the start of a new three-year accountable grant period during which several new country programmes began. The first quarter was also notable for the UK General Election (7 May 2015) that affected the ability of the UK political party programmes to be sustained during that period. These factors caused initial underspend The overall spend against forecast was 94.5%. Implementation progress appears satisfactory to date, albeit with some variation between individual programmes and outputs.

Total programme expenditure for 2015/16 amounted to £5,864,614 of which DFID contribution was £2,364,218 (40.3%). The cost drivers by expenditure were as follows:
- Political Party Programmes: 35.4%
- Parliamentary Programmes: 25.5%
- Programme Staff: 11.0%
- Integrated Programmes: 6.5%
- Corporate Staff Costs: 8.8%
- Premises and Overhead Costs: 7.6%
- Research Programmes: 3.6%
- Rapid Response: 0.9%
- Security: 0.7%
Expenditure by Output was as follows;
- Output 1: £3,718,659 (63.4%)
- Output 2: £958,571 (16.3%)
- Output 3: £372,267 (6.3%)
- Output 4: £378,127 (6.5%)
- Output 5: £436,989 (7.5%)

Overall expenditure on programmes exceeds the 70% which is in line with the projection in the business case. Overheads are below the 9% which was the upper limit in the business case.
There is no evidence of drastic change to the assumptions originally set out in the business case. Reported actual financial figures meet the criteria prescribed out there, for example that over 70 per cent of the costs will go on the Political Party, Parliamentary and Integrated programmes (actual: 79 per cent), and that overheads will be no more than nine per cent of total spend (actual: 7.6 per cent).
VfM performance compared to the original VfM proposition in the business case
At present, WFD does not have a uniform framework or indicators to drive and analyse its performance against the ‘three ‘e’s’ (economy, efficiency and effectiveness). Interviews with the majority of senior management and programme staff confirmed that they still conceive VFM chiefly in terms of ‘economy’ rather than ‘efficiency’ and ‘effectiveness’. Hence they are well versed in positive behaviours relating to cost-minimisation - for example when purchasing travel tickets, procuring goods and services, or offering (and expecting) relatively modest remuneration for WFD-related work. Most seem less familiar with the concepts and definitions of effectiveness and efficiency.
WFD has indeed developed a draft VFM framework based upon DFID and NAO principles, intended for implementation in 2016/17. This represents good progress, in that it sets out how WFD-specific processes can be adapted or embedded to support each of the ‘three ‘e’s’. In this sense, it is – like WFD’s current focus on minimising costs - input-based rather than output- or outcome-based, since it assumes that optimising the timing and nature of processes relating to quality, programme design, etc., will by definition maximise both efficiency and effectiveness. This is a reasonable assumption, but as the draft framework itself acknowledges, more work is now needed to develop actual measurement approaches such as benchmarking and cost-effectiveness metrics.
This is a complex topic. There are key challenges such as the large differences between the type of activity carried out, the difficulty of making outputs (or even costs) comparable, and the importance of including metrics of quality as well as activity in order to reach defensible conclusions.
Assessment of whether the programme continues to represent value for money
Assuming that current output/outcome trajectories can be maintained, and costs controlled as they have been to date, there seems no reason why VFM (in as much as it is currently being assessed or quantified through anything other than inputs) should not be maintained as the programme continues. An important part of achieving VFM is making sure that the structures and systems already implemented remain sustainable in future, and more work is needed to support this. Quality of financial management
While there were concerns over the quality of WFD’s financial management and forecasting in the past (leading to an official warning from DFID in 2012/13), recent years have seen considerable improvement. WFD’s financial management is good: DFID is regularly kept up-to-date on issues regarding forecast and invoices are submitted on time. During the year the variance between forecast expenditure and actual expenditure was 5.4%, which is judged to be acceptable. At the end of the 2015/16 Financial Year, WFD held a balance of DFID funds amounting to approximately £135,000 which will be offset against the first payment for 2016/17.

The risk that funds are not used for intended purposes or accounted for is low. WFD sets out its intended activities at the beginning of the year, with budget allocations. DFID requires transparent access to financial information within the partner agencies in relation to funds provided by DFID as specified in the Accountable Grant.

Regular audits conducted by National Audit Office and BDO[2] have found WFD to have an effective financial management systems in place. Previous Audit Reports have been without qualification and financial management systems are considered robust.
Moreover, WFD has been taking steps to establish robust, documented procedures. In addition to a new Programme Manual, senior Finance staff have also been working on an official Finance Manual, which should improve financial management by codifying procedures and reducing reliance on ad hoc workarounds.
WFD’s efforts to improve high-level financial controls as part of its overhauled structure and governance arrangements include providing the Board with programme progress and expenditure using a graphical dashboard/traffic light approach will allow improved scrutiny of actual spend against budget.
R8. In addition to its VFM framework, WFD should further develop in consultation with DFID its concept of VFM, ensuring it is operationalised across the organisation by October 2016, with suitable indicators and means for assessing, particularly in terms of efficiency and effectiveness. Data should be provided in future DFID reporting and programme evaluations.

Date of last narrative financial report	16 May 2016
Date of last audited annual statement	June 2015 (FY 2014/15)

## E: RISK (½ page)
Overall risk rating: Moderate
This assessment reflects the average risk level attributed to the individual outputs plus additional assessment of recent adoption of new systems and software for programme and project management, and associated training of relevant staff.
Overview of programme risk
WFD’s key organisational risk management structures are as follows:
- The Board of Governors appoints the Chief Executive and Accounting Officer as Risk Director, to ensure effective risk management. The Board’s Audit and Risk Assurance Committee are responsible for oversight of WFD’s risk management.
- WFD’s Risk Policy is reviewed regularly. An internal Risk Management Group chaired by the Chief Executive is responsible for ensuring implementation of the risk policy at programme level, and for learning of lessons. All corporate risks are assigned to a risk owner. Risk management is undertaken in accordance with corporate best practices.
- WFD’s corporate Risk Register is incorporated in the annual Business Plan. The Register is organised in line with WFD’s three Strategic Objectives, and monitored through quarterly reports to the Board on the Business Plan. The Audit and Risk Assurance Committee reviews WFD’s approach to risk management at each meeting, and the Board undertakes an in-depth review of risk annually.
The key potential risks to the programme identified by WFD are shown below.
- Insecurity or political instability in countries of operation disrupts overall programme
- Security threats to programme teams disrupt overall programme
- Reduced openness to external support, including restrictions on freedom of speech and association, prevent WFD operating in significant number of locations
- Poor coordination in programme countries undermines reputation of UK activities
- Perception of political bias in programme countries prevents WFD operating
- Domestic (UK) criticism of support to parties overseas
- Poor WFD policy skills undermine programme effectiveness
This list covers the key risks to which the programme is subject, and that WFD has not overlooked any obvious threats to programme delivery. Although some of these risks, if realised, are serious, they would be unlikely to result in a complete breakdown of programme implementation. WFD’s project portfolio is sufficiently diverse and geographically spread that one set of local / regional circumstances is unlikely to affect more than a handful of projects at once.
A comprehensive traffic-lighted assessment of all key risks is contained in the WFD corporate Risk Register.
Outstanding actions from risk assessment
There are no outstanding actions at present.

## F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
Despite a slow start owing to external circumstances such as the UK elections (Party offices), terrorist attacks (e.g. Tunisia) and snap elections in beneficiary countries (e.g. Serbia), progress against planned outputs has generally been satisfactory to good. There have been a number of cases of over-performance against key targets (for example research outputs under Output 5), which in one sense is encouraging. Underperformance against individual targets will not impact significantly on ‘delivery against planned timeframe’, since there are no other inter-dependencies or final ‘deliverables’ for most of the programmes involved - ‘supporting democratic governance’ does not in itself have a finite endpoint or objective.
A further relevant factor with regards to WFD’s project and programme management is the introduction of a Programme Manual, based on an adapted version of the ‘PMD Pro’ management standard. The development of the manual, which was officially released in May 2016, has been accompanied by the provision of PMD Pro training to key personnel, and it is likely that this new documentation and skill set will contribute further to good programme management and hence reduce risks to timely delivery.
Performance of partnership
Our interviewees’ feedback on WFD from partner organisations (both formal and less formal) was generally very positive, particularly with regard to ‘softer’ issues such as working relationships and communication. Two UK government officials in separate beneficiary countries noted that their local WFD office was extremely pro-active in providing them with information and updates on relevant issues and activities - which in their experience was not always the case with other implementing partners.
Parliamentary stakeholders in the UK and beyond were also highly positive about partnership and cooperation with WFD. Senior MPs in the Western Balkans spoke of their close joint working with WFD in embedding financial governance and oversight in the region’s parliaments. Feedback from Ghanaian and Tunisian partners was similarly positive, suggesting overall that WFD has been fulfilling the recommendation from a previous review that it ‘should focus on building long-term and trusted relationships with its national partners as a means of enhancing its results’.[3]
[3] See Programme Completion Report - Westminster Foundation for Democracy: Transforming Political Parties and Democratic Institutions: An integrated approach to party-to-party, cross-party and parliamentary assistance.
UK Parliament personnel also see WFD as an effective partner, and indeed some commented that relations had become more pro-active, co-operative and ‘outward-looking’ since recent changes to WFD’s management structure and modus operandi. One suggestion as to how this type of partnership working might be made even more effective was for WFD to employ more staff with direct Westminster Parliamentary experience alongside their international development credentials.
Meanwhile, the newly developed partnership between WFD and academia, aimed at enhancing WFD’s research output (see Output 5) has also proven fruitful, both in terms of the volume of material produced and the feedback on working relationships provided by our interviewees. Both sides acknowledge that the work is challenging, but acknowledge the mutual ‘spirit of enquiry’ and culture of openness and engagement in which it is carried out.
Asset monitoring and control
WFD is responsible for the ownership, custody, maintenance and control of any assets to be purchased with DFID funds. WFD maintains an asset register centrally and in country, consisting mainly of office furniture and IT equipment. As the majority of WFD’s field offices are rented on short leases or received as a ‘benefit in kind’ from host parliaments and WFD’s principal work relates to procurement and delivery of services rather than assets, risks around asset management are low. There appear to be appropriate controls and procedures in place for managing WFD assets..

## G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant)
N/A - There is no conditionality in this programme, as WFD implements its work directly and there are no partnership principles attached to this programme.
## H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The intervention requires a strong monitoring and evaluation framework to provide clear evidence of results and value for money of the intervention, for accountability purposes, and to contribute to learning in the field of international democratic governance assistance.

In addition to external reviews such as the current assignment, WFD uses the following mechanisms for monitoring programme progress and associated issues over the year:
- The WFD Board Sub-Committee on Programme Quality meets quarterly to review lessons from implementation of past WFD programmes and to consider important issues to inform future programmes.
- There is an Annual Meeting to review WFD strategy and HMG strategic priorities and review of risks/discussions around new risks.
- There are quarterly WFD reports (including from individual projects and programmes at country/regional level), senior level meetings and programme delivery boards
Management arrangements and oversight mechanisms within WFD have been significantly strengthened. Although these are not the main subject of the Annual Review and are assessed more generally in the Evaluation, they have contributed significantly to stronger strategic direction, improved relationships with FCO and DFID and better partnerships with other Westminster institutions.
Monitoring progress throughout the review period
Improved support. WFD staff and other stakeholders commented to us that central monitoring and evaluation (M&E) support has continued to improve over the last year, building on the positive improvements identified in 2015 evaluations.
Revision of some indicators is needed. Some qualitative / outcome targets were formulated in such a way that it was not fully clear what outcome they were seeking to capture. The drafting of examples (‘instances’) feeding into reported performance against them also seemed to leave room for ambiguity and misinterpretation. Indicators 1.1 and 1.2, for example, are problematic - in terms of both definitions and reported performance. Some of the output targets may not be sufficiently challenging. For example in the area of gender equality (part of Output 1), the target was exceeded by 400 per cent, and in the area of research publications (Output 5) by 460 per cent.
Influencing and incentives. Several of our interviewees noted that much of WFD’s activity around relationship-building and influencing is not captured by its existing reporting.
Lesson learning. Interviewees were positive about programme planning, design, policies, implementation and M&E, but several queried the extent to which the resultant learning was feeding into the next round of activity. WFD has been using a number of approaches which should help to address this point - in particular, a ‘lessons learned’ section in programme level Annual Reports, annual retreats and dissemination of ‘stories of success’ by the central M&E and Communications teams.

R9. WFD should encourage its country staff to consider how their daily relationships and interactions contribute to programme logframe outputs and to record this influencing work.. Indicator 1.3 should be revised to reflect the greater number of activities following annual review. Indicator 5.2 should be revised to reflect the extent to which WFD is promoting its research and coverage within the democracy assistance community.

R10. Good progress should continue, and internal dissemination of lessons should be further enhanced across WFD.