Annual Review - Summary Sheet

Title: Norwegian Refugee Council (NRC): Legal assistance to prevent demolitions and displacement in the OPTs.
Programme Value: £6.5m		Review Date: 20th April 2015
Programme Code: 202443	Start Date: 1st April 2013	End Date: 30th September 2016

Summary of Programme Performance

Year	2013/14	2014/15	2015/16
Programme Score	A	A+	A+
Risk Rating	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

DFID’s support to the Norwegian Refugee Council’s (NRC’s) Information, Counselling and Legal Assistance (ICLA) programme has continued to help prevent demolitions and displacement in the Occupied Palestinian Territories (OPTs) between April 2015 and April 2016.

There has been a spike in the number of demolitions being carried out by the Israeli Government since January 2016, particularly in Area C of the West Bank. Demolitions are now being carried out at their fastest rate since the United Nations (UN) started collecting data in 2009. The programme has responded well to this deterioration but the large spike in demolitions demonstrates a shift in the operating environment.
NRC has been able to respond to increased demand for the ICLA programme while still maintaining a high quality of delivery. NRC has made good progress in increasing their gender focus, with high numbers of female beneficiaries reporting that they had gained a better understanding of and involvement in their cases. In response to previous Annual Review recommendations, NRC has also made progress in developing the accessibility of their advocacy materials through their website. NRC has strengthened co-ordination with the Palestinian Authority (PA).

Two higher level risks have developed within the review period: the shrinking of ‘humanitarian space’ in Gaza, which is affecting NRC’s operations, and a need for greater outreach with vulnerable Bedouin communities in Area C to ensure understanding of NRC’s IHL-based approach to legal aid. DFID will remain closely engaged with NRC to help mitigate these risks.

Summary of recommendations for the next year

DFID and NRC should review the ongoing need for support to Palestinian women who were displaced through the 2014 Gaza conflict and agree appropriate targets for the next six months. Combined with the programme’s increased focus on gender, this could be expanded into a broader assessment of women’s needs in relation to Housing, Land and Property (HLP) rights / Legal Aid to inform future programming.

In the remaining six months of the DFID programme, NRC should look to engage further with missions based in Jerusalem, Ramallah and Tel Aviv to assess how their advocacy materials are being used by the international community and shape their future advocacy strategy given the increase in demolitions.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202443/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202443/documents/

Outline of the programme

DFID’s funding to NRC supports the delivery of legal aid to defend the HLP rights of Palestinians in the OPTs, specifically through the provision of legal counselling, information and assistance for the protection of Palestinians affected by or at risk of displacement. The ICLA programme has been operating since 2010 and DFID is its second largest donor, after the Swedish International Development Agency (SIDA).

In 2014, DFID extended the business case by one year to continue our support up until March 2016. In 2016, DFID extended the business case by a further six months to the end of September 2016, in order to ensure there is no gap in the provision of legal aid during a spike in demolitions, while the UK’s future legal aid programme is agreed.

Expected results

The last annual review conducted in April 2015 assessed NRC’s progress against targets for financial years (FY) 2013/14 and FY14/15, concluding that NRC had exceeded expectations in their performance against expected results. The 12 month extension therefore set an even higher level of targets for NRC to achieve in FY15/16 and this annual review will assess NRC’s progress against the following results:

- 450 Palestinian households will have received legal counselling and/or representation following potential HLP violations in the Gaza Access Restricted Area;
- 5 discriminatory and/or unfair laws, policies or practices will have been exposed through public interest cases;
- 600 people will have received HLP rights training or technical assistance from NRC;
- 40 advocacy briefings will have been delivered on specific HLP issues (verbal or written);
- 4 incidents where power holders act positively on information received from NRC in an effort to reduce forced displacement;
- 10 technical services, including advice and/or training, will have been delivered to the PA to strengthen their capacity;
- NRC will be working with the UN Development Programme (UNDP), the Palestinian Authority (PA) and legal aid providers on 5 cooperation areas for the development of a sustainable legal aid system for HLP law; and
- 50% of beneficiaries experiencing residency or access restrictions will have received a remedy (grant of permit, registration or civil documentation provided) due to legal assistance provided by NRC.

This programme contributes to DFID’s international development objectives and feeds into the DFID Departmental Results Framework (DRF).

Context

The operating context has deteriorated in the reporting period, with an increase in the number of Palestinians displaced due to demolitions and evictions in the West Bank.

The Israeli authorities demolished 502 Palestinian structures between January and March 2016, already 86% of the number of demolitions in 2015 (585).  Demolitions are now proceeding at their fastest rate since the UN started collecting data in 2009. The demolitions (Jan-Mar 16) displaced 672 Palestinians, half of whom (331) are children, and affected more than 1,896 people in total. The majority affected are Bedouins in Area C, already some of the most vulnerable communities in the OPTs.

2016 has also seen an increase in demolitions in the E1 area on Jerusalem’s periphery. Bedouin in the Jerusalem periphery are already under pressure to accept relocation packages, while their land is ‘zoned’ for settlement expansion by the Israelis. Most do not want to move, but demolitions ratchet up the pressure on them to do so, creating a coercive environment.

There was continued need for HLP support in Gaza to facilitate reconstruction after the 2014 conflict. A large number of Gazans were displaced by the conflict, and still more required assistance to rebuild and repair damaged homes. Legal support is required to obtain property documentation, building permits and reconstruction grants.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The outcome of this project is that Palestinians at risk of displacement within the OPTs are better able to uphold their housing, land and property rights through provision of legal aid services and increased access to justice.

NRC has performed very highly against outcome-level targets during the reporting period, substantially exceeding four targets and slightly under-achieving on one. The only area of under-achievement, the incidents of power holders acting positively in response to NRC’s information, is beyond the direct control of the programme. However, NRC have documented 4 instances where states or multilateral and international organisations have taken action directly linked to timely information provided by NRC. In the future, it will be important to assess NRC’s plan for providing advocacy materials to ensure that they are responding to the different needs of key stakeholders (for example in Tel Aviv, Brussels, Jerusalem, etc.).

Indicators measuring outcome.	Milestone 2015/16	Progress 2015/16
Percentage of households who receive a temporary suspension of demolition order due to legal representation provided through NRC	95% / (12 month target: max 5 of 100 cases)	99% / (3 demolitions out of 516 cases)
Percentage of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex disaggregated)	80% / (Average for m/f)	95% [1] / (Average for m/f)
Number of incidences where power holders act positively on information received from NRC in an effort to reduce forced displacement.	5	4
Percentage of beneficiaries who obtain residency permit or other registration as a result of NRC services	50%	60%[2]
Percentage of women surveyed in households receiving legal representation and counselling who report sufficient knowledge of their case.	60% / (WB 50%, Gaza 80%)	68% / (WB 50%, Gaza 85%)
[1] West Bank Average: 99% (100% females and 99% males). Gaza Average: 90% (95% males and 85% females).
[2] Average 60% sex disaggregated data: 63% males and 57% females.

Output score and description

The overall output score is A+, indicating that the programme is over-achieving against expected results.

Output number	Output Description	Impact Weight (%)	Output Performance	Risk
1	Emergency Legal Response: Provision of emergency legal counselling and representation to Palestinians at risk of displacement in Area C and Gaza.	30%	A+	Minor
2	Preventative Legal Response: A longer term legal strategy that helps to prevent demolitions and displacement	30%	A+	Minor
3	Policy Change Response: Influencing policy change on HLP and residency rights violations through advocacy.	30%	A+	Minor
4	PA Capacity Building Response: Strengthen the capacity of the PA to provide legal aid in HLP cases.	10%	A++	Minor

Key lessons

Despite the deterioration in the political situation since October 2015 and an increase in the number of demolitions since January 2016, NRC has been able to adapt and in many cases scale up their legal aid provision. The exceptionally high levels of success rates for beneficiaries targeted by demolition or eviction orders (99% of 516 cases managed) demonstrates the continued value and relevance of the ICLA programme, and the high output-level indicator results show the increase in demand for support in response to the increase in demolitions.

However, while the programme is performing strongly, a higher level of co-ordination in the international policy response is required. NRC will not alone be able to deliver this, but they can support its development through strong and timely advocacy materials.

Gender

NRC has continued to develop its focus on gender. NRC overachieved in targeting women and responding to the different needs of males and females as recommended by last year’s Annual Review. For example:

- Following NRC training, 85% of women beneficiaries in Gaza reported a sufficient level of knowledge on their HLP legal cases (compared to 73% last year).
- In October 2015, NRC carried out a legal empowerment activity for Bedouin women in all 23 communities in the Jerusalem periphery to raise women’s involvement in their cases.

There remain some areas where the programme supports a higher number of male than female direct beneficiaries; this is reflective of the higher numbers of male-headed households, and NRC’s strengthened approach on gender is ensuring that there is greater awareness among indirect female beneficiaries in these areas.

Recommendations from previous Annual Review

The recommendations from the 2015 Annual Review were as follows. Progress on implementing recommendations is considered below.
- DFID to discuss the plans for evaluation of the project and carry out an evaluation before the end of the funding period. This should be timed to feed into the decision about continued funding after 2015/16.
- NRC to continue to work on improving the accessibility of briefing and advocacy materials. DFID to monitor and review at next Annual Review/Project Completion Review.
- NRC to continue to strengthen its gender focus. DFID to monitor and review at next Annual Review/Project Completion Review.

Key actions

DFID and NRC should review the ongoing need for support to Palestinian women who were displaced through the 2014 Gaza conflict and agree appropriate targets for the next six months. Combined with the programme’s increased focus on gender, this could be expanded into a broader assessment of women’s needs in relation to Housing, Land and Property (HLP) rights / Legal Aid to inform future programming.

In the remaining six months of the DFID programme, NRC should look to engage further with missions based in Jerusalem, Ramallah and Tel Aviv to assess how their advocacy materials are being used by the international community and shape their future advocacy strategy given the increase in demolitions. This should include making advocacy materials more widely available in Arabic for beneficiary communities.

Has the log frame been updated since the last review?

Yes: the log frame was updated to include targets for the programme’s extension into financial year 2015/16. A further update will be required for the final 6 months of the programme (to September 2016).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Emergency Legal Response- Provision of emergency legal counselling and representation to Palestinians at risk of displacement in Area C and Gaza.
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones 2015/16	Progress by March 2016
1.1	# Of male and female beneficiaries receiving legal counselling on HLP and residency issues.	Total 950 comprising: / West Bank: 500 (HLP) / Gaza: 450 (HLP)	Total 1,078 comprising: / West Bank: 507 (387m/120f) (HLP) / Gaza: 571 (571m) (HLP)
	# Of opened and ongoing cases of legal assistance.	Total 500: 100 new 400 ongoing in the West Bank: / 400 ongoing cases (HLP) / 100 new cases (HLP	Total 982: 739 new and 243 ongoing in West Bank and Gaza: / 243 ongoing cases (HLP) / 283 new cases (HLP) / 456 new cases in Gaza
1.3	# of Palestinian women displaced during operation Protective Edge in Gaza who receive legal counselling and/or representation from NRC or NRC partners	100 women	100 women

*In Gaza, an further 456 cases were opened this year, focusing on HLP documentation to enable reconstruction.

Key Points

Output Indicator 1.1 Counselling: NRC has responded to a high level of need for legal counselling, exceeding the overall target. Counselling sessions in the West Bank are more likely to result in the need for legal representation in court, but to avoid double counting, counselling services which result in a court case are included in the cases figures rather than the counselling. This is reflected in the increased number of new court cases in the West Bank (Output 1.2).

In Gaza, the ICLA programme exceeded the counselling target and was able to provide services to 571 IDPs, to assist them in obtaining HLP documentation and thus enabling them access to reconstruction grants. The 2014 conflict has had a devastating impact on the Palestinian population in Gaza and has resulted in the displacement of thousands of men, women, boys and girls. The ICLA programme continues to provide technical assistance to the Shelter Cluster members in Gaza and, through the referral system between NRC and the UN Relief and Works Agency (UNRWA), so far has received more than 7,000 cases of IDPs whose houses were completely destroyed as a result of the conflict.

Output Indicator 1.2 Legal Assistance: The overall case target was exceeded. As mentioned above, there was a higher level of legal representation for HLP than on counselling. In Gaza, 456 HLP cases were opened during the reporting period focusing on ownership documentation of the houses destroyed by the 2014 conflict. The NRC legal team provided several follow-up sessions with affected IDPs to support them legally to obtain the required HLP documentation to prove ownership including, but not limited to, building permits, sale contracts, land deeds and inheritance deeds.

Output Indicator 1.3 Legal support for Women: In 2015, the ICLA programme continued to prioritise support to displaced women to improve their access to HLP rights. During the reporting period, NRC was able to provide legal support services to 100 women who have become IDPs since the 2014 conflict, to increase their security of tenure and assist them obtaining required HLP documentation for the reconstruction of their houses.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Annual Review from 2015 recommended shifting the focus of NRC’s work in Gaza following the July/August 2014 conflict. It recommended the indicator regarding Access Restricted Areas (ARA) work in Gaza be changed to read Number of beneficiaries assisted by NRC following Operation Protective Edge who obtain ownership documents, a rental contract or a resolution of an HLP issue as a direct result of NRC assistance.

In response to this recommendation, the indicator was changed and now reads the following: ‘#of Palestinian women displaced during ‘Operation Protective Edge’ in Gaza who receive legal counselling and/or representation from NRC or NRC partners’. This new indicator serves a two-fold purpose: to focus on NRC’s work in Gaza following the last 2014 conflict; while focusing on their gender strategy.

Recommendations

DFID and NRC should review the ongoing need for support to Palestinian women who were displaced through the 2014 Gaza conflict and agree appropriate targets for the next six months. Combined with the programme’s increased focus on gender, this could be expanded into a broader assessment of women’s needs in relation to HLP rights / Legal Aid to inform future programming.

Output Title	Preventative Legal Response - A longer term legal strategy that helps to prevent demolitions and displacement
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones 2015/16	Progress by March 2016
2.1	Number of people receiving HLP and residency training or technical assistance from NRC (sex disaggregated)	600 total comprising: / West Bank: 350 (250m/100f) / Gaza: 250 (175m/75f)	692 total comprising: / West Bank: 436 (210m/226f) / Gaza: 256 (149m/107f)
2.2	Number of instances where beneficiaries of training or technical assistance have used information received from NRC training and technical assistance in their work.	This indicator is no longer tracked as an output; instead we monitor the feedback as an outcome indicator.	N/A - Outcome Indicator
2.3	Number of people receiving information services (sex disaggregated)	Total 1,750 comprising: / West Bank: 550 (400m/150f) / Gaza: 1,200 (600m/600f)	Total 1,851 comprising: / West Bank: 647 (334m/313f) / Gaza: 1,204 (564m/640f)

Key Points

Output Indicator 2.1 Technical support and training: In the West Bank there has been a high demand for NRC’s HLP and residency technical training, helping lawyers and humanitarian actors build their understanding of the complex legal environment they have to operate in. 436 beneficiaries benefited from 24 training sessions conducted by NRC on the legal aspects of house demolitions and restrictions on movement.

The ICLA team in Gaza conducted 12 training sessions on HLP rights and laws for legal practitioners, law school students, UN, and INGO staff and community leaders (‘mukhtars’). As a ‘go-to’ agency in the area of HLP issues, NRC was able to provide UNRWA site engineers involved in the post-war damage assessment of the Gaza Strip, with technical legal trainings on HLP issues.

89% of trainees have reported using the knowledge gained from the training sessions during preparation of written documents or briefs, legal reports, provision of legal advice or casework, conduction of legal research, provision of advice on field work and in project planning/implementation.

Output Indicator 2.3 Information sessions: In the West Bank there was a higher than anticipated need for information on issues related to house demolitions and restrictions on movement, – which is reflected in the increased number of beneficiaries (647) attending information sessions.

The ICLA Programme in Gaza was able to reach the information session target and provided legal awareness raising sessions to 1,204 persons through either group or individual sessions. Feedback from beneficiaries has identified how essential knowledge in HLP has become in Gaza, particularly following the 2014 conflict, and there have been requests for more sessions on HLP.

Summary of responses to issues raised in previous annual reviews (where relevant)

It was recommended in the 2015 annual review to increase the target for indicator 2.2 in order to reflect overachievement. In updating the log-frame following the annual review it was agreed that feedback from beneficiaries on the use of training sessions was better monitored as an outcome indicator.

Recommendations: No recommendations specific to output 2.

Output Title	Policy Change Response: Influencing policy change on HLP and residency rights violations through advocacy.
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones 2015/16	Progress by March 2016
3.1	Number of advocacy briefings given on specific housing, land, property and residency issues (verbal or written).	40	140 / (67 on West Bank issues and 73 on Gaza Strip issues)
3.2	Number of research documents prepared on identified HLP and residency issues.	10 / (5 West Bank, 5 Gaza)	10 / (6 West Bank and 4 Gaza).
3.3	Number of discriminatory and/or unfair laws, policies or practices exposed through public interest cases.	5 cases	29 cases / (13 new and 16 ongoing)

Key Points

Indicator 3.1 Advocacy briefings: 140 verbal and written advocacy briefings were given on specific HLP issues related to the West Bank and Gaza. In the West Bank, NRC has been particularly active in attempting to counter the ongoing demolitions of Palestinian homes and infrastructure, through advocating for respect for HLP rights, through numerous meetings and briefings, in Jerusalem, Tel Aviv and Brussels. NRC has also conducted a number of field visits for DFID and visiting diplomats and politicians, as well as briefing visiting British parliamentarians.

NRC have documented 4 instances where states or multilateral and international organisations have taken action directly linked to timely information provided by NRC. NRC’s follow-up has shown the positive outcomes which can be achieved by public and private lobbying on areas such as demolitions and confiscations.

Indicator 3.2 Research: NRC produced 10 publications focused on HLP and residency. Six of these focused on the West Bank and a further four reports were published on Gaza (full list at annex 1).

Indicator 3.3 Public interest cases: NRC and partners worked on 13 new and 16 ongoing public interest cases challenging unjust HLP issues.

Recommendations from previous Annual Review:

“DFID to discuss with NRC how they can continue to improve the accessibility of their briefing and advocacy materials including possibly adding an additional indicator to help monitor this. DFID to monitor progress and steps outlined by NRC above and assess at the next Annual Review/Project Completion Review.”

NRC has delivered several improvements to their advocacy since 2014, including strengthening their engagement with the EU and reaching out further to the PA.

Recommendations

In the remaining six months of the DFID programme, NRC should look to engage further with missions based in Jerusalem, Ramallah and Tel Aviv to assess how their advocacy materials are being used by the international community and shape their future advocacy strategy given the increase in demolitions. This should include making advocacy materials more widely available in Arabic for beneficiary communities.
Output Title	PA Capacity Building Response: Strengthen the capacity of the PA to provide legal aid in HLP cases.
Output number per LF		4	Output Score	A++
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones 2015/16	Progress by March 2016
4.1	Number of technical services provided to the PA to strengthen their capacity.	10 technical services	45 technical services
4.2	Number of direct issues of cooperation where NRC is actively working with UNDP and PA and legal aid partners on development of a sustainable legal aid system for housing, land and property law	10 direct issues	45 direct issues

Key Points

Indicator 4.1 Technical services: There were 45 technical services provided to PA including;
- The NRC funded land expert provided technical support for PA cases to PA lawyers and the Wall and Settlements Unit in relation to the mapping of demolitions, land seizure orders or declarations of ‘state land,’ settlement and outpost expansion.
- NRC supported information sessions in areas where the Ministry of Agriculture conducts activities in the West Bank, as well joint information sessions with the Ministry of Local Government.
- NRC also provided technical support, working closely with the Hebron Rehabilitation Committee (HRC) in Hebron and the contracting surveyor, to the HRC/PA challenge of settler takeover in Hebron.
In order to build the capacity of PA ministries' staff members, training to staff of the Ministry of Agriculture was carried out on HLP issues in Area C in February 2016. Another training session was carried out with Ministry of Education staff on HLP and settler violence affecting schools. The PA Wall and Settlement Unit was supported with a consultant to assist with co-ordinating the work of the Unit’s lawyers.

Indicator 4.2 Issues of cooperation: There have been forty-five direct issues of co-operation which represent substantive legal cases – not minor co-ordination events or meetings – for example;
- At the request of the Wall and Settlement Unit, NRC has contracted a consultant who works on co-ordinating the work of five lawyers. The aim of this co-operation is to provide the PA with the resources for more systematic and institutionalised knowledge of cases, and with the ability to analyse trends to facilitate strategic policy decisions related to legal aid delivery.
- NRC continued to work closely with the Protection Cluster and as co-chairs of the Legal Taskforce in the establishment of a network of legal aid providers.
- NRC has renewed four MoUs with PA agencies,
- NRC also assisted the PA on advocacy on cases adopted by the Wall and Settlement Unit cases and assisted the PA in developing oversight and accountability systems for their provision of legal aid.

Recommendations None
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers of this project are grants to partners, lawyers’ fees and staff salaries. The value for money of the grants to partners and lawyers’ fees is measured principally by the number of cases dealt with, but also by the positive impact of this legal work on the lives of Palestinians. Fees are paid to private lawyers, partner Civil Society Organisations (CSOs) employing in-house lawyers and other legal consultants.

There is a tension in the legal aid system is to strike a balance between low legal fees and the provision of high quality legal services. Payment of low fees may result in poor quality legal work, thus compromising the goal of ensuring access to justice and fair trial standards. The situation is particularly challenging in the OPTs on account of the complexity of cases, the need for specialists in certain areas of the law (including housing, land and property law), the need for Hebrew speaking qualified lawyers and the limited pool of available lawyers. Some beneficiary communities also show a strong preference for private lawyers. Many of the public interest cases funded by the NRC require a high level of legal expertise and a remuneration rate sufficient to attract quality lawyers.

VfM performance compared to the original VfM proposition in the business case

Economy: NRC has developed and implemented a legal aid fee structure for private lawyers. It considers the advantages and disadvantages of working with private lawyers, using a mixed approach to ensure high quality legal representation and additional capacity to take on cases to supplement the role of CSOs. NRC maintains a Table of Fees for legal procedures used to evaluate the cost for each legal case.  The Table of Fees was developed by the ICLA programme in 2013 following market research into fees charged by legal practitioners in the West Bank and factoring in a ‘legal aid’ discounted rate.  The Table is designed to balance consistency and cost-effectiveness in legal fees and services and is reviewed periodically. The Table is consistent with the NRC approach internationally and EU rules.

Efficiency: The efficiency of the programme has improved significantly over the last year as NRC have greatly reduced consultancy fees for research reports though doing more of this work in-house, except where specific expertise was needed.

Cost effectiveness: NRC nationalised one international position during the review period and used the funding gain for additional programme activities. In 2014, NRC finalised a research study into the cost of displacement which found that the total cost incurred per household displaced is over £100,000. Our original business case estimates that it costs some £4,700 per case to provide legal advice to prevent demolitions and evictions. This figure has not significantly changed over time. It is therefore still far more cost effective to prevent displacement through providing legal assistance than to provide compensation or humanitarian aid after displacement has occurred.

Over the period 2013-2016 an estimated £1,445,142  has been spent directly on legal cases which challenge demolitions or evictions. 2,541 eviction or demolition orders have been suspended as a result. The average household impacted by displacement has been analysed to suffer economic damage worth NIS680,648 ($185,362).[3] Averting 2,541 evictions/demolition orders can therefore be estimated to be worth 2,541 x $185,362 = $471,004,842 (£330,427,686). The benefit/cost ratio is £330,427,686/£1,445,142. In other words, every £1 spent returns £228.60 in benefits. This is a good rate of return.
[3] This is comprised of a number of factors, including loss of property (house and/or land owned by the household), loss of productivity due to worsened living conditions and legal fees and fines levied by the Israeli courts. Shir Hever (2015) The Economic Impact of Displacement

Assessment of whether the programme continues to represent value for money

According to the measures outlined above, the programme continues to represent good value for money. The residency work has continued to provide good value for money as a large number of legal issues for beneficiaries can be resolved through a one-off counselling session. Such counselling is relatively inexpensive, compared to full case representation.

Quality of financial management

NRC’s financial forecasting has been strong over the reporting period, with less than 10% variance between forecast and expenditure for three out of the four quarters.

Date of last narrative financial report	01/10/2015
Date of last audited annual statement	31/12/2015

E: RISK

Overall risk rating: Minor/Moderate/Major/Severe

The overall risk rating is moderate.

Overview of programme risk

We have seen an increase in the risks to this programme over the reporting period.

We do not assess a high level of financial risk in the programme due to the strong due diligence procedures which NRC has in place with down-stream partners, and the direct delivery model in Gaza means that we can rely on our strong oversight of NRC as the direct implementer.

Programme outputs	Risk	Risk Level	Mitigation	Update April 2016
Output 1: Provision of emergency legal aid to Palestinians at risk of displacement in Area C and Gaza (Emergency legal response)	Changes in the legal system and practice make it increasingly difficult to successfully challenge demolitions and displacement.	Moderate	The private lawyers and NGOs that provide legal aid on behalf of NRC are very experienced and have access to much expertise regarding the complex legal system. Trends and changes are tracked and analysed and used in advocacy to bring international awareness and pressure in support of the right of Palestinians to defend their HLP rights.	. There have been some shifts in legal service provision, with a pool of new legal representation beingsecured and NRC are conducting out-reach to the affected communities to explain the changes
	Renewed airstrikes on Gaza destroy homes and livelihoods increasing the need for emergency legal aid.		Current NRC strategy for Gaza is to promote registration of property and security of tenure so that with renewed demolitions/damage the process of rebuilding is easier and quicker thus ultimately requiring fewer legal aid services.	The closing space for operations in Gaza is challenging the ability of NRC to operate in the context. NRC are not able to comply with demands from the de facto authorities to share information and this has led to the repeated closure of the Gaza office (April 2016).
Output 2: Delivery of a longer term legal strategy that helps to prevent demolitions and displacement (Preventative legal response)	Changes in the legal system, increasing lobby from settler groups and political priorities mean that it is increasingly difficult to prevent demolitions and displacement.	Moderate	NRC is very experienced and has access to much legal and local expertise (advisory board etc.) regarding the legal context of the OPTs.	N/A
Output 3: Influencing policy change on housing, land and property (HLP) violations through advocacy (Policy change response).	Shifting policies increase the pressure on Palestinian communities in Area C making it more difficult to positively influence policy change.	Moderate	Increasing international interest in the Middle East Peace Process counterbalances Israeli practices of settlement expansion. Advocacy is built into the programme to leverage international pressure on the HLP rights of vulnerable Palestinians.	N/A
Output 4: Capacity of PA institutions built to prevent displacements in Area C, East Jerusalem (capacity building response)	PA policy priorities do not include building legal aid capacity.	Moderate	NRC works closely with the PA to identify priorities and feasible options for strengthening capacity.	N/A

Outstanding actions from risk assessment

DFID is closely monitoring the impact of the current closure of NRC offices in Gaza and we will follow-up on the new structure of legal provision to Bedouin communities in Area C to ensure that there is a suitable level of up-take.
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

As outlined above, NRC continues to deliver according to the agreed targets, overachieving in some target indicators.

Performance of partnership

We maintain regular contact with NRC both in one to one meetings, co-ordination forums and during field visits and briefings which they regularly organise for DFID and FCO high level visitors or new staff. NRC provides us with narrative and financial reports on time and in line with the agreed schedule.

The Donor Coordination Meetings that were initiated in 2012 have been continued through the reporting period (during the past six months, two donor co-ordination meetings took place). These meetings bring NRC’s donors together to discuss current challenges, contextual changes, and future direction and to coordinate on advocacy initiatives. The meetings are useful to increase donor co-ordination and communication, but they do not significantly reduce NRC’s administrative burden.

In the remaining 6 months of our existing programme we will co-ordinate closely with NRC to find a suitable level of co-ordination and ensure that evaluation and reporting requirements are streamlined.

Asset monitoring and control

This programme does not fund major assets, but rather NRC’s ongoing activities principally through paying lawyers’ fees, providing grants to partner NGOs and staff salaries. However, DFID pays for office stationery and equipment. To monitor assets, DFID requests an updated asset list every 3 months.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The partnership principles are not relevant in managing and monitoring the programme, although NRC’s work does help to reduce poverty, achieve land and livelihoods-related MDGs, and promote respect for human rights and international law. As outlined in Output 4 above, NRC does support the technical capacity of the Palestinian Authority (PA) for which DFID has a Partnership Principle Assessment. DFID OPTs carry out quarterly assessments against the partnership principles as part of our disbursements to the State Building and Service Delivery Grant.

H: MONITORING & EVALUATION

Evidence and evaluation

We are able to monitor the impact of NRC’s work through regular field visits, which NRC organise in order to brief the international community about the challenges facing Palestinian communities (particularly Bedouin and herding communities) that are vulnerable to demolitions and displacement
Many of the activities funded – the provision of legal aid, training etc. - are carried out by downstream partners who have direct agreements with NRC. It is therefore not possible for DFID to directly monitor all aspects of NRC’s work, although NRC works very closely with partners to ensure effective delivery of results.

Several internal evaluations were carried out of different aspects of this NRC programme during 2013 and 2014. In 2012, programme wide assessments were carried out.

In the remaining 6 months of our existing programme DFID will agree a plan for assessing the impact of the programme with NRC that can inform both our project completion report and feed in-to the design of any further support.

Monitoring progress throughout the review period

In addition to this annual review process which was carried out in close communication with the manager of NRC’s ICLA project, NRC provide narrative updates against indicators every six months which allow us to monitor whether they are on track to meet results targets. They also contribute updated data twice a year to the DFID Results Framework and Operational Plan results that are collected and analysed centrally.

As mentioned above, NRC regularly organise field trips for diplomatic missions and high level visitors, including from the British Government, to vulnerable communities, providing us with many opportunities to meet with the beneficiaries of NRC’s work and monitor progress.