Programme Completion Report - Top Sheet

Review Date:	June 2016

Title: / State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria
Programme Code: PO 4052/CNTR 200708082			Start Date: August 2008	End Date: April 2016

Summary of Programme Performance
Year	2009	2010	2011	2012	2013	2014	2016
Programme Score	A	A+	A+	A+	A+	A+	A+
Risk Rating	High	High	High	High	High	High	High

Financial Position
Original Programme Value	The original contract dated 16th July 2008 was for a programme value of £41,141,961.
Extensions/ amendments	There have been 14 Contract Amendments, the largest being CA8, CA9, and CA10, covering the expansion of the programme to five additional states, extension by an additional year and scaling up of activities in Jigawa, Lagos and on Federal work. These took the programme value from £42,482,649 to £59,199,835. CA12 provided an additional nine months’ extension to take the programme through Nigerian elections. CA12 took the programme value to £65,127,109
Log-frame revisions (with dates)	Revisions followed contract amendments as well as recommendations arising from the Annual Reviews. Revisions are dated: May 2009, September 2010, February 2011, July 2012, June 2013, June 2014 and February 2015.
Total programme spend	The programme is projected to spend £62,394,858 by close.

Follow up actions required following closure

Immediate,
It will be essential for the new programme to maintain momentum in selected key areas. During the inception period, through the remainder of 2016, there are several interventions that should proceed without delay and/or lengthy review and these include: public financial management – 2017 budget process, Zero Based Budgeting and internally generated revenue and on public service management – broadening and deepening the implementation of service charters and providing quality assurance to those states implementing their human resource management information system (HRMIS).

 During the inception period,
Decide on the modalities and ‘packages’ of support that will be provided to each level in the proposed typology of future state engagement, namely: Level 1 – Kano, Kaduna and Jigawa, Level 2 - Lagos and Enugu ‘hubs’ plus surrounding states, and Level 3 ‘transitional states’ - Anambra, Niger, Zamfara and Katsina. Even within these 3 Levels, there may be a need to differentiate the packages to reflect previous track records of reform, current reform commitments and then the actual progress in delivering on commitments. Furthermore, Yobe should be treated as a special case and given Level 1 type support, in part to reflect its reform progress in a difficult conflict environment as well as providing a ‘bridge’ to the new reconstruction programme for the north east.

- The Problem Driven Iterative Adaptive (PDIA) approach needs further development in relation to (a) integrating it into a revised Theory of Change and (b) identifying stimulus measures that will ‘incentivise’ the take up and roll out of workable solutions and reforms across the public service.
- The continued use of the Public Expenditure and Financial Accountability Assessment and the State Evaluation and Accountability Tool, in their present or modified form, needs to be considered.

The results framework for the new programme should ensure that (a) the achievement Outputs, Outcome and Impact are all to be measured by indicators which are readily available and (b) the logic between the Outputs, Outcome and Impact clearly differentiates between these different levels and that is possible to generate the evidence to validate the intervention logic captured in the Theory of Change. In particular, the Impact objective needs to be framed in terms that ensure the achievement of the Outcome objective is linked clearly to the intended Impact.

Post inception period,
Routine reporting needs to be simplified and refocused; progress reports should be shorter and consideration should be given to flagging issues and opportunities rather than documenting compliance with work plans.

A. Introduction and Context

DevTracker Link to Business Case:	5236811
DevTracker Link to Log frame:	3600859

Outline of programme

Set up in 2008, the State Partnership for Accountability, Responsiveness and Capability (SPARC) was designed as a technical assistance programme. The intended Impact was ‘Nigeria’s own resources used efficiently and effectively to achieve the Millennium Development Goals (MDGs)’, whilst the Outcome was ‘the efficiency and effectiveness of selected state governments’ use of public resources enhanced’, to be delivered through four Outputs:
- Output 1: Policy and strategy development, monitoring and evaluation processes improved.
- Output 2: State public financial management processes improved.
- Output 3: State civil service performance processes improved.
- Output 4: Federal support to state governance improved.

SPARC was designed as one of a suite of State Level Programmes (SLPs) to leverage improved pro-poor service delivery. The other DFID programmes are: a) State Voice and Accountability (SAVI), b) Education Sector Support Programme in Nigeria (ESSPIN), c) Partnership for Transforming Health Systems Phase 2 (PATHS2), and, d) Growth and Employment in States (GEMS). The overall collective objective was to increase the efficiency and effectiveness of utilisation of Nigeria’s resources to achieve the MDGs. Over time, the SLP suite diminished in ‘connectivity’ as individual programmes moved into new states and not necessarily in tandem. SPARC originally worked in five states (Enugu, Jigawa, Kaduna, Kano and Lagos) and then expanded to a further five by 2012 (Anambra, Katsina, Niger Yobe and Zamfara) as part of DFID's Operational Plan for Nigeria 2011-2015. This geographical expansion was mirrored only by SAVI.

Following the 2015 elections, reform momentum has increased in many states. The analysis of reform progress, since the elections in early 2015, shows that the most reformist states are Kaduna, Yobe and Lagos, whilst the least reformist is Katsina. There are some similarities in the reform mix between states, which indicates that states are emulating each other and following leadership from the federal level. The majority of states have rationalised or streamlined MDAs and reduced the number of political appointments. There is also a common focus on reducing overhead expenditures and increasing internally-generated revenues (IGR).

What it has achieved

Over the life of the programme, SPARC’s achievements are extensive, ranging across the 4 outputs listed above. Visible results have been delivered across the core business processes in the majority of the 10 state governments, as evidenced by:

Policy and strategy, monitoring and evaluation: implementation of more rigorous, policy based state development plans (SDPs); alignment of medium term sector strategies (MTSSs) with the priorities in the SDPs and the available funding; mainstreaming of gender and social inclusion objectives into these development plans; more effective monitoring and evaluation of results through the inclusion of explicit targets in the plans, introduction and capacitating of state bureaus of statistics and the creation of a Community of Practice to enable practitioners to share experiences; and the beginnings of annual performance reporting by sectors

Public financial management: strengthened budget processes resulting in the approval of more realistic and credible spending plans; the adoption of a structured approach to establishing affordable budget ceilings through the use of the Economic Fiscal Update, the Fiscal Strategy Paper and the Budget Policy Statement; there is now a significant demonstrable linkage between costing of new policy initiatives (policy), investment decisions (planning), and recurrent cost implications (budgeting)

Public sector management: organisational mandates have been mapped in all 10 states with the potential for eliminating duplication and achieving significant cost savings; corporate planning has been completed in a selection of states and MDAs; new human resource management policies and guidelines have been adopted; and Service Charters are being rolled out to encourage the public’s engagement in monitoring service standards

Federal level support: assisted with the design and implementation of the Conditional Grants Scheme which distributed Debt Relief funding to state and local governments and these grants resulted in improved school enrolments, increased access to health centres together with increased immunisations and antenatal care.

SPARC’s support has contributed to tangible changes which have resulted in states making significant savings and generating more revenue. For example, SPARC helped Enugu, Kano, Jigawa, Niger and Zamfara States recover funds from dormant bank accounts, supported initiatives that improved revenues in Anambra, Enugu, Lagos, Kaduna and Katsina, helped remove 'ghost' workers from payrolls in Kaduna, Katsina and Zamfara, reduced procurement costs and/or improved due process practices in Anambra, Enugu, Lagos and Jigawa and recovered outstanding debts in Kaduna. Through these initiatives, it is estimated that an additional £600 million has been freed up for delivering basic services since the programme began.

SPARC’s success in working on gender equality and inclusiveness falls into the categories of awareness raising, mainstreaming gender issues in to the key planning documents and policy statements, building skills and starting to establish gender disaggregated data for monitoring and evaluation.

In terms of the overall performance of individual states, Anambra and Lagos feature at the top of the ranking (see Table 2 below). Less evident, but in many ways far more impressive, has been the achievement of the Yobe State Government. As SPARC concluded[1], “Given the risks, vulnerabilities, and impacts on human security resulting from insurgency in Yobe State, it is worth crediting policymakers in government and other stakeholders for their impressive work and reform drive. Now that security is improving, their achievements create a solid foundation for further reforms and improvements in governance”.
[1] ‘Yobe State Synthesis: Reform Journey 2011-2015’. SPARC, February 2016

Close collaborative working with SAVI has enabled SPARC to contribute to capacity building in the State Houses of Assembly (especially around budget issues) and to raising awareness in both CSOs and state governments about the implications and requirements of the new Freedom of Information legislation.

SPARC’s development and use of its knowledge management system has been a significant feature in its approach to ‘accelerated learning through sharing’ for both partner and non-partner states (reaching an additional 10 non-partner states) and for stakeholders at the Federal level, such as the Nigeria Governors Forum. Further details are provided in Section B below at ‘Lessons and how these have been shared’.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The programme’s Outcome is the ‘efficiency and effectiveness of the 10 selected state governments use of public resources is enhanced’.

Over its lifetime the programme has also played a leadership role that has made a positive contribution to DFID Nigeria’s delivery of its Operational Plan objectives. Government resources are being used more effectively through improved financial management processes. SPARC, with SAVI, has promoted transparent government finance and accountable public institutions to help Nigerians hold decision makers to account. It has worked with the State Houses of Assembly to increase transparency and public access to information and debates; there is now greater transparency especially around the budget process.

Table 1 below summarises Outcome target performance by Outcome indicator across the whole programme.

  Table 1: Summary of Outcome Performance
Indicators	Score	Description
Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	C	Substantially did not meet expectation
Realism and predictability of multi-year capital and recurrent budgets.	B	Moderately did not meet expectation
Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	A+	Moderately exceeded expectation
Responsiveness and success of State Governments to National initiatives to improve state performance.	A	Met expectation

Performance across the 10 states also varied, as Table 2 illustrates.

Table 2: State performance in achieving Outcome targets
State	Outcome performance[2]
Anambra	100%	A++
Lagos	83%	A+
Niger, Yobe, Zamfara	75%	A
Jigawa	66%	B
Kano	58%	C
Enugu	50%	C
Katsina	33%	C
Kaduna	17%	C
[2] Measured as a percentage using the Red, Amber, Green (RAG) scoring where Green=1, Amber/green=0.5, Amber=0.25 and Red and Red/Amber=0

There are many complex and inter-related reasons for these variations in performance. There is no single set of critical success factors or inherent barriers to change; as the programme has learned ‘no one size fits all.’ But what is evident is that political will and commitment are the overriding pressures for change and this is linked to the importance of continuity in political leadership, especially across administrations. But it is important to note that improvements in performance are not linear and there are examples, such as in Enugu and in Kano, where performance has ‘dipped’ over the lifetime of the programme. Enugu was back on track at project close but Kano’s momentum is yet to be re-established by the new administration.

Output score and description

The overall Output score is ‘A+, moderately exceeded expectation’.

Table 3: Summary of Scoring by Output together with weightings
Output	Score	Description	Weighting
1. Policy and strategy development, monitoring and evaluation processes improved	A++	Substantially exceeded expectation	25%
2. State public financial management processes improved	A+	Moderately exceeded expectation	40%
3. State public service management processes improved	A++	Substantially exceeded expectation	25%
4. Federal support to state governance improved	A	Met expectation	10%

Table 4 illustrates state performance at Output level

Table 4: State performance in achieving Output targets
State	Output performance
Anambra	100%	A++
Enugu	96%	A++
Kaduna	94%	A++
Yobe	94%	A++
Niger	92%	A++
Jigawa	91%	A++
Lagos	91%	A++
Kano	89%	A
Zamfara	86%	A
Katsina	75%	B

Lessons and how these have been shared

There is strong evidence that ministries, departments and agencies (MDAs) have a far stronger capability to prepare development plans and budgets. The expertise was strengthened in the central MDAs in all of the states; the extent to which this expertise has been built in sector MDAs is more variable both across sectors in states and between states. Typically the capability is more evident in the health and education sectors, especially where PATHS2 and ESSPIN have been present. However, the evidence that this improved organisational capacity has translated into improved service delivery is weak.

The lessons learned have been captured in a range of documents produced by the programme[3]. The significant, high level lessons of particular relevance to the successor governance programme include:
[3] These key lessons are extracted from ‘Theory of Change Self Evaluation Report’, SPARC report to DFID, January 2016

- Politics matters - Working with existing political arrangements and structures (using political economy analysis) can result in pockets of impact on service delivery and improvements to citizens’ lives emerge when on-going high level political commitment is given, as well as the investment of significant financial resources
- Governance reform is not linear and no single approach works in all states or at the same time. Therefore:
    - Greatest prospects for success occur where the state government is driving its own reform agenda
    - Importance of adopting a multi-faceted, flexible, adaptive and politically informed approach through i) Working with existing political arrangements and structures; ii) constant vigilance and awareness radar (eyes and ears on the ground to influence key players); iii) alliance building; iv) applying a facilitative approach to understand technical processes: building confidence and empowerment; v) underpinning reform with the necessary tools, instruments, training/advisory (based on reiteration, feedback loops); vi) providing technical assistance tailored to needs and with a sustainability/learning focus; vii) State peer-learning (SG to SG intra programme, and programme to a wider constituency (use of help desk, resource centre)

SPARC has achieved a high level of results in some cases, but recognises that it is a
significant step from improving the efficiency and effectiveness of public resources to
better manage services and improve citizens’ lives. Identifying the contribution of SPARC’s successor programme to improvements in public service delivery and on citizens’ lives will require significant investments in budget tracking, service monitoring and impact assessment.

Selected issue-based work directed at specific service delivery problems could be a useful addition to the future governance reform programme.

SPARC has implemented an extensive and impressive knowledge management system. In addition to the SPARC website and its accessible library of programme related documents, tools and guidelines, the programme has also continued to build up its library of tutorial videos on SPARC’s YouTube Channel. SPARC has used digital platforms to bring tutorials and news about reforms to a wider audience through SPARC Governance News on Facebook, and SPARC Nigeria on YouTube. In addition, the programme has operated a technical help desk, Access for Sharing Knowledge (ASK), which has enabled the programme to deepen its work in partner states as well as to reach out to non-partner states. This facility will be transferred to the Nigeria Governors’ Forum with guaranteed funding for 2 years from the Gates Foundation. A PFM database for all 36 states has been established jointly with the World Bank and options to transfer its ongoing management to a national organisation are being explored.

In July 2015, SPARC officially became a member of the Effective Institutions Platform of the Organisation for Economic Cooperation and Development (OECD). More than 60 SPARC resources as well as SPARC’s Resource Centre have been uploaded to their library. The collaboration with the University of Sussex-managed Eldis website also continues, where the Resource Centre has been hosted since first released.

## C: DETAILED OUTPUT SCORING

Output Title	Policy and strategy development, monitoring and evaluation processes improved
Output number per LF		1	Output Score	A++
Risk:		High	Impact weighting (%):	25
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[4]	Progress[5]			Score[6]
		% of states where ‘fully/largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’[7]
1.1 Extent to which policy and strategy making processes meet good practice standards.	State Development prepared in line with good practice standards	100	0	0	A++
1.2 Quality and comprehensiveness of policies and strategies.	The 2015-2017 MTSS’s are consistent with Strategy content standards	89	11	0	A+
1.3 Extent to which results frameworks are comprehensive and measured.	The 2015-2017 MTSS’s contain a comprehensive Results Framework with KPIs (including G&SI disaggregation)	100	0	0	A++
1.4 Extent to which performance management processes are being used	Annual reviews of sector performance completed in line with good practice standards	100	0	0	A++
1.5 Extent to which political commitment to governance reform is evident.	State governments continue to make scheduled progress with their reform agendas	80	20	0	A+
[4] These targets are generic and are presented as illustrations of the type of targets being used since the 2016 targets for each indicator vary significantly between states and for brevity are not shown. The actual progress listed is a summary synthesis of progress reported against state logframes completed by the PCR team. For a detailed description of progress against state level logframes, including state specific targets, see the Final Logframe Progress Report, February 2016 held by SPARC
[5] Progress is reported against actual achievement against the targets specified in each state logframe
[6] Scoring of each target is based on the % of states where progress is assessed as ‘fully/largely achieved’ using the following scale where 0% ≤ C < 60% ≤ B < 70% ≤ A < 80% ≤ A+ < 90% ≤ A++ ≤ 100%. Note, for comparison with earlier years, this scale has been modified, in agreement to DFID, to reset the ‘A’ standard at 70% rather than 50% as previously used in earlier Annual Reviews
[7] ‘Not achieved’ includes (a) no evident progress or (b) too early to measure

Key Points
Many of the states, post the 2015 elections, are updating their State Development Plans (SDPs) informed by the development priorities of the new Governors. These revisions are being made using the planning guidelines adopted by previous administrations following the guidelines and training provided by the programme. The updated SDPs are expected to comply largely with the planning guidelines introduced by SPARC. In all cases, it is expected that these new SDPs will drive the development agenda in each state and provide the framework for sector plans and for budget allocations.

States, such as Enugu for example, are intending to use their new SDPs as the framework for defining and prioritising their governance reform agenda. Several states are looking to update or introduce development partner agreements around which to structure external assistance both in terms of technical assistance as well as funding.

Summary of responses to issues raised in previous annual reviews (where relevant)
Provide a roadmap for establishing State Statistics Bureaus. Actioned.

Recommendations for future programmes
Continue to urge state governments to adopt the Comprehensive Development Framework model (along the lines of Kaduna) to frame and guide development partners’ engagement with the state on implementing their SDPs.

Ongoing support to the State Bureaus of Statistics (or equivalent M&E departments where SBoSs not present) to further embed performance and results monitoring and reporting.

Output Title	State public financial management processes improved
Output number per LF		2	Output Score	A+
Risk:		High	Impact weighting (%):	40
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress			Score
		% of states where ‘fully / largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’
2.1 Extent to which the budget is credible and policy based.	Budget process informed by (a) Economic Policy Update (b) Fiscal Strategy Paper and (c) Budget Policy Statement with budget ceilings better aligned to MTSS’s	80	20	0	A+
2.2 Extent to which the budget is comprehensive and transparent.	Annual budget documentation better meets PEFA standards such as Budget Calendar and Budget Call Circular	78	11	11	A
2.3 Level of predictability and / control in budget execution.	More realistic forecasts of internally generated revenues using revenue/cash forecasting model	88	12	0	A+
2.4 Quality of accounting, / recording and reporting.	Improved accounting and budget performance reports produced in compliance with IPSAS and FAAC standards	75	25	0	A
2.5 Extent and quality of external scrutiny and audit.	State Auditor General Offices completing more effective annual audits	100	0	0	A++

Key Points

One of the major successes resulting from SPARC’s intervention has been the introduction and routine adoption of a structured and well informed budget formulation process across most of the 10 states. For example, economic and fiscal updates, fiscal strategy papers and budget policy statements have been prepared and used to guide and support the 2015 budget processes in Anambra, Enugu, Jigawa, Niger, Yobe and Zamfara. Budget call circulars, which meet the requisite content requirements, have been prepared by state government in Anambra, Kaduna, Niger, Yobe and Zamfara. Medium-term revenue forecasts and sector ceilings and guidance on including capital projects have been prepared and used to guide 2015 budget development in Enugu.

Adopting budget realism and credibility remains a challenge, especially for some of those new governments preparing their first post-election budget; Kano and Jigawa are prime examples of where the proposed expenditure levels are clearly not fundable from Federal transfers and internally-generated revenues.

The ‘fiscal crunch’ arising from the fall in oil prices has provided an important impetus for better budget preparation as well as for budget execution. Looking to the future, greater attention will need to be paid by state governments to issues of cash management, debt management and capital expenditure profiling. Continued support to strengthen the management of internally generated revenue will be needed.

Recommendations for future programmes
PFM reform needs to continue across the whole spectrum of processes. Over time, the emphasis should shift from budget formulation to budget execution and the tracking of spending performance in delivering the expected service standards.

Continued support to IGR will be needed especially in the areas of improving tax collection efficiency and effectiveness. However these reforms, together with the computerisation of tax administration, will present significant demands on the limited technical assistance budgets; caution is urged to avoid redirecting a disproportionate amount of the new programme’s resources to this one, complex reform stream.

Output Title	State public service management processes improved
Output number per LF		3	Output Score	A++
Risk:		High	Impact weighting (%):	25
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress			Score
		% of states where ‘fully / largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’
3.1 Clarity and appropriateness of public service organisation and operational management	Mandates reviewed and organisational restructuring commenced, informed by corporate plans	100	0	0	A++
3.2 Extent to which HRM policies and organisation are in place.	HRM policies revised and HRM improvement plans being implemented	100	0	0	A++
3.3 Extent to which establishment planning and workforce planning, management and development is in place.	Establishment and workforce plans being developed	89	11	0	A+
3.4 Extent to which MDA performance management / policies and procedures are in place.	Service Charters being introduced with annual reviews	100	0	0	A++

Key Points
The extensive mandate mapping exercises carried out across the states have helped inform the several states’ downsizing of the number of ministries following the election of new governments.

Several states (including Enugu, Lagos, Anambra and Yobe) are in the process of implementing HRMIS’s. Many states have completed successfully the first stage of implementation, namely the reconciliation of payroll data with the establishment lists (nominal roll). As a result, ghost workers have been identified and removed resulting in cost savings. The second stage, implementing the human resource management modules, may prove to be more challenging. It will be important for the successor programme to stand ready to provide technical and quality assurance support to help ensure implementation of these modules proceeds on a timely basis.

The use of Service Charters to help stimulate service delivery improvements is growing in popularity and they are now present in all 10 states. SERVICOM Units have been established in Kano and Enugu. The monitoring of actual performance in delivering the Service Charters has commenced in Lagos, Jigawa, Enugu and Kano. The experience of the Kano State Water Board is of particular interest. Starting with the Service Charter, the Board then moved on to completing a Corporate Plan in order to provide a structure and longer term vision of the areas that needed to be improved. It is likely, following the experience of the Corporate Plan, that the Board will come to realise that wider operational performance improvements will be needed. This is a good example of problem driven iterative adaptation (PDIA).

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 AR recommended SPARC to “help embed HRM reforms through continued support to HoS and reform mandated organisations”. Actioned.

Recommendations for future programmes
The lessons learned from the difficult experience of implementing the Federal Government’s Integrated Payroll and Personnel System should inform the implementation plans of those states embarking on the introduction of their HRMIS. The new programme’s primary role should be that of quality assurance to help ensure that appropriate processes are followed, in line with good international practice.

Service Charters offer a mechanism for improving service delivery through increased citizen accountability and need further support.

Output Title	Federal support to state governance improved
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress	Score
4.1 Effectiveness of National mechanisms for improving state / governance.	(a) At least three states have been / supported to begin implementation of / their SPoAs. / (b) Strategic options paper for transition of the MDG-CGS / scheme post 2015 has been prepared / and submitted. / (c) At least 50% of Nigeria Governors’ / Forum Secretariat (NGFS) 1st year / objectives have been achieved.	(a) Anambra, Ekiti and Niger states are in the process of implementing their SPoAs. / (b) A concept note for a Strategic Options Paper has been produced and approved by the CGS and a desk review of relevant materials has commenced. / (c) 55% of 1st year NGF Strategic Plan objectives have been implemented.	A
4.2 State governments have a mechanism for accessing and sharing lessons through appropriate Federal organisations	At least 10 state governments are / sharing SPARC lessons with other / states.	Achieved, in 18 states including following non SPARC states: Abia, Cross River, Delta, Ebonyi, / Ekiti, Imo, Osun, Ondo, Ogun, Oyo and Taraba.	A+

Key Points
The State Peer Review Mechanism (SPRM) process has still not progressed to completion beyond the pilot states to include other non-pilot states. Progress slowed in the pre and post-election periods. It will be interesting to see if the new Governors’ interests and active engagement in the SPRM process grows and gains momentum.

In terms of information sharing, there has been a rapid increase in demand for support from the ASK Help Desk. In line with NGF’s mandate to support all 36 states, it expressed interest in taking over the help desk facility, leading to the agreement to establish the NGF Help Desk. NGF personnel have been trained on the administration of a help desk platform by SPARC KM, and discussions brokered by SPARC between the NGF and Bill and Melinda Gates Foundation on resources have resulted in a two-year funding commitment of £175,000 per annum (totalling £350,000), with the possibility to extend for an additional year. In April 2016, the Help Desk, along with SPARC tools, will have a new institutional home with the NGF.

Recommendations for future programmes
1. Continued support to the NGF is important, both in terms of assisting with the roll out of the SPRM as well as providing high quality advice on significant issues such as internally generated revenues and the wider application of ZBB within the broader PFM reform agenda.
2. Linking the work with the NGF to future support to the National Economic Council could help to strengthen inter-governmental relations.
3. Any consideration of future support to the Sustainable Development Goals Office (the successor to the MDG Office) needs to be assessed in the context of the role of the Ministry of Budget and Planning and the risk of potential overlap/duplication of functions.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
In terms of the breakdown of spend, the main categories are TA fees and programme activities. The spending on fees has varied between 66% and 45%[8] over the years, and has averaged at around 59%. This level of spend on TA is common for programmes which rely on TA modality such as SPARC. As an example, SPARC recorded a lower level than FEPAR (76%) on percentage of fees in total spend. On programme activities, the average spending represented 27% of total, varying between 16% and 47%[9]. The remaining category (called ‘overheads’ in reporting by the SLPs) covering living costs, airfares, etc represents around 14%. This was a similar level of spend in this category in, for instance another state level programme, GEMS 3. The breakdown on fees, activities and overhead costs was provided by SPARC for each state that it has operated in.
[8] This was during the last year when SPARC says more work was undertaken by national teams rather than using short term inputs.
[9] The latter high share of the last year was due to PEFA assessments completion.

VfM performance compared to the original VfM proposition in the business case

SPARC did not have VfM measures articulated at the outset, as the design of the programme pre-dates the Business Case requirements. But SPARC developed an impressively detailed (24 indicators covering all 3 Es, and across all outputs and states) VfM framework which they have reported against consistently since 2013.

Economy:
- Average consultancy fee rates showing a downward trend year on year, by 7 to 12%. SPARC also reported on fee rate savings based on a method which compared fee rates against a baseline period of inception. Over 8 years, this amounted to £1.9m in savings. Again, these were captured for each state of activity and federal levels.
- Savings (around £0.6m) through cost conscious behaviour on sharing of venues, utilising partner facilities, negotiations with service providers on rent, insurance, etc. and increased use of national consultants.

Efficiency:
- SPARC’s reporting on efficiency has focused on capturing spend trends on logframe output milestones. SPARC used 4 different indicators (2 of which are related to costs, therefore are VfM indicators): Spend per % point of activity milestone delivery and Spend per % logframe output milestone delivery. This is impressively captured across all outputs and states and there was a downward trend on these, demonstrating an efficient delivery.
- Output 2 (on improving state public finance management) recorded the highest spend (averaging at around 32% of the spending), followed by outputs 1 and 3 (25% and 24% respectively). Output 4 (on federal support to state governance) and 5 (on knowledge management and M&E) spent better than others consistently, in terms of budget utilisation, not by budget scale.

Effectiveness:
- Following a recommendation from the last year’s Annual Review, an econometric analysis was commissioned by SPARC. The study found that; ‘…there has been a strong statistically significant and large association between SPARC interventions and improved outcomes of two very basic PFM indicators’[10]. This provides a good piece of evidence that shows linkages with SPARC’s work to PFM improvements, because it compares SPARC states with non-SPARC ones.
  [10] ‘Governance Reform in Nigerian States: Econometric Analysis of SPARC Support’, SPARC, Jan 2015, p.23.
- Other results in the form of estimated efficiency savings (such as, reducing debt stock in Enugu, sorting pension contributions in Jigawa, and increases in revenue collection in Anambra) have been monetized and reported. These results indicate that the value of benefits, in monetary terms, was above levels of spending by SPARC.
- Knowledge management related benefits: Knowledge management has been a strong feature of SPARC throughout implementation. SPARC’s high-quality and extensive reporting documents different aspects of the ‘reform journey’ that they have undergone. ASK and other databases that were developed are influential and frequently referred to.

Equity: SPARC has adopted a flexible approach with different entry points and subsequent interventions tailored to each state. These have included: identifying a key champion and supporting him/her with advice and capacity building to do G&SI advocacy; collaboration with SAVI and Gender Working Group; including G&SI in policy, planning and service charters; and development and use of tools and working with partners. Also useful are tools such as inclusiveness and responsiveness ranking of states. SPARC has documented its achievements and lessons on G&SI; and the achievements were corroborated by interviewees during the fieldwork.

Assessment of whether the programme represented value for money
The VfM proposition of the governance SLP suite (SAVI and SPARC) is to achieve equivalent or greater improvements in the use of Nigerian resources measured in terms of reduced losses through corruption and waste and more productive use of expenditure, in a strategic way towards the longer-term change. An underlying assumption is that the enormous scale of Nigerian public finances means that even a modest shift in resources in percentage terms can have very substantial deliver significant returns for the government of Nigeria and Nigerian citizens. This logic remains valid.

For the purpose of illustration, the programme asserts[11] that it has contributed to, through improved systems and processes, the additional £1.125 billion spending by state governments, of which £437.26 million (39%) was spent on health and education services. SPARC also played a significant contribution towards embedding and sustaining reforms, strengthened budgets and starting to help states to addressing the fiscal challenge by improving domestic revenue.
[11] SPARC Working Paper ‘Value for Money’. February 2016

Quality of financial management during programme
The total programme spend at end of June 2016 is £62,394,858.20. Out of a £65m (final) budget, this represents slightly over 95% utilisation. This is considered good, given low levels of utilisation at various periods during implementation, at about 70% (2011/2012) and 78% (2013/2014).

In terms of financial forecasting, performance has varied in the last few quarters due to delays in appointment of key officials in states and disruption of activities. However, DFID’s narrative and financial reporting requirements have been adhered to, as well as the auditing requirements, as confirmed by DFID programme management. There were three audits completed, the last one dated March 2015. Those confirmed compliance with internal financial controls and international accounting standards.

Date of last narrative financial report	Final Quarterly Progress Report to December 2015 – February 2016, with associated invoices
Date of last audited annual statement	Closure audit for the period 1st April 2015 to 31st March 2016 – signed off. Unqualified opinion expressed by external Auditors.

E: RISK

Quality of risk management over the life of the programme
SPARC has been assessed as a high risk programme throughout its implementation. It is a high risk due to a complex operational environment characterised by low willingness for governance reform, general insecurity, and transitional challenges with electoral periods. SPARC has operated with a Programme Manual which incorporates a Security Plan – this is regularly updated, the most recent version being October 2015. The programme also has a Programme Manual on Risk Management, again regularly updated, with the latest dated December 2015. There has been high quality due diligence in risk management over the lifetime of the programme. Of particular note is that results have been delivered in Yobe State despite insecurity and challenges to programme delivery due to the Boko Haram insurgency. Also, SPARC’s briefing on the ‘Preparation for Elections’ has seen governance reform successfully transition political change in nearly all states affected by elections; and despite political will and corruption, the programme has delivered consistently on its milestones.

The DFID Contract Performance Review May 2015 to October 2015 noted “SPARC goes beyond expectations on risk management and mitigation. Their transition plan served as the model for other programmes and has helped DFID Nigeria to continue delivering in an unpredictable environment.” The programme scored 5 out of 6 for Appropriate and Effective Identification and Management of Risks.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Over the eight years of programme implementation, progress and delivery against milestones have remained on track. Continuity has been maintained and sustained both during the scaling up from 5 to 10 states from 2012 and the transition through two national elections in 2010 and 2015. The consistent AR scorings at A+ confirm this successful track record.

Performance of partnership (s)
The DFID Contract Performance Review May 2015 to October 2015 gave a total supplier (DAI, incorporating HTSPE) score of 83%. The review specifically noted “Milestones on the Logframe have been met on time and to very high standards” and scores the programme 5 out of 6 in this area. And that “SPARC leads the field on reporting. They meet all their obligations and proactively provide big picture considerations which inform wider DFID programming” and also scoring 5 out of 6 for this area. The review also noted the SPARC teams have performed well in all states, and that the programme has excellent leadership, is excellent at problem solving and consistent in communicating.

SPARC has developed a close working relationship with SAVI. In addition to their collaborative work on joint political economy analyses, the two programmes have aligned their work plans to jointly build the capacity and common understanding of CSOs and Government officials and to help strengthen the capacity of incoming State Houses of Assembly, especially around budget issues. More recently SPARC and SAVI have worked together on the 2016 budget process, providing joint briefings to DFID.

In addition SPARC has supported the work of other SLP suite programmes including more recently with GEMS on the issue of internally generated revenue and the restructuring of the State Boards of Internal Revenue.

Asset disposal and value obtained by DFID
SPARC maintains an asset registry and an inventory list. A full asset disposal and transition plan has been implemented. SPARC has disposed over 60% of its assets and the value of the proceeds returned to DFID centre while about 40% of assets have been transferred to the new programme.

H: MONITORING & EVALUATION

Evidence and evaluation
SPARC is subject to an external evaluation as part of the SLP suite of programmes. The result of this evaluation is expected mid-2016.

For each state, the programme established performance baselines across all 3 outputs using the Public Expenditure and Financial Accountability Assessment (PEFA) and the State Evaluation and Accountability Tool (SEAT) indicators and rankings. These assessments were updated on two further occasions during the life of the programme and they provided helpful mechanisms through which to engage the support and interest of stakeholders in the states. However, as tools for measuring achievements over the years, their use has proved to be less valuable. The experience suggests that states become more critical of their performance as they become more experienced in delivering reform efforts. As a result, the programme explained the 2015 results, which broadly revealed no significant ‘across the board’ improvements in performance, in terms of a more rigorous application of the standards to be achieved rather than lack of progress. Also the costs of carrying out these assessments are on the high side. So looking to the future programme, there needs to be a decision on the future usefulness of these two assessment methodologies and, if necessary, on what alternative approaches could be used to measure performance change.

In terms of capturing evidence of the validity of SPARC’s Theory of Change, the programme found it a challenge to substantiate the link between its Outcome and Impact objectives. In terms of the results chain, it is a large step to move from achieving an Outcome of ‘efficiency and effectiveness of the 10 selected state governments’ and the Impact of ‘Nigeria’s own resources used efficiently and effectively to achieve the Millennium Development Goals (MDGs).’ Given this ‘disconnect’ between these 2 high level programme objectives, and in order to have another ‘more achievable’ step in the intervention logic, SPARC adopted an Intermediate Impact objective of ‘better basic services are delivered’. Also to help with framing the evidence requirements to substantiate the Theory of Change, the programme reframed the Impact objective in terms of ‘improving citizens’ lives’. It is against this background that SPARC captured a substantial body of evidence in support of its Theory of Change.

The programme completed several case studies over 2014 and 2015 and these have focused on establishing the evidence between the output-outcome and outcome-intermediate impact levels in the programme Theory of Change. In addition, specific research studies have been implemented including: a) a Triangulation Study in 2014 and again in 2015 which triangulates and correlates a range of data sources with SPARC’s own results and data from three perspectives: assessments of state government performance; citizens’ perceptions; and expert/external sources, and b) an Econometric Study of the relationship between PEFA outcome indicators and SPARC support. All of these studies have been helpful in validating the programme’s Theory of Change. There are measurable results, with 9 examples of quality technical assistance leading to 3 examples of efficiency and effectiveness in service delivery. Furthermore, the evidence ‘suggests’ that there are 4 examples of better services delivered and 3 examples of improvements to citizens’ lives.

For the future programme, its Theory of Change and logframe need to ensure that there are no major ‘disconnects’ between Outputs, Outcome and Impact. Particularly, the Impact objective must be within the reach and influence of the programme with the relevant assumptions being capable of measurement. Also, when defining Outcome indicators and milestones, it will be important for these not to measure an activity but rather the change in behaviour or results arising from the introduction of new ways of working.

Monitoring progress throughout the programme

SPARC has implemented a comprehensive monitoring system which includes the following components: M&E MIS, Performance Management reports, Quarterly Progress reports, Annual Progress report, Annual Change Programme Performance reviews and VfM assessments. Whilst progress reporting has been comprehensive, the resulting documentation is lengthy and detailed (with Quarterly Progress reports averaging over 100 pages). In part, this has reflected the size of the programme but also the breadth of the logframes (3 outputs across 10 states plus 2 outputs for federal, adding up to around 140 indicators) and the complexity of the progress assessment methodology (Red, Amber, and Green). For the future programme, routine reporting needs to be simplified, perhaps with a greater emphasis on flagging issues and opportunities rather than documenting compliance with work plans.

In addition to these more formal monitoring processes, ongoing implementation monitoring took place at all levels of SPARC. State and Federal teams were in touch with their Government counterparts on a daily basis, following up on agreed actions, helping to review documents prepared by Government and participating in various Committees and Technical Working Group meetings in order to monitor reforms. In addition, through the cross-SLP coordination mechanisms, SPARC managers at state and programme levels contributed to monitoring progress in cross-programme collaboration.

This review was carried out by the Independent Monitoring and Evaluation Project (IMEP) as part of a joint Programme Completion Review of the SPARC, SAVI, FEPAR and V2P programmes in 2016. The SAVI review was led by Kenneth Robson with support from Gabriel Ojegbile and Gulden Bayaz (VfM). The Government of Nigeria was represented by Mukhtar Tanko (NPC Observer).