Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme’s performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	June 2016

Title: State Accountability & Voice Initiative - Nigeria
Programme Code: CNTR 200708083	Start Date: Aug 2008	End Date: 30th April 2016

Summary of Programme Performance

Year	2009	2010	2011	2012	2013	2014	2016
Programme Score	n/a	2	2	A	A+	A+	A
Risk Rating	med/high	med/high	med/high	med/high	med/high	med/high	med/high

Financial Position

Original Programme Value	(July 2008) £20,233,323
Extensions / amendments	There have been 7 contract amendments taking the total value of the project to £33,719,219. The majority of these amendments were covering the expansion of the programme to five additional states, extension by an additional year and scaling up of on Federal work.
Log-frame revisions (with dates)	Changes were made to the logframe at the mid-term review in April 2011. Since the mid-term review the indicators have not been changed to a significant extent, but the milestones have been adjusted on an annual basis to reflect progress, expectations of future performance and SAVI’s expansion plans. Further changes were made in 2013 solely to Output 5.
Total programme spend	Actual spend to end of programme £32,432,838.47 with the final invoice expected in July 2016

Follow up actions required following closure

The second pillar of the Public Sector Accountability and Governance Programme (PSAGP) will provide a new phase of voice and accountability programming. The following points cover general recommendations relevant to managing the transition from SAVI to PSAGP. More specific recommendations following from the assessment of SAVI’s five outputs are reported in Section C of this ARIES form.

R1) Make use of lessons learned from SAVI. The successor programme will need to draw on lessons learned from SAVI (and FEPAR) on how to promote voice and accountability most effectively using the ‘facilitated partnership’ model (see detailed lessons in section B below). SAVI’s approach has evolved considerably over the course of the project, and the new programme will need to reflect SAVI’s learning, while providing space for further experimentation and adaptation. The PSAGP logframe and design of indicators will need to be overhauled to reflect increased understanding of voice and accountability processes that has been gained over the course of the SAVI programme.

R2) Reinvigorate programming in focal states (Lagos, Enugu, Kaduna, Kano and Jigawa). The new programme will need to reinvigorate the partnership model in these states drawing on innovative practices developed by SAVI outside of the original focal states. There are concerns that, while the results have been achieved, SAVI teams in some of the original states (especially Lagos), deviated from good practice.

R3) Define an approach to working in transition states. The future programme will transition out of some states where SAVI has been working. In these cases it will be essential to prioritise measures that help to consolidate progress and ensure sustainability of governance changes delivered by SAVI. The new programme should have a responsible exit from states where SAVI programming has proven successful and where there is good reform potential for the future. Yobe stands out as a special case, where continued full scale programming (through PSAGP or another programme) is recommended to build on and preserve the considerable gains delivered by SAVI.

R4) Develop a regional hub approach. In the Southwest and Southeast DFID intends that PSAGP will operate according to a hubs and spokes model centred on Lagos and Enugu. There is a need to develop viable models for regional outreach and experience sharing. This should involve transferring good practice from the hubs and searching for existing examples of good practice in the ‘spokes’ states, which can be built on and replicated. There may be scope to develop mechanisms for states within a particular region to compete for PSAGP support and demonstrate their commitment to using PSAGP resources effectively.

R5) Ensure close collaboration between the three PSAGP pillars focussed on specific policy issues and core governance processes. SAVI and SPARC have already been cooperating well, but collaboration has mainly been ad hoc and opportunistic rather than a result of joint programming and work planning. These deficiencies will need to be addressed in the new programme.[1]
[1] Note that these issues are addressed in a separate PCR paper on SPARC-SAVI coordination.

R6) Build a strong federal component into the future programme. The successor programme will need to build on SAVI’s state level work, and incorporate elements of FEPAR’s external advocacy and accountability initiatives at Federal level. Since the majority of the future programme team are drawn from former SAVI staff (with only a few former FEPAR staff) there will be challenge to gear up to working at Federal level. Working successfully at Federal level will require a combination of the following: (1) recognising that civil society, media and the legislature function very differently at state and federal levels (SAVI’s facilitated partnership model will require considerable adaptation to work successfully at federal level), (2) being highly focussed and selective on a limited set of manageable issues, (3) linking federal and state initiatives to deliver synergies, (4) recognising that political risks of voice and accountability work are greater at federal level, and enhancing the risk management strategy accordingly.

R7) Link community level engagement into the programme. There is an intention that the new programme will build on SAVI’s experiments to link community level engagement to state level policy and planning processes. A key element of this will be building on SAVI’s partnership with V2P (which has worked well previously in Anambra) in South East and testing the model in Kaduna. At the same time, collaboration with M4D in Kaduna, Kano and Jigawa should be further strengthened. The new programme will need to devote considerable attention to developing a realistic and manageable scale up process that is well adapted to the varying context in each state. Specific challenges and recommendations are also highlighted in the V2P ARIES form.

R8) Make more effective use of tools from Political Economy Analysis (PEA) and Problem Driven Iterative Adaptation (PDIA). SAVI has made effective use of PEA tools to adapt its programming to different state level contexts and respond to opportunities created by political openings and electoral transitions. However, PEA has so far mainly been focussed on macro-level analysis of the state context, and has not often drilled down into specific issues and problems. This would help the successor programme to identify particular policy blockages where reform is feasible and where SAVI supported actors can play an important role. In many cases this analysis will need to be continuous rather than one-off in order to support lesson learning and programme adaptation. It would be worthwhile for the successor to identify a number of PDIA pilots to test this approach and establish good practice. Water policy in Kano state would be a good test case building on experience gained from SAVI’s work with the Wudil Advocacy Partnership and addressing a specific blockage in water policy reform.

## A: INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	4521418
DevTracker Link to Log frame:	5028958

Outline of programme and what it has achieved

Unaccountable governance and attendant corruption are major reasons for Nigeria’s growing inequality and lack of progress in poverty reduction. Public policy and public expenditure tend to be oriented towards serving patronage networks and winning elections rather than the provision of public goods and services. One of the main reasons for this is the lack of citizen demand for more accountable governance. Change agents who could act as potential reform constituencies tend to be disconnected, disorganised, lacking capacity, lacking voice and lacking connections to political processes.

The State Accountability and Voice Initiative (SAVI) has worked at state level to build the capacity of constituencies who can create pressure for more accountable governance. It aimed to deliver the following outcome: State houses of assembly, civil society, media and citizens demonstrate more effectiveness in demanding better performance from government and holding government to account.

SAVI worked to deliver five outputs:

1. Civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring.
2. Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes.
3. More open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government.
4. Improved systems of transparency, public engagement and financial oversight in state houses of assembly
5. Other development partners take a more sustainable and replicable approach to strengthening voice and accountability.

By strengthening the demand-side of governance reform, SAVI complemented the supply-side work of the State Partnership for Accountability, Responsiveness and Capacity (SPARC), which provided technical assistance to strengthen accountability systems and processes in state governments. SAVI was also designed to support the work of the other State Level Programmes (SLPs) including the Partnership for Transforming Health Systems 2 (PATHS 2), Education Sector Support Programme in Nigeria [ESSPIN]) and Growth and Employment in States (GEMS) at state level.

SAVI began work in 2008 in 5 states (Enugu, Jigawa, Kaduna, Kano and Lagos), and in 2011 extended its reach to three additional states (Zamfara, Katsina and Yobe). In 2013 SAVI further extended its activities to Anambra and Niger.

SAVI had been due to end in July 2015, but the programme was extended to the end of April 2016 with a £6 million additional budget. This has facilitated the transition to the successor programme, the Public Sector Accountability and Governance Programme (PSAGP), starting in May 2016.

Context: The context of the states may be viewed on a continuum from those driven by purely personalised and patronage politics to those where political leaders are committed to the delivery of public goods and services for the benefit of citizens as a whole rather than narrow clientielist groups. The majority of states in which the programme operated were the former. Working within this context, SAVI has been able to build inclusive, sustainable and replicable models of getting citizens more engaged in key policy, planning, service delivery and accountability processes.

Results: There is strong evidence that as a result of SAVI engagement, State Houses of Assembly have become more open and transparent, and in some states are performing their executive oversight functions more effectively. Media has become more engaged in reporting governance issues and connecting citizens to policy discussion. SAVI’s logframe targets have been met or exceeded indicating that it has made a substantial contribution to improving institutional and organisational capacity. There are also strong indications of SAVI’s broader influence, including numerous examples of where elements of SAVI’s approach are being replicated by other organisations in Nigeria and internationally.

SAVI has tracked 157 case studies where there is evidence that citizen engagement facilitated by SAVI and its partners has contributed to improved policies and practices resulting in better service delivery and development outcomes including for the poor and marginalised. The domesticating of Nigeria’s gender policy for application to Muslim populations in Jigawa, which has Shari ‘a law is one example. The policy which is being implemented has ensured tangible gender indicators and goals are now fully integrated in planning and execution. Another example is a breakthrough on disability policy and legislation in Lagos state in 2012. The SAVI supported Lagos Civil Society Disability Partnership lobbied successfully for the Special Peoples Law on Disability. Following the passage of the law, the government has established a state-funded office to implement it government work-streams and budgets are now mainstreaming disability issues.

Limitations: While recognising these important achievements, it is important to stress that SAVI’s results have yielded only partial or incremental change but have not yet led to transformational change in the broader political economy factors that have generally acted to undermine public accountability. SAVI was not expected to transform the broader political economy context, but has demonstrated that there is considerable space within this context to strengthen citizen engagement in governance and accountability processes, and to use this to drive new norms in state agencies and state-society power relations. So far, this has mainly been achieved by working on ‘softer’ policy issues relating to service delivery that are unlikely to generate a strong political backlash, and there has been a tendency to work more at the early stages of policy and budget preparation rather than monitoring and advocacy concerned with subsequent delivery. SAVI was also designed to work more or less exclusively on state level governance processes, although SAVI has experimented with some initiatives to strengthen citizen engagement in local governance and to engage with federal institutions to add value to its state level work.

Future potential: The success of SAVI as a demonstration project indicates considerable potential for the successor programme. There is scope to scale up SAVI’s work by extending and replicating islands of success, to begin to work on more challenging governance issues with a stronger focus on addressing fundamental political economy problems, and to foster gradual changes in citizens’ expectations and social norms that are required for accountable governance.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

Outcome indicators 1-3 measure the level of functionality of State Houses of Assembly, Civil Society and Media as agents of voice and accountability as measured by the SAVI Governance Index. Scores are derived from expert ratings (measured on a five point scale) through an independent peer review mechanism in each state.

Outcome indicator 4 measures the cumulative number of demonstrable changes in policy and implementation by state and local governments in response to public demand where there is evidence of attribution to SAVI's approach.

Outcome indicators have been subject to a data quality assessment by the IMEP/PCR team (See Section H), which has affected the scoring for outcome indicator 4. All four outcome indicators have shown considerable improvement over the course of the SAVI programme. The endline targets have been narrowly missed for indicators 1-3. The targets set for SAVI have been revised upwards over the course of the programme, and are judged by the review team to be sufficiently challenging and reflecting an appropriate level of ambition.

Overall outcome rating:

Outcome Indicator	Mid 2012 scores (midline)	Mid 2015 scores / (endline)	Mid 2015 targets	Best performing: (change in ratings from 2012 to 2015)	Worst performing: (change in ratings from 2012 to 2015)	Rating / (PCR team)
#1 / (SHoA)	All States: 2.45 / SLP: 2.65 / ZKY: 2.18 / A&N*: 2.16	All States: 3.12 / SLP: 3.33 / ZKY: 3.03 / A&N: 2.73	All States: / 3.2 / SLP: 3.6 / ZKY: 3.0 / A&N: 2.7	Yobe (2012: 2.18; 2015: 3.73) / Zamfara (2012: 1.55; 2015: 2.73) / Jigawa (2012: 2.64; 2015: 3.82) / Enugu (2012: 2.45; 2015: 3.55)	Katsina (2012: 2.82; 2015: 2.64) / Kaduna (2012: 2.64; 2015: 2.64) / Lagos (2012: 3.00; 2015: 3.27)	A
#2 / (CS)	All States: 2.37 / SLP: 2.84 / ZKY: 1.64 / A&N*: 2.32	All States: 3.22 / SLP: 3.58 / ZKY: 2.67 / A&N: 3.14	All States: / 3.5 / SLP: 4.2 / ZKY: 2.9 / A&N: 2.7	Yobe (2012: 1.55; 2015: 3.27) / Enugu (2012: 2.45; 2015: 3.75) / Anambra (2013: 2.09; 2015: 3.27) / Jigawa (2012: 2.82; 2015: 3.91) Katsina (2012: 1.73; 2015: 2.73)	Kaduna (2012: 2.91; 2015: 2.82) / Zamfara (2012: 1.64; 2015: 2.00) / Niger (2013: 2.55; 2015: 3.00) / Kano (2012: 3.09; 2015: 3.73)	B
#3 / (Media)	Mid 2013 (baseline) / All States: 2.94 / SLP: 3.14 / ZKY: 2.54 / A&N: 3.04	All States: 3.35 / SLP: 3.49 / ZKY: 3.13 / A&N: 3.35	All States: / 3.6 / SLP: 3.8 / ZKY: 3.5 / A&N: 3.2	Yobe (2013: 2.54; 2015: 3.23) / Enugu (2013: 2.92; 2015: 3.62) / Kano (2013: 2.92; 2015: 3.54) / Zamfara (2013: 2.31; 2015: 2.85) Katsina (2013: 2.77; 2015: 3.31)	Kaduna (2013: 3.23; 2015: 3.15) / Jigawa (2013: 3.38; 2015: 3.54) / Anambra (2013: 3.15; 3.46) / Niger (2013: 2.92; 2015: 3.23) / Lagos (2013: 3.23; 3.62)	B

#4 (Demonstrable Changes) / A = Total / B = Number reflecting the voice of women & other excluded groups / C = Number resulting from replication / D = Number occurring outside SAVI states	Late 2014 score / A = 89 / B = 50 / C = 46 / D = 3	End 2015 score / A = 157 / B = 97 / C = 74 / D= 8	End 2015 target / A = 93 / B = 43 / C = 31 / D = 8	Greatest number of demonstrable changes reported this year (2014/15) / Jigawa (12), / Yobe (10) / Niger (6)	Least number of demonstrable changes reported this year (2014/15) / Kaduna (1), / Kano (2), / Lagos (3)	PCR rating / A+

Reflecting the three stages of programme expansion, SLP states refer to Enugu, Jigawa, Lagos, Kaduna and Kano; ZKY states refer to Zamfara, Katsina and Yobe; A&N refers to Anambra and Niger.
* baseline scores from mid-2013 are used here for Anambra and Niger – 1 year later (less) than for the other states.
** averaged across equally weighted states and indicators: see SAVI 2015 Programme M&E Framework.

Commentary. There has been considerable variation in performance between states as measured by changes in the SAVI Governance Index (outcome indicators 1-3). Such differences can be expected given the diversity of political conditions in the states, which affect the potential for governance reform. These differences also reflect variations in SAVI’s approach which have evolved over time. There is a marked difference in between the original five SLP states, where SAVI began work in 2008, and the newer states introduced in 2011 and 2013. On average there have been greater and faster improvements in governance index scores for the newer states than the SLP states. SAVI have followed a more hands-off and flexible approach in the newer states, which has involved broader outreach to a wider group of civil society partners, less prescription in the selection of issues, greater use of multi-stakeholder advocacy partnerships (including representatives of civil society, media, State Houses of Assembly and MDAs), and the use of media programmes and Public Policy Dialogues as a tool to mobilise citizen engagement around locally defined issues. SAVI has also employed more effective ways of working in the newer states through better staff recruitment, team leadership, and closer adherence to technical guidance on the engagement and empowerment process and relationship management.

The improved performance in the new states reflects well on SAVI’s capacity for lesson learning and adaptation, and its ability to respond to DFID’s drive for low cost scale-up. However, there are also concerns that SAVI’s push to expand and test new models in the new states may have resulted in a loss of focus on improving performance in the original five SLP states. Over time it has become increasingly clear that the original approach was too focussed on providing intensive capacity building support to a few immediate partners and not sufficiently engaged with broader civil society. This has limited SAVI’s outreach and also resulted in cases where Advocacy Partnerships have become excessively dependent on SAVI support. SAVI has attempted to refresh its approach in the original SLP states by applying lessons from the new states. From the three states visited by the PCR team, there appeared to have been a turnaround in SAVI’s approach in Enugu, limited signs of change in Kaduna and no evidence of changed practices in Kano. According to SAVI, although milestones have been achieved, the approach (how the SAVI team worked) used in Lagos seemed to have left SAVI partners dependent on SAVI support (see Section C).

For outcome indicator 4, the largest numbers of changes in policy and implementation have been recorded in the original SLP states because these states have had longer to deliver results. However, results are already being recorded in the new states, in some cases more rapidly than in the original SLP states. Overall, Jigawa, Kano and Yobe have recorded the highest number of results under outcome indicator 4. The low number of new cases recorded since the 2014 Annual Review suggests a weakening of momentum in Kaduna, Kano and Lagos.

Since the last annual review SAVI has done further analysis categorising the outcome indicator 4 results. A large proportion of reported results (39%) relate to changes in government policy and practice. There are fewer instances of changes in budget allocation (9%) and budget release (8%). However, this year saw a marked increase in evidence of changes at the level of policy implementation (39% of the total results reported). 65% of the reported changes are relevant to gender and social inclusion issues and/or are reported to have strengthened the voice of women and other socially excluded groups.

Output Score and Description

Overall output score: A outputs met expectation.

Individual output scores (see part C for details):
Output 1: A+ (20%); Output 2: A+ (20%); Output 3: A+ (20%); Output 4: B (30%); Output 5: A++ (10%)

Lessons and How These Have Been Shared

SAVI has proven to be a valuable opportunity for experimentation, learning and adaptation on effective approaches to promoting voice and accountability. Some key lessons learned are highlighted below. The sharing of these lessons is discussed under output 5 in Section C below.

SAVI’s model of facilitated partnerships has proven to be effective, and results have been superior to what would have likely been achieved through a more traditional, challenge fund programme providing grants to civil society. The facilitated partnership approach has involved the avoidance of grants, provision of focussed technical assistance and mentoring, empowerment of partners to develop their own agendas and work plans (supported by limited SAVI funding linked to particular activities), and a behind the scenes role for SAVI brokering connections and facilitating networks.

SAVI’s approach to facilitating partnerships has evolved considerably over the course of the programme. There has been a shift away from providing very focussed and intensive support to a few select partners, to broader and more flexible engagement with citizens, civil society and other demand side actors. The latter approach has generally proven to be more effective.

SAVI has made considerable progress in strengthening connections between civil society, media and State Houses of Assembly. This has been critical to enabling more effective advocacy on a wide range of issues.

Early in the SAVI programme the focus of advocacy work was almost exclusively on upstream policy and planning issues, including the preparation of new legislation. This reflected an expectation that many of the downstream implementation issues would be addressed by DFID sector programmes (PATHS2 and ESSPIN). However, such linkages did not develop to the extent expected; with the result that SAVI’s focus on upstream policy engagement was not matched by a sufficient focus on downstream engagement. The focus on preparing new bills has delivered limited returns in the Nigerian context where the enforcement of laws has always been the principal challenge. Over time SAVI has rebalanced its focus to cover both upstream policy preparation, downstream implementation and monitoring and evaluation of results. This has helped to increase the effectiveness of the programme.

The use of political economy analysis (in the form of state level reports and staff’s tacit knowledge) has been critical to helping SAVI adapt to diverse state contexts and identify good opportunities to promote constructive policy engagement. However, there has been less use of problem focussed political economy analysis, which would have been useful to identify effective strategies to address particular policy problems and reform blockages. There are several examples of cases where problem driven PEA connected to more iterative and adaptive programme might have led to better results (e.g. the Wudil water group in Kano, who have experienced political resistance to their proposal to change water legislation in the state).

SAVI’s best results have usually been delivered in partnership with other DFID programmes (although some good results have been delivered by SAVI acting on its own). Linkages with other DFID programmes have often been critical to the effectiveness of SAVI supported work. Partnership with SPARC has been essential to bridge SAVI’s mainly demand-side approach to governance reform and SPARC’s mainly supply side focus. Partnership with sectoral programmes (PATHS2 and ESSPIN) has been important to provide SAVI’s Advocacy Partnerships with access to technical expertise on particular sectoral problems.

## C: DETAILED OUTPUT SCORING

Output Title	Civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring
Output number per LF		Output 1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress
Indicator 1.1 measures the strength of civil society partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring. / The indicator is based on a self-assessment tool completed by the Advocacy Partnerships (Partnership Capacity Assessment).	On a five-point scale, the mid 2015 target for the average PCA score across all Output 1 APs was set at: / SLP states: 4.1 ZKY states: 2.9 / A&N states: 1.6	In the SLP states (Enugu, Jigawa, Kaduna, Kano & Lagos) the average PCA score rose from 3.9 in late 2014 to 4.1 at mid 2015, meeting the set expectation. In the ZKY states (Zamfara, Katsina & Yobe) there was a significant increase in score from 2.9 to 3.5 over the same period, exceeding the set expectation. Likewise, in the A&N states (Anambra & Niger) where the score increased from 1.2 to 2.3 during the year under review. / Improvements against this indicator have been most significant in Niger, Kaduna, Anambra and Zamfara this year. Progress was recorded in all states with the exception of Lagos. / Rating A+
Indicator 1.2 measures the level of independence of the Advocacy Partnerships from SAVI using the same PCA tool as for indicator 1.1.	This was set at: / SLP states: 4.1 ZKY states: 2.8 / A&N states: 1.9	The average score across Output 1 APs for this indicator increased from 4.0 in late 2014 to 4.5 at mid 2015 in SLP states, moderately higher than expectation. The score increased from 2.9 to 3.6 in ZKY states between over the same period, and in A&N states the score increased from 1.5 to 2.9, far exceeding expectation in both sets of new states. / Improvements against this indicator have been most significant in Niger, Zamfara, Anambra and Kano this year. All states recorded an increase. / Rating A+
Indicator 1.3 records cases of replication where civil society partnerships that are not directly supported by SAVI have adopted aspects of the approach used by SAVI supported partners. Each count is recorded & evidenced in state replication diaries.	The collective target for all 10 states was set at: / 54	The combined cumulative number of ‘replication’ results to date against this indicator is 83 for all 10 states, far exceeding set expectation. This mid 2015 figure represents an increase of 22 results on top of a total of 61 reported in late 2014. / Improvements against this indicator have been most significant in Kano, Enugu and Jigawa this year. Only six states recorded an increment this year – there were no results recorded in Lagos, Zamfara, Yobe and Anambra. / Rating A++

SAVI continues to make good progress against all three output indicators, with the aggregated score for one having substantially exceeded expectation. An overall rating of A+ appears justified for this output.

Key points

Over the past one year, there has been steady progress against Output 1 indicators, and SAVI supported Advocacy Partnerships have gained in capacity and confidence. Over the past year there has generally been a faster increase in scores in the new states than in the original SLP states. Yobe, Anambra and Niger have performed particularly well. The differences between states reflect the following factors:

- Advocacy Partnerships are more mature in the SLP states, and there are diminishing returns to further support.
- In some of the SLP states, Advocacy Partnerships have become excessively dependent on SAVI support. This weakness is most extreme in Lagos, where the issue of inappropriate payment of short-term TA and per diems was highlighted in the 2014 Annual Review. SAVI Lagos has subsequently stopped making such payments resulting in a significant decline in the level of engagement between SAVI and its partners.
- SAVI has adopted a different approach to working with Advocacy Partnerships in the new states, characterised by a more inclusive, hands-off and flexible approach that is more focussed on network building, constituency outreach, use of the media and citizen mobilisation. This appears to be reflected in the good performance of the new states as measured by output 1 indicators.

There is a concern that the monitoring tools for output 1, the Partnership Capacity Assessment (PCA), is not well suited to SAVI’s new approach to working with Advocacy Partnerships that it has developed in the new states. The PCA is mainly focussed on measuring aspects of organisational development and skills acquisition within well defined groups. This was suited to SAVI’s original approach of working intensively with a few selected partners, but less appropriate to newer approaches that have shifted towards broader outreach to wider sections of civil society. New indicators will need to be developed for the successor programme to measure this more effectively.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 AR Recommendation	Action taken by SAVI
R1) Complete an internal evaluation of key aspects of SAVI’s performance by end June 2015 including comparison of the approaches used to promote issue-based advocacy in different states and their relative effectiveness focussing particular on apparent differences between the original 5 SLP states and the new states (Zamfara, Katsina and Yobe). Consider whether output indicators 1.1 and 1.2 require modification in the light of adaptations to SAVI’s approach.	Completed. No formal internal evaluation document, but numerous discussions held on the issue during Technical Group Meetings and cross-state learning events. SAVI leadership fully aware of different approaches used in different states.
R2) Include in the internal evaluation a study of the relative effectiveness of different approaches to replication. One source of evidence could be an online or telephone questionnaire sent to organisations who may have been influenced by SAVI (repeat of 2013 recommendation).	Partially completed. Replication issues discussed in Technical Group Meetings and measured using replication diaries. No formal survey conducted.
R3) Conduct a review of the extent to which members of Advocacy Partnerships have benefitted from per diem payments and low rate consultancy fees, and whether this has distorted incentives and undermined group independence and sustainability. Develop clear guidelines on the use of such payments.	Completed. State visits and Technical Group Meetings used to address the issue. Comprehensive guidelines on ‘payments to partners’ in line with SAVI’s preferred technical approach in place since 2015. Implementation of guidelines in most states (including Lagos), although information gaps remain in Zamfara and Jigawa.
R4) Undertake a review post-elections of whether new issues have gained political traction and popular interest and whether it will be possible to address these through existing, modified or new advocacy partnerships. This should be part of a broader revision of state level political economy analyses to be undertaken jointly with SPARC.	Partially completed. Post-election political economy analyses conducted jointly with SPARC in 2 stages. These have mainly been broad brush rather than drilling down to specific issues and problems.

Recommendations for future programmes

R9) Adopt and further develop the approach to working with Advocacy Partnerships that SAVI has developed in the new states. Since PSAGP will be focused on the SLP states, working methods in these states will need to be adapted to take on board lessons learned from the new states. PSAGP should continue to support viable Advocacy Partnerships, but should discontinue practices that have led to excessive dependency on SAVI.

R10) The successor programme should be able to provide a more diverse and graduated set of instruments to work with advocacy partners at different stages of organisational development to cater for different types of relationships with the programme (hands on or arm’s length support). Very selective use of grants could be made for well capacitated partners, where this will contribute to rather than distort their own agenda.

R11) The new programme should identify new issues and partners to work with on the basis of broad outreach to civil society using tools such as using media programming and public policy dialogues. The portfolio of issues should include some of the issues covered by SAVI, but should shift towards addressing more challenging issues relating to economic management, the fiscal crisis, private sector development and anti-corruption.

R12) PSAGP should develop new tools for monitoring capacity building and policy engagement by civil society in line with the recommended shift towards broader outreach and flexible partnerships around a broader set of issues. This should draw on experience gained from the use of SAVI’s Partnership Capacity Assessment, but should be more suited to measuring changes across a broader set of partnerships.

Output Title	Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes.
Output number per LF		Output 2	Output Score	A+
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress
Indicator 2.1 measures the strength of Output 2 Advocacy Partnerships in terms of their internal capacity, external relations and skills in engaging state budget and planning processes. / The indicator is based on the Partnership Capacity Assessment tool used for Output 1.	On a five-point scale, the mid 2015 target for the average PCA score across all Output 2 APs was set at: / SLP states: 3.7 ZKY states: 3.3 / A&N states: 1.5	The average PCA score rose to 4.4 (increase from 3.9 in late 2014) in SLP states by the end of 2015, and to 3.9 (increase from 3.3) in ZKY states and 2.2 (from 1.1) in A&N states. / Improvements against this indicator this year have been most significant in Niger, Kano and Zamfara. Progress was recorded in all 10 states, though minimal in Jigawa and Enugu. / Rating A+
Indicator 2.2 measures the level of independence of the Advocacy Partnerships from SAVI using the same PCA tool as for indicator 2.1.	This was set at: / SLP states: 4.0 ZKY states: 3.1 / A&N states: 1.4	The average score across the APs for this indicator increased from 3.8 in late 2014 to 4.5 at the end of 2015 in SLP states and from 3.0 to 3.7 in ZKY states, and from 1.0 to 2.0 in A&N states. / Improvements against this indicator this year have been most significant in Niger, Zamfara, Kaduna and Kano. Progress was recorded in all 10 states, though minimal in Jigawa, Yobe and Anambra. / Rating A+
Indicator 2.3 records cases of demonstration and replication where civil society partners supported by SAVI under Output 2 provide direct support to partnerships and platforms supported and replicated under Output 1 to engage state budget and planning processes. Each count is recorded & evidenced in state replication diaries.	The collective target for all 10 states was set at: / 54	SAVI reports 68 replication results so far in SLP & ZKY states combined in 2015 (increase from 59 results reported in late 2014) under this output. Anambra and Niger are yet to record any replication results. / Improvements against this indicator have been recorded this year in Kano and Lagos. Jigawa, Kaduna and Yobe recorded a slight increase, but none in Enugu, Zamfara and Katsina. / Rating A+

SAVI has made good progress against all three output indicators, with most of the aggregated scores having moderately exceeded expectation. An overall rating of A+ appears justified for this output.

Key points

Following the recommendation in the 2013 Annual Review, SAVI has increased its focus on downstream issues of budget and policy implementation under Output 2. This includes work on expenditure tracking, monitoring the delivery of services on the ground and completion of public works. The original model developed by the Project Monitoring Partnership in Jigawa has served as a demonstration to others: e.g. the APaGG group in Enugu and the Budget Tracking Partnership in Yobe. While moving into these downstream areas, SAVI has also sought to maintain a focus on upstream budget planning. SAVI maintains that its most effective Advocacy Partnerships working on output 2 have sought to cover the budget process in a holistic way covering both upstream planning and downstream implementation. An effective balance appears to have been struck in Yobe, Anambra and Niger.

There has also been a shift towards involving citizens more directly in budget and project monitoring processes. For example, the Know Your Budget partnership in Kaduna, has organised a series of zonal town hall meetings to discuss local development priorities, which are then fed into state level advocacy processes. In Anambra SAVI has entered into a partnership with the Voices to the People (V2P) project working with Town Unions to develop Community Action Plans (Charters of Demand) that SAVI partners have helped to feed into state level budget and planning processes through the State House of Assembly, media and civil society groups. There is also considerable potential to strengthen linkages between SAVI supported output 2 partnerships and the M4D project in Kaduna, Kano and Jigawa. This could enable more effective community participation in LGA budgeting and project monitoring. Following on from the recommendation of the 2014 Annual Review, the PCR team noted that collaboration between SAVI and M4D has been improving, but there have not been many joint initiatives focussed specifically on local budget and planning processes. In Jigawa the SAVI supported Project Monitoring Partnership has been active in LGAs where M4D is working, and is increasingly connected with Community Based Organisations working with M4D on local budget and planning issues.

Summary of responses to issues raised in previous annual reviews

Under the 2014 Annual Review the recommendations for Output 1 were also applicable to Output 2. See the preceding section for details on the extent of adoption of these recommendations. Two additional recommendations were proposed for Output 2.

2014 AR Recommendation	Action taken by SAVI
R5) Continue exploring opportunities to strengthen civil society engagement in monitoring downstream budget and policy implementation including expenditure tracking, monitoring the delivery of services on the ground and completion of public works. Include an assessment of the relative effectiveness of alternative approaches in the proposed internal evaluation.	Completed. The effectiveness of different approaches to output 2 work has not been formally evaluated, but issues have been discussed in depth by State teams at Technical Group Meetings. There has been a shift in the focus of output 2 towards downstream budget implementation. However, SAVI has rightly sought to maintain a balanced approach covering both upstream budget planning and downstream implementation.
R6) Step up SAVI’s work linking community level groups and service user groups to state level policy, budget and planning processes. This should usually be conducted in partnership with other programmes. There is a particular opportunity for joint working with M4D, which should be urgently explored.	Partly completed. SAVI’s work with V2P in Anambra state has demonstrated an effective model for linking community level engagement to state level budget processes. Collaboration between SAVI and M4D has been improving, but there have been few examples of joint programming relating to budget and planning processes (exception Jigawa – see above).

Recommendations for future programmes

R13) The PSAGP should continue to work on budget and planning processes. Reflecting lessons learned from SAVI, a balanced approach is required combining engagement in upstream budgeting and planning and downstream monitoring of budget releases and project implementation.

R14) Future work on budgeting, planning and project monitoring should emphasise the need for civil society groups to facilitate broad citizen participation rather than restricting these activities to narrowly defined advocacy groups.

R15) The future programme should increasingly link its budget, planning and project monitoring work to community level engagement and engagement with local government. The partnership with V2P should be scaled up as proposed recognising that a measured and realistic approach is required to programming in new states outside of Anambra. Collaboration with M4D on local government planning processes should be enhanced.
Output Title	More open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government
Output number per LF		Output 3		Output Score		A+
Risk:		Medium		Impact weighting (%):		20%
Risk revised since last AR?		No		Impact weighting % revised since last AR?		No
Indicator(s)			Targets		Progress
Indicator 3.1 measures the cumulative number of partnerships using SAVI approaches that are supported by leadership in civil society, the media, State Houses of Assembly and government. This is now measured by SAVI partners through use of their PCA self-assessment tools (which included a supplementary sub-indicator).			The collective targets for all 10 states were set at: / institutionalising: 20 / promoting: 47 / facilitating: 70 / permitting: 84		SAVI reports that 30 partnerships and platforms now receive a level of leadership support strong enough to be viewed as ‘institutionalising’. On lower levels of leadership support, all targets were exceeded with 93 partnerships receiving promotional support, 112 receiving facilitative support and 120 receiving permissive support. / Significant improvements for this indicator have been observed this year in Kano, Enugu, Niger and Jigawa. Least progress was recorded in Lagos, Katsina and Kaduna. / Rating A++
Indicator 3.2 measures the cumulative number of partnerships and platforms using SAVI approaches (including SHoAs and directly supported media houses) that are progressively including the voice of women and other socially excluded groups in the context of their work. This is now measured through use of a supplementary PCA tool administered by partners engaged in promoting gender and social inclusion.			The collective targets were set for all 10 states at: / institutionalising: 25 / promoting: 43 / facilitating: 64 / permitting: 78		Progress against this indicator appears to be ahead of target at the lower levels (promoting, facilitating and permissive support), but still falls short of the target at the highest level (institutionalising). SAVI reports that only 22 partnerships and platforms in 2015 had ‘institutionalised’ the voice of women and other socially excluded groups; while 75 partnerships were ‘promoting’ their voice; 97 were providing ‘facilitative’ support; and 104 were providing ‘permissive’ support. / Large improvements under this indicator have been recorded this year in Kano, as well as Enugu and Jigawa. Least progress was recorded in Katsina, Lagos and Zamfara, with a slight drop in numbers in Katsina and Lagos. / Rating A
Indicator 3.3 measures the extent of public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability. This is now measured by partners through use of their PCA self-assessment tools, and through a standardised ‘civic education’ data collection and analysis tool for citizens.			The aggregated targets were set at: / SLP states: / 77% for partners 69% for citizens / ZKY states: 75% for partners 50% for citizens / A&N states: 59% for partners 79% for citizens		SAVI reports that 83% of partners (up from 76% in 2014) and 90% of citizens (up from 73% in 2014) in SLP states have an acceptable level of understanding in 2015. While in ZKY states the figures are now 70% of partners (up from 65% in 2014) and 81% of citizens (up from 62% in 2014), and in A&N states are now 67% of partners (up from 44% in 2014) and 73% of citizens (slightly up from 72% in 2014). / Improvements against this indicator have been most significant in Niger, Kano and Jigawa among partners and in Kaduna, Katsina and Jigawa among citizens this year / Rating A+
Indicator 3.4 measures the strength of SAVI supported media partners’ internal capacity, external relations and programing skills in supporting other partners’ achievement of their objectives under all 5 outputs through use of media. Baselines were established in 2012 using a media OCA tool.			On a five-point scale, the mid 2015 target for average Media OCA scores was set at: / SLP states: 4.1 ZKY states: 3.2 / A&N states: 3.2		The average media OCA score for all SAVI-supported media partners by mid 2015 was 4.1 in SLP states (up from 4.0 in late 2014), 4.1 in ZKY states (up from 3.6 in late 2014) and 3.8 in A&N states (up from 2.8 in late 2014). / Improvements against this indicator have been most significant in Niger, Yobe and Kano this year. / Rating A+

SAVI has made good progress against these output indicators, with all scores meeting or exceeding targets. An overall rating of A+ appears justified for this output.

Key points

A major contribution of SAVI’s work under output 3 has been to strengthen relationships between civil society, media and State Houses of Assembly. There is evidence from most states that these three groups of actors are interacting much more regularly and engaging jointly on policy issues as a result of SAVI support. The model of the Voice and Accountability platform, bringing together influential individuals from civil society, media and the State House of Assembly, as well as the executive, has proven to be particularly effective in strengthening relationships and facilitating constructive engagement. The Voice and Accountability Platform in Kano and Niger are particularly strong in this respect, and good progress has been made in Enugu and Jigawa. In Kaduna and Lagos it has proven more challenging to develop strong relationships between civil society, media and State Houses of Assembly.

SAVI’s work with media organisations has become increasingly effective in building media capacity to mobilise the media to report on governance issues and connect citizens to policy discussion. In 2015, initial support from SAVI stimulated numerous examples of innovative media programming covering governance and policy questions. SAVI supported media organisations played an effective role in promoting voter education and facilitating electoral debates. In spite of these clear successes, there is a sense that SAVI has been quite slow to realise the potential of media work, which did not begin in earnest until after the mid-term review. The use of the media as a strategic partner to identify salient issues and to mobilise citizen engagement around these has mainly been evident in the new states. There is considerable potential to learn lessons from this experience and scale up media work further under the successor programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 AR Recommendation	Action taken by SAVI
R7) Step up engagement with the media in the pre-and post-election period to train and mentor media houses on covering election processes, and encourage additional programming on key policy questions, including interviews and phone ins with prospective candidates and incoming administrations (possibly following the model of the Public Policy Dialogues). SAVI may opt for a big push in media engagement in the election period, which may require budget and staff reallocation (in particular as SAVI has just lost one Media Development Specialist). In working with the media during this sensitive period, SAVI will need to stress its apolitical role, and encourage responsible discussion of issues of policy substance rather than personalities and political intrigue.	Completed. At least 3 state teams have supported open debates with candidates, and others have mobilised media during the election period to support voter education and policy debate through civic education programmes.
R8) Investigate the reasons for the large jump in civic education scores recorded under indicator 3.3.	Completed. The change in scores appears to relate to state teams more rigorously following the assessment methodology.
R9) As part of the proposed internal evaluation conduct a study on different approaches used by SAVI and partners to promote civic education, and their relative effectiveness. Consider opportunities to apply techniques of social marketing to civic education.	Not completed. Comparative study of approaches to civic education not yet completed. Assessment of opportunities to use social marketing limited to consultations with V4C and initial internal reflection.

Recommendations for future programmes

R16) PSAGP should build on valuable experience gained from SAVI’s engagement with the media. PSAGP pillar 2 should devote a greater share of its resources to media work than under SAVI. This should include traditional media, as well as social media and social marketing using ICTs. The approach should include capacity building for individuals (media practitioners) and organisations (engagement with media executives and owners), as well as promoting the ability of traditional media to interact with citizens. M&E indicators should be redesigned to focus on measuring the effectiveness of media work in promoting citizen engagement in governance processes and encouraging government responsiveness. There should be less emphasis on monitoring organisational development of media houses (the current focus of OCA scoring).

R17) PSAGP should continue SAVI’s work in linking actors from civil society, media and State Houses of Assembly, as well as reform minded actors in the executive. Innovative practices developed by SAVI, such as V&A platforms should be further developed and replicated. More relevant indicators should be developed to measure the strength of these relations than has been the case under SAVI’s output 3 (see indicator 3.1).

Output Title	Improved systems of transparency, public engagement and financial oversight in state houses of assembly
Output number per LF		Output 4	Output Score	B
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress
Indicator 4.1 measures the level and quality of systems for recruitment and retention of house support staff and aides. / Scores are derived from an annual Organisational Capacity Assessment (OCA) for this indicator and 4.2, 4.3 and 4.4.	On a five-point scale the mid 2015 target for the average SHoA OCA score was set at: / SLP states: 3.5 ZKY states: 3.4 / A&N states: 2.1	The average OCA score for this indicator fell from 3.3 in late 2014 to 2.8 in mid 2015 in SLP states, and from 3.8 to 2.6 in ZKY states. Meanwhile, A&N states recorded a modest increase in score from 1.3 in late 2014 to 1.9 by mid 2015. / Only Enugu, Niger and Anambra recorded progress this year. No improvement was recorded in Lagos and Yobe, while the average scores dropped in all other states – significantly in Katsina, Jigawa and Kaduna. / Rating B
Indicator 4.2 measures the level of quality of systems for induction and monitoring of compliance with House rules and procedures.	This was set at: / SLP states: 4.2 ZKY states: 3.8 / A&N states: 3.0	The average OCA score for this indicator fell from 4.3 in late 2014 to 3.6 in mid 2015 in SLP states, and from 4.3 to 3.7 in ZKY states. Meanwhile, A&N states recorded a modest increase in score from 1.8 in late 2014 to 2.3 by mid 2015. / Greatest progress was recorded in Lagos, Yobe, Niger and Anambra this year. The average scores dropped in all other states except Enugu, dropping significantly in Jigawa, Kaduna and Katsina. / Rating B
Indicator 4.3 measures the level and quality of systems for public access to information and processes in the House and representation of public interests by members.	This was set at: / SLP states: 3.1 ZKY states: 3.2 / A&N states: 1.9	The average OCA score for this indicator fell from 3.5 in late 2014 to 3.0 in mid 2015 in SLP states, and from 3.7 to 2.7 in ZKY states. However, A&N states score increased significantly from 1.1 in late 2014 to 2.3 by mid 2015. / Good progress was recorded in Niger this year, with marked improvements also in Anambra and Kano. Average scores dropped in all other states except Zamfara and Yobe, dropping significantly in Katsina, Jigawa and Lagos. / Rating B
Indicator 4.4 measures the level and quality of systems for scrutinising public financial documents in the House.	This was set at: / SLP states: 3.4 ZKY states: 3.2 / A&N states: 1.8	The average OCA score for this indicator fell from 3.5 in late 2014 to 3.2 in mid 2015 in SLP states, and from 3.5 to 2.5 in ZKY states. However, A&N states score increased significantly from 1.3 in late 2014 to 2.1 by mid 2015. / Greatest progress was recorded in Niger, Enugu and Kaduna this year. Average scores dropped in all other states bar Anambra and Yobe, dropping significantly in Katsina, Jigawa and Kaduna. / Rating B
Indicator 4.5 measures the cumulative number of house committees and state houses improving the quality of their systems based on approaches initially demonstrated with SAVI support. Each count is recorded and evidenced in state replication diaries.	The collective target for all 10 states was set at: / 73 committees / 40 houses	As of mid 2015, SAVI reports improvements in 81 house committees and 45 state houses, up from 65 and 38 respectively in late 2014. / Greatest progress was recorded this year in Niger and Yobe on improving house committees, and in Katsina and Kano on improving neighbouring state houses. Little or no progress was recorded on either in all the other states. / Rating A+

Although there have been some improvements in output 4 indicators in some states (Niger, Anambra, Enugu and Yobe stand out as good performers), overall performance has been disappointing and average scores have declined. An overall rating of B appears justified for this output.

In spite of disappointing score for this output, it must be emphasised that over the course of the SAVI programme, there has still been a measurable improvement in the capacity and systems of State Houses of Assembly. While the State Houses of Assembly have yet to fulfil their potential to hold the executive to account, SAVI has demonstrated that good results can be achieved in a very challenging institutional context where state legislatures are generally regarded as having been co-opted and drawn into the patronage system.

SAVI attributes this poor performance mainly to the 2015 legislative elections. The protracted period of election campaigning has diverted the attention of members of the State House of Assembly away from performing legislative oversight function towards partisan politicking. Newly elected members tend to be less conversant with legislative systems and roles, in spite of induction training provided by SAVI and State Houses of Assembly. At the same time changing leadership of many State Houses of Assembly and competition for political control have resulted in revisions to house rules eroding SAVI-supported progress to date.

Another reason for lack of progress has been the stalling of key pieces of legislation designed to increase the autonomy of State Houses of Assembly. Prior to elections, the Constitutional Review process failed to secure financial autonomy for State Houses of Assembly. Post elections, there has been a noticeable increase in executive interference in administrative appointments to State Houses of Assembly, which undermines House Service Commission legislation.

Summary of responses to issues raised in previous annual reviews (where relevant)
2014 AR Recommendation	Action taken by SAVI
R10) Explore options for further development of federal level work in support of State Houses of Assembly. In the light of possible engagement with the National Assembly through the successor programme explore options for joint programming with FEPAR and DDiN relating to the National Assembly.	Mainly completed. As part of its federal engagement strategy, SAVI has further developed its collaboration with the Conference of Speakers and Chamber of Clerks and other national level bodies providing support to State Houses of Assembly. Discussions with FEPAR and DDiN have taken place on support to the National Assembly and SAVI and FEPAR have jointly completed a political economy analysis of the National Assembly.
R11). Continue to follow-up progress on the constitutional review process with respect to SHoA autonomy, and draw on the lessons learnt from those SHoAs that have already established their own budget lines on challenges and opportunities to strengthen systems for self-accounting and financial transparency.	Completed. The Constitutional Review failed due to lack of Presidential assent. SAVI considers that the process has still been valuable in drawing attention to the issue of financial autonomy for State Houses of Assembly, and supportive constituencies could be reactivated in future.
R12) Within three months of the February elections conduct an assessment of the political makeup of the legislatures, identifying opportunities and constraints for SAVI support. Undertake this work as part of broader state level political economy updates to be conducted jointly with SPARC.	Completed as part of joint SPARC-SAVI Political Economy Analysis of the states.

Recommendations for future programmes
R18) During the PSAGP inception conduct a broad and self-critical reflection with members and staff of State House of Assembly on the results of the SAVI partnership, what has worked and what hasn’t.

R19) In future ensure a balance between working to support internal SHoA systems and strengthening external relations between the State House of Assembly, constituencies and media. During SAVI the emphasis has tended to be more on the former than the latter.

R20) Ensure that future support to State Houses of Assembly is provided in support of a mutually agreed set of activities defined in an MoU and Action Plan setting out responsibilities of each party. This should draw on good practice developed by SAVI (e.g. linking SAVI support to Enugu SHoA Legislative Term Agenda)

R21) Ensure that future support to State Houses of Assembly is not limited to occasional training events, but includes regular interaction and mentoring in support of a jointly agreed programme of support.

R22) Assess the impact of the unsuccessful attempt in 2014/15 at national level to secure greater financial autonomy of the state legislatures (and also auditor generals) through the constitutional review and national conference processes on the relationship between the executive and legislature in each state – and draw lessons for future work on strengthening federal/national-state linkages.

Output Title	Other development partners take a more sustainable and replicable approach to strengthening voice and accountability
Output number per LF		Output 5	Output Score	A++
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Targets	Progress
Indicator 5.1 measures the cumulative number of other development partners (as individuals) accessing and taking-up relevant and useful lessons learnt by SAVI and its local partners. Each count is recorded and evidenced in state replication diaries against a 5-point scale.	Mid 2015 targets for all SAVI teams (including Abuja and UK teams) were set at total: / attempting: 52 / planning: 63 / participating: 97 / interested: 169	SAVI reports show by mid 2015 there were 78 other development organisations within which individuals were taking-up relevant and useful lessons from SAVI to the level of ‘attempting’ to apply the learning/approach in the context of their own activities (up from 55 in late 2014). On lower levels of uptake – ‘planning’ to apply the learning/ approach (up from 67 to 113), participating in the learning/approach (up from 103 to 170), and interested in the learning/approach (up from 174 to 230) – all 2015 targets were also exceeded. / Rating A++
Indicator 5.2 measures the cumulative number of firm commitments by other development partners (as organisations) to replicate key aspects of SAVI and its local partners’ approaches. Each count is recorded and evidenced in state replication diaries against a 5-point scale.	Mid 2015 targets were set at total: / institutionalising: 17 / promoting: 35 / facilitating: 56 / permitting: 89	SAVI reports that by mid 2015 there were 31 firm commitments made by other development organisations (as whole organisations) to ‘institutionalise’ the learning/approach taken-up from SAVI (up from 14 in late 2014). On lower levels of commitment – organisational ‘promotion’ of uptake of the learning/approach (up from 30 to 67), ‘facilitation’ of uptake (up from 57 to 107), and ‘permission’ to uptake (up from 82 to 131) – all 2015 targets were also exceeded. / Rating A++
Indicator 5.3 measures the depth of each commitment reported under Indicator 5.2. Each count is recorded and evidenced in state replication diaries against a 5-point scale.	Mid 2015 targets were set at total: / core values underpinning every aspect (‘roots’): 8 / core strategic aspects (‘trunk’): 23 / whole practical aspects (‘branches’): 50 / practical tools/ strategies (‘twigs’): 73	SAVI reports that by mid 2015 there were 21 firm commitments made by other organisations (as whole organisations) that reflect the core values underpinning every aspect of SAVI’s learning/ approach (up from 6 in late 2014). On lower levels of depth of commitment – core strategic aspects (up from 18 to 42), whole practical aspects (up from 43 to 64), practical tools/strategies (up from 56 to 83) – all 2015 targets were also surpassed. / Rating A++

SAVI has made significant progress against all three output indicators, with most of the scores having substantially exceeded expectation. A rating of A++ appears justified for this output.

Key points

Output 5 indicators point to an increasing number of development projects and partners in Nigeria adopting elements of SAVI’s approach. At state level, this is particularly evident this year in Kano, Kaduna and Katsina, where there has been the greatest number of organisational commitments to date (5 per state) to institutionalise the learning and approach of SAVI in the course of replication.

SAVI has also become more influential at national level and outside Nigeria. In the past year SAVI has uploaded more high quality communications materials (case studies, think pieces, approach papers and resources / programme tools) onto its “online knowledge sharing platform” (i.e. website www.savi-nigeria.org). More interactive face-to-face communications work in the UK and the US has earned the programme greater international attention. SAVI continues to participate in discussions on ‘new direction in governance’ and ‘doing development differently’ as an example of politically smart, locally led, problem driven iteratively adaptive development practice, backed by a growing community of thinkers and practitioners spanning the UK and US (led by the ODI and Harvard University).The programme participated in global debates on ‘social accountability’ (organised by GPSA in Washington), as a leading case study, which has attracted the attention of USAID and others.

Summary of responses to issues raised in previous annual reviews (where relevant)

2014 AR Recommendation	Action taken by SAVI
R13) Work with DFID to develop a common set of cross programme guidelines on good practice in promoting voice and accountability in order to promote more harmonised approaches and avoid programmes working at cross purposes.	SAVI has continued to promote good practice and engage with other projects to address weaknesses in their approaches to V&A work. However, no cross programme guidelines have been developed. To be taken up by PSAGP.
R14) Continue to develop knowledge management products on the SAVI website. Ensure that online material is organised in a form that can easily be transferred to the successor programme.	Largely completed. Numerous additional materials have been uploaded to the website over the past year.

Recommendations for future programmes

R23) Recognising that SAVI has already achieved considerable external influence, consider whether it is still useful to track individual cases of replication. Develop jointly with PSAGP pillar 3 a broader influencing strategy to communicate the value of citizen engagement in policy processes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The cost structure at the end of the project duration was as follows: TA fees (49%); programme activities (24%); operating costs which include daily living costs, office running costs and airfares (23%) with the remaining 4-5% on management costs paid using milestone payments. For the successor programme there is potentially room to reduce spend on some of the categories: for example, almost half of the expenses under operating costs (and 11% of total spend) was office running costs, and this could be reduced by co-location with other DFID projects in the states.

The high percentage of costs on TA reflects SAVI’s model of delivering change through facilitated partnerships, which require large time inputs from experienced staff. SAVI has been able to economise on TA costs by relying mainly on long-term, locally recruited staff and limiting the use of short-term and international consultants. Long-term TA costs have made up over 87% of total TA costs. An average 66% of short term TA days were used by national consultants, against 34% international. SAVI’s TA costs are similar to or lower than other DFID Nigeria governance programmes.[2]
[2] For example, FOSTER recorded 48% (December 2014), SPARC 59%.

VfM performance compared to the original VfM proposition in the business case

The VfM proposition of the governance SLP suite (SAVI and SPARC) is to achieve equivalent or greater improvements in the use of Nigerian resources measured in terms of reduced losses through corruption and waste and more productive use of expenditure, in a strategic way towards the longer-term change. An underlying assumption is that small improvements in the governance public resources have the potential to deliver significant returns for the government of Nigeria and Nigerian citizens. This logic remains valid.

The following points present highlights of SAVI’s recent VFM reports.

Economy:

- Downward trends in fees (particularly in long-term and short term national) and in the use of STTA from 9% at the start of the programme to only 4% by close.
- Final average fee rates on national and international consultancy rates are lower than, or within the range of external benchmarks available.[3] Good practices recorded such as benchmarking of fees across Palladium programmes.
  [3] DFID PEAKS bands, FOSTER programme, FEPAR, other SLPs such as GEMS.
- Evidence of cost savings through adherence to good procurement practices.

Efficiency:
- Increases in output scores have been achieved more quickly and at lower cost in the new states than in the original SLP states. This analysis has been very useful in terms of highlighting inefficiencies and incentivising evidence-based reflection, learning and planning in SLP teams to improve VfM performance.
- In the 2012 Business Case, as part of the 9 measures, a ratio of 80% to 20% for frontline delivery vs administrative costs was set as a target. What emerges however is close to 70% to 30%.
- Over 100% total budget utilization is expected by the end of the programme, which represents good spending and financial management performance.

Effectiveness:

- SAVI’s VFM effectiveness scores measure changes in outcome indicators compared to spending by state and by year. This again shows better value for money in the new states than the original SLP states. Although there are challenges attributing changes in outcome scores to SAVI intervention, the markedly different pattern of results and expenditure in these two groups of states provides further evidence that VFM has been greater in the new states than the original SLP states (see chart below of the relative VFM effectiveness)
- SAVI’s Case studies and the Results Evidence Sheets trackers provide useful VFM evidence at effectiveness level although it has proven challenging to quantify costs and benefits in financial terms.
- SAVI is widely credited, by stakeholders and practitioners in and outside of Nigeria, with innovative ways of working with civil society in Nigeria and this is of significant value.
- SAVI has worked effectively with other programmes including SPARC, V2P, and M4D among others. Some estimates of financial savings resulting from this collaboration are provided in quarterly reports.[4] This is a good VfM practice to highlight, as well as being one of the 9 key measures which SAVI performed well against.
  [4] This is different from ‘counterpart’s contribution where SAVI had challenges to quantify contributions, mainly intellectual, from their partners in media and civil society. What is referred to here is the tracked cost savings in various collaborations, for example with V2P.

VFM effectiveness compared by state

Notes: The lines indicate how SAVI governance index scores (outcome indicators 1-3) have changed in each state as cumulative SAVI expenditure has increased. Generally, the new states (especially Anambra, Katsina, Niger and Yobe) have witnessed a greater increase in outcome score for a lower expenditure.

Equity:

The strongest evidence of SAVI’s results in addressing gender and social inclusion is provided by outcome indicator 4, which counts “demonstrable changes in policy and implementation by state governments in response to public demand where there is evidence of attribution to SAVI.” Of the 157 case studies, 97 (65%) related to changes that are relevant to gender and social inclusion. 39% of the case studies provided evidence of government actively promoting the voice of excluded groups, with a further 5% reflecting government action that serves to institutionalise their voice.

The following examples provide a small selection of results recorded under outcome indicator 4 that are relevant to gender and social inclusion.

Jigawa (2013) Jigawa is the first Northern Sharia State to pass its own Gender Policy. This led to the incorporation of inputs from women into the State’s Comprehensive Development Framework (CDF) in 2014.

Kano (2015) Kano State Government disbursed NGN41M (£164,000) to all 44 LGCs to cover the first instalment of monthly allowances for PWDs. This is an implementation of the earlier budget allocation for PWDs reported in 2014 following a series of advocacies by the SAVI-supported Gender and Social Inclusion Advocacy Partnership.

Kaduna (2014) for the first time, the Kaduna State Ministry of Women Affairs developed a 4-year strategic plan with assistance from SAVI-Supported Gender Working Group.

Assessment of whether the programme represented value for money
There is strong evidence that SAVI has generated sufficient benefits to justify the £33m invested judged from two key perspectives.
Firstly, SAVI has recorded several cases where an estimated £37 million worth of financial benefits can be identified in terms of reduced waste of public resources and the reallocation of public resources towards more productive ends.[5] There are also examples where joint work with SPARC closed down space for corruption. For instance, joint work between SPARC and SAVI led to substantial procurement reforms in Enugu State. By improving the way in which tenders and bids for contracts were scrutinised, using price intelligence, and ensuring necessary rules were adhered to, NGN17.5 billion (£46 million) was saved in 2012 and 2013.
[5] SAVI final VFM case study analysis 2016 – note that there are limitations on VFM calculations for voice and accountability programmes where benefits often do not lend themselves to quantification. It is therefore prudent to put ‘health warnings’ that financial attribution needs to be taken as indicative rather than definitive.

Secondly, the significant contribution that SAVI played towards the longer term identifiable improvements of governance at state level particularly in strengthening the voice of citizens including the poor and marginalised. By virtue of its work to strengthen the functionality of civil society, media and State Houses of Assembly, citizens’ voice can now be channeled into state level policy and processes.

Quality of financial management during programme
By adhering closely to financial forecasts and the overall budget, SAVI’s actual spend came to £32,432,838.47 as against a total budget of £33.7 m. SAVI has demonstrated very good financial management.

Milestone based payments replaced direct billing of management costs in 2013/14. These have been paid in full to date with the variance reflecting adjustment in the scheduled payments of some of the milestones compared to the original budget and payment schedule during the reporting period.

All DFID reporting requirements have been met, and have been approved by DFID and the service provider Palladium. This includes monthly reporting of unit costs of expenditure on staff costs for invoicing, revised monthly financial forecasts, updated procurement plan, quarterly assets and conflict of interest declaration, six-monthly programme assessments for DFID and internal programme reviews.

An external audit was not undertaken during 2014-15 due to the previous high levels of compliance. All recommendations from the 2013-14 audit were implemented. A closure audit was carried out covering the last financial year, that is the period from April 1st 2015 to March 31st 2016 with an unqualified opinion expressed by the external Auditors.

Date of last narrative financial report	March 2016
Date of last audited annual statement	Closure audit for the period 1st April 2015 to 31st March 2016 – signed off.

## E: RISK

Quality of risk management over the life of the programme

Security of programme staff and assets

SAVI routinely updates security procedures as part of the general security architecture for the programme. A full time (cost-shared with other Palladium projects) security manager has been in post since mid-2012. Additional security requirements (e.g. upgrading of office structures and the formulation of “enforceable” operating instructions) were necessary given the intensity of Boko Haram attacks from late 2011 to early 2015 in northern States, and criminality in the Middle Belt and SS, SE and SW Regions. Support was given to all drivers with Defensive Driver Training, to all staff with Hostile Environment Awareness Training (HEAT), Roadside First Aid Training, and skills development for State Teams around conflict sensitivity, daily / weekly security assessments and subsequent trend analysis. Close collaboration was also established with DFID Regional Representatives, Advisers and Risk Management Team to proactively address potential security risks and required mitigation responses on a monthly basis.

Programmatic risks

Intimidation of SAVI-supported partners was mitigated by the adaptation of their advocacy strategies to avoid confrontation and promote collaborative engagement. SAVI has exercised sensitivity in the selection of issues and partners and has avoided working with particularly contested issues and controversial actors. SAVI has carefully adapted its work around elections according to its assessment of risks. SAVI also maintained a close working relationship with other programmes, and DFID at state level, which has been useful to assess political and security risks.

Fraud and corruption

SAVI does not provide grants to partners and therefore avoided associated fiduciary risks. To avoid fraud and corruption, good quality financial management systems and controls were put in place and regularly updated, to accommodate revisions in both Palladium and DFID rules and requirements. Monthly monitoring of financial records against implemented activities was routine. A “whistle-blower” policy was put into action and supported by regular financial audits and reviews.

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

SAVI has delivered on the majority of their output and outcome level targets. A final contract amendment (contract amendment no.8) was submitted to DFID in February 2016 to accommodate the adjusted time-frame for this completion review and closing of the programme (delayed by 2 months). This was to ensure staff retention for an additional two months through a virement of funds between budget lines at no additional cost to DFID.

Performance of partnerships

SAVI’s key partnership has been with SPARC. This is analysed in depth in the accompanying PCR paper on SPARC-SAVI coordination.

In addition, a close working relationship has continued with IMEP, especially with the work around citizens’ perception surveys (CPS), the SLP suite end-line evaluation and work towards the PCR. The ‘technical outputs/work’ of SAVI has been better recognised by other SLPs, especially at state level, as providing a more replicable and sustainable approach to citizens’ engagement in governance reforms, working with ESSPIN and PATHS2 toward better education and health services. The partnership with the Growth Employment and Markets in States (GEMS) suite of programmes has seen traction with GEMS3 in respect of initiatives for improving internally generated revenue (IGR) and required legislation, and taxation at state level. Although slow to start, areas of collaboration are developing between SAVI and M4D in relation to civil society participation in LGA planning and oversight processes of government services. A less well-defined partnership has been developed with MNCH2, the strength of which varies on a state-by-state basis where the two programmes’ footprints overlap. There has been a varying level of joint working with other DFID programmes on state level political economy analysis, and political engagement conducted on a joint basis. Finally, SAVI is in the process of developing a relationship with the WB in support of their ‘doing development differently’ (DDD) initiative.

One area of weakness has been SAVI’s relationship with FEPAR. A joint SPARC-SAVI-FEPAR work plan was developed for the past year, but only one activity has been delivered (the joint PEA on the National Assembly). FEPAR has an external advocacy and accountability component, but there has been relatively little cross fertilisation of ideas and approaches. As the SAVI successor programme will be working at both state and federal level, it is important for it to draw on experience gained by FEPAR at federal level in managing voice and accountability initiatives.

Asset disposal and value obtained by DFID

A full asset register was updated on a quarterly basis and its contents validated over a number of years by the external auditors. As part of the transition process from SAVI to a successor programme, an agreed strategy for retention and disposal of assets was formulated. The approved criteria to determine the possible utility of assets for the successor programme was based on future economic savings for DFID. The criteria take into account the age of the item, its state of repair, associated maintenance and rising repair costs, future life expectancy and the cost of replacement. By the end the programme, about 40% of SAVI assets were disposed through public auction with the value of the proceeds returned to DFID and the remaining assets were transferred to the new programme.

## H: MONITORING AND EVALUATION

Evidence and evaluation

There were no major changes in the external evidence base used for evaluation in 2015 and 2016. SAVI has invested heavily in its M&E systems, which has proven very valuable for the purposes of accountability, learning and adaptation. Overall the quality of evidence provided has been satisfactory for the purposes of conducting the Programme Completion Review.

Data quality assessment. The Programme Completion Review has briefly assessed the quality of documentation and evidence underpinning the outcome indicators scores. The SAVI Governance Endline reports completed in mid 2015 were found to be comprehensive and of good quality. In addition to the quantitative ratings, the reports provide considerable qualitative evidence that is used to explain, contextualise and justify changes in ratings. IMEP has not observed the assessment process directly, but the quality of documentation suggests that the assessment process was thorough, well informed and subjected to critical discussion.

For Outcome Indicator 4 the PCR had more concerns about the quality of documentation of evidence supporting the 157 case studies indicating changes in policy and implementation. This issue has been raised as a concern in previous annual reviews, but the 2014 annual review noted a significant improvement in the quality of documentation leading to greater confidence in this indicator. For the purpose of the PCR, a random sample of 20 Results Evidence Sheets was assessed to determine: (a) whether changes described were a significant change in policy and implementation, and (b) whether sufficient evidence had been provided to justify claims that SAVI support had contributed to the result (assessment matrix available on request). On the first test, 15 out 20 case studies were found to be significant changes in policy and implementation, but five were found to refer to changes in processes of consultation, which are fully in line with SAVI’s approach, but have not yet resulted in a change in policy or the implementation of policy. On the second test, 9 out of 20 case studies were found to provide strong evidence of SAVI contribution to the result. A further 5 case studies provided a moderate level of evidence, and 6 cases provided weak evidence. Only half of the case studies (10/20) satisfied the reviewer that the case study was both describing a significant change in policy and implementation and providing moderate or strong evidence of SAVI contribution.

The evidence gaps for outcome indicator 4 noted by the PCR team are likely to reflect mainly weaknesses in documentation rather than the absence of results. Taken together the evidence reviewed in the PCR and in previous annual reviews still indicates a very good result. But it is a concern that data quality issues have arisen again after a big improvement in 2014. This suggests that SAVI’s claims of 157 significant results needs to be viewed with caution. It is very likely that the target of 93 has been exceeded, but a more conservative rating of A+ rather than A++ appears warranted in view of the uncertainty and evidence gaps.

The PCR has not conducted a data quality assessment for output level scores. However, several issues have been raised (referred to in Section C) about the continued relevance of some of the output indicators in the light of adaptations to SAVI’s facilitated partnership approach. The successor programme will provide an opportunity to revamp the M&E framework in line with lessons learned from SAVI’s new thinking on promoting voice and accountability.

Monitoring progress throughout the programme

This review was carried out by the Independent Monitoring and Evaluation Project (IMEP) as part of a joint Programme Completion Review of the SPARC, SAVI, FEPAR and V2P programmes in 2016. The SAVI review was led by Gareth Williams with support from Sunny Kulutuye and Gulden Bayaz (VfM). This ensures continuity, as Gareth Williams has led SAVI reviews since early 2011.

This review draws on documentary evidence and interviews conducted in Abuja, Kano, Kaduna and Enugu over a four-week period. The PCR mission was instructed by DFID not to carry out state visits to any other states. However, it was possible to interview SAVI state teams from Jigawa and Yobe who were called to Kano to participate in a series of half day meetings. Extensive meetings were held with the SAVI core team in Abuja.