Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Business in the Community: Private Sector Engagement Programme
Programme Value: £755,000		Review Date: 14th July 2016
Programme Code: 203417	Start Date: 15th July 2013	End Date: 15th July 2018

Summary of Programme Performance
Year	2014	2015	2016­
Programme Score	A	A+	­­­A+
Risk Rating	Low	Low	Minor

Summary of progress and lessons learnt since last review

As with last year’s review, Business in the Community (BITC) continues to exceed expectations for this project. After three years of the project there is increasing awareness and interest among businesses, especially BITC member companies, to engage on international disaster response (IDR). The programme has helped to strengthen the engagement of these companies, and to inspire others to find out more. The project is exceeding expectations as set out in the logframe. The International Disaster Relief Awards are getting bigger and better. Non-government organisation (NGO) consultation is increasing with 2 large consultations held over the year, and NGOs being included in a number of the BITC events that were run during the year. In addition to encouraging business to attend the World Humanitarian Summit (WHS), BITC co-hosted a business focussed event there.

Summary of recommendations for the next year

It is recommended that BITC keep a watching brief on opportunities to explore and identify case studies and award entries from private sector engagement in conflict affected settings, while acknowledging that this is a particular challenge.

BITC to keep a watching brief on the appropriateness of the use of the terminology ‘international disaster relief’.

BITC to continue to monitor what other types of matching tools are being developed.

Logframe to be revised with stretching 2017 milestones. Indicator 3.2 to be removed from logframe. Consider rephrasing indicator 1.3 to capture the other articles produced by BITC which work to provide the case for business involvement.

BITC to explore how businesses can best communicate IDR success stories in corporate communications.

BITC to consider how to take forward lessons from WHS.

BITC to continue to deepen links with humanitarian networks.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log Frame

The UK is providing up to £755,000 over a 5 year period to BITC to help improve the coordination and effectiveness of the UK private sector when they respond to humanitarian emergencies.

The intended impact of the programme is that the private sector is better harnessed to reduce human suffering in humanitarian disasters.

The intended outcome of the programme is that the private sector operating in the UK is better prepared to respond quickly, effectively and appropriately to humanitarian crises

Specific outputs include:

Increased insight and understanding for business on how they can best assist during humanitarian emergencies. This involves the development and delivery of annual BITC International Disaster Relief Award as part of the BITC International Disaster Relief programme (IDRP), and the production and dissemination of best practice guidelines, case studies and insight reports.

Partnerships between NGOs and businesses created. This is done through forums for collaboration and development of a “Matching Tool” to identify and link businesses’ actual, and potential, contributions and engagement on this agenda with NGOs.

Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response. This is done through capacity building for business to identify their unique contribution and evidenced in the number of businesses showcasing their International Disaster Relief programme in their corporate communications.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment.
The BITC private sector engagement programme has exceeded expectations in year three. The programme delivered on its core business, exceeding some targets. The response of the private sector, operating in the UK, to major crises has been encouraging in terms of both the scale and sophistication of the contributions increasingly moving beyond philanthropy.

Overall output score and description – A+, the project is moderately exceeding expectations

The overall output score is an A+. Most milestones have either been met or exceeded. The quality of the project remains high, and is having a tangible impact on businesses engagement in disaster relief as evidenced by the very high standard of entries for the International Disaster Relief Awards, and the positive role BITC played in supporting business during, for example, the Nepal Earthquake response.

BITC’s well established and maintained database of members helps ensure that they have a strong reach to business personnel who are able and interested in furthering business engagement in international disaster relief. BITC also makes good use of pro-bono and other support from members to ensure good value for money.

Key lessons

BITC learns and adapts throughout the project cycle. Draft guidance for business on international disaster relief was reviewed by 10 humanitarian agencies, and suggestions for improvement were put forward and incorporated in the guidance.

The review of the Nepal Earthquake response was an opportunity to bring together 8 companies and 6 humanitarian organisations to share lessons on the response. These included: providing communications support through in country teams, making customer support / social media teams available to process enquiries from affected communities, and supporting communications through using business employees with knowledge of local languages.

Reflecting on WHS preparations it was noted that to engage high level business leaders in high level events, good timing, planning, and clear senior level communication is crucial.

Key actions

Key actions are captured in the recommendations section.

Has the logframe been updated since the last review?

No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 / Development and delivery of annual BITC International Disaster Relief Award as part of the BITC International Disaster Relief Programme (IDRP)	International Disaster Relief (IDR) Awards held annually from 2014-2018.	Milestone met and exceeding expectations in quality. The / IDR Award is on schedule to be held in July 2016.
1.2 / Number of best practice case studies identified.	Third set of case studies published by June 2016 (15 new)	Milestone exceeded. / 8 case studies of shortlisted entries for the IDR Award are on the BITC website and referenced in an editorial in the Financial Times published on the 7th June. / In addition, 10 mini case studies have been produced during the reporting period in relation to the refugee crisis.
1.3 / Insight papers articulating the business case for business engagement in disaster relief	First insight paper produced December 2015	Milestone met. / An insight paper has been written and is ready to go on the website in line with the logframe milestone. However, it was agreed with DFID that rather than publish it now, it is better to publish it alongside the latest research in the Autumn, end Sept/Oct. This allows for more focus on the Awards, the new finalists and case studies, the summer break and enables BITC to achieve maximum impact when it is published.
1.4 / Online guidance for business engagement with humanitarian community on BITC website	Refresh and populate BITC website with Award winners and case studies.	Milestone Met. / BITC website populated accordingly.

Key Points

The IDR Award process continues to proceed in a highly professional manner. The event continues to get bigger and better each year. The award workshop preparing the IDR Award was extremely well attended. There has been a 27% increase in entries from around the world. DFID attended the assessment and judging process on 9th March. An award shortlist was announced on 22nd April and finalists were announced in the Financial times giving increased exposure to the Award process. The FT also carried an editorial on the 7th June. A Gala event is planned for the 11th July.

In addition to progress on indicator 1.3, through the course of the year, BITC have produced a number of blogs, opinion pieces and other articles on various disaster relief related topics such as: ‘Silent Disasters’, ‘Relief Resistance and Redesign’, ‘World Humanitarian Day’, ‘The Refugee Crisis’ and examples of business contributions. These are articles which provide insight on the case for business engagement and are in effect functioning as ‘Insight papers’. See recommendation below.

In addition to progress on milestone indicator 1.4 for this review period, the draft guidance for business on international disaster relief has been reviewed by 10 humanitarian agencies. They were asked to feedback on any areas they felt were missing, ‘red flags’ on the content, and any key messages they felt were critical for business to understand. The feedback was positive and humanitarian agencies were very encouraging that this tool is being developed for business. Suggestions for improvement were also put forward, including additional ideas for how companies can contribute to disaster resilience and preparedness, and insight on the appropriate processes for gifts in kind donations. The final content is due to be sent for design and production in the next quarter.

Summary of responses to issues raised in previous annual reviews (where relevant)

All recommendations from last year’s annual review have been acted on. The 2016 Award has been promoted strongly through relevant networks.

There was a recommendation to explore and identify case studies and Award entries from private sector engagement in conflict affected countries. Progress has been made on this, though it is acknowledged that this is a particular challenge given the sensitive nature of engagement in conflict settings.

It was agreed that the recommendation to refine the terminology from ‘international disaster relief’ to incorporate the wider contribution that BITC is making to the whole humanitarian programme cycle, should be dropped. ‘International disaster relief’ was considered to be appropriate and recognisable for BITC’s audience.

Recommendations

It is recommended that BITC keep a watching brief on opportunities to explore and identify case studies and award entries from private sector engagement in conflict affected settings, while acknowledging that this is a particular challenge.

BITC will keep a watching brief on the appropriateness of the use of the terminology ‘international disaster relief’.

Consider rephrasing indicator 1.3 to capture the other articles produced by BITC which work to provide the case for business involvement.

Output Title	Partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 / Number of new partnerships between NGOs and business establish supported by the Matching Tool [to match requests from humanitarian organisations with business offers of support.]	Pilot testing of Matching Tool concept by December 2015. / ‘Matching Tool’ first iteration developed and rolled out by June 2016	Milestone met / The concept was developed, refined and then tested at an event hosted by a business featuring their partnership with an NGO and with a simulation run by another private sector organisation who developed the Matching Tool prototype on a pro bono basis. This has been shared at the first event of BITC's Responsible Business Week on 18th April.
2.2 / Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business.	4 meetings with NGOs on engaging with business held by December 2015 / After action review of role of business in major disaster response held with businesses and humanitarian partners.	Milestone exceeded / BITC ran two large consultations with the NGO sector and in addition ran more events and also included NGOs in a number of the 10 events that were run during the year. / A workshop took place on 9 February to review the role of business in 2015 Nepal earthquakes.

Key Points

BITC have secured pro bono support from a company for the development and testing of the Matching Tool prototype which can be tested by companies and humanitarian organisations. Working with two member companies, BITC developed and designed an event which aimed to profile the role of business in IDR followed by a simulation exercise on 18 April to support the testing process of the Matching Tool. This brought expertise from the company’s Global Crisis Centre and simulation development teams. A final version of the Matching Tool will be further developed and produced.
A workshop took place on 9 February to review and reflect on the role of business in the 2015 Nepal earthquakes. The workshop was attended by 18 people, representing 8 companies and 6 humanitarian organisations. The group heard presentations from three companies from different sectors explaining how they had mobilised following the earthquakes, and from two NGOs explaining how they had worked with corporate partners.
The group discussed what had worked well in terms of business support, what had been challenging, the missed opportunities, and what they would do differently next time. The workshop concluded with a ‘Speed Matching’ session, where companies and humanitarian organisations exchanged ideas about different ways business could support future responses.
The feedback from participants was very positive, and it was felt that it will be helpful to repeat this type of event following future disasters. The discussions will also inform the next iteration of the Matching Tool.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations from the previous annual review have been acted upon. BITC have been engaged with UNOCHA around the Connecting Business Initiative and BITC have looked at various ways of mapping high risk countries. Both of these were requested last year.

Recommendations

BITC to keep continue to monitor what other types of matching tools are being developed.
There is currently no milestone for 2017 under output indicator 2.1 the logframe should be revised with a 2017 indicator for indicator 2.1.

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 / Capacity building for business to identify their unique contribution and better understand how it can be used.	Disaster simulation exercise / Seminar/ webinar series on key aspects on businesses unique contribution / Training for business on key aspects of online guidance	Achieved / Disaster simulation exercise took place in April 2016. This was a successful event with a great deal of interaction, engagement and feedback. / During the course of the year BITC ran some 10 events, each time emphasising businesses unique contribution. Key aspects of the online guidance were featured in these events.
3.2 / Number of face to face meetings with business targets	No milestone for this reporting period	While there is no milestone for this reporting period, this is being exceeded. / See recommendation below
3.3 / Recommendations on role of business in disaster relief put forward to DFID to inform World Humanitarian Summit (WHS) 2016 preparations	Business leaders encouraged to attend WHS in May 2016	Achieved, including hosting a WHS side event.
3.4 / Number of businesses showcasing their International Disaster Relief programme in their corporate communications	Review of number of BITC companies showcasing IDR in corporate communications June 2016	This has been completed with a report provided and it is clear that there has been a development in the reporting of IDR activities in companies’ external communications .

Key Points

BITC will run another capacity building event on the 11th July. This will futher share the Matching Tool and feature finalists of this year’s awards.

The BITC International Campaign Team participated in the WHS global consultation in Geneva from 13-16th October. BITC, in partnership with other business groups, hosted a side event, Public-Private Partnerships for Resilience and Localized Response, at the World Humanitarian Summit.

While no milestone was set for indicator 3.2, BITC conduct large numbers of face to face meetings with business as part of their routine business. The milestone is regularly exceeded as part of day to day BITC activities. It does not need to be monitored and should be removed from the logframe.

Milestone 3.4 is noted as a challenge. Companies often have limited space to use in corporate communications in which core business information needs to take a priority. This can mean that IDR work may not be able to feature strongly. During the next quarter, tracking of key metrics will be carried out, including analysing a sample of BITC member companies’ annual reports and sustainability reports to identify if and how companies are referring to International Disaster Relief in their external communications. This will allow changes to be tracked against a similar exercise conducted in May 2015.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations in the previous review have been addressed. In relation to the WHS: BITC engaged in the WHS process in relation to business engagement. In relation to working with existing humanitarian networks: BITC also have links with START Network, BOND, DEC and others.

Recommendations

While no milestone was set for indicator 3.2, we noted BITC conduct large numbers of face to face meetings with business as part of their routine business. The milestone is regularly exceeded as part of day to day BITC activities. It does not need to be monitored and should be removed from the logframe.

BITC to explore how best businesses can communicate IDR success stories in corporate communications.

BITC to consider how to take forward lessons from WHS.

BITC to continue to deepen links with humanitarian networks.

Remove indicator 3.2 from logframe.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost driver is salary costs. Charge out rates and levels of engagement were agreed with partners in advance.

VfM performance compared to the original VfM proposition in the business case

The business case notes that this project offers value for money as it capitalises on BITC’s strategic position as a central source of advice and guidance for the private sector and their existing experience of partnering with the public sector to leverage business to address social challenges. BITC has a broad range of experience in:

- Identifying, articulating and driving the business case responsible and sustainable business action.
- Providing fora to share expertise, information, research and best practice
- Capacity building and partnership brokering, whether in the UK or internationally.

Throughout the reporting period BITC has continued to demonstrate against these VFM criteria.

Assessment of whether the programme continues to represent value for money

The project continues to represent VFM. Using its networks and communications tools, BITC has brought together a large number of businesses to share expertise, information, research and best practice.
In terms of costs and timeliness, BITC represent good value for money. BITC has also leveraged its existing business network to reduce costs to the programme. BITC has been able to access members’ venues and resources for events and other activities. The utilisation of business venues, catering and other business resources saves on procurement costs of hiring venues and purchasing equipment, manging events, consultancy fees and software. Pro bono support has been provided by BITC member companies for various events and activities.

Quality of financial management

Narrative and financial reporting remains timely and of a high quality. Spend rate for the project is on track.

Date of last narrative financial report	May 2016
Date of last audited annual statement	December 2015

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

The risk rating for this project remains Minor

Overview of programme risk

The risk of there being insufficient interest and commitment among business and humanitarian agencies to pursue this agenda remains low, and has proved throughout the programme to be low. Evidence from the programme is that there is a strong desire amongst business and NGOs to pursue this agenda, and that business is willing to contribute to the disaster responses that have occurred since the programme started.

One risk with a mitigating action was identified this reporting period around the Matching Tool. It was noted that, through BITC research on the Matching Tool, several examples had been identified of similar initiatives that failed to succeed because the systems were not sufficiently adaptable, and placed too high a burden on users to maintain and update their information. To try to mitigate this risk, BITC are taking the time to make sure that the technology component of the Matching Tool is right, developing a system that is as light touch as possible and which draws were possible on existing information sources.

Outstanding actions from risk assessment

No further actions outstanding form risk assessment

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project is delivering well against the timeframe.

Performance of partnership (s)

There have been several staff changes within programme teams at DFID. Despite this, good relationships have been developed and there is common agreement on the direction of the programme and ways of working. To ensure that good relationships are maintained, and to further capitalise on the good linkages found through DFID, regular and more structured quarterly catch-up meetings will be established with BITC at DFID.

Asset monitoring and control

No assets over £1,000 have been made for this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

A survey of business and humanitarian organisations is currently underway, as a follow up to the baseline survey conducted in 2014. The results of this survey will be collated and analysed in the next quarter, and will form the basis of a report to be shared with DFID and external audiences. The results will help BITC to design future programme activities and ensure the programme remains relevant to the core target audiences.
During the next quarter, tracking of key metrics will also be carried out, including analysing a sample of BITC member companies’ annual reports and sustainability reports to identify if and how companies are referring to International Disaster Relief in their external communications. This will allow changes to be tracked against a similar exercise conducted in May 2015.

Monitoring progress throughout the review period

This annual review was completed by the DFID Senior Responsible Officer, Programme Manager and the divisional Commercial Advisor. DFID staff met with staff from BITC to discuss progress and used BITC’s quarterly reporting. BITC also provided an initial assessment of progress for discussion. Progress has been focussed on commitments made for the project in the logframe.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process