## Logframe
PROJECT NAME | Southern Africa Regional Response to El Nino
IMPACT | Impact Indicator 1 |  | Baseline September 2016 |  |  |  | Target August 2017 (end of programme)
Reducing suffering of crisis affected people in Southern Africa through improved food security and nutrition of vulnerable households, and reduced mortality of children and other vulnerable groups. | % of targeted households with improved food and nutrition security in Lesotho, Madagascar and Malawi | Planned | 0% |  |  |  | 80%
|  | Achieved |  |  |  |  | Lesotho: Madagascar: Malawi:
Source
FAO will provide final survey on 5% beneficiaries: dietary diversity, food hunger scale, food consumption score beneficiary satisfaction survey.
| Impact Indicator 2 |  | Baseline September 2016 |  |  |  | Target October 2017 (end of programme)
| Mortality rate of children under 5 admitted for treatment of Severe Acute Malnutrition in Madagascar, Mozambique and Zimbabwe | Planned | Madagascar: 4.4% Mozambique: 10% Zimbabwe: TBA |  |  |  | Madagascar: ≤ 2% Mozambique: ≤ 4.9% Zimbabwe: ≤ 4.9%
|  | Achieved |  |  |  |  | Madagascar: Malawi: Mozambique: Zimbabwe:
Source
This is captured in the UNICEF programme logframe. UNICEF data collection will include SMART surveys and health facility reports. Note that Malawi is not included in this indicator as nutrition services are not funded in Malawi under this particular arrangement. For UNICEF, indicators will be reported on every 6 months.
OUTCOME | Outcome Indicator 1 |  | Baseline September 2016 | 0 | 0 | 0 | Target August 2017 | Assumptions
Beneficiaries improve their health, nutrition, food production and/or have a stronger livelihood asset base. | % of beneficiaries harvesting diversified food crops or able to keep their livestock . | Planned | 0% |  |  |  | 90% harvest diversified crop 80% able to keep livestock | Rainfall in rainy/lean season enables crop diversification and survival of livestock. There are no major outbreaks of disease or pest amongst livestock or crop. Household livelihoods are not destroyed by other extreme events such as cyclones and flooding. Basic social services are available in the target area. Markets are functioning and there are no new major economic shocks. Coordination and leadership supported by DFID funding results in more effective and efficient response delivery.
Achieved
Source
FAO service provider reports and final FAO beneficiary survey.
| Outcome Indicator 2 |  | Baseline September 2016 |  | 0 |  | Target October 2017
| Recovery rate (%) for treatment of Severe Acute Malnutrition complies with SPHERE standards. | Planned | Madagascar: 61% Malawi: 90% Mozambique: 60% Zimbabwe: 59% |  | >75% |  | >75%
|  | Achieved |  |  | Madagascar: Malawi: Mozambique: Zimbabwe: |  | Madagascar: Malawi: Mozambique: Zimbabwe:
Source
UNICEF reporting to DFID, on the basis of SAM treatment reports in health facilities.
INPUTS (£) | DFID (£) |  |  | Other (£) |  |  | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline September 2016 | 0 | 0 | 0 | Target August 2017 | Assumptions
Livestock and agricultural assets of target households are protected through to the end of the lean season. | # households able to protect their livestock and agricultural assets via agricultural support. | Planned | 0 |  |  |  | 75 000 | Projects start on time with allocation of funding from donors taking into consideration agricultural production seasonality. Recipients of agricultural assistance including seeds are provided with appropriate inputs for the climatic conditions and rainfall duration/cycles. Stable security situation prevails in the target area. Beneficiaries have access to land and they are able to produce. No further extreme adverse climatic events. No major outbreak of plant pests and diseases. Market access remains stable and market operating normally. Restocking of livestock and agricultural assistance occurs alongside food and cash assistance for affected people.
|  | Achieved |  |  |  |  | Lesotho: Madagascar: Malawi:
Source
FAO reporting to DfID
| Output Indicator 1.2 |  | Baseline September 2016 | 0 | 0 | 0 | Target August 2017
| # of households supported through livestock support interventions (animal feed, veterinary services, vaccination, water, restocking) | Planned | 0 |  |  |  | 92 000 (Lesotho 6 000; Madagascar 9 000; Malawi 77 000)
|  | Achieved |  |  |  |  | Lesotho: Madagascar: Malawi:
Source
FAO reporting to DfID on the basis of service provider reports
| Output Indicator 1.3 |  | Baseline September 2016 | 0 | 0 | 0 | Target August 2017 (end of programme)
| % of Households targeted by FAO are able to keep or improve size of herds | Planned | 0 |  |  |  | 80%
|  | Achieved |  |  |  |  | Lesotho: Madagascar: Malawi:
IMPACT WEIGHTING (%) |  | Source
40% |  | FAO reporting to DFID
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline September 2016 |  |  |  | Target October 2017 | Assumptions
Increased quality and coverage of nutrition, health and WaSH services for communities targeted. | # children aged 6-59 months who are screened for malnutrition | Planned | Madagascar: 0 Mozambique: 0 Zimbabwe:0 |  |  |  | Madagascar: 160,000 Mozambique: 120,000 Zimbabwe: 164, 153 | Project starts on time with allocation of funding from donors taking into consideration the sustainability of WaSH interventions including the impact of new water services on both beneficiary and non-beneficiary households. Communities in which UNICEF works are engaged in WaSH construction in a manner that fosters their ownership of water and sanitation services. The information and messages provided by UNICEF can be acted on by people reached (e.g. messages concerning hand washing are accompanied by access to sufficient water). Stable security situation prevails in the target area. Water infrastructure rehabilitation works not affected by the rainy season / La Nina. There is no significant increase in cost of supplies and contractors or exchange rate fluctuations significantly affecting the capacity of partners to deliver programme activities to these targets.
|  | Achieved | 0 |  |  |  | Madagascar: Mozambique: Zimbabwe:
Source
UNICEF reporting against the programme logframe. Note, Malawi is not a target country for nutrition activity under this particular arrangement.
| Output Indicator 2.2 |  | Baseline September 2016 |  |  |  | Target October 2017
| # health care workers trained in emergency nutrition and/or child health care | Planned | 0 |  |  |  | Madagascar: 1812 Mozambique: 105 Zimbabwe: tbd Malawi: 3534
|  | Achieved | 0 |  |  |  | Madagascar: Mozambique: Zimbabwe: Malawi:
Source
UNICEF reporting against the programme logframe. In Zimbabwe, UNICEF will target on basis of the proportion (target 60%) of principal caregivers of children < 2 years reached with key nutrition, health, WASH and HIV prevention and treatment key messages.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline September 2016 |  |  |  | Target October 2017
50% | # people supported with water and/or sanitation services, temporary or long lasting | Planned | 0 |  |  |  | Madagascar: 10,000 Mozambique: 40,000 Zimbabwe:144,000
|  | Achieved | 0 |  |  |  | Madagascar: Mozambique: Zimbabwe:
Source
UNICEF reporting against the programme logframe.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline September 2016 |  |  |  | Target August 2017 | Assumption
| % satisfaction rate in WFP user satisfaction survey. | Planned | n/a |  |  |  | 80%
Increased quality and timeliness of information on humanitarian needs and national and UN capacity in reporting this in the region. |  | Achieved | [5 empty] | Information collected by UN agencies and with affected Governments is timely and transparent and available to decision makers and humanitarian agencies.
Source
WFP reporting on Special Operation 200993: Augmentation of WFP support to the SADC Secretariat and member states in response to El Niño-related drought. The user satisfaction will be based on an online survey which will be administered on all the external recipients of the mVAM bulletins from the FNSWG to get some feedback on the mVAM and also to SADC and members of the logistic coordination team.
| Output Indicator 3.2 |  | Baseline September 2016 |  |  |  | Target August 2017 (end of programme)
| Number districts reporting updated information on malnutrition at least quarterly | Planned | Madagascar: 8 Mozambique: 8 Zimbabwe: 10 |  |  |  | Madagascar:11 Mozambique: 27 Zimbabwe: 10
Achieved
Source
UNICEF reporting against the programme logframe. This indicator indicates the functioning of sub-national functional nutrition information systems. UNICEF information sources will include
| Output Indicator 3.3 |  | Baseline September 2016 |  | Baseline March 2017 |  | Target August 2017
| Provision of technical assistance to OCHA to support effective coordation of regional El Nino response and the production and dissemination of high quality humanitarian information and analysis on needs, priorities and funding. | Planned | High quality and timely reports are available and transparent. Technical support provided to coordination mechanisms. |  | High quality and timely reports are available and transparent. Technical support provided to coordination mechanisms. |  | High quality and timely reports are available and transparent. Technical support provided to coordination mechanisms.
Achieved
Source
This is a qualitative indicator. Tangible outputs should include UN action plan updates, humanitarian outlook documents, country response documents, food security forecasts and funding maps and tables. Key to reporting on this indicator will also be qualitative feedback gathered by DfID on the effectiveness of OCHA's coordination and information sharing via the OCHA Regional office for Southern Africa.
| Output Indicator 3.4 |  | Baseline September 2016 |  | Baseline March 2017 |  | Target August 2017
| Provision of technical leadership into coordination structures of international response. | Planned | Attend donor, partner, coordination meetings and provide technical inputs. |  | Attend donor, partner, coordination meetings and provide technical inputs. |  | Attend donor, partner, coordination meetings and provide technical inputs.
Achieved
Source
This is a qualitative indicator. Provision of technical leadership into coordiantion structures will include representing DfID at relevant meetings, influencing agendas and decision-making, developing strong working relationships with UN agencies, other donors, partners and affected governments, and advocating for a more effective humanitarian response. Key to reporting on this indicator will also be qualitative feedback from DFID CO, meetings attended and technical outputs produced.
| Output Indicator 3.5 |  | Baseline September 2016 |  | Baseline March 2017 |  | Target August 2017
| Provision of technical assistance into the design, implementation, monitoring and evaluation of programme, including strengthening capacity of partners. | Planned | Develop strategy, and design and manage programme. |  | Manage programme, plan and conduct monitoring of partner projects and evaluate (lessons). |  | Conduct monitoring of partner projects and evaluate (lessons).
Achieved
Source
This is a qualitative indicator. Provision of technical assistance will include (i) production/input into analytical information products, (ii) development of response strategies, business cases and annual reviews, (iii) successful implementation of innovative programmes, (iv) conducting of monitoring visits and (v) production and dissemination of lessons learning.
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£)
10%
INPUTS (£) | DFID (FTEs)
INPUTS (HR)

## Sheet1 (hidden)
Low
Medium
High