Annual Review - Summary Sheet

Title: Building Disaster Resilience in Pakistan
Programme Value: £40.8 million [until 2020/21]		Review Date: 15 July 2016
Programme Code: 203264	Start Date: 20-7-2014	End Date: 31-03-2020

Summary of Programme Performance
Year	2015	2016
Programme Score	B	B
Risk Rating	Moderate	Moderate

Acronyms

AR	Annual Review
BAR	Bilateral Aid Review
BDRP	Building Disaster Resilience Programme
CBDRM	Community Based Disaster Risk Management
DDMAs	District Disaster Management Authorities
DFID	Department for International Development
DRM	Disaster Risk Management
DRR	Disaster Risk Reduction
FAO	Food and Agriculture Organisation of the United Nations
MYHP	Multi Year Humanitarian Programme
NDMA	National Disaster Management Authority
OJEU	Official Journal of the European Union
PCD	Procurement and Commercial Department
PELP	Pakistan Evidence and Learning Platform
PDMAs	Provincial Disaster Management Authorities
UNDP	United Nations Development Programme

Summary of progress and lessons learnt since last review

The Building Disaster Resilience Programme (BDRP) was approved by the Secretary of State in 2014 with the outcome that the resilience of crisis-affected communities will be improved through: risk assessment, planning, mitigation and preparedness measures and emergency response. The programme will initially work in Punjab and Sindh to help flood affected communities to plan, prepare and mitigate the effects of disasters, and will build the government’s own capacity to better manage and respond to disasters. The programme is currently programmed to run until 2021.

This is the second annual review to score a ‘B’. The procurement of the programme has been slow which has affected progress towards achieving the intended outcomes.

In January 2016 the programme budget was reviewed through the Bilateral Aid Review (BAR) and Spending Review of DFID programmes following the introduction of the UK Aid Strategy in November 2015. This resulted in a reduction in the overall programme budget from £76.3 million to £40.8 million. The team has since reviewed the programme scope, implementation plans and timeframes, to reflect the revised budget and ensure value for money.

BDRP is divided into two phases. Phase One which is currently awaiting contract signature, will run for up to 24 months, including an eight month inception phase. In Phase Two, lasting up to five years, the programme will be scaled-up to a broader set of communities, taking into account lessons learnt in Phase One.

Summary of progress:

Output 1: Effective Governance Structure
The governance structure plan is in place and will be implemented upon signature of contracts. This year, discussions on a more effective governance structure have taken place and are ready to be implemented once the contract is in place.

Output 2: Inclusive community disaster management committees implement plans; financed projects based on risk assessment
Progress has been made on this output through finalising the Official Journal of the European Union (OJEU) procurement process. A consortium has been identified and lengthy contract negotiations have been concluded for Community Based Disaster Risk Management (CBDRM[1]). The contract start date is expected to be August/September 2016.
[1] In this document the consortium which will deliver Output Two referred to as the ‘CBDRM Supplier’

Output 3: Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels
This output focuses on institutional strengthening and capacity building of national and provincial government partners to better manage and respond to disaster risk. In procuring the organisation to deliver the output, DFID initially approached the World Bank’s Disaster Risk Management (DRM) team in August 2015, in line with the approach recommended in BDRP’s business case. In September 2015, we concluded that the proposal did not fit with the requirements of BDRP and therefore DFID sought approval to engage an alternative multilateral, the UN’s Food and Agricultural Organisation (FAO). This year, contract negotiations with FAO have now been concluded and a Framework Agreement will be signed with FAO in August/September 2016.

As partner and relationship management is critical to the success of BDRP, the team has continued to work with key humanitarian and resilience stakeholders such as Pakistan’s National Disaster Management Authority (NDMA), Provincial Disaster Management Authorities (PDMAs), District Disaster Management Authorities (DDMAs), NGOs, other relevant UN agencies and the World Bank. Some of these bodies will have roles in the governance structures of the BDRP (the NDMA, DDMA and PDMA, as well as implementing partners). Others (UN agencies, NGOs and the World Bank) are key stakeholders in the sector, and strong coordination will be essential to successful implementation of the programme.

Output 4: A comprehensive research programme initiated to pilot and test new innovations and approaches to DRR and DRM to inform better future development of national resilience plans and priorities
This output was intended to be the BDRP programme’s support for a Pakistan Evidence and Learning Platform (PELP), which would have been co-financed by the BDRP and DFID’s Multi Year Humanitarian Programme (MYHP) because both programmes will benefit from the lessons learned. However, following the reduction in the overall BDRP budget in January 2016, the team decided to finance this output solely through MYHP for the duration of the 24 month BDRP inception phase. It has therefore not been scored in this review and is now weighted at 0%.

Summary of recommendations for the next year

BDRP remains critical to DFID’s overall Pakistan portfolio and ability to deliver support to some of the poorest people in Pakistan and communities most affected by natural disasters. The recommendations will avoid any further loss of time in procurement; step up the pace of delivery once contracts and agreements are signed; and build early momentum which can be effectively capitalised on if the programme moves to Phase Two.

The team should focus on mobilisation for Output One and Output Two. This involves dedicating time to the identification of deliverables, and key review points. DFID and the CBDRM supplier should work closely to set achievable inception and implementation milestones for 2016 and beyond. Early proactive engagement with the programme partners in the inception phase is required to establish governance arrangements, and agree on workplans and budgets for the first two years.

During the inception period, the DFID team must ensure the logframe update is completed by April 2017, to reflect the changes referred to above.

The team should seek follow-up to ministerial approval at the end of Phase One (24 months) prior to a scale-up to a Phase Two contract for Output Two on the CBDRM component.

When the team seeks ministerial approval for the CBDRM contract after 24 months, the team should seek approval for an overall time extension to the BDRP, which would allow for a total of six years of delivery to help achieve all the planned outcomes. This would bring the programme end date to 2022, and would also require approval from Treasury as the programme would run beyond the end of the current Spending Review period:

Activities	Month	DFID FY
Programme Approval	Jul-14	14/15
Procurement complete and contracts signed	Jul- 16	16/17
Full Programme Implementation begins	Sept-16	16/17
Six years of programme delivery ends	Sept-22	22/23
PCR of programme due	Dec-22	22/23

The team should finalise governance structures to ensure strategic direction and oversight of the programme, agree Terms of Reference, and ensure the CBDRM supplier organises the first meeting to set direction with all partners and Government counterparts from the NDMAs and the PDMAs. Strong relationship management from DFID will be key to the success of the programme, therefore it is important from the outset for DFID and partners to define the delivery approach and clarify roles and responsibilities.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	n/a (going through OJEU)
DevTracker Link to Log frame:	n/a (going through OJEU)

Outline of the programme
Investing in resilience effectively reduces people’s vulnerability to shocks and enables better and more appropriate responses. It is proven that investing in building resilience to disasters saves both lives and money[2]. The UK government is providing an investment of £40.8m over six years (2016-2021) to help build resilience to disasters in Pakistan though better planning, preparedness, response, and improved resourcing at the government and community levels. The Government’s National Disaster Management Plan has been taken into consideration while designing this programme.
[2] https://www.gov.uk/government/publications/the-economics-of-early-response-and-disaster-resilience-lessons-from-kenya-and-ethiopia

Output One – Effective governance structure
This Output aims to establish an effective decision making and advisory body to provide management and strategic oversight to the implementation of the BDRP programme. The structure will facilitate information sharing between provinces and create linkages between Outputs.

Output Two - Building resilience through Community-Based Disaster Risk Management (£35.8m), by introducing practical measures to mitigate risks from disasters and increase community resilience to shocks. Selected villages and communities will develop hazard maps and risk management plans. Responses to minimise and mitigate the risks identified will then be implemented.
Output Three - Strengthening district, provincial and national disaster management capacity (£5m), through increased provincial and district technical capacity in hazard mapping, preparedness and contingency planning as well as disaster response. This will be delivered by the FAO in close coordination with the delivery partners for the CBDRM work under Output Two.
The programme originally had four outputs but because PELP is now no longer part of BDRP, it has been omitted from this annual review. Additionally Output One ‘Effective Governance Structure’, will begin once contracts are signed so the focus of this past year has been in finalising the CBDRM and capacity building arrangements under Outputs Two and Three.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
At this time, there is no progress to report against the overall programme outcome. A summary of ratings against outputs is presented below.

Overall output score and description

Output	Title	Weight	Output Rating
1	An effective governance structure	15%	B
2	Inclusive community disaster management committees implement plans; financed projects based on risk assessment	50%	B
3	Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels	35%[3]	C
4	A comprehensive research programme initiated to pilot and test new innovations and approaches to DRR and DRM to inform better future development of national resilience plans and priorities.	0%	N/A[4]
Overall Programme Rating			B
[3] The weighting for Output 3 has now been increased from 25% to 35% since the last Annual Review as Output 4 no longer falls under BDRP.
[4] This is N/A because PELP has been taken out of the BDRP programme

Key lessons:
DFID team staffing constraints affected our ability to maintain momentum: The programme has suffered from significant staffing gaps in the DFID team since its inception. This increased procurement delays and compromised core programme delivery and made it harder to engage effectively and consistently with key programme partners, including the government.

Turnover in government counterparts affected ownership and progress against establishing governance arrangements: Frequent turnover within the government of Pakistan has impeded the team’s ability to effectively liaise with one of our key stakeholders, the NDMA and build ownership of the programme; greater stability would help establish clear governance arrangements and strong oversight at an early stage to help mitigate programme risks.

Budget adjustments affected the scope of the programme and procurement process. The BAR / spending review resulted in the programme budget being reduced by approximately 47% in January 2016, further delaying contract negotiation and award.

Key actions:
Prioritise getting contracts awarded for both the CBDRM supplier and FAO so they can mobilise and begin programme activities.

Re-energise partnerships with key stakeholders, particularly provincial and national government, to finalise governance and management arrangements. Given that BDRP will be delivering in complex political and fragile environments, early clarity on roles, responsibilities and coordination is essential.

Whilst PELP is no longer an output of BDRP, the programme must ensure it captures and share key resilience lessons. The programme team must therefore actively engage with national, regional and global resilience communities to share key lessons with wider fora such as the Global Resilience Partnership, NGO resilience networks and think tank organisations such as the Overseas Development Institute (ODI), and in post-World Humanitarian Summit policy dialogue.

Has the logframe been updated since the last review?

No. Procurement was ongoing and the inception phase of the programme was expected to have begun by this annual review. Last year the logframe was updated to add a governance output so that progress can be better measured in the early years of the programme.

A revised logframe will be developed during the inception phase and finalised between January and April 2017. The new logframe will remove Output Four (PELP) and add indicators under Output One to establish a clear working relationship between BDRP and the MYHP on resilience learning.

The revised logframe will also need to reflect adjusted programme outcomes / beneficiaries reached, following the budget adjustment. There is a need to ensure clear alignment with the MYHP, a tighter focus on key risks and vulnerabilities, and fewer districts / villages for the first two years under Output Two on CBDRM.

## C: DETAILED OUTPUT SCORING (1 page per output)

Overall Governance of the BDRP

Output Title	An effective governance structure
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones - July 2016	Score	Progress
Strategic and Management Committee meeting being operational and meeting frequently	Strategic Committee has met twice and Management Committee has met three times	B	Moderately not meeting expectations. / The first official Steering Committee is planned as soon as the programme goes live. Whilst programme implementation not yet started, discussions on how best to streamline and make the governance structure effective are underway. DFID has used the past year to maintain proactive engagement with key stakeholders including NDMA, multilaterals and the wider humanitarian/resilience community. Once the agreements for the CBDRM and Capacity/Institutional work (Outputs Two and Three) are finalised, the team will use the inception phase to finalise governance structures, roles and responsibilities.
Sharing between provinces and linkages between components through information sharing	Steering Committee agendas include lessons learned from components of the programme which have implications for other components. Secretariat disseminates information and lead suppliers present findings to the Steering Committee.	B	Programme implementation has not yet started, although governance structures which will enable this information sharing are underway. DFID has used the past year to maintain proactive engagement with key stakeholders including PDMA, multilaterals and the wider humanitarian / resilience community. PDMAs are aware of the implementation plans and geographical spread of the programme.

Key Points

This output is intended to achieve a dynamic and responsive decision making & advisory body, able to provide effective management and strategic direction for BDRP and has been assessed as ‘Moderately not meeting expectations’ (B).

Programme implementation is now likely to start in September 2016 and the scope of the pilot phase will need to be adjusted to reflect the revised budget. Fresh conversations with programme partners on revising, downscaling and prioritising budgets and workplans are underway. Additionally there has been staff turnover within the NDMA and PDMA, requiring new relationships to be built and managed. Once programme implementation starts, there should be swift progress on finalising governance structures and TORs, and holding the first Steering and Management Committee meetings. DFID may re-visit the composition of the committees and frequency of meetings once BDRP starts, the objective being to ensure an appropriate level of engagement for effective oversight and strategic direction.

Lastly, through BDRP’s interaction with PDMAs, the programme team’s aim is to gather learning from other DFID Pakistan programmes working at the same provincial and district levels (e.g., MYHP and governance programmes such as Aawaz) in order to better understand the incentive structures and political economy which determine how devolved levels of government can work effectively in Pakistan.

Summary of responses to issues raised in previous annual reviews

The last annual review recommended that indicators to measure the success of the governance structure (Output One) should be improved, to allow for better coordination between BDRP and the MYHP (see first recommendation below). Consequently the team has reflected on this and in consultation with MYHP, will amend the log frame indicators as soon as the procurement process is finalised.

The last annual review also recognised the critical role of the BDRP Secretariat in helping to facilitate relationships between the different delivery partners. During the inception period, the programme team will consider the best place for the Secretariat to be located within BDRP (possibly sitting with the CBDRM Programme Implementation Unit, with FAO providing technical support). This will be clearly articulated and discussed with all stakeholders and reviewed after the inception period to ensure that the ‘management organogram’ is the most effective it can be to deliver the programme.

Recommendations

At the end of the inception phase, the CBDRM supplier should provide terms of reference for the programme’s overarching governance structure, with a view to ensuring a close relationship with MYHP and providing clarity of roles and responsibilities from the very outset of the programme.

Once programme implementation begins, the DFID team should work closely with the CBDRM supplier (Output Two) and FAO (Output Three) to carve out an effective and inclusive system of governance. A formal strategic meeting with all partners and Government counterparts from the NDMAs and PDMAs should be planned for the inception phase in order to achieve this.

Output Two: Community Based Disaster Risk Management

Output Title	Inclusive community disaster management committees implement plans; financed projects based on risk assessment
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones - July 2016	Score	Progress
Number of inclusive community disaster management committees formed and maintained (developing existing committees or building new committees), which are progressing with high quality planning and delivering against plans.	At least 15%	B	Moderately not meeting expectations. / Given the external factors, DFID has made progress in getting through an OJEU process and subsequent lengthy contract negotiations. A proposed start date planned for Aug / Sept 2016.
% target population scoring between 4 and 6 on resilience scorecard from village level interventions	CBDRM Service Provider trained in livelihood activities; Inception period finalised and workplan for implementation of phase one agreed	B
% target population benefitting from Union Council (UC) level projects	Inception period finalised and workplan for implementation of phase one agreed	B
Number of good quality proposals put to local districts for financing or co-financing	Procurement significantly underway for service provider to begin activities in September 2015	B

Key Points

This output is intended to build the disaster resilience of communities by better planning, preparing and mitigating the effects of disasters, and has been assessed as ‘Moderately not meeting expectations’ (B).

Since approval, the team has taken forward procurement although progress has been slower than planned due to staff changes on the part of government, and resource constraints. These challenges have now been addressed and the pace of progress is picking up.

Interventions and the delivery structures under this Output need to be adapted to reflect the revised budget. The supplier will be required to provide key deliverables at the end of the inception period, including Terms of Reference for the programme governance structure, a detailed monitoring and evaluation framework, a revised logframe, as well as implementation scenarios against the budget available under Phase One and Phase Two.

Simultaneously, DFID is negotiating a contract with FAO to provide technical expertise on building resilience of smallholder agriculture and local food systems (Output Three). FAO will lead on risk and vulnerability assessments to facilitate planning for Phases One and Two of the programme. This should help accelerate work in this sector. In order to make this support deliver effectively, FAO’s management and staff must be fully integrated within the management and the staff of the CBDRM supplier. Discussions to best enable this have already begun.

Summary of responses to issues raised in previous annual reviews

The last annual review recommended that the BDRP governance structure needs more work to ensure respective roles and responsibilities of FAO and the CBDRM supplier are clear. The review also recommended that there is a mechanism for ensuring that perspectives and lessons that arise from delivery at the community level inform the institutional strengthening component (Output Three). Going forward, regular engagement through DFID’s Management and Strategic Committees will ensure lessons are shared proactively amongst the CBDRM supplier and FAO, and that overall coordination is maintained.

One recommendation in the last Annual Review was that the DFID team should ensure the Terms of Reference for the OJEU procurement clearly specify the requirement for the CBDRM supplier to work together with FAO on the livelihood elements of disaster risk management. Through a robust bid evaluation process, DFID was able to identify a supplier who demonstrated a strong knowledge and understanding of community based approaches and how their work will link with other relevant disaster risk reduction initiatives in Pakistan. A number of follow-up meetings have taken place between DFID and the CBDRM supplier and there is a clear understanding of the coordination required with FAO, particularly during the inception phase.

Last year, the programme was on-track to sign a contract for CBDRM by early 2016. Whilst, implementation has not begun, the CBDRM contract is now with ministers for sign off. Now that major delays have been overcome, we expect to be able to proceed to implementation by August / September 2016.

Recommendations

The DFID team should begin planning now how best to gather and present the best evidence for the end of Phase One programme review. This evidence will be used to assess programme performance and determine whether BDRP should be scaled up after Phase One, including supporting the case for a Phase Two, which would need to be approved by ministers.

While seeking approval for the CBDRM contract, the DFID team should seek approval for a two-year extension, to ensure there are a full six years of delivery after completion of procurement. Prior approval will also be sought from Treasury as the programme runs beyond the end of the current Spending Review period.

Output Three: Capacity Building and Institutional Strengthening

Output Title	Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels
Output number per LF		3	Output Score	C
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Score	Progress
Staff at PDMA and DDMA level in Sindh and the Punjab trained in disaster risk assessment and response / Information and guidance including codes, advice and construction methods developed and disseminated / Coordination mechanisms between response agencies and community organisations / civil society / Standard Operating procedures making funds available to PDMAs and NDMAs in a timely manner / Staff of Line Department incorporating DRR / DRM in project designs / A national risk assessment platform comprising technical agencies (geology, meteorology), flood commission and others	PDMA and NDMA staff in 5 districts trained and have produced disaster management plans; >75% of village Disaster Management Committees in 5 districts report useful meetings with their DDMA at least once in the previous 6 months Staff trained in activities addressing resilience Funding allocated that allows Standard Operating procedures across PDMAs and DDMAs	C	No direct progress has been made against the milestones because Output 3 is sequenced to start after Output 2 has begun. / Progress has however been made in selecting FAO as the supplier for this output and negotiating with both FAO and other UN partners on organising workplans and budgets to best deliver these milestones.
Comprehensive Geographical Information System (GIS) based database established reflecting all known risks and natural/man-made hazards (Climate change, earthquakes, weather events, conflict etc) / A risk financing strategy developed to enable the Government to access liquidity after disasters / Partnerships developed with the private sector for the provision of life and asset insurance cover	Hazard plans for 5 districts available Joint donor / Government of Pakistan / private sector testing of the validity of insurance and compensation schemes in disaster-prone areas	C
Existing and planned donor-financed activities mapped and shared with the Government of Pakistan at regular intervals / National capacity developed to measure the impact and options for investments in DRM / Regular high level donor / government meetings held to ensure coordination and information exchange	Government of Pakistan coordinated spread sheet of active and planned donor interventions, estimated costs and timescales / Donors and key Government of Pakistan agencies and departments meeting on a regular basis to embed resilience into all Government of Pakistan programmes	C

Key Points

This output is intended to deliver more effective government capacity to enable better management and response to disasters and has been scored as ‘substantially did not meet expectations’ (C).

The weighting within this component has also been revised upwards i.e. to 35%, as a result of removing Output Four, the ‘Pakistan Evidence and Learning Platform’ from BDRP.

The business case identifies multilaterals as the preferred delivery partners for Output Three. DFID therefore solicited a proposal from the World Bank Disaster Risk Management team on institutional strengthening in August 2015. However, by October 2015 the team concluded that the proposal was not sufficiently aligned to the logframe to deliver the most effective progress for this output. FAO was then approached as an alternative delivery partner.

FAO will deliver a clearly defined set of deliverables on institutional strengthening under a Framework Agreement, for the first two years of the programme, at which point DFID will reassess whether arrangements should continue for the remainder of the programme or the approach needs to be adjusted. Their strength on agriculture and livelihoods will help complement the work being delivered around Output Two. Additionally, their experience and reputation will ensure a good working relationship with the Government. The DFID team is currently working closely with FAO to refine the proposal i.e. scaling back/staggering rollout to match the revised budget.

FAO are on track to begin implementation in August 2016, starting with a pre-inception visit to districts to enable multi-hazard vulnerability profiling assessments. Risk profiling, which will look at issues such as flood and drought, is initially planned for two districts each in Punjab and Sindh. These profiles will then be used to determine what the most efficient and effective CBDRM interventions could be during Phase One of the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

At the time of the last annual review, DFID had approached the World Bank to deliver on the institutional strengthening component. Delivery of technical assistance through the Bank was reconsidered in September 2015 therefore setting the timeline back for Output Three. FAO was then approached in late 2015 to submit a proposal.

The last annual review recommended that the risk assessment being developed and applied under this output must be consistent and coordinated with the methodologies being applied for the CBDRM work. This will be taken forward during the inception phase once programme implementation begins.

The last annual review also strongly recommended BDRP’s coordination with the wider humanitarian and resilience communities. Engagement with other donors and interaction with regional initiatives such as the Asia Regional Team’s Climate Proofing for Growth and Development programme will benefit the programme. In April 2016, a team member from the Asia Regional Climate Proofing Growth and Development programme visited Islamabad to explore opportunities to better link regional climate work to the BDRP.

Recommendations

The success of the programme depends on clarity of roles and responsibilities. DFID should ensure partner relationships are managed effectively. Once implementation begins, DFID should proactively engage with key government stakeholders and work closely with the suppliers to ensure roles and responsibilities are clear and managed effectively.

As FAO will lead on the hazard and vulnerability profiling assessments which will inform the work of Output Two (CBDRM), DFID should ensure both partners work closely together to achieve a consistent and coordinated methodology for the CBDRM work.

DFID should already be working to better link the disaster risk financing component of BDRP to other similar initiatives (around disaster risk financing) and input lessons to other relevant resilience forums both within and beyond Pakistan.

DFID should ensure that DFID Asia regional team climate initiatives continue to be aligned and complement BDRP and MYHP activities.

Output Four: Pakistan Evidence and Learning Platform

Output Title	A comprehensive research programme initiated to pilot and test new innovations and approaches to DRR and DRM to inform better future development of national resilience plans and priorities.
Output number per LF		4	Output Score	Not scored
Risk:		Moderate	Impact weighting (%):	0%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Number of evidence studies and documents produced on DRR to climate extremes that are based on consultations with a wide number of players and disseminated	Published information available on the location, type and scale of research and piloting taking place Competitive bids received for initial research funding; At least three project-financed research projects identified and being implemented; two annual dissemination workshops one out of Islamabad	This output is not being scored as PELP is no longer being procured under BDRP. Funding for PELP will come solely from MYHP for at least the next two years. The weighting has been reduced to 0% and the logframe will be adjusted to reflect the change at next revision.
Number of meetings held with key line departments and with NDMA to encourage uptake and inclusion of research results into policy documents and annual work plans	At least three donors – Government of Pakistan meetings held annually (including NDMA, Department of Energy and Climate Change (DoECC), Earthquake Reconstruction and Rehabilitation Authority (ERRA) as a minimum). Should include two representatives from provincial level government

Key Points

This output has not been scored as the PELP is no longer included within the BDRP for reasons cited above. This component is now being procured and funded under the MYHP and will not be assessed as part of this annual review.

PELP has been designed to generate research and evidence on humanitarian and resilience interventions, and will be used to inform BDRP’s programme implementation. It is important that BDRP retains close engagement with PELP to allow for an effective feedback cycle. We anticipate that evidence generated through PELP will help inform the case for resilience building at community, district and provincial levels.

Summary of responses to issues raised in previous annual reviews (where relevant) - N/A

The last annual review recommended that the research component should include looking at how the right incentives for better resilience and disaster preparedness in Pakistan. It was also recommended that the PELP should demonstrate how it will work with other relevant research funders, such as Research and Evidence Division’s Humanitarian Research Team. The procurement for PELP will commence over the coming months and although it now falls under MYHP, these are still key recommendations that the will be fed across and taken forward once PELP is procured.

Recommendations

The DFID team should ensure engagement with PELP through the MYHP so that lessons and knowledge are fed back to improved BDRP interventions and programming.

Remove PELP from the BDRP logframe.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Since the last annual review, the overall programme budget has been reduced by approximately 47%. This has resulted in an overall shift in the projected expenditure and the spending plan has been adjusted as follows:
- Output One: Effective governance structure - No cost
- Output Two: CBDRM - £35.8m
- Output Three: Institutional Strengthening - £5m
- Output Four: Pakistan Learning and Evidence Programme (removed)

The first two years (Phase One) of the programme will largely constitute preparation, testing and evidence gathering around best CBDRM practice. The team will revert to Ministers at the end of project year two, to demonstrate progress and value for money, and secure approval to continue and scale up the CBDRM work. The per village costings will be revised and geographical coverage will be determined after a thorough analysis of the total outreach and impact possible given the total budget.

VfM performance compared to the original VfM proposition in the business case

Given the high costs and frequency of disasters in Pakistan, increases in resilience at the community level are expected to result in reductions in both the immediate impacts, and in the costs of recovery after natural disasters. In the BDRP business case (2014), the cost benefit analysis proposed that the original cost of the entire programme would be ‘less than the additional DFID humanitarian response required if CBDRM were not delivered’. This calculation will need to be revisited in light of the budget adjustment.

Discussions have been ongoing with the CBDRM supplier and FAO to ensure value for money in light of the adjusted budget. DFID have discussed fiscal controls and risk management with the suppliers, and has requested suppliers to set up reporting systems where DFID can review value for money at regular intervals.

Assessment of whether the programme continues to represent value for money

Once the CBDRM supplier is on board, vulnerability profiling to assess the needs of disaster prone areas/communities will help determine and refine the scale and scope of interventions in a village / district. This will allow the team to revise the cost benefit analysis.

Recommendations:

The CBDRM supplier should agree value for money metrics for the programme with DFID and monitor progress throughout delivery.

Quality of financial management

Other than programme design cost and consultancy fees for interim technical support through DFID’s Conflict, Humanitarian and Security Operations Team Department, the programme has very low spend to date.

As part of the inception period, the team will work with partners to develop robust financial controls. Output Two (the CBDRM component) will involve delivery through a number of consortium partners and therefore the lead implementing agent will be expected to strengthen and streamline delivery structures. Strong financial scrutiny of downstream partners will be enforced from the start with a specific focus on due diligence, spot checks and continuous audit processes. Under Output Two, 10% of payments will be linked to milestones aligned to the programme’s logframe, which will be revised during the inception period. Effective technical oversight from DFID is expected through a continuous review of quarterly narrative and financial reports.

Output Three, focused on institution strengthening will be delivered through a Framework Agreement with FAO, which includes clauses on sound financial management and fraud.

Regular auditing and third party monitoring will help ensure effective fraud and corruption monitoring. Breakpoints and key milestones which have been negotiated into contracts will allow for contract termination.

Both implementing partners have been subject to full due diligence reviews in-country.

Recommendations:

The DFID team should work closely with the CBDRM supplier to develop milestones linking quarterly payments to specific targets in the workplan

The DFID team should continue to monitor expenditure by all partners and ensure partners continue to effectively forecast expenditure in line with DFID’s internal financial forecasting requirements.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk:

The overall risk remains unchanged at moderate. A programme delivery plan has been used to monitor programme performance and procurement risks. A programme risk matrix has been developed. It will be continually updated and be used as a monitoring tool. The following risks will need to be closely monitored:

Context

Under the current timescales, the programme partners are expected to begin implementation by August / September 2016. At this time of year the likelihood of a natural disaster affecting Punjab and Sindh provinces due to monsoon floods is high and could lead to further delays in implementation. The team will ensure that through partners under DFID’s MYHP Natural Disasters consortium, relief activities begin immediately allowing for a faster recovery time so that the programme can continue.

The programme’s effectiveness depends to some degree of ownership from the NDMA, PDMAs and DDMAs. Therefore constant engagement with those bodies will be needed throughout the life of the programme. Although the programme has been shared and approved by the NDMA, the DFID team and its partners will develop a governance structure so that all stakeholders involved in the programme are aware of their respective roles and responsibilities. An exchange of letters will be signed with the NDMA to formally seek their endorsement and partnership.

Delivery

Reduced budget allocations have resulted in a need for programme partners i.e. the CBDRM supplier and FAO, to revisit their project scope and workplans. The implementation plans for the CBDRM and capacity building work will be refined and finalised during the inception phase to reflect the current budget allocation. DFID and partners have started to revisit the original technical design to ensure that the programme continues to deliver core results and contribute to managing disaster risk in Pakistan.

Safeguarding

Village / Union Council selection will be based on the findings of the Multi Hazard Vulnerability Profiling led by FAO. However, prioritisation of villages and Union Councils to be targeted under the current budget may mean that some of the neediest communities may be unable to access the programme during the first phase. This may be viewed unfavourably by some of the communities. This risk will be managed by ensuring there is enough programme visibility and communities are made aware of the selection criteria and programme scope so it is not perceived as unfair exclusion. The inception mission planned with FAO and the CBDRM supplier should help address some of these concerns. Subject to approval after Phase One, outreach is expected to increase over time to include a greater number of vulnerable communities from disaster affected districts and villages across Pakistan.

Reputational

The implementation of this programme is highly anticipated, and DFID’s commitment to building disaster resilience has been discussed widely with key stakeholders including the Government of Pakistan. However, and continued delays carry a reputational risk for DFID. We are confident that the programme is now getting back on track and the DFID team are managing this risk through continued engagement with the NDMA through their involvement in the procurement process for the CBDRM supplier.

Outstanding actions from risk assessment:

There are no outstanding actions as the programme has been under procurement in the last reporting period.

Recommendations:

DFID should work with all suppliers to develop a risk matrix that captures the key risks and that this is used as a monitoring tool. The CBDRM supplier will be expected to lead on progress reporting on the risk matrix at DFID’s quarterly Management Committees.

DFID should work with the suppliers to refine programme delivery post inception under the revised budget allocations and ensure a transparent criteria is adopted in the selection of districts to target the most vulnerable communities during the first phase of programme delivery.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe.

The programme has been unable to begin full implementation since approval in July 2014. The procurement for Output Two (CBDRM) began in July 2015 with the successful bidder identified in December 2015. The contract is now with ministers for sign-off, a few months later than planned. Since the last annual review, FAO was been selected to lead on Output Three (institutional strengthening) in partnership with United Nations Development Programme and the World Food Programme. Discussions have been held over the last few months to refine aspects of their proposal to meet the new funding envelope.

Performance of partnership(s)

There is limited information available to report on performance of partnerships from the last reporting period as the primary focus has been on procurement. The identified suppliers under both Outputs Two and Three are known to be strong partners in their relative sectors with comparative advantages to address key aspects of CBDRM and capacity building of government institutions. The NDMA has already endorsed both these initiatives and the team will sign an exchange of letters with the Government of Pakistan to clarify management and governance arrangements, and provide a framework on which to work together for the duration of the programme.

Programme performance will be reviewed through DFID’s quarterly Management Committee and a six-monthly Strategic Committee, chaired by the NDMA. The Committee will provide strategic direction, oversight and ensure lesson learning, information-sharing and coordination between the different programme components.

DFID will continue to engage in the Disaster Risk Reduction sector in Pakistan through a forum currently chaired by the World Bank and Asian Development Bank. The forum will be an opportunity to feedback any key lessons from the programme as well as promote better coordination with other actors implementing similar initiatives. A coordination mechanism between BDRP and DFID’s MYHP will also be discussed to establish complementarities and avoid duplication in activities.

Asset monitoring and control

The key supplier under CBDRM Output Two will be required to adopt DFID’s asset policy as covered under DFID’s Smart Rules. An asset register to record all assets purchased using programme funds will need to be submitted to the DFID team quarterly and regular spot checks will also be conducted. The supplier will be required to ensure a transparent and competitive purchasing process and embed this within the overall Standard Operating Procedures of the programme. Limited asset purchase is envisioned under Output Three (institutional capacity), however the team will still ensure the partner understands DFID’s asset policy and meet DFID’s reporting requirements on this.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The programme is not delivered through government systems and therefore no explicit conditionality was attached. DFID however has ensured that the programme contributes to Government of Pakistan objectives through alignment with its National Disaster Management Plan.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is a limited evidence base for large scale CBDRM work in Pakistan. The BDRP programme is expected to generate useful results on how CBDRM alongside institutional strengthening can help address disaster risk management and build the resilience of vulnerable communities.

As it is focussed on providing support at the community level, the CBDRM supplier will be required to maintain continuous engagement (such as engaging with the community based organisations), which will provide regular feedback to implementing partners. This will help to inform better programming while addressing the needs of vulnerable communities. DFID will work with implementing partners to design a robust impact evaluation framework which provides a narrative on the outcome and impact of the programme which would further validate the programme’s theory of change.

Third party monitoring is critical for projects as a monitoring and risk management tool, as it ensures independent oversight of activities at the delivery level. DFID has included Third Party Monitoring into the CBDRM contract (Output Two). The team will explore opportunities for using some third party monitoring support under the PELP project, procured under the MYHP, to help ensure that the evidence generated is fed into improving resilience interventions and policies.

Monitoring progress throughout the review period

The programme team has been using the delivery plan as a key tool in monitoring core progress. There has been regular engagement with the procurement team and a contract delivery plan has been maintained to monitor programme timelines and mitigate procurement risks.

DFID will agree arrangements regarding tracking progress against the logframe, and the monitoring and evaluation strategy with partners. Individual logframes for the CBDRM supplier and FAO will feed into the overarching programme logframe. Work will also need to be done to align and mirror indicators and coordinate on results reporting. DFID and partners will engage on a monthly basis in the form of review meetings to stocktake, discuss challenges and review work planning.

VALID[5] is independently evaluating the MYHP and the team will use the findings and lessons learnt from the evaluation to inform programme design and implementation on how to better build on the resilience of the most vulnerable populations.
[5] VALID have been contracted by Research and Evidence Division (RED) and CHASE to run a multi-country evaluation of multi-year humanitarian and resilience programmes. The will predominantly be focusing on VFM for multi-year humanitarian verses annual financing through: • Operational cost saving (staff, procurement, proposal writing and currency risk) • Early action (speed of responses) • Predictability (pre-positioning of stocks, pooling orders, leveraging of additional funds, cost savings from long-term investments).

Recommendations:

As a priority, the team should update the programme logframe during inception. DFID and the CBDRM supplier will work closely to set achievable inception and implementation milestones for 2016 and beyond and ensure these are finalised by April 2017.