Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Monitoring, Evaluation and Learning Programme (formerly the ‘Results, Evidence and Knowledge Programme)
Programme Value: £12.72 million – UK total comprised of: / DFID £7.885m / DECC £4.39m / DEFRA £0.445m		Review Date: July 2016
Programme Code: / 203516	Start Date: / 1 August 2014	End Date: / 1 August 2019

Summary of Programme Performance
Year	2014/15	2016
Programme Score	A	A
Risk Rating	Low	Moderate

Summary of progress and lessons learnt since last review

This programme is developing innovative and ambitious approaches to monitor, evaluate and learn from a large, important, diverse and complex portfolio of over 200 programmes.

 It includes the following specific areas of work:

1. A large monitoring, evaluation and learning programme of work (Climate Change Compass) that aims to develop 16 Key Performance Indicators (KPIs) and synthesise evidence and learning from ICF programmes. This work is led by IMC Worldwide.
2. A contract that is developing and testing an indicator that will enable HMG to understand the number of forest dependent people with livelihood benefits protected or improved as a result of ICF support. This work is led by IFRI.
3. Development of an indicator to measure indoor air pollution. This work is led by the World Health Organisation.
4. A web-based knowledge platform that aims to support collection and management of results and evidence. This work is led by Gaisoft.
5. Small projects that have aimed to test innovative approaches to learning, with the aim of informing the Climate Change Compass programme

Over the past twelve months, the ICF Monitoring, Evaluation and Learning programme has delivered a range of useful, timely and relevant outputs. These include delivery of an inception report with plans for monitoring, evaluating and learning from the International Climate Fund (ICF); development of an indicator to enable programmes to measure indoor air pollution; and pioneering work in Nepal to develop and field test an indicator to help us understand the difference our funding is making to the lives of forest dependent people. We have been proactive in engaging and working collaboratively with a range of multilateral agencies including the Climate Investments Funds (CIFs), the Global Environment Facility (GEF), the Green Climate Fund (GCF) as well as the Rockefeller Foundation, EuropeAid DevCo, Sida and Norad to share learning and good practice. This has supported our ability to develop timely, appropriate and robust plans that reflect best international practice.

The cross-government management team includes staff from DFID, DECC & Defra. The team has worked in a supportive and collaborative way to deliver a ‘one government’ programme of work, although there have been times when cross-government working has resulted in duplication of tasks. Lessons learned and ways of working have been shared with the Foreign and Commonwealth Office (FCO) and other government departments to facilitate effective cross-government working practices.

Key lessons learned from the programme include:

1. Establishing an Independent Advisory Group (IAG) for a complex progamme of monitoring, evaluation and learning work plays a crucial role in mitigating risk and increasing the quality of deliverables. The group has provided extremely important and relevant feedback, which has improved the design and approach of the main MEL contract (Climate Change Compass).
2. When establishing a cross-government programme of work it is important to be realistic about the programme management resources required. The ICF MEL Programme Manager plays a crucial role in ensuring effective co-ordination across three Departments and three technical streams of work. For this programme it is important that the team includes a 0.5FTE B1 or A2L Programme Manager based in DFID. The programme manager plays an essential role in monitoring and recording changes to approach and agreed decisions in adaptive programmes.
3. We have learned that clearly defined and agreed roles of the cross-government management group play an important role in facilitating collaborative and positive working relationships and minimising duplication of tasks and conflict. Effective management of a technical programme like Climate Change Compass requires HMG to have the technical expertise in house to assess the quality of deliverables and ensure the efficient use of resources. Finally, with multiple workstreams occurring in parallel, it’s important that time and resource is allocated to each workstream in advance to mitigate any risk that ‘overspend’ in one area does not reduce resource available to another.
4. It is important to proactively engage with multilateral organisations and other government departments to mitigate and manage risk by ensuring the programme is aligned with international best practice.
5. Commissioning innovative and new approaches to monitoring, evaluation and learning are more time and resource intensive that a traditional monitoring and evaluation programmes. Innovative programmes require close monitoring and adaptive management techniques and need to be resourced accordingly.

Summary of recommendations for the next year
1. Continue to work collaboratively across HMG, review and revise if necessary the principles and ways of working between the three Departments. A review should reflect on lessons learned in the inception phase of the programme. [By late October 2016, DFID SRO for the programmes]
2. Proactively liaise and engage with the IAG to monitor and develop strategies to minimise risks associated with the programme of work. [Monitoring on a quarterly basis by IMC & HMG]
3. Continue to proactively engage international partners including the GCF, GEF, CIFs and EuropeAid to share good practice, lessons learned and to harmonize monitoring, evaluation and learning strategies. [Quarterly engagement by DFID Evaluation Adviser]
4. Encourage and monitor reporting on the KPIs by ICF funded programmes. If there are low levels of reporting and self-selection bias (with some programmes only choosing to report on very few or certain KPIs) liaise and escalate as appropriate through the new ICF governance arrangements. [To be led by DFID’s Statistics Adviser in consultation with DECC’s M&E Adviser on a quarterly basis]
5. In the next 3 months IMC and HMG will work together to revise the log frame, risk register and issues log based learning from the inception phase and advice from the Independent Advisory Group [To be led by IMC and completed by end of August 2016]

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4446481.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4355305.xlsx

Outline of the programme
The UK is providing £12.72 million over 4 years (2014/15-2017/18) through the ICF Monitoring, Evaluation and Learning Programme. This programme will enable HMG to understand and communicate results, evidence and lessons learned from the £3.9 billion International Climate Fund. This programme will drive increased effectiveness of international climate spend to maximise the impact of each pound spent to improve poor people’s lives today and in the future; and provide evidence to help build support among governments, civil society and private sector for financing climate change-related programmes and policies This will allow the UK to influence major international partners, including the United Nations Framework Convention on Climate Change (UNFCCC), the World Bank and the Green Climate Fund and encourage other donors to take UK pilots to scale.

The programme includes the following specific areas of work that are being led by contractors:

1. A large monitoring, evaluation and learning programme of work (Climate Change Compass) that aims to develop 16 Key Performance Indicators (KPIs) and synthesise evidence and learning from ICF programmes. This work is led by IMC Worldwide.
2. A programme of work that is developing and testing an indicator that will enable HMG to understand the number of forest dependent people with livelihood benefits protected or improved as a result of ICF support. This work is led by IFRI.
3. Development of an indicator to measure indoor air pollution. This work is led by the World Health Organisation.
4. A web-based knowledge platform that aims to support collection of and facilitate sharing of results and evidence. This work is led by Gaiasoft.
5. Small projects that have aimed to test innovative approaches to learning, with the aim of informing the Climate Change Compass programme.

The programme will build global knowledge and evidence about the relationships between low carbon, climate resilient development, economic growth and poverty reduction. Equally, the information gathered through this programme will enable HMG to make informed decisions about future investments, strengthen public accountability and support results-based performance management. The direct cost to DFID is £7.885 million (62%). DECC and DEFRA will provide £4.39 million (34.5%) and £445,000 (3.5%) of the funding respectively, in line with their percentage shares of the ICF budget.

The programme has four outputs:

Output 1: Provision of robust and appropriate tools and data to track core results across all relevant programmes (building on and supporting current ICF KPIs and programme monitoring).

Output 2: Generation of evidence and knowledge that address key strategic questions through fund level evaluations and synthesis work (building on programme-level evaluations), including whether and how the ICF has achieved transformation, and what the most effective delivery routes are and approaches for mobilising public and private climate finance.

Output 3: Knowledge Platform to enable the collection, aggregation, management and sharing of data and evidence across the ICF portfolio and among a wide range of users.
Output 4: Effective dissemination and promotion of learning across development partners and stakeholders to: encourage the use and application of the tools, lessons, knowledge and evidence generated through the ICF, support alignment of monitoring and evaluation activities and systems going forward, and help raise awareness and drive greater public and political support for assisting developing countries to manage the threats and opportunities from climate change.

Three of the four outputs (1, 2 and 4) for this programme will be delivered through a main contract (Climate Change Compass). Two sub-components of output 1 are delivered through separate arrangements set up by DFID:

- an Accountable Grant with the International Forestry Resources and Institutions (IFRI) to deliver a methodology for the forest dependent people Key Performance Indicator and associated data collection; and
- a Memorandum of Understanding with the World Health Organisation (WHO) / United Nations Development Programme (UNDP) to develop baseline data on the health benefits of clean energy (change in mortality / morbidity as a result of indoor air pollution from solid fuel use).

Output 3 is being delivered through a separate contract that has been procured through the Cabinet Office managed G-Cloud arrangement. DFID has led the programme management and procurement of all outputs, with DECC and DEFRA providing ongoing engagement through involvement in procurement processes, technical assurance of all processes and outputs and participation in a cross-Whitehall management team.

Over the past 12 months, specific work for Output 4 has also been delivered by a consortium of independent consultants that developed the Sustainable Learning Development Dialogues and other small learning projects that have been led by independent consultants.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment A

The outcome defined in the log frame is an increase in evidence-based policy programming and delivery of climate change interventions. The Annual review has found that this outcome is on track to be achieved by the programme

Evidence collected and analysed for the annual review shows that over the past twelve months, the ICF Monitoring, Evaluation and Learning programme has delivered a range of useful, timely and relevant outputs. These include delivery of an inception report with plans for monitoring, evaluating and learning from the International Climate Fund (ICF); development of an indicator to enable programmes to measure indoor air pollution; and pioneering work in Nepal to develop and field test an indicator to help us understand the difference our funding is making to the lives of forest dependent people. We have been proactive in engaging and working collaboratively with a range of multilateral agencies including the Climate Investments Funds (CIFs), the Global Environment Facility (GEF), the Green Climate Fund (GCF) as well as the Rockefeller Foundation, EuropeAid DevCo, Sida, KfW and Norad to share learning and good practice. This has supported HMG’s ability to develop timely, appropriate and robust plans to monitor, evaluate and learn from the International Climate Fund.

Overall output score and description: A

The scores of the four outputs are as follows:

Output 1: Provision of robust and appropriate tools and data Score: B

Output 2: Generation of evidence and knowledge that address key strategic questions	Score: A
Output 3: Knowledge and results platform. Score: A+
Output 4: Effective dissemination and promotion of learning. Score: A

Annual outcome assessment

The annual assessment of the programme is ‘A : Met expectations’. This assessment is based on a review of the four outputs scores and reflects the revised logframe for the programme.

Key lessons

1. Establishing an Independent Advisory Group (IAG) for a complex progamme of monitoring, evaluation and learning work plays a crucial role in mitigating risk and increasing the quality of deliverables. The group has provided extremely important and relevant feedback, which has improved the Climate Change Compass programme’s design and approach. When developing terms of reference that include working collaboratively with an Independent Advisory Groups it is important that sufficient time is included in project timelines and budget to enable effective engagement and collaborative development of plans.
2. When establishing a cross-government programme of work it is important to be realistic about the programme management resources required. The ICF MEL Programme Manager plays a crucial role in ensuring effective co-ordination across three Departments and three technical streams of work. For this programme it is important that the team includes a 0.5FTE B1 or A2L Programme Manager based in DFID. The programme manager also plays an essential role in monitoring and recording changes to approach and agreed decisions in adaptive programmes.
3. We have learned that clearly defined and agreed roles of the cross-government management group play an important role in facilitating collaborative and positive working relationships and minimising duplication of tasks and conflict. It is important to regularly review how the cross-government team is working together and consider feedback from our partners. Effective management of a technical programme like the MEL requires HMG to have the technical expertise in house to assess the quality of deliverables and ensure the efficient use of resources. With multiple workstreams occurring in parallel, it is important that time and resource is allocated to each in advance to mitigate any risk that ‘overspend’ in one area does not reduce resource available to another.
4. To increase engagement from stakeholders and maximise learning from the experience of delivery partners, HMG should encourage programmes to commission a programme of real-term learning to complement programme evaluations. Flagship DFID programmes including BRACED, KNOWFOR and CDKN are exploring synergies between evaluation and a programme of real-time learning work. Members of the Climate Change Compass programme’s Independent Advisory Group have provided positive feedback about the value of synergies between the programmes’ evaluation and real-time learning streams of work.
5. It is important to proactively engage with multilateral organisations and other government departments to learn from their experience, share learning and plans. Our work in this area has played a key role in mitigating and managing risk by ensuring the programme is aligned with international best practice. This work has also enabled the UK to influence and inform the development of multilateral and bilateral agencies plans. Our engagement with the Climate Investment Funds (CIFs) has supported the CIFs to develop appropriate, relevant and timely monitoring, evaluation and learning plans.
6. Commissioning innovative and new approaches to monitoring, evaluation and learning are more time and resource intensive that a traditional monitoring and evaluation programmes. Innovative programmes require close monitoring and adaptive management techniques and need to be resourced accordingly. In addition, technical programmes need to be managed by HMG staff with specialist technical skills.
7. Monitoring, evaluating and learning from a large and diverse portfolio rather than a programme involves intensive learning, collaborative working, piloting and testing new approaches in the early stages of the programme to ensure that plans and approaches are relevant, timely and appropriate. Plans, budgets and agreed ways of working need to be develop to reflect this approach.

Key actions

1. Continue to work collaboratively across HMG, review and revise if necessary the principles, expectations and ways of working between the three Departments. A review should reflect on lessons learned in the inception phase of the programme. [By late October 2016, DFID SRO for the programmes]
2. Proactively liaise and engage with the IAG to monitor and develop strategies to minimise risks associated with the Climate Change Compass programme of work. [Monitoring on a quarterly basis by IMC & HMG]
3. Continue to proactively engage international partners including the GCF, GEF, CIFs and EuropeAid to share good practice, lessons learned and to harmonize monitoring, evaluation and learning strategies. [Quarterly engagement by DFID Evaluation Adviser]
4. Engage with contractors at strategically important decision points to ensure that activities are appropriate, robust, relevant and tailored to needs of ICF priority stakeholders in all three Departments (including DFID country offices). [To be agreed in July 2016 by the SRO ]
5. Facilitate appropriate levels of engagement and consultation with the Team Leader of the main Monitoring, Evaluation & Learning programme (Climate Change Compass) and the HMG Senior Policy Advisers with responsibility for developing the strategy for future climate investments.
6. Monitor the uptake of KPIs by ICF funded programmes. If there are low levels of reporting and self-selection bias (with some programmes only choosing to report on very few or certain KPIs) this should be escalated through the new ICF governance arrangements.
7. Revise the log-frame to ensure that it is relevant and appropriate for the next 12 months and develop the MEL’s meta-learning programme of work to ensure we learn from the innovative pilots that occur over the next 12 months –[To be completed by Cross-Gvt team by October 2016]
8. In the next 3 months IMC and HMG will work together to revise the risk register and issues log based on advice and feedback from the Independent Advisory Group [To be led by IMC and completed by end of August 2016]

Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING

Output Title	Provision of robust and appropriate tools and data to track core results across all relevant programmes.
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of usable Key Performance Indicators developed for collecting results data (excludes KPIs 3 and 10).	14	Achieved
Number of usable Key Performance Indicators used for collecting results data.	TBC	13
Proportion of ICF programmes that report against at least one KPI. / Disaggregated number reporting on KPI 15.	80%	Partially achieved: 70% of programmes with budgets of over £1million (based on ICF programmes receiving funding in 2015/16)
Number of usable supporting methodologies developed and used for collecting data	7	Not Achieved
Methodology for the Forest dependent people Key Performance Indicator and associated data collection	Collection of data in-country and development of methodology by IFRI. & or Pilot presentation of indicator, based on sample data and analysis by IFRI.	Achieved: IFRI has completed data collection and analysis from Nepal.
Updated baseline data on the Health benefits of clean energy by the World Health Organisation.	Updated baseline and benchmark for 2014-2019 established.	Achieved

Key Points

The main Monitoring, Evaluation and Learning contract (Climate Change Compass) is still within the inception phase. The inception report includes initial plans to develop KPI methodologies, field-test and support the use of KPIs as programme management tools that help programmes understand their results.

The inception report provides some initial plans about how to integrate KPI work with evaluation and learning activities. It also includes details about how to prioritise and develop sub-indicators, field test these and strategies for increasing reporting of KPIs. Communication and project management capacity have been identified as areas for improvement for the Climate Change Compass monitoring team, but over the past month we have agreed strategies to improve communication and project management.

The KPI supporting methodologies will be developed over the next 12 months. In late 2015, the HMG management group agreed with the Climate Change Compass programme that it would not be appropriate or represent value for money to start work on developing the supporting indicators before the work to prioritise KPI development plans has been completed. This log frame indicator will be reviewed and amended when the as when the log frame is revised.

The Climate Change Compass KPI team have completed a draft set of status review for each of the KPIs. These provide an overview which considers how widely each KPI is used, how accessible and useful the methodologies and guidance are, areas for development and analysis of indicators that other institutions such as the GCF and the CIFs are using. They also analyse how useful the indicators are at supporting project management. These documents will be finalised over the next 6 months with input from HMG staff and form the basis for prioritisation of the KPI workplan. All KPIs will be included in the prioritisation exercise. There are some concerns about the extent to which current plans reflect the degree to which climate finance is integrated within wider ODA expenditure and that reporting against all indicators is not mandatory.

In the next twelve months, the HMG management group will research and analyse why not all programmes are reporting on the KPIs. We will subsequently develop appropriate strategies to increase uptake and reporting on the KPIs.

Climate Change Compass is also responsible for the development of an indicator to assess the value of ecosystem services. A high level plan has been developed with the aim of enabling programmes to assess the value of ecosystem services protected by programmes. This indicator is closely related to two other forestry KPIs which are both being developed and field tested through different contracts with other organisations (IFRI and Ecometrica). The Climate Change Compass monitoring team organises regular meetings between IFRI and Ecometrica to ensure a coherent and co-ordinated approach which maximises value for money for HMG. Over the past three months this way of working has resulted in co-operation between IFRI and the Climate Change Compass monitoring team through a survey in Brazil which dramatically reduced the costs of obtaining important data. A similar activity is being planned in Ghana. It is important that time and costs associated with meetings are monitored very closely and that the budget for each indicator is agreed by all three Departments at the end of the KPI prioritisation stage.

The Climate Change Compass Monitoring team hosted a workshop on the ICF’s Transformational Change indicator. This highlighted best practice and promoted interaction between those successfully reporting and other programme managers interested in reporting. Feedback from the event was positive and participants reported that it provided clear guidance and ideas. As a result of this work, an increasing number of ICF programmes now plan on reporting to this indicator.

Our funding to the WHO has enabled the development of an indicator that is supporting national governments to understand use of clean fuels and technologies at a household level. This is supporting measurement of progress towards Sustainable Development Goal 7.

The WHO programme of work has produced a report “Burning Opportunity: Clean Household Energy for Health, Sustainable Development, and Wellbeing of Women and Children”. This has synthesised data on gendered impacts of household air pollution and identifies data gaps. This work aims to raise awareness and has supported the WHO to develop and pilot a series of survey questions on household cooking, heating and lighting to measure progress towards the SDG7 indicator.

Recommendations

- Increased integration of climate finance across ODA will lead to an increase in the number of programmes spending climate finance. However, many of these will not have climate change as their main goal. It is therefore essential that these programmes are supported to report on the ICF KPIs through the development of appropriate, relevant guidance. It is also important that the KPIs are useful tools that support programmes to manage performance and enable them to understand their results.
- The Independent Advisory Group has provided highly valuable feedback throughout the inception period to improve the quality and relevance of plans as well as to mitigate and manage risk. This system could be more commonly used in DFID programming and should be continued in to the implementation period.
- The cross-government management team will monitor the communication and project management capacity and skills of the Climate Change Compass monitoring team.
- The cross-government management group will monitor KPI plans carefully to ensure that they are practical, represent value for money and are relevant to ICF programmes. They will also ensure that this work complements activities being undertaken by other organisations and reflect best international practice.

Output Title	Generation of evidence and knowledge that addresses key strategic questions and evidence gaps.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Strategic programme of evidence from the ICF is generated that is relevant, robust and responsive to gaps in the evidence base	Inception report for robust, relevant evaluation and learning plans delivered	Achieved

Key Points

The Climate Change Compass team has delivered high quality, appropriate and relevant plans to evaluate and facilitate learning across the ICF portfolio in an inception report.

The Inception report recommends that 12-15 strategically important questions are identified through the thematic learning groups and discussions with stakeholders across HMG.  These questions will form the basis of all evaluation and learning activities. Methods to collect and analyse data and timeframes for delivery of findings will be based on needs for evidence and learning by stakeholders across HMG. The evaluation approach will primarily collect and analyse secondary evidence that is available through programme level evaluations, annual reviews and other published sources of evidence. The learning stream of work will primarily use interviews and facilitated discussions to identify learning and experience across the portfolio.  HMG, the contractors and the Independent Advisory Group agree that given the size, decentralised nature and complexity of the portfolio this is the most appropriate approach to evaluate and support learning across the ICF.

The Independent Advisory Group (IAG) has provided a range of timely, insightful and constructive feedback that has increased the quality and relevance of the plans and mitigated risks to the programme. The IAG has recommended that HMG accepts the inception report and they have commented that the plans are innovative, relevant and appropriate for a complex portfolio of climate change programmes. They recommend that we move ahead and pilot these to understand whether they are deliverable and appropriate, and that we reflect, learn and adapt plans when this is necessary based on feedback from HMG staff and the IAG.

Given the innovative nature of the plans that include combination of evaluation and real-time learning the IAG has recommended that HMG develops appropriate plans to monitor and mitigate risks in partnership with the contractors. Specifically, the IAG has commented that “While any innovation inevitably will bring some risks that will need to be monitored, there generally seems to be a good appreciation of these.” (IAG members feedback on MEL Inception Report in June 2016).

The evaluation is using a flexible, demand-driven approach and has an expert evaluation adviser guiding the use of this approach. The demand-driven aspect allows the evaluation to respond flexibly to future evidence needs of HMG and its delivery partners. The Climate Change Compass team is working with the ICF thematic working groups to ensure evaluation and learning plans are aligned with HMG’s needs for evidence and learning.

As a result of our successful engagement with the Climate Investment Funds (CIFs), lessons learned and good practice from the ICF MEL programme has informed the development of the CIFs Evaluation & Learning business plan and strategy.

We are engaging with and sharing learning with the Resilience Monitoring, Evaluation & Learning Community of Practice (CoP) to support the development of an effective and appropriate Community of Practice. Our work with this CoP is sharing of good practice and learning about monitoring, evaluation and learning about resilience building programmes with multilateral organisations (including the FAO), international NGOs and other partners.

The Climate Change Compass team has piloted a technical call down facility that has provided technical advice to support programmes to develop log frames. DECC Advisers have provided positive feedback about this service.

Our proactive engagement with colleagues working to monitor and evaluate the FCO’s Prosperity Fund to share lessons learned from the ICF Monitoring, Evaluation & Learning programme is reflected in Prosperity Fund’s monitoring, evaluation and learning strategy. This demonstrates the value of continued engagement with other government departments.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. Over the past 12 months, HMG has continued to proactively liaise and engage key stakeholders including the GCF, GEF and CIFs to ensure that the programme reflects international best practice.
2. We have worked collaboratively with the expert independent advisory group to ensure international best practice informs the programme and ensures the highest possible quality and relevance of outputs.
3. The Climate Change Compass contractors have engaged and worked closely with policy advisers with responsibility making decisions about future climate investments to ensure that plans are aligned with the needs of HMG.

Recommendations

1. To ensure that the ICF MEL programme delivers and communicates timely, relevant and accessible evidence that can inform future strategy and investment decisions, IMC’s Team Leader should engage in regular discussions with HMG Senior Policy Makers who are leading work to develop a strategy for future UK climate finance investments. This should complement the ICF MEL team’s work with the ICF Resilience, Low Carbon Development and Forestry thematic strategy and learning groups.
2. Sufficient DFID Programme Management time should be allocated to this programme to support its successful delivery. This should be at least 0.5 FTE of a B2 or A2L Programme Manager. All Departments involved should consider how they should contribute programme management and administrative resources to the programme to ensure equitable contributions.
3. HMG should continue to be proactive in engaging with strategically important multilateral and bilateral agencies to share learning, plans and ensure that the programme continues to develop in a way that minimises risk, maximises quality and is aligned with international best practice.
4. HMG should work closely with IMC to develop a meta-learning programme early in the implementation phase to ensure we are learning throughout the process about how best to create change from learning and evaluation.

Output Title	Development of knowledge management and results platform (Knowledgebase).
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Delivery of a shared web portal for climate results between the ICF partners (including DFID country offices).	Knowledge Platform used for Sept 2015 Results Commission	Achieved / September results commission was cancelled however the Platform was used for the Spring 2016 results commission.
ICF generated evidence is used by stakeholders within HMG and the International Community.	Knowledge Platform receives visits from 120 unique users (number to be defined July 2016)	Achieved (189 uniques users)

Key Points
The Knowledge Platform was used successfully in both the 2015 and 2016 results collections. Both collections ran well and the increased functionality of the platform allowed for easier quality assurance of results.

The platform has increased functionality, it contains programme data necessary for accurate tracking of cross HMG climate finance, as well as adaptation, and mitigation and forestry spend which is used to report to the UNFCCC.

A reports module has been established which simplifies the process for obtaining key data, this information can be accessed by analysts across DFID, DECC & Defra.

The Knowledge Platform played a key role in preparation for the UNFCCC meetings in Paris and has provided relevant and timely information that was used in negotiations.

The climate finance tool within the Knowledge Platform that is used by HMG departments to calculate spend through multilaterals was upgraded over the past 12 months and to improve its efficiency and accuracy.

Summary of responses to issues raised in previous annual reviews (where relevant)

The recommendation from the previous annual review was that the platform is developed with relevant training and tools to better support programmes to report results. This has been achieved. Gaiasoft have provided a range of e-learning tools and advice that has been tailored to the needs of programmes. In addition, the development of the Knowledge Platform has been supported through constructive discussions between IMC and Gaiasoft about how the Climate Change Compass Programme and Knowledge Platform can work together to deliver relevant, timely and useful tools for programmes.

Recommendations

1. HMG should work with Gaiasoft to support greater use of the Knowledge Platform among ICF programmes. HMG should continue to champion and promote the benefits of using the Knowledge Platform as a tool to measure results and record accord accurate information about climate finance. The Climate Change Compass programme’s engagement with programmes about use of key performance indicators and the knowledge platform should support the increased reporting of results through the Knowledge Platform.
2. It is important that any further development of the Knowledge Platform is aligned with the Aid Management Platform. It is likely that this will eventually provide much of the additional functionality needed from the Knowledge Platform. Any transition between the two must be well planned.
3. A learning outcome from the wider MEL programme is the value of having an Independent Advisory Group. Given the specialist skills needed in developing a digital platform we recommend creating an advisory group that provides specific advice for the Knowledge Platform. To date much support has come from DFID’s digital team and the Government digital service team. Increasing the role of these and other options should be investigated as part of any knew contract.
4. Support useful, relevant and timely discussions between the Climate Change Compass team and the Knowledge Platform teams to maximise the value of both contracts and help drive learning across the ICF.

Output Title	Effective promotion of learning to development partners and stakeholders
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Agreed process to engage key stakeholders in learning dialogue	50	Achieved
Agreed principles for high quality effective learning	10	Achieved
Improvements in understanding and effectiveness of learning across ICF investments	TBC	N/A

Key Points
Over the past 12 months, the ICF MEL programme has piloted and delivered a new qualitative approach to learning through the Sustainable Development Learning Dialogues. This was designed specifically to inform the main MEL contract . This approach has used appreciative enquiry centred around specific questions and thematic methods of analysis to identify lessons learned about integration and green growth from programmes. This approach has received positive feedback and a very high level of engagement from staff across DFID and bilateral programmes including BRACED. Feedback included: ‘It was useful to be involved in reviewing and analysing data collected from programmes’ DFID Adviser. However, feedback from advisers has also shown that some stakeholders would have found more specific findings more relevant and helpful to inform programme delivery and development decisions. eg: ‘Many of the findings were quite general and were interpreted in different ways by different people’ DFID Adviser. This learning will inform development of the Climate Change Compass programme.

A process was agreed to engage key stakeholders and an event was held in May that was attended by staff at DFID, DECC, ODI, CDKN and the BRACED consortium to share learning and discuss the method. We will be evaluating if, how and in which contexts elements from this approach have been used in autumn 2016 and whether they can be used in the Climate Change Compass programme in late 2016.

Through the programme we have developed ten principles for effective learning. These principles have received extremely positive feedback from DFID advisers and programme managers. The work is aligned with and supporting DFID’s wider organisational learning strategy. It is supporting programmes to be designed in ways that will support more decisions across CED and GRD’s programmes to be informed by evidence and learning (eg: the design of DFID’s forestry programmes and Energy Africa campaign). These principles have been shared with and are informing the work of our partners including the Climate Investment Funds (CIFs) and bilateral programmes such as BRACED.

CED’s Evaluation Adviser and Head of Change Team have noted an increase in the number of proactive requests for support in how to better capture learning within programme and evaluation design. This indicates that the work is supporting a positive change in team culture and better understanding of the value of integrating learning within future investments and real-time learning within evaluations.

When implementing innovative and new approaches to learning (e.g. the Sustainable Development Learning Dialogues), it is both time and resource intensive. Innovative pilot programmes require close monitoring and adaptive management techniques and need to be resourced accordingly. It is also important that any pilot of a learning technique includes within its final deliverables a separate write-up of the process implemented. This supports replication and quality assurance of new techniques.

The ICF Learning plan has been developed and accepted by the ICF Management Board.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. DECC & Defra have been consulted and engaged in the learning programme of work and we will continue to work closely with staff in both departments to ensure that plans are aligned with their needs and expectations.
2. The ICF Learning plan is complete and forms part of the wider ICF strategy.
3. We have played a proactive role in engaging with external partners, including the CIFs, GCF, MDBs and NGOs to share plans and learning. For example, we have shared our MEL plans and approaches with the Evaluation & Learning team at the CIFs and are working to ensure our learning strategies reflect international best practice and informing decision-making to maximise Vfm.

Recommendations

1. Continue to play a proactive role in engaging and liaising with external multilateral and bilateral partners to share learning plans, exchange good practice and sustain good working relationships.
2. Develop appropriate learning milestones for the main ICF MEL contract that enable DFID to assess the development of appropriate, credible, relevant and timely plans that meet the expectations and needs of stakeholders. This process should be informed by advice from the learning lead in the IAG.
3. Ensure relevant and effective synergies between the learning streams of work and both the evaluation and monitoring/KPI streams to ensure they are complementary, enhance the effectiveness and support of each stream of work. This approach should also maximise value for money for HMG.
4. To develop a strategy to evaluate learning to understand if and how learning has informed the development of practice and design of programmes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key costs drivers for the programme are the cost of external expertise and resources through four contracts that support the collection, analysis and communication of results, evidence and lessons learned from the ICF. This programme of work is necessary to understand and demonstrate results and lessons learned that will provide an evidence base for future climate investments by HMG and our international partners. It is also crucial to demonstrating accountability to the public in relation to a significant investment of public funds.

There are no changes to cost drivers that were identified in the Business Case.

VfM performance compared to the original VfM proposition in the business case

Economy: The suppliers for the main Monitoring, Evaluation and Learning contract were procured through an open competitive process to ensure international competition and value for money from a wide variety of suppliers. This process was led in accordance with best international practice in procurement. In addition, procuring the majority of services through one main contract is judged to provide good value for money because it avoids significant staff resource spent managing a variety of smaller contracts, thus reducing staff time and administration costs.

Efficiency: DECC and DFID Evaluation Advisers and Statisticians have generally been satisfied with the time frame for the delivery of services and the quality of deliverables. DFID and DECC Advisers have proactively reviewed and provided feedback about the number of people and days involved in delivering each output to ensure VfM.

Effectiveness: Advisers at DFID, DECC & Defra have confirmed that the IFRI, WHO, Climate Change Compass and Knowledge Platform contracts are highly relevant to ICF programmes and the capacity of HMG to report results and demonstrate the impacts of the ICF. The services provided by the suppliers to date have been thorough, useful and the majority have been completed to acceptable standards. Advisers at DFID, DECC & Defra have monitored the effectiveness, quality and relevance of the main Monitoring, Evaluation & Learning contract’s plans and deliverables with advice from the Independent Advisory group (IAG). It is evident that the more technically challenging the area of work, the more technical resource needed to manage effectively and this will be considered going forward. This has supported delivery of high quality and relevant evaluation and learning plans that represent VfM. Some of the KPI plans that have been developed through the main contract have been less relevant to the current status of ICF programmes, as they do not sufficiently reflect the degree to which reporting is not mandatory and the importance of integration of climate finance within ODA funded programmes.
Assessment of whether the programme continues to represent value for money

The programme is judged to represent good value for money.

Quality of financial management

Acceptable

Date of last narrative financial report	June 2016
Date of last audited annual statement	June 2016

E: RISK (½ page)

Overall risk rating
Moderate

Overview of programme risk

The key risks that are related to the programme include:

- Limited capacity of HMG staff with relevant skills and time to engage in this programme of work.
- Differential capacity to manage the respective workstreams across Departments.
- Lack of co-ordination and clarity of roles and responsibilities between staff from different Departments leading to duplication of tasks, providing advice to contractors that is not co-ordinated and confusing.
- Lack of progress in the KPI workstream, which means that the impact of the programme on results collection 2017 will be limited.
- Lack of synergies between the main Monitoring, Evaluation & Learning contract and the development of the strategy for UK Climate Investments - and lack of understanding of decision-making, particularly for DFID programmes
- Low buy-in and take up of ICF KPIs due to the perceived complexity and time involved in reporting
- Low engagement and interest from internal and external partners due to evidence and learning perceived to be not relevant to needs or using inaccessible language and methods to communicate.
- Challenge of using an appropriate framework and gathering robust evidence from a highly complex, decentralised and diverse portfolio of programmes, rather than one programme.
- The chosen evaluation approach is highly innovative and untested within climate change programmes and carries associated risks.
- A limited pool of consultants with skills to deliver a successful programme of work.

Key actions undertaken in the past 12 month to mitigate risks include:

Working in ways that reflect the clear roles and responsibilities of Departments that are formalised in a MoU. These roles and responsibilities and ways of working will be reviewed and amended as appropriate based on the experiences of the inception phase in the next 3 months.

Team Leaders in DFID and DECC proactively reviewing human resources available to monitor the capacity and sufficiency of staff to effectively manage the programme. A challenge over the past 12 months has been the lack of programme management staff and time allocated to the programme.

The Independent Advisory Group are mitigating risks related to the quality of deliverables, engagement of partners and risks relating to the complexity and diversity of the portfolio by providing timely, relevant and appropriate feedback about the quality and relevance of plans.

Outstanding actions from risk assessment

In the next 3 months IMC and HMG will work together to revise the risk register and issues log based on advice and feedback from the Independent Advisory Group. We will monitor and manage the contract based on these documents with support for the Independent Advisory Group. As and when this is appropriate we will escalate issues with Senior Civil Servants to ask for advice.

We will also develop a structured plan and way of working between HMG staff with responsibility for developing the UK Climate Investment Strategy and the consultant to support the relevance and alignment of plans. All three Departments will agree areas of expenditure across the MEL programme to ensure that overspend in one area does not impact upon resources and deliverables in other areas.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Delays caused by finalisation and approval of the Terms of Reference for the MEL programme of work by the five Government Departments involved in the ICF, will mean that all of the activities will now complete in August 2019, rather than March 2018. However, we expect significant progress and delivery of major outputs in relation to the main contract to be achieved by March 2018.

Performance of partnership (s)
Advisers at DFID, DECC and Defra have generally been satisfied with the quality, relevance and timeliness of outputs delivered by partner agencies to date. The plans developed for the KPIs are less relevant to the current status of ICF funded programmes, given that reporting is voluntary rather than mandatory and the increasing integration/mainstreaming of climate finance. In addition, current methodologies do not sufficiently support consistency of reporting.

To address these concerns, the next phase of the contract will involve development of more comprehensive guidance and methodologies for the KPIs and work to prioritise the development of strategically important KPIs that can improve programme management and facilitate more comprehensive reporting of results.

A key challenge in the next 12 months will be to ensure that the contractors work effectively with senior policy colleagues responsible for developing the future UK Climate investment strategy to ensure that evidence and learning informs strategic decisions about future investments. Over the next 4-6 weeks we will further clarify expectations and agree appropriate levels of engagement between HMG and IMC Worldwide during the implementation phase of the contract and provision of technical advice.

Asset monitoring and control
NOT APPLICABLE

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

NOT APPLICABLE

H: MONITORING & EVALUATION (½ page)

Monitoring progress throughout the review period

Monitoring and evaluation arrangements are considered sufficient for this programme.

Alpine/GaiaSoft, IFRI and the WHO produce regular quarterly reports with performance and financial updates that are reviewed by the Programme Managers and relevant policy advisers at DFID. In addition, the contract manager of the Knowledge Platform is seeking regular feedback from ICF programme managers about the use and accessibility of the Knowledge Platform. This feedback is informing the development of the Knowledge Platform. We have received a financial and narrative report for the main ICF MEL contract for the inception phase of the contract. During the implementation phase of the main MEL contract (early July 2016-August 2019) we will continue to receive quarterly financial reports and monthly narrative reports.

There have been weekly meetings with Advisers at DFID, DECC and Defra to monitor and assess progress and harmonization between all outputs and streams of work. This has ensured a co-ordinated cross departmental approach to managing progress and performance toward to procuring the main Monitoring, Evaluation and Learning contract.

Monthly cross-government meetings and quality assurance reviews of all outputs by analysts at DFID, DECC and Defra have played a key role in monitoring and evaluating the main Monitoring, Evaluation and Learning contract. In addition, an independent expert advisory group has been established to support HMG’s capacity to evaluate the quality of the deliverables of the programme and ensure that they are aligned with international best practice.

ANNEX A 2014/15 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Monitoring, Evaluation and Learning Programme (formerly the ‘Results, Evidence and Knowledge Programme)
Programme Value: £12.72 million		Review Date: 1 August 2015
Programme Code: / 203516	Start Date: / 1 August 2014	End Date: / 1 August 2018

Summary of Programme Performance
Year	2014/5
Programme Score	A
Risk Rating	Low

Summary of progress and lessons learnt

Over the past twelve months the ICF Monitoring, Evaluation and Learning programme has delivered a range of useful, timely and relevant outputs. These include a web-based Knowledge Platform that is supporting the collection of ICF programme results and knowledge, a cross-government Monitoring, Evaluation and Learning strategy. DFID has also procured a comprehensive and complex monitoring, evaluation and learning contract that will strengthen collection of results, generate robust evaluative evidence and share lessons learned within HMG and to strategically important external partners.

Activities over the past year have led to the development of valuable plans and outputs that are a strong foundation for the four year programme. Positive feedback about the quality, timeliness and relevance of outputs has been provided by staff at DFID, DECC and Defra.

 Key lessons learned from the programme include:

1. Effective cross-government collaboration is crucial to ensuring that the complex programme successfully meets the needs of HMG, external stakeholders and delivers the highest quality outputs.
2. Building successful relationships and collaborating across different organisations takes time and may impact on the speed at which a programme can deliver results.
3. Sufficient Technical Adviser and Programme Management staff, time and skills across HMG is central to delivering a successful and complex programme of work. It is important that senior managers in all HMG Departments regularly review the availability of internal expertise and staff resources, and take appropriate action where necessary, to ensure delivery of a successful programme.

Summary of recommendations for the next year

1. Continue to work collaboratively across HMG to develop robust plans and quality assure outputs in accordance with international best practice.
2. Undertake research to understand why some ICF programmes do not report results through the Knowledge Platform. Subsequently, develop a strategy to incentivise reporting of results.
3. Ensure that monitoring, evaluation and learning activities are complementary and harmonized
4. Proactively engage international partners including the GCF, GEF, CIFs and EuropeAid to share good practice, lessons learned and to harmonize monitoring, evaluation and learning strategies.
5. Based on the findings from the Inception Report of Output 2, prepare a cost and/or time extension for the main Monitoring, Evaluation and Learning contract that reflects any additional VAT costs, needs for additional work and costs related to the timeframe of the ICF.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process