## Sheet1
PROJECT NAME | UK Humanitarian Response in CAR 2015-2016
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
Save lives and reduce suffering of the population affected by the ongoing crisis in CAR, including refugees in the region | Cumulative number of individuals reached with DFID humanitarian assistance in CAR and CAR regional in 2014/2016 (includes double counting across agencies | Planned |  |  |  | 1460735
Achieved
Source
Achieved
FAO, ICRC, CHF, SI consortium, IMC consortium, UNHCR, MSF, WFP, START network
OUTCOME | Outcome Indicator 1 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
Central Africans access essential services through multi sectoral relief effort | Cumulative number of Individuals reached with DFID humanitarian assistance (food, health, cash, agricultural inputs) in CAR in 2014/2016 (includes double counting across agencies) | Planned |  |  |  | 993728 | Security situation does not deteriorate and agencies are able to continue operating.
Achieved
Source
FAO (1st + 2nd project), ICRC (single counted beneficiaries - See IRS), CHF (single counted beneficiaries - See IRS), SI consortium, IMC consortium (Benef of 1st project - no double counting).
| Outcome Indicator 2 |  |  | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
| Cumulative number of Individuals reached with DFID humanitarian assistance in CAR regional in 2015/2016 (includes double counting across agencies) |  |  |  |  | 467007
MSF, WFP (cumulative total of 2 contracts), UNHCR Chad, UNHCR Cameroon (Cumulative total 3 contracts), START network
| Outcome Indicator 3 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
| Crude mortality rate in prefectures of intervention does not increase | Planned | 3.14, 3.34, 0.82, 0.75, <5 |  | 3.14, 3.34, 0.82, 0.75, <1 | 3.14, 3.34, 0.82, 0.75, <1
Achieved
Source
October 2014 and 2015 SMART survey results (Bangui, Ouham, Nana Gribizi, Basse Kotto, Haute Kotto), Cameroon East and Adamaoua, MSF.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
£40m
INPUTS (HR) | DFID (FTEs)
1.5 A2/A2L, 0.5 B1
LIVELIHOODS AND FOOD SECURITY
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
The agro-pastoral production in the targeted areas is improved and reinforced | Number of people reached through general food distribution (GFD) and cash transfers by ACF/ DRC/ SI | Planned |  |  | 480
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ACF/ DRC/ SI |  |  |  |  | High
| Output Indicator 1.2 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
| Number of people reached through livelihood assistance by ACF/ DRC/ SI | Planned |  |  | 158750
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ACF/ DRC/ SI (Beneficiary table Result 1 + result 2) |  |  |  |  | High
| Output Indicator 1.3 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
| Proportion of the targeted population improving their Coping Strategy Index Score | Planned |  |  | 50%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ACF/ DRC/ SI |  |  |  |  | High
| Output Indicator 1.4 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of people reached through general food distribution, cash and voucher (GFD) by ICRC | Planned |  |  | 8932 |  | based on 2013 final results and based on a DFID contribution of 6.6% of the appeal (this may change if the appeal or contribution changes)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ICRC MTR + end of year report |  |  |  |  | Medium
| Output Indicator 1.5 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of people reached with livelihood assistance by ICRC | Planned |  |  | 4015 |  | based on 2013 final results and based on a DFID contribution of 6.6% of the appeal (this may change if the appeal or contribution changes)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ICRC MTR + end of year report |  |  |  |  | Medium
| Output Indicator 1.6 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of people reached in food security/livelihood sector by CHF | Planned |  |  | 3540 |  | Based on CHF beneficiary reach in 2014 (as presented in the 2014 annual review) and the assumption that we can extrapolate that with a contribution twice as large in 2015 we will have this share of beneficiaries
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CHF (Nb: See original IRS + reach increased for equivalent of £4m). |  |  |  |  | High
| Output Indicator 1.7 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (July 2016) | Target (Dec 2016) | Assumption
| Number of people who have received livelihood assistance through FAO. | Planned |  |  | 172060 | 372060
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | FAO (The full target is the cumulative total of target reach under 205/16 project + target reach under the 2016/17 programme.) |  |  |  |  | Medium
IMPACT WEIGHTING (%) | Output Indicator 1.8 |  | Baseline (April 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
20% | Food security for 4 to 6 months is ensured for beneficiaries. | Planned |  |  | 95 | 95
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | FAO |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | Not included in this logframe | Not included in this logframe |  | 100%
INPUTS (HR) | DFID (FTEs)
HEALTH AND NUTRITION
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
Affected population have an improved access to healthcare | Number of beneficiaries reached in the healthcare sector by ICRC | Planned |  |  | 30422 |  | ICRC expected reach in health an protection is not provided. However based on 2013 final results and based on a DFID contribution of 6.6% of the appeal (this may change if the appeal or contribution changes)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ICRC |  |  |  |  | High
| Output Indicator 2.2 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of beneficiaries reached in the healthcare sector by CHF | Planned |  |  | 120888 |  | Based on CHF beneficiary reach in 2014 (as presented in the 2014 annual review) and the assumption that we can extrapolate that with a contribution twice as large in 2015 we will have this share of beneficiaries
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CHF (Initial £2m + £4m approved in Sep 2015==>Initial targetx3) |  |  |  |  | High
| Output Indicator 2.3 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of beneficiaries reached in the healthcare sector by the IMC consortium | Planned |  |  | 269354 | 269354
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | IMC/ SC/ MENTOR/ Oxfam (Same reach with 2016 cost extension as same population covered) |  |  |  |  | High
| Output Indicator 2.4 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Health service utilization rate (based on number of beneficiaries reached with new consultations) | Planned |  |  | 1 consultation per person per year | 1 consultation per person per year
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | IMC/ SC/ MENTOR/ Oxfam |  |  |  |  | High
| Output Indicator 2.5 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Number of acute malnutrtion cases from the targeted areas that gain access to treatment | Planned |  |  | 1277 | 1795
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | IMC/ SC/ MENTOR/ Oxfam |  |  |  |  | High
| Output Indicator 2.6 |  | Milestone 1 (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
| Cured rate among children treated for MAM and SAM | Planned | 70% |  | >75% | >75%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | IMC/ SC/ MENTOR/ Oxfam |  |  |  |  | High
IMPACT WEIGHTING (%) | Output Indicator 2.7 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
10% | Number of health facilities with access to sanitation with a ratio of 1 latrine/ 20 users | Planned | 0 |  | 10
Achieved
|  | Source |  |  |  |  | RISK RATING
IMC/ SC/ MENTOR/ Oxfam
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | Not included in this logframe | Not included in this logframe |  | 100%
INPUTS (HR) | DFID (FTEs)
PROTECTION
OUTPUT 3 | Output Indicator 3.2 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
Central Africans enjoy an improved protection environment | Number of benificaries supported in the protection sector by the CHF | Planned |  |  | 43080 |  | Based on CHF beneficiary reach in 2014 (as presented in the 2014 annual review) and the assumption that we can extrapolate that with a contribution twice as large in 2015 we will have this share of beneficiaries
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CHF (Initial £2m + £4m approved in Sep 2015==>Initial targetx3) |  |  |  |  | High
| Output Indicator 3.3 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
| Number of benificiaries supported in the protection sector by the SI consortium | Planned |  |  | 74600
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ACF/ DRC/SI |  |  |  |  | High
| Output Indicator 3.4 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Dec 2016) | Assumption
| Increase in the % of people who have percieved an improvement in their protection and safety situation (e.g. cases of violence, conflict, inter or intra community disputes, abuse, family revenges) | Planned |  |  | 25%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | ACF/ DRC/SI |  |  |  |  | High
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (June 2016) | Target (Sep2016) | Assumption
10% | Number of GBV survivors who access remedial services through IMC, DRC and ICRC. | Planned | N/A |  | N/A | N/A
|  | Achieved |  |  | 1682
|  | Source |  |  |  |  | RISK RATING
|  | IMC/ SI / ICRC: For IMC + ICRC, target not defined for this indicator. (GBV: Source ICRC Annual rep + IMC logframe + SI narrative Q2 + Q3 + Q4) |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | Not included in this logframe | Not included in this logframe |  | 100%
INPUTS (HR) | DFID (FTEs)
PERFORMANCE OF THE SYSTEM AND COORDINATION
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
The CHF actively contributes to strengthened humanitarian coordination and response | Percentage of overall funding received from all donors by 30 June 2015 is allocated before 31 December 2015 / received by 31 December 2015 and allocated before 30 Jubne 2016. | Planned | N/A |  | >80%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CHF (allocation documents / MPTF gateway) |  |  |  |  | High
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (March 2015) | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumption
15% | Percentage of projects monitored through field visits within their project duration | Planned |  |  | 40%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CFH quarterly reports |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | Not included in this logframe | Not included in this logframe |  | 100%
INPUTS (HR) | DFID (FTEs)
REGIONAL REFUGEE RESPONSE (Cameroon, and Chad)
FOOD SECURITY (WFP)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumptions
Central Africans receive basic food assistance in Cameroon. | Number of people reached through general food distribution (GFD) in Cameroon. | Planned | 0 | 86100 | 145567 |  | Security environment enables the continuation of operations. Data on support to refugees is reliable. There are no pipeline breaks or ration reductions. WFP planning figures on the number people requiring assistance reflect arising needs. Target for food assistance is for a period of 3 months.
Achieved
IMPACT WEIGHTING (%) |  | Source |  |  |  |  | RISK RATING
10% |  | WFP reporting (Comulative total - Milestone 2 = total 1st + 2nd contract, ie 86,100+59,467) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
| 2014: £2.5 million contribution (March 2015 indicator). 2015: £1.5 million contribution (March 2016 indicator). |  |  |  | 100%
INPUTS (£) | DFID (FTEs)
HEALTH AND NUTRITION (MSF)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone 1 (Dec 2015) | Milestone 2 (March 2015) | Target (Dec 2016) | Assumptions
Central African children in Cameroon receive treatment for acute under-nutrition. | Rehabilitation recovery rate (%) for children suffering Severe Acute Under-nutrition (SAM) who have received MSF Community Based Management of Acute Malnutrition. | Planned | 55 | 65 | 75 |  | Other actors provide the necessary complementary activities including registration, protection, general food distribution, shelter and water and sanitation.
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | MSF nutritional register/ MSF reporting to DFID. |  |  |  |  | Medium
| Output Indicator 6.2 |  | Baseline | Milestone 1 (Dec 2015) | Milestone 2 (March 2015) | Target (Dec 2016)
| Number of people reached with MSF health interventions. | Planned |  |  | 30000
Achieved
Source
IMPACT WEIGHTING (%) |  | MSF reporting .
5%
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
| 2014 £1 million |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
MULTI-SECTOR (UNHCR)
OUTPUT 7 | Output Indicator 7.1 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumptions
Central Africans arriving in Cameroon as refugees have their most basic needs met, including shelter and water and sanitation. | Average supply of water per person per day in the 7 refugee sites reaches a minimum of 15 litres per day in Cameroon (WASH) | Planned | 12 | >15 | >15 |  | Security situation does not deteriorate. Agencies continue to gain access to beneficiaries. Data is reliable. Implementing partners have capacity to deliver. Agency funding levels are sufficient for partners to provide assistance across the population of Central Africans arriving in Cameroon and Chad. UNHCR's planning figures for the number of refugees arriving in Cameroon and Chad reflects the arising number of refugees.
Achieved
Source
UNHCR reporting
IMPACT WEIGHTING (%) | Output Indicator 7.2 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
20% | Number of emergency shelters provided in Chad (Shelter) | Planned | 100 | 636
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | UNHCR reporting |  |  |  |  | Medium
| Output Indicator 7.3 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
| Number of people reached by with UNHCR multi-sector assistance in Chad. | Planned |  | 56000
Achieved
Source
UNHCR reporting
| Output Indicator 7.4 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
| Number of people reached by with UNHCR multi-sector assistance in Cameroon. | Planned |  | 60000 | 68704
Achieved
Source
UNHCR reporting (The March 2016 figure is the cumulative total of 60,000 (AR reported under 1st contract) + contribution to 2nd appeal (8,704)
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
2014: £5 million overall contribution UNHCR Cameroon, and £1.5 million UNHCR Chad.
INPUTS (HR) | DFID (FTEs)
MULTI-SECTOR (START Network)
OUTPUT 8 | Output Indicator 8.1 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016) | Assumptions
Central Africans receive multi-sector assistance both in refugee camps and outside of camps in communities in Cameroon. | Number of people reached with multi-sector humanitarian assistance with START network activities. | Planned | 0 |  | 179,526 people (91,196 female, 88,330 male) |  | Management and governance structures established by the START Network to manage to contribution. Agencies represented on the peer-managed committees have the resources (people/time) to invest in this activity. Agency representatives on the peer-managed committees are able to review without agency bias. Projects submit timely reporting formats with good quality data. Project managers are willing to adjust their activities in response to lessons learned, and contractual commitments allow these changes. Agricultural production is a sustainable activity for refugees beyond the life of this programme, and diversifies their intake of food which meets their nutritional requirements.
Achieved
Source
START Network reporting
IMPACT WEIGHTING (%) | Output Indicator 8.2 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
10% | Start Network mechanisms deliver rigorous decision-making for selecting projects and learning. | Planned | Limited capacity on the ground for inter-agency coordination and no peer-review mechanism in place for decision-making and learning | Decisions made by the Project Selection Committee are well-documented in meeting minutes and transparent selection criteria are used. Decisions are based on needs analyses, evidence of the project’s engagement with affected people and the technical strength of proposals. | Lessons learned have been documented with evidence of adjusting programmes in response to emerging needs analyses, engagement with affected people and the findings of their technical teams. Programmes are course-corrected if needed.
Achieved
Source
START Network reporting, DFID-START Network dialogue on lessons learned
| Output Indicator 8.3 |  | Baseline | Milestone 1 (March 2015) | Milestone 2 (March 2016) | Target (Dec 2016)
| Proportion of beneficiaries (5481) who report an increase in vegetable production and acceptable food consumption score at the end of the project. | Planned |  |  | At least 80% beneficiaries report increased vegetable production and have an acceptable Food Consumption Score at the end of the program.
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | START Network reporting, DFID-START Network dialogue on lessons learned; post-harvest monitoring, PDM. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
| £3 million |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)