Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value: £8,014,091		Review Date: 1 July 2016
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Medium	Major

Summary of progress and lessons learnt since last review

COUNTDOWN is a research consortium dedicated to investigating cost-effective, scale-up and sustainable solutions, necessary to control and eliminate the seven most common Neglected Tropical Diseases by 2020. COUNTDOWN has made good progress in the past year, with all milestones met or partially exceeded. It has established its research programme in Ghana and Cameroon, and following the approval to expand the research in Nigeria, and re-establish activities in Liberia, progress has been also been made establishing research in these countries as well.

There has been positive engagement with key policy makers in the targeted countries, including the Minister of Health in Cameroon involved in the in-country launch and an opportunity to engage with the World Health Organisation (WHO) African Regional Program Review Group for Neglected Tropical Diseases (NTDs) at COUNTDOWN’s partner meeting in Accra.

Publications have included four submissions of articles to peer reviewed journals, including Lancet Infectious Diseases and International Health, and COUNTDOWN staff co-authoring a book chapter on the Social and Economic Impact of Neglected Tropical Diseases in Sub-Saharan Africa.

As the programmes are developed, COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. DFID has also spoken to COUNTDOWN regarding tightening up its financial accounting, with accurate budgeting, and only claiming for expenditure that has already been spent.

Summary of recommendations for the next year
1. COUNTDOWN should ensure that its submissions to peer-reviewed journals and knowledge products; presentations/ blogs/ briefs are as operationally relevant as possible, and be targeted to key policy makers in affected countries and implementing organisations (ACTION: COUNTDOWN – ongoing)
2. COUNTDOWN should increase its collaboration with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. DFID will ensure that COUNTDOWN is involved in NTD partner meetings whenever these take place. (ACTION: COUNTDOWN & DFID – immediate and ongoing)
3. COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. (ACTION: COUNTDOWN – immediate and ongoing)
4. COUNTDOWN should reconsider its proposed work on products (particularly diagnostics), following discussion with DFID, and ensure this work is complementary to the work of the DFID funded Product Development Partnerships in this area. (ACTION: COUNTDOWN – November 2016)
5. DFID has discussed with COUNTDOWN regarding improving the financial management, with accurate budgeting, and only claiming for expenditure that has already been spent. (COUNTDOWN – already actioned, following meeting with DFID)

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

Outline of the programme

DFID’s Research and Evidence Department (RED) commissioned a programme of NTD Implementation Research that will directly contribute to the achievement of the 2020 NTD elimination and eradication goals through providing a greater understanding of how best to cost-effectively and sustainably deliver integrated NTD Control Programmes at scale.

This is linked to DFID’s wider work on tackling NTDs, and DFID has committed £245 million to supporting the control of Neglected Tropical Diseases (NTDs) over the period 2011-15.

The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) programmes to treat and control up to 7 NTDs (schistosomiasis, lymphatic filariasis, onchocerciasis, trachoma and three soil transmitted helminths) simultaneously.

The total amount of funds available for the programme was £15 million. Following a tendering process, Liverpool School of Tropical Medicine (LSTM) was awarded a contract for £7,012,587 and this has recently been increased to £8,014,091for delivering this research programme. The increased figure will allow them to upscale their work in Nigeria, a country with one of the greatest NTD burdens globally.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A – outcome met expectations

The outcome indicator is improved availability, acceptability, affordability, and accessibility of NTD interventions to individuals and communities. COUNTDOWN’S theory of change has been adjusted in order to articulate assumptions about how programme activities will have to unfold for the project to move from outputs through intermediate outcomes to the ultimate desired outcome. This will enable assessment about whether COUNTDOWN is successfully progressing through the theory of change.

COUNTDOWN is still at a very early stage of the programme, and it is not possible to clearly assess whether the outcome will be met. However there are indications that it is progressing well, with establishment of research studies and good involvement of key stakeholders in the targeted countries.

Overall output score and description: A – outputs met expectations

COUNTDOWN has made good progress in the past year, with all output milestones met or partially exceeded. It has established its research programme in Ghana and Cameroon, and following the approval to expand the research in Nigeria, and re-establish activities in Liberia, progress has been also been made establishing research in these countries as well.

There has been positive engagement with key policy makers in the targeted countries, including the Minister of Health in Cameroon involved in the in-country launch and an opportunity to engage with the WHO African Regional Program Review Group for NTDs at COUNTDOWN’s partner meeting in Accra.

Publications have included four submissions of articles to peer reviewed journals, including Lancet Infectious Diseases and International Health, and COUNTDOWN staff co-authoring a book chapter on the Social and Economic Impact of Neglected Tropical Diseases in Sub-Saharan Africa.

As the programmes are developed, COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale.

COUNTDOWN has addressed gender across the programme, raising the profile of NTDs and gender globally, including running a workshop on equity, gender, disability and NTDs at the American Society of Tropical Medicine and Hygiene conference, and looking into measures of gender equity through expanded access to treatment for Female Genital Schistosomiasis (FGS).

Key lessons
The challenges regarding financial management highlighted for DFID the importance of monitoring partners’ statement of accounts. It was through this monitoring that DFID identified that LSTM was claiming some funds in advance of need, which was outside the terms of the contract. By addressing the issue early, and discussing the problem in person with LSTM, it was possible to identify solutions together. As a result of these actions, this problem has been rectified.

Key actions
The key actions for COUNTDOWN are to increase communication and collaboration with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. To maximise the outcomes of the research towards the theory of change, COUNTDOWN should ensure that its written submissions (whether to peer-reviewed journals or knowledge products) are as operationally relevant as possible, and that COUNTDOWN remains focussed on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD programmes at scale. Discussions have already taken place with COUNTDOWN regarding tightening of financial management, with accurate budgeting, and only claiming for expenditure that has already been spent, which has been addressed.

Has the logframe been updated since the last review?
Yes. Following the expansion of the research programme into Nigeria, and re-establishment of activities in Liberia, DFID worked with COUNTDOWN to review the logframe, milestones and indicators. Therefore the logframe has been significantly updated since the last annual review to take into account these changes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		Y (revision of risk categories)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Evidence-based strategies identified through COUNTDOWN research and evidence synthesis initiatives.	Research begins in two countries (Ghana and Cameroon) in response to priority needs of NTD policy makers and programmes.	Met. Evidence gaps identified through multi-stakeholder meetings at national, regional and district levels in both Ghana and Cameroon.
Open-access knowledge products/ peer reviewed journal articles.	3 peer reviewed articles submitted.	Slightly exceeded. 4 peer reviewed articles and submitted for publication
Open-access knowledge products; presentations/ blogs/ briefs.	40 products developed and disseminated.	Slightly exceeded. 59 blogs added to the COUNTDOWN website and Twitter Feed

Key Points

Output met expectations. Whilst the research is at an early stage, COUNTDOWN has been able to establish its research programme in Ghana and Cameroon, with research activities initiated and preliminary surveys carried out. The work in Cameroon has included alternative strategies for use of doxycycline for control of onchocerciasis, and DNA extraction to allow optimisation of novel diagnostic techniques. COUNTDOWN should liaise closely with the DFID funded Product Development Partnerships that are working on drugs and diagnostics for NTDs to ensure complementarity between these areas of work, and ensure COUNTDOWN remain focused on its core priorities (see recommendation in output 3). The work in Ghana included co-authoring a book chapter on the Social and Economic Impact of Neglected Tropical Diseases in Sub-Saharan Africa with COUNTDOWN colleagues. Following DFID approval for COUNTDOWN to recommence activities in Liberia, COUNTDOWN is planning research activities to start in late 2016, following a 6 month inception period. Approval was also given to extend the research into Nigeria, and COUNTDOWN has focussed on establishing operations and recruiting in Nigeria.

The four articles submitted to peer reviewed journals, include Efficient and equitable control of schistosomiasis and helminthiasis submitted to the Lancet Infectious Diseases, a COUNTDOWN on control of NTDs to Parasitology, a call to action for female genital schistosomiasis to Journal of Parastiology, and Tailoring mass drug administration to context to International Health.

Summary of responses to issues raised in previous annual reviews (where relevant)

COUNTDOWN has responded to the recommendations in last year’s annual review to expand activities in Nigeria, and to lay out a specific, limited scope of work in Liberia, both of which have been agreed by DFID. COUNTDOWN has also revised the logframe to take account of the changes in the programme, which has been agreed by DFID, and is reflected in this year’s annual review.

Recommendations

COUNTDOWN should ensure that its submissions to peer-reviewed journals and knowledge products; presentations/ blogs/ briefs are as operationally relevant as possible, and be targeted to key policy makers in affected countries and implementing organisations (ACTION: COUNTDOWN – ongoing)

Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control.
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	35%
Risk revised since last AR?		Y (revision of risk categories)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Revised NTD national plans and roadmaps in SSA countries as updated by evidence of scale up of pro-poor, effective and efficient approaches.	Knowledge gaps identified through a collaborative process at National/ State/ District level involving MoH partners, multisectoral policy makers and key stakeholders in 2 COUNTDOWN countries.	Met. Conducted a series of activities in Ghana and Cameroon to clarify and prioritise knowledge gaps collaboratively
Multi sectoral networks influenced to include evidence-based NTD programme strategies in planning within and beyond the health sector.	COUNTDOWN begins examining National/ State/ District operational plans in 2 COUNTDOWN countries to determine NTD priorities and assess which would benefit from new evidence-based strategies and multi-sectoral working.	Met. Activities ongoing in Ghana and Cameroon, and will start in other focal countries later this year.
Case studies demonstrate a portfolio of change in the utilisation of evidence occurring at a national, state and district level.	2 case studies describe policy/ operational plan analysis priorities in two countries (Ghana and Cameroon).	Met. 2 relevant case studies produced. Cameroon - Onchocerciasis and Liberia - Health System approach

Key Points
The output met expectations. A stakeholder meeting, convened in Accra, was used to share information on the research project’s purpose and activities, and discussed how collaboration among multi-sectoral partners could be strengthened in support of NTD programming, and what research evidence was needed to support implementation of the NTD programme. A preliminary set of policy and programme improvements were identified to which the evidence generated by COUNTDOWN could contribute; these included i) vector control for lymphatic filariasis, and more effective collaboration with the malaria programme, ii) treatment strategies for onchocierciasis, iii) measures of gender equity, iv) documented improvements in treatment compliance, v) integration of schistosomiasis surveillance into policy programming, vi) expansion of delivery channels for praziquantel to tackle schistosomiasis.

The Minister of Health in Cameroon was involved in the in-country launch on 9th October 2015. Various stakeholder meetings have taken place, which identified research priorities (from an operational perspective) to be; i) co-endemicity of lymphatic filariasis, onchocerciasis and loa loa, ii) addressing reinfection of schistosomiasis, iii) targeting / reach of deworming campaigns.

Three case studies were included in COUNTDOWN’s annual report. However the case study for Ghana was not included in the indicator above, as it was more a general reflection on approach to MDA, rather operational plan analysis specific to Ghana. Three strands of research were identified which address the NTD operational priorities with relation to control of onchocerciasis in Cameroon. In Liberia, several priority implementation research areas were identified for COUNTDOWN through stakeholder consultation. These included i) leadership and governance (including collaboration between Ministries of Education, Agriculture and Health), ii) health financing, and iii) supervision/motivation/management of health staff, iv) resilience of supply chain mechanisms, and v) re-mapping of disease prevalence. It is important to ensure that NTDs remain the focus of this work on health systems, and caution should be taken to avoid mission creep into more general health systems research.

Summary of responses to issues raised in previous annual reviews (where relevant)
The logframe and indicators have been updated.

Recommendations

Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country based research communities.
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Y (revision of risk categories)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Involvement of multi-sectorial stakeholders at national, state and district level in developing linkages, partnerships, mentorships across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming.	Evidence of increased awareness of NTD policy making environment and interactions between disciplines and across sectors to design research.	Met. Multi-sector engagement developing partnerships across the sectors on defining cross-cutting NTD evidence gaps, knowledge exchange and developing workplans for priorities.
COUNTDOWN stakeholders engaged in implementation research training to conduct research and effectively disseminate and make use of the research.	COUNTDOWN stakeholders establish implementation research and research uptake capacity building goals at national, state and district level for scale up of integrated NTDs.	Met. Capacity building activities implemented during early stages of the identification process.

Key Points

Outcome met expectations. There have been inception meetings and stakeholder mapping in all targeted countries, with an emphasis in involvement with national authorities, NTD partners, academic institutions, funding agencies and NGOs. COUNTDOWN’s partner meeting in Accra (April 2016) provided the opportunity to engage with the WHO African Regional Program Review Group for NTDs. Workshops took place on molecular DNA diagnostics and Kato-Katz techniques for detection of Schistosoma eggs in stool. There was also a workshop to help participants understand, appraise and use systematic reviews in neglected tropical diseases. The topics are relevant at this early stage in the programme, but not in line with COUNTDOWN’s longer-term milestone of “implementation research and research uptake capacity building goals at national, state and district level for scale up of integrated NTDs”. COUNTDOWN presented at the Coalition for Operational Research on NTDs (COR-NTD), the major annual NTD implementation meeting, which was highly appreciated by those present at this meeting, including other government funders.

Summary of responses to issues raised in previous annual reviews (where relevant)

The logframe indicators and milestones have been updated. COUNTDOWN should continue to do more to share information and collaborate on a regular basis with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. There has been insufficient collaboration with the full range of partners to date.

Recommendations

COUNTDOWN should increase its collaboration with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. DFID will ensure that COUNTDOWN is involved in NTD partner meetings whenever these take place. (ACTION: COUNTDOWN & DFID – immediate and ongoing)

COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. (ACTION: COUNTDOWN – immediate and ongoing)

COUNTDOWN should reconsider its proposed work on products (particularly diagnostics), following discussion with DFID, and ensure this work is complementary to the work of the DFID funded Product Development Partnerships in this area. (ACTION: COUNTDOWN – November 2016)
D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

To date the main cost-drivers have been in relation to establishing the consortium and building in-country partnerships. Fees and travel costs have featured highly, together with the costs involved with the launch events in both Ghana and Cameroon. Although fees and travel will continue to be significant, we expect direct research costs to increase as workplans are agreed and activities come on-stream.

In relation to technical oversight COUNTDOWN have instigated a number of strategies and guidelines to ensure best practice and that all partners are operating in harmony to the same standard.
- Procedure for data management that will ensure scientific and field data is integrated, cleansed, migrated and managed across platforms to produce accurate and consistent information.
- Publication guidelines have been submitted and approved by the COUNTDOWN management committee, which will ensure that authorship of outputs is equitable by supporting junior researchers and inter-country authorship.
- Communications strategy developed to provide an overview of the critical thinking that has informed the direction of communications and research uptake work.

VfM performance compared to the original VfM proposition in the business case

VfM measures were considered as part of the contract negotiations and we have continued to evaluate through the programme management process. Logframe indicators have been agreed that are stretching and incentivise COUNTDOWN to deliver measurable results. Economy, Efficiency, Effectiveness and Cost-Effectiveness are the key drivers and COUNTDOWN’s approach targets all of these areas.

VfM has been improved as a result of COUNTDOWN’s expansion into Nigeria, the country with the largest burden of NTDs globally, and therefore has the greatest potential global impact for NTDs. The original budget for the new work has been significantly reduced through negotiation and we are now happy that the cost is appropriate.

Assessment of whether the programme continues to represent value for money

The review team assesses that the programme continues to represent value for money. COUNTDOWN has adopted the “Barr and Christie (2015)” approach for assessing value for money which recognises that the “value” a project produces typically evolves from simple process and output related measures early in project implementation, to more complex outcomes and impact level accomplishments as a project moves closer to delivering its goals. This approach embeds the “four E’s” within a matrix that combines three types of indicators (monetary, quantitative and qualitative) and three degrees of measurement rigour (benchmark, comparison and stand-alone). Value for money and the theory of change will be closely evaluated as part of the wider programme monitoring and evaluation.

Quality of financial management

This has been a challenging aspect of the programme during the past year. In late 2015, it became apparent that COUNTDOWN were holding significant unspent DFID funds, contrary to the terms of the contract. The funds have since been re-paid to DFID. DFID met with COUNTDOWN in Liverpool about the situation, and identified actions to strengthen financial management. LSTM were wholly open and responsive to DFID feedback and made every effort to resolve this issue quickly. DFID accountant was wholly involved throughout offering advice and joining discussions with LSTM.

DFID has agreed to COUNTDOWN’s request for advance payments for some smaller sub-contractors. DFID are satisfied that there are no liquidity problems and it is LSTM policy on advancing to sub-contractors that prevents them meeting this liability directly. DFID has checked the audited financial statements.

Date of last narrative financial report	29 April 2016
Date of last audited annual statement	2 November 2015

E: RISK (½ page)

Overall risk rating: Major

Risk has increased from last year’s annual review. In addition to DFID’s recategorisation of risk from three to four levels, the risk of the programme has increased, due to the inclusion of Nigeria within the focus countries, and the financial challenges that the programme has experienced in the past year.

Overview of programme risk

- The external context is a major risk, due to the challenges of working in insecure states in Nigeria. This is being mitigated through working closely with national and local authorities and organisations in Nigeria, and particularly the involvement of Sightsavers that have a long history of operating in these areas in Nigeria. With the Ebola outbreak coming under control in West Africa, this has reduced the external context risk in this region.
- The delivery risk continues to be major, due to the early stage of the programme in a challenging area of research, and therefore the programme has not yet had an opportunity to clearly demonstrate its performance.
- The operational risk is moderate. DFID is well placed to manage the programme, through the Health Research Team, as well as strong involvement of the NTD hub of the Health Services Team. DFID Nigeria is a DFID focus country, but DFID does not have a presence in Liberia and Cameroon, and therefore any DFID country level engagement will be challenging in these countries.
- The safeguarding risk of the programme is minor, with minimal risk of harm from the research.
- The fiduciary risk is major, due to the challenges with financial management in the past year of the programme. DFID has mitigated this through working closely with COUNTDOWN to address these concerns, including a visit to Liverpool from DFID Research Manager, Programme Manager and Finance Manager to discuss these risks, and identify what action was required.
- There is minimal reputational risk of the programme currently, and therefore this risk is minor.

Outstanding actions from risk assessment

DFID has discussed with COUNTDOWN regarding improving the financial management, with accurate budgeting, and only claiming for expenditure that has already been spent. (COUNTDOWN – already actioned, following meeting with DFID)

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on target to deliver the research within the envisaged timescales. The inception Phase ended in late 2015 and although some of the inception activities were rolled forward to implementation (developing workplans, protocols for ethical reviews), there is clear evidence that things are moving forward. Ghana and Cameroon projects are up and running, with Nigeria and Liberia making good progress.

Performance of partnership (s)

There has been good engagement of the partnership, with active involvement of the programme partners in all focus countries. COUNTDOWN acknowledged the challenge of time required to coordinate activities between multidisciplinary teams, across multiple countries and partner institutions, but highlight that there is considerable acceptance from consortium members of the added value to working collectively. COUNTDOWN are coordinating harmonised activities, and maximising effective communication between all stakeholders.

Asset monitoring and control

COUNTDOWN maintain an asset register that records goods and equipment purchased from programme funds that cost in excess of £1,000 and hold a residual value (i.e. non-consumables), this also applies to downstream partners. The register is available to DFID for inspection on request. No spot-checks have been carried out during the review period, but DFID reserve the right to do so, including site visits where necessary.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

This is not applicable for this programme. The partnership principles were not used in monitoring this project as it does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

LSTM has taken over responsibility for overall monitoring of the programme against the logframe. During the year, DFID worked with COUNTDOWN to agree a revised log-frame, milestones and indicators.

One of the non-governmental-organisations part of the consortia, FHI360, is responsible for evaluating the value for money and the theory of change to capture the causal chain between COUNTDOWN’s outputs and its ultimate impact. Roles and responsibilities for data capture have been agreed within the consortium to measure progress within the Logframe, with internal quarterly milestone reporting periods.

COUNTDOWN have provided an annual report with logframe, workplan, finance summary, theory of change, publications guidelines, communications strategy, risk strategy and LSTM fraud bribery and corruption policy.

Monitoring progress throughout the review period

DFID has been in regular contact with COUNTDOWN during the year. This has included a visit by three DFID officials to Liverpool to meet with COUNTDOWN. There have also been regular telephone calls, and e-mail communications about the programme.

The review was conducted by health advisers and programme managers within the Health Research Team together with input from the DFID focal point for NTD operational programmes in the Health Services Team in Policy Division, who provided feedback from the DFID funded operational programmes about COUNTDOWN.