ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Humanitarian Preparedness & Response (HPRP)
Country or region targeted	Bangladesh
Type of cost extension (if applicable)	Time and cost extension: / Six months / £5,000,000
Original project budget	£20,000,000
Original project start and end dates	June 2011 – June 2016
Cost extension value (if applicable)	£5,000,000
New project end date (if applicable)	December 2016
Business Case Quest Document No.	3106313

INFORMATION
What is the project’s purpose?
The HPRP business case seeks to address the recurrent nature of disaster risk and associated humanitarian vulnerability in Bangladesh through three ‘windows’: / Rapid response to disaster events; / Institutional preparedness and planning and logistical support; / Building the evidence base for more effective responses; / Rapid response to disaster events / Climate induced and recurrent disaster events are the primary driver of humanitarian need in Bangladesh. Such events impact millions of people each year with the same communities often impacted by different events during the course of a 12 month period. For example, cyclone Komen affected districts of south-east Bangladesh in August 2015. The same regions of the country were affected by monsoon flooding two months earlier. / This component of the HPRP business case enables the UK to respond quickly and at scale to disaster events. In addition, the UK has used this window to support Rohingya refugees from Burma who are residing in Bangladesh. In 2011 when the HPRP business case was submitted to Ministers the prevailing operational environment in Bangladesh precluded the UK from supporting Rohingya refugees. However, recent positive changes in Bangladesh, principally the release of the government’s ‘National Strategy on “Undocumented Myanmar Nationals”, have facilitated UK humanitarian engagement. / Since 2011 the UK has provided more than 200,000 people with emergency humanitarian relief. Following cyclone Mahasen in 2013 the UK reached nearly 15,000 people along the coastal belt. In September 2014 nearly 100,000 people in northern districts received financial and in-kind assistance following monsoon flooding. In addition, 33,000 Rohingya refugees living in formal camps in south-east Bangladesh have benefitted from food and nutritional support in 2015. / Institutional preparedness and planning and logistical support / This window of the business case seeks to strengthen the leadership and coordination capacities of the international system and includes a specific focus on logistical preparedness. / Since 2011 DFID-B has made a series of targeted investments aimed at strengthening both disaster preparedness and coordination. Support to the Joint Needs Assessment (JNA) programme and the Logistics Cluster have been significant in this regard. / Since 2011, via UK funding, UN agencies, international and national NGOs have implemented a series of coordinated assessments led by the JNA programme. Such assessments have provided humanitarian actors and the Government of Bangladesh (GoB) with a shared understanding of the impact of different disaster events. Importantly this programme has also given voice to disaster affected communities. / In addition, the UK has also supported, under this window, the International Organisation for Migration who has led coordination related work for Rohingya activities. This support has contributed to improvements in the humanitarian operating context for relief agencies. / Building the evidence base for more effective responses / Funding to the JNA programme has made an important contribution to improving the evidence base for humanitarian action. / A major output of the JNA were a series of Secondary Data Reviews (SDRs). SDRs were produced for six separate disaster events including cyclones, river flooding and waterlogging. The SDRs provide analysis about the sectoral impacts of disasters and so are useful planning resources for humanitarian actors from contingency planning and response perspectives.
What is the objective of the cost extension or other changes?
The HPRP has performed soundly over the period 2011-2015, receiving successive ‘A’ scores in annual reviews since its inception. All remaining uncommitted funds set aside for responding to disaster events have now been expended. To maintain our ability to respond to any future events and support ongoing needs, an extension to the business case is needed. / This extension will be used to support the UK’s commitment to gender equality as articulated in the International Development (Gender Equality) Act 2014. For example, we will ensure that those women we support with post-disaster assistance play a meaningful role in programme delivery. Under the current Business Case disaster relief interventions are overseen by Project Implementation Committees, comprised of beneficiaries, with implementing agencies ensuring women are properly represented on such structures. We will look to replicate this approach under the extension and in doing so we will strengthen the role of women in disaster affected communities and enhance their voice and decision-making abilities. / Further support to Rohingya refugees in camps will also address the specific needs of pregnant and lactating women. Rohingya activities will also be delivered through “Block Committees” comprised of men and women refugees elected by their peers. / The cost and time extension is required for two principal reasons. / To enable DFID-B to respond to potential urgent needs during the October – November cyclone season and into early 2016. / UK funded research shows that cyclones are twice as likely to occur during the post-monsoon period, running October – November, than the pre-monsoon period of April - May. A cost extension would enable DFID-B to quickly respond in the event of a cyclone or related extreme weather event. / Latest El Niño reporting from the UK Meteorological Office indicates a “strong event is currently established”. The UK Meteorological Office notes that “above-average temperatures are likely across the Indian sub-continent, accompanied by below average rainfall during the retreat of the Southwest Asian Monsoon.” / Whether El Niño will mean a heightened risk of cyclonic storms is not clear. Some scientists have suggested that a rise in sea water temperature, which may follow given the predicted impacts of El Niño, could engender large damaging cyclones. See http://www.thedailystar.net/impacts-of-el-ni-o-in-bangladesh-27083 / Given the unpredictable nature of the impacts of El Niño we judge that having finances readily available and on-hand would be advisable. However, such funds would only be utilised in the event of a crisis or to support preparedness activities should weather forecasts indicate the development of a storm system in the Bay of Bengal. / To ensure the interrupted provision of food assistance to Rohingya refugees living in formal camps in south east Bangladesh. / In early 2016 the World Food Programme (WFP) faces a pipeline break for its food aid operation for 33,000 Rohingya refugees living in Kutupalang and Nayapara camps. At present WFP lacks donor finances for the period March – September 2016. / Unless funds are forthcoming the organisation will have to take steps to resource this period from within existing and committed finances. This is likely to require reducing the numbers of people it supports or reducing the size of the monthly food basket it provides. / Given the prevailing humanitarian context in the camps, food security and nutrition indicators are both highly concerning (see Figure below) and as camp residents are wholly reliant on food aid from WFP for their basic survival, UK support would help to fill an urgent gap. / Nutritional status of refugees in Kutupalang and Nayapara camps, (2007-13)
What is the additional and total support the UK will provide?
Under the HPRP the UK to-date has provided £20 million. An extension of £5 million will increase the HPRP to £25 million. / HPRP Business Case £20 million / Intervention name Agency Business case window Amount provided / Relief Support for flood and cyclone - affected Population in Need in South-East Bangladesh Care (on behalf of the National Alliance for Risk Reduction & Response Initiatives (NARRI)) Rapid response to disaster events £2.3 million / Emergency food assistance to flood affected households in south-east Bangladesh World Food Programme (WFP) £700,000 / To enable Tropical Storm Mahasen affected households to reduce food insecurity and restore livelihoods Plan (on behalf of NARRI) £1.8 million / Food security and livelihood recovery for flood affected people in south-east of Bangladesh Care £2 million / Enhancing food security in Cox’s Bazar district, Bangladesh WFP £2.5 million / Financial support for flood affected households WFP £400,000 / Protracted Relief & Recovery Operation WFP £1.9 million / Emergency food assistance to flood affected households in south-east Bangladesh WFP £1.6 million / Recovery for flood affected people in north-west Bangladesh Oxfam (on behalf of NARRI) £300,000 / Waterlogging in south west Bangladesh: A case for providing food security assistance to most vulnerable and poorest households WFP £1.8 million / Adaptive early recovery in waterlogged areas of south western Bangladesh WFP £1.91 million / Support to International Organisation for Migration (IOM) for improving capacity and coordination in humanitarian interventions for refugees in Cox’s Bazar International Organisation for Migration Rapid response to disaster events £350,000 / Sub-total: Rapid response to disaster events £17.56 million / Joint Needs Assessment programme Care Building the evidence base for more effective responses £309,000 / Sub-total: Building the evidence base for more effective responses £309,000 / Air support – Bangladesh Mission Aviation Fellowship Institutional preparedness and planning and logistical support £1.18 million / Strengthening the humanitarian coordination architecture in Bangladesh United Nations Development Programme £500,000 / Strengthening the Logistics Cluster – emergency preparedness in Bangladesh WFP (on behalf of the Logistics Cluster) £267,000 / Sub-total: Institutional preparedness and planning and logistical support £1.95 million / HPRP Business Case Extension £5 million / Agency / intervention Business case window Recommended allocation Indicative allocation per FY / WFP, Protracted Relief & Recovery Operation for Rohingya Refugees Rapid response to disaster events £2 million 2015/2016: £292,000 / 2016/2017: £1.75 million / Agency TBC. Funds earmarked for responses to extreme climate events etc. Approximately £3 million 2015/2016: £1.5 million / 2016/2017: £1.5 million / Care, Joint Needs Assessments Building the evidence base for more effective responses Approximately £100,000 2015/2016: £83,000 / 2016/2017: £17,000 / Note that the above allocations are indicative. Accurately forecasting expenditure by individual quarters and by financial years is, for the most part, problematic. For example, we can accurately forecast expenditure of £292,000 in FY 2015/2016 with an additional £1.75 million in 2016/2017 through WFP given what know of the organisation’s finances and the level of humanitarian need amongst camp-based Rohingyas we aim to address. However, we are not able to accurately forecast when and if additional finances will be allocated given this is contingent on the UK responding to a disaster event.
What are the expected results?
An additional £5 million could deliver the following results: / 1. Disaster response: In the event of a cyclone or other extreme weather event a contribution of approximately £3 million could be to support approximately 30,000 households / 132,000 people with an integrated package of relief and recovery support. Such support could potentially include immediate financial assistance through cash-for-work schemes alongside in-kind contributions of seeds and tools to help replace lost assets. An allocation of £3 million could also be used to resource ‘first phase’ interventions of a 90 day duration through the Rapid Response Facility (RRF). The RRF was most recently used in Nepal where an allocation of £3 million enabled the UK to reach 300,000 people with a range of services. / 2. Rohingya: A contribution of approximately £2 million to WFP will provide 33,000 Rohingya people with monthly food assistance, delivered through an electronic voucher system, for a period of seven months. Within this overall number 10,000 pregnant and lactating women and young children will receive additional targeted nutritional support and 12,000 school-age children will benefit from school-feeding. / 3. Institutional preparedness: In addition to the above, an allocation of up to £100,000 over the coming seven months could help to resource the conduct of coordinated assessments and other related activities via the JNA programme. The cyclone Komen response illustrated that whilst there is good support for the concept of coordinated assessments amongst NGOs, UN agencies and the GoB there is mixed capacity to plan for and implement timely assessments. Support to the JNA programme will help to resource a robust assessment capacity during a period of climatic unpredictability. During the extension period we will work with the JNA programme to ensure rapid post-disaster assessments with a view to quickening the supply of relief aid.
What is the approach to implementation?
Additional resources will be delivered by a range of implementing partners: / WFP will oversee delivery of Rohingya related activities; / The iNGO Care will lead delivery of the JNA programme; / Contingency funds for disaster response activities, if required, will likely be delivered by UN agencies and iNGOs.
Describe any key changes to the original business case?
Additional resources will be delivered in a manner compatible with the original business case. The majority of resources will be provided via output one - ‘Provision of emergency assistance and recovery support to households most affected by disasters’.