Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Migrating out of Poverty - Research Programme Consortium
Programme Value: £6,425,233.		Review Date: October 2015
Programme Code: 114334-101	Start Date: Implementation started Sept ‘11 (after year inception)	End Date: June 2017

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	68.75	B	A	A
Risk Rating	High	High	Medium	low

Summary of progress and lessons learnt since last review
The Migrating Out of Poverty (MOOP) Research Partnership Consortium (RPC) has made very good progress this year. The strengthened approaches to leadership, management, research quality, and strategy setting that were noted in last year’s review have been further consolidated, strengthening the consortium approach and ensuring that delivery (data collection, analysis and research outputs; and log frame targets) and spend are now on track.
MOOP’s approach to gender has taken a step change this year – a high point was MOOP’s international conference on migration and gender which elevated research and policy engagement beyond ‘women migrants’ and into ‘migration and gender’, examining gender dynamics in migrant sending households, and gendered differences in migrant experiences[1]. MOOP partners had to go through the conference competitive process (application by abstract etc) which also reinforced quality assurance in MOOP.
[1] MOOP Conference on Gendered Dimensions of Migration: Four New Results The broad conclusions from the conference corroborate existing evidence on the economic drivers of migration; both women and men migrate in response to changing rural markets, to earn higher returns for their labour and in pursuit of urban employment and lifestyles. But the real value added of the papers was to highlight how entrenched inequalities are reproduced in the experience of migration, not just for women but also for men. For example, - Migrant women from Northeast India take advantage of their ethnic features to enter beauty, care and hospitality work in the city, but in doing so they become stereotyped in highly constraining ways, e.g. being barred from speaking at work because they were passed off as Thai masseuses. - Little attention has been paid to cultural constraints shaping male migration; yet, several papers pointed to the complexities of slavery-like relations that shape male life paths, e.g. in Cameroon young men from the CAR have to adopt the deferential demeanour of yester-years’ slaves to establish social relations with older female guardians who control their earning opportunities. - Women’s earning power does not necessarily empower them in all arenas of decision-making. To preserve their social status, female Bangladeshi migrant workers avoid challenging their husbands’ prerogative to control the remittances that they send. - An important mismatch exists between remittance senders’ intentions and receivers’ valuation of remittances in kind. In the Philippines tensions arise between remittance senders and receivers: the (female) remitters sacrifice their well-being and lifestyle in order to remit while the receivers value the gift in relation to their middle-class aspirations regardless of the cost of providing it.
MOOP and partners have demonstrated wide-ranging policy engagement and uptake this year. Public debates on migration have become yet more heated in the last 12 months. MOOP makes clear that Mediterranean migration was specifically excluded from MOOP’s research at inception, but MOOP’s experts have engaged in private to offer evidence-informed expertise in debates, including with DFID.
However, MOOP partners have been visible in ‘hot’ migration policy debates elsewhere in the world, particularly in relation to the vulnerability of Rohingyas (RMMRU, Bangladesh) and xenophobic attacks on migrants in South Africa (ACMS, SA). MOOP partners’ credibility is built on solid, long-term research and engagement on important but less emotive migration policy themes – as an example of this range, RMMRU’s successes this year include:
- Being the ‘go to’ experts for information on Rohingyas in South Asia and SE Asia region.
- Influencing Govts of Malaysia and Bangladesh to allow migration via private labour contracts (contracts were previously govt-to-govt only, ignoring the biggest drivers of mutually beneficial economic migration. Next year 0.5m will migrate under the revised regime).
- Influencing MoU between Saudi Arabia and Bangladesh to explicitly allow female domestic workers to retain mobile phones for safety and welfare, including to contact labour attaches. (Between Jan and Sept 2015, >7500 women migrated from Bangladesh to Saudi Arabia).
Summary of recommendations for the next year
1. Logframe: DFID will upload agreed revised logframe to DFID management system (done).
2. Intern strategy: MOOP to develop a revised plan for achieving target of 17 interns (6 more) by 2017 if possible (MOOP to report by next quarterly meeting).
3. Gender mainstreaming: MOOP’s Gender Lead will produce guidelines to define ‘sensitive to gender’ for logframe indicators, and make spot checks on a sample of returns (MOOP to report on plan by Jan 2016 quarterly meeting).
4. Policy audience data (output 2): MOOP to consider means of increasing feedback response rates by participants at external facing events, including (e.g.) SMS and smart phone-accessed surveys (share update at next quarterly review).
5. Future funding options: MOOP and DFID will consider options for a costed extension for the period post June 2017, including the degree to which MOOP can add research themes more directly relevant to the irregular migration patterns that are high policy priorities for DFID/HMG (discuss at quarterly meetings; consider proposal at next annual review or sooner).
Progress on recommendations from last year’s review:
MOOP’s secretariat and DFID have acted on all recommendations from last year’s review. MOOP provided data on partners’ receipt of MOOP/DFID funding as a proportion of overall budgets (for period Oct 14-Sept 15: ACMS 9%; CMS 23%; ARI 25%; RMMRU 38%). Engagement with DFID country offices and policy teams has increased since last review and DFID and MOOP will seek opportunities to further develop engagement. MOOP has increased the use of ‘voices of migrants’ in communication products[2].
[2] Migrants’ voices in MOOP communication products Working Papers 24-27 all contain some direct quotes and more accounts of migrants’ lives. Collins's blogs (http://migratingoutofpoverty.blogspot.co.uk/2015/07/migration-and-changing-intra-household.html and http://migratingoutofpoverty.blogspot.co.uk/2015/03/the-impact-of-migrating-for-domestic.html) contain ‘migrant’s voices’ directly and accounts of migrants lives. Priya's blog (http://migratingoutofpoverty.blogspot.co.uk/2014/12/dirty-jobs-but-brighter-future-migrant.html) and Kuda's (http://migratingoutofpoverty.blogspot.co.uk/2015/08/after-migrant-leaves-home.html) highlight individual migrant's experiences. ARI's film 'Gone Home' (https://vimeo.com/115239237) and the linked site relating 'stories from Munshiganj' (http://storiesfrommunshiganj.com/home.html)
A. Introduction and Context

DevTracker Link to Business Case:	2137641
DevTracker Link to Log frame:	4619082

Outline of the programme
DFID agreed a £6,425,233 contract with the University of Sussex (2011-17) for the Migrating out of Poverty (MOOP) Research Partnership Consortium (RPC). The RPC generates new, high quality research and evidence related to migration and poverty, creates new datasets, engages policy makers, and builds capacity. Its research aims for a better understanding of the relationship between migration and poverty, and the factors that mediate it. This builds on the work of the DFID-funded University of Sussex Development Research Centre on Migration, Globalisation and Poverty (2003-09).
The Consortium works in five regions – East, West, and Southern Africa; South Asia; and Southeast Asia. The lead partner is the Sussex Centre for Migration Research, with five other core partners: Bangladesh’s Refugee and Migratory Movements Research Unit (RMMRU); Ghana’s Centre for Migration Studies (CMS); Asia Research Institute (ARI) at the National University of Singapore; African Centre for Migration & Society (ACMS) at Witswatersrand University; and Kenya’s African Migration and Development Policy Centre (AMADPOC). MOOP has associate partners across the regions.
The intended results are:
Impact: state and societal actors will have utilised a strong evidence base on internal and regional migration to produce pro-poor migrant policies in at least 5 countries in 5 regions.
Outcome: improved access to and demand for internal and regional migration evidence by targeted development policy stakeholders in at least 5 countries as a result of an improved understanding of migration and poverty linkages, and how this can be used to maximise benefits of migration for development and minimise risks or negative impacts.
Outputs:
1. New research: A coherent body of high quality, policy relevant new knowledge on internal and regional migration. This will include new open access databases to provide a critical resource to migration researchers globally. It will also include at least 35 research outputs that specifically address gender dimensions, with a focus on women and girls.
2. Policy engagement: Improved engagement and dialogue with key stakeholders, to promote research uptake and understanding of findings related to internal and regional migration and poverty linkages.
3. Capacity: Enhanced strategic capacity of consortium members to conduct research, and enhanced capacity of key stakeholders in government and civil society to participate in policy framing processes.
At MOOP’s inception, migration was becoming a prominent theme in global development policy, with at least 740m people migrating internally (HDR 2009) and another 80m migrating within the global South (Ratha and Shaw 2007), often to improve development prospects for themselves and their families. Research had shown that migration can contribute towards achieving the MDGs by improving life choices, empowering disadvantaged groups, improving access to health and education, and reducing poverty (HDR 2009). However, it can also have negative impacts with migrants exposed to new vulnerabilities (e.g. violence) or limited access to services.
Southern governments and international donors are becoming more aware of the importance of migration for poverty reduction. However, they lack evidence and data to help maximise the benefits of migration and minimise potential harms. Existing datasets do not adequately cover the types of migration that poor people engage in, the drivers of migration, and the economic and social impacts on both receiving and exporting communities.
MOOP will help to address this research gap by providing high quality, open access evidence on internal and international migration at the local, national and international levels, to provide a sound evidence base for more effective policies.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment: The outcome assessment is ‘A’ – progress towards Outcome meets expectations. MOOP also collects data on logframe impact and outcome indicators and these are on track with 2015 targets.
Overall output score and description: MOOP has had a strong year, and is on track to deliver all output milestones (all three outputs score ‘A’, with some individual indicator milestones exceeded).
MooP’s management systems are effective and efficient; the quality and timeliness of consortium delivery has further improved; and appointment of MooP’s gender lead has addressed a gap noted in last year’s annual report, with delivery of a high quality international conference on gender and development demonstrating the step up in performance.
Key lessons: a key lesson this year is the impact that a dedicated and experienced gender lead can have on a research programme – with tangible improvements in analysis, planning, and events.
MOOP’s investment in management systems continues to bear fruit – the EXCEL work planner drives timely delivery of complicated workplans with geographically diverse partners. This should have a knock on effect on the wider work of MOOP partners. MOOP continues to ‘learn by doing’ in the ethical and practical dimensions of making public its anonymised qualitative datasets (see output 1 below).
Key actions: See recommendations above.
Has the logframe been updated since the last review? Yes – the Singapore partners’ meeting included a logframe workshop. The MooP secretariat refined the workshop notes into proposed logframe revisions. These changes are relatively minor – they simplify the language of the output statements, and add additional indicators for outcome and impact reporting. The accepted revised logframe is at Quest Ref 5210292.

## C: DETAILED OUTPUT SCORING

Output Title	A coherent body of high quality, policy relevant new knowledge on internal (and regional) migration / Proposed wording: High quality and policy relevant knowledge on internal and regional migration
Output number per LF		1	Output Score	A
Risk:		medium	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
1.1 # of internal and regional databases made available to the research community (i) qualitative and (ii) quantitative	0		3 Qual / 3 Quant	6 Qual / 5 Quant	Quantitative milestone on track (3 data sets available with two more being tested and will be published by Sept 2016). The first working papers from the household surveys have been published (Zimbabwe, Ghana, Bangladesh) with one more (Ethiopia) imminent. / In addition, MOOP has a unique, cross-country knowledge base on two migration streams of high significance for the rural poor: construction work and domestic work. Together these absorb >200 million adults (plus large numbers of children) worldwide, predominantly from poor and socially excluded communities. MOOP research highlights the important role played by these flows in improving living standards and educating the next generation, despite the precarious nature of much of the work. / Qualitative milestone partially achieved and now amended – the plan to make data public after simple anonymization was challenged because individuals could still be identifiable from their detailed answers. Eliminating this possibility would remove much of the information useful for research. Moreover, research subjects approved use of data ‘for research’ and not any other use. Therefore MOOP proposes to host anonymised data and make this available on application to bone fide researchers only. / Cleaned, anonymised, ‘gated’ data will be available from Sept 2016, after MOOP researchers have had first access. DFID supports this approach.
1.2 # of internal and regional migration policy relevant projects comprising research and related engagement activities completed according to plan	0	8	18	29	Milestone on track – 17 events completed, with 18th (on domestic and construction workers in Ghana) complete by end October.
1.3 # of research outputs: / i) peer reviewed articles, / ii) working papers, / iii) policy briefs, conference papers/ presentations / iv) book chapters (*added this year)	0,0,0,*	0,2,3,*	3, 27,12,15	12,40,15,25	Milestone exceeded – cumulative production is 9, 31, 20, 24, with increasing ‘throughput’ from working papers to peer reviewed articles, although not all outputs by MOOP partners regarded as ‘MOOP related’ are explicitly derived from MOOP’s major data collection.
1.4 # of research outputs that significantly address gender dimensions, including a focus on women and girls	0,0,0,*	0,6,1,*	1,10,6,7	6,15,10,15	Milestone exceeded - results to date are / 2, 17, 7, 7. / Recruitment of gender lead has had clear positive impact on production of significant gender gender analysis.

Key Points: a notable achievement is completion of the Zimbabwe quantitative survey, which has generated a high quality dataset in a context where such surveys are very hard to negotiate permission for, and so are scarce. The field work meant overcoming a range of bureaucratic, logistic, and capacity challenges. The data will be a valuable new resource for researchers in Southern Africa and beyond. Delivery of Ethiopia survey was also stretching given that there is no MOOP partner based in country
MOOP is also generating a panel dataset in Ghana designed to calculate more accurate counterfactuals for migrants than is usually possible (i.e. how they and their household would have fared had they not migrated). MOOP has two observations (2013 and 2015) on each of 1132 households as well as interviews with 60 recent migrants at destination. These data – to be released by September 2016 - will be unique and of great interest to other researchers.
Headline findings from Ethiopia household survey include the high poverty rates of sampled migrant families (expenditure on food averaging 80%) with 70% being internal migrants, and international migrants mainly female domestic workers in the middle east. Remittances are an importance source of income for Ethiopian households, accounting for upto 20% of household expenditure for households with international migrants. Preliminary analysis suggests that remittances have a larger impact on investments in health and education than on food expenditure. Expenditure data shows only small differences between migrant and non-migrant households, though 84% of respondents viewed households with migrants as being better off.
In contrast, in Zimbawe international migration (most within Southern Africa and South Africa) is more prevalent than internal (~60:40). Households with migrants are only very slightly better off than those without. In subjective assessments of their own circumstances, 55% of households with migrants felt better off as a result of migration (44% felt ‘worse off’). Nearly half of households with migrants had negative views of on the impacts of migration, possibly because of concerns for safety in a context of xenophobic violence.
As part of this review, DFID’s SRO asked relevant DFID country teams and HQ policy teams to review MOOP Working Papers (WPs[3]) using a simple format that the GCSD team has applied in a range of recent research programme reviews. DFID reviewers provided summary feedback on WPs on Nepal, Indonesia/Singapore (2 separate papers), Zimbabwe (2 reviews of 1 paper) and Ghana. These reviews have been shared with MOOP, with the caveat that DFID advisers are a very specific policy audience and MOOP’s research outputs are primarily a public good, not advice for DFID.
[3] MOOP working papers produced in this reporting year (Downloads at: http://migratingoutofpoverty.dfid.gov.uk/publications/workingpapers ) WP31	Sept 2015	Migration and Social Networks: Evidence from Bangladesh WP30	Sept 2015	Pragmatic Pathways: Critical Perspectives on Research Uptake in the Global South WP29	Sept 2015	Migrating out of Poverty in Zimbabwe WP28	Sept 2015	Are Migrant Households better off than Non-Migrant Households? Evidence from Ghana WP27	April 2015	How Migration into Urban Construction Work Impacts on Rural Households in Nepal WP26	Feb 2015	Migration and Precarious Work: Negotiating Debt, Employment, and Livelihood Strategies Amongst Bangladeshi Migrant Men Working in Singapore’s Construction Industry WP25	Feb 2015	Structural Conditions and Agency in Migrant Decision Making: A case of domestic and construction workers from Java, Indonesia
On average, DFID reviewers found ‘choice of topic/contribution to field’ to be ‘Good’; research design and methodology ‘Good’; ‘style and structure’ to be ‘Good’; but were more critical of ‘policy relevance’. Some DFID reviewers were critical of the WPs’ limited number of policy recommendations. This view may be at odds with DFID Research and Evidence Division (RED)’s evolving approach to assessing the quality of individual research products, which favours ‘cogency’ (ensure that any conclusions and recommendations directly relate to research findings) over lengthy recommendations that may be reasonable but do not relate specifically to the research.
Response to issues raised in previous reviews: as described above, MOOP’s gender lead has had a clear impact on the quality and consistency of gender analysis.
Recommendations:
Gender mainstreaming: Output indicators 1.4 and 2.3 are self reported by MOOP partners. To further ensure quality, MOOP’s gender Lead will produce guidelines to define ‘sensitive to gender’ and make spot checks on a sample of returns (MOOP to report on plan by next quarterly meeting).

Output Title	Improved engagement and dialogue with key stakeholders (Policy Makers, Media, NGOs, Migrant organisations and Research users) to promote research uptake and understanding of research findings related to internal and regional migration and poverty linkages. / Proposed wording: Effective engagement and dialogue around research findings by policy makers, practitioners and the media
Output number per LF		2	Output Score	A+
Risk:		medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
2.1 # of external events attended by PRC partner staff in which pro-poor approaches to regional and internal migration are discussed.	20	40	70	100	Milestone exceded by considerable margin. / A cumulative total of 190 events recorded in 2015 performance data. This exceeds the end of project target.
2.2 # of key stakeholder representatives participating in RPC external facing events proportion surveyed (& % of these reporting enhanced understanding of pro-poor approaches to migration)	30	200	600, / 60%, / 70%	900, / 75%, / 75%	Milestones partially on track. 990 participants; 12% completing feedback; 40% of these reporting enhanced understanding. / 990 key stakeholder representatives have attended MOOP events – which exceeds the end of project target. / Data is collected through post event attendance lists; and feedback surveys. The % indicators aim to incentivise MOOP partners to collect feedback at the end of events but it is proving difficult to ensure compliance as participants often decline to complete a survey, or provide only partial feedback.
2.3 # of RPC external facing events sensitive to gender dimensions of migration	0	7	50	75	Milestone exceeded. 60 externally facing MOOP events have included a focus on the gender dimensions of migration.

Key Points: MOOP’s partners continue to engage with policy makers, particularly in Bangladesh, Ghana, Singapore and South Africa as well as at UK and global fora. This year the clearest example of influence is RMMRU’s role in shaping two elements of Bangladeshi migration policy: (a) the agreement between the governments of Bangladesh and Malaysia to permit private contracts for migrants rather than the government-to-government regime that had ruled previously and largely eliminated migration and (b) the MoU with the Saudi government to ensure that female migrants from Bangladesh have access to their mobile phones. The numbers of new migrants potentially affected this year are 500,000 and >7500 respectively.
MOOP has also encouraged more diverse research and policy engagement products and strategies, including use of social media, photos, films, and exhibitions documenting migrants’ own accounts of their lives and journeys. Film and photos were prominent at the Singapore international conference (including visual anthropology, and ‘Balikbayan Box[1]’ - a Youtube musical video about the Philippine migration experience), and an exhibition on LGBTIQ migrant experiences in Brighton (‘Queer Crossings’).
[1] https://www.youtube.com/watch?v=WSMw7trHUcU
Response to issues raised in previous reviews: MOOP continues to produce synthesis outputs including its newsletter. Since the last review it has expanded the use of ‘migrants’ voices’ in research products and policy outputs.
Recommendations
- MOOP to consider means of increasing feedback response rates by participants at external facing events, including (e.g.) SMS and smart phone-accessed surveys (share update at next quarterly review).
- DFID to introduce MOOP to World Bank WDR 2017 team on ‘Governance and Law’ as potential policy influencing target for MOOP research (by Oct 2017)

Output Title	Strategic capacity of consortium members to conduct research, and of key stakeholders in government and civil society to participate in policy framing processes is enhanced enabling them to collectively shift the terms of the debate. / Proposed wording: Strengthened capacity of consortium members and partners to design and deliver academically rigorous and policy relevant research, and to share findings with external audiences
Output number per LF		3	Output Score	A
Risk:		low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
3.1 # of interns reporting improved capacity to do research (or engage with it)	0	4	11	17	Milestone on track. / To date, 10 Interns report an improved capacity to do, or engage with, migration research.
3.2 # of consortium partner staff reporting improved capacity as a result of attending a training course, placement or fellowship	0	5	40	50	Milestone on track. / To date 42 partner staff report an improved capacity. / Data is generated from reviews undertaken by partners in July/August each year. The number is cumulated number of individual event duplets, and excludes secretariat members.
3.3 # of boundary partners and key stakeholder representatives who report improved capacity after participation in consortium training sessions	15	50	300	400	Milestone exceeded. / 510 boundary partners report improved capacity. MOOP has worked to improve the method and quality of feedback following outward facing events.

Key Points: MOOP’s internship scheme aims to help young researchers to gain specialist research skills and experience and so build capacity for future migration research. This year MOOP sent interns to RMMRU in Bangladesh and ARI in Singapore. One intern has been selected for another internship with International Catholic Migration Commission in Brussels and reports that her experience with RMMRU was discussed favourably at the interview.
MOOP’s original design envisaged that all MOOP partners would host a series of interns. This has proved difficult in implementation becaue of factors such as diverging academic timetables, and restrictive visa regimes. Supporting 6 more interns in the final year will be difficult. MOOP will consider options for hitting this target.
Training delivered by MOOP this year includes both internal and external initiatives:
- NVivo training to ARI and CMS staff to support analysis of qualitative research.
- Global Communications team training in communication technical skills.
- Quantitative and Qualitative research leads (appointed to improve research quality) delivering bespoke in-situ support in Ghana, Bangladesh and Zimbabwe, in addition to continuous feedback on project proposals and advice on methodology.
- Gender Lead strengthened mainstreaming of gender throughout MOOP activities.
- Training for external actors included CMS (Ghana) training on migration for ECOWAS intergovernmental organisations. CMS training last year for Ghanaian media resulted in establishment of ‘Media Network on Migration’ (MENOM), raising MOOP’s profile and strengthening media discussion of migration more generally.
Responses to issues raised in previous review: MOOP has continued to work with partners to strengthen work planning, delivery, and financial systems. This year MOOP re-examined internship strategy, and increased funding to ensure that internship costs were wholly covered by MOOP, to avoid cost being a barrier to Southern applicants. In practice this has not dramatically increased applications or success (in a competitive process) by Southern applicants.
Recommendations
MOOP to develop a revised plan for achieving target of 17 interns (6 more) by 2017 if possible (MOOP to report by next quarterly meeting).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Key cost drivers are staff & travel costs (direct and indirect) £1,034,766.48, research consumables £48,697.79, Meetings and Conferences £71,141.28, Capacity Building £9,565.53 and Office running costs £33,601.99. MOOP is fully aware of the need to maximise VfM within the planned budget. Spending on research is on track against financial forecasts.

VfM performance compared to the original VfM proposition in business case
VfM performance is in line with expectations; overall the programme is on track to meet targets, and its intended purpose (to generate new evidence and improve analysis of existing evidence on the factors that mediate the impacts of migration on poverty is used and applied by policy makers and other relevant stakeholders to address international development goals and reduce poverty) is still a good fit.
Assessment of whether the programme continues to represent value for money
The programme continues to offer good VfM. The consortium has a range of processes and safeguards to ensure that VfM is assured throughout the programme cycle, and works to strengthen all three elements of DFID’s VfM framework. Peer review (including gender review) is used for all new proposals. This includes reviewing the profile/experience of proposed researchers for each project; proposed budgets; and scrutinising the links between research and research uptake elements, timelines, milestones and deliverables. Expenditure on overheads for partners and Secretariat has been reviewed to ensure that these deliver efficient and effective research and research uptake. DFID has agreed the revised budget for years 4, 5, and 6.
Financial risk has been addressed by The University of Sussex by developing an improved Excel-based project management system that allows Secretariat and partners to review payment and deliverable schedules, and allows them to flag peak times of activity and months when multiple deliverables are due. This has resulted in better time-keeping on delivery of the research outputs.
MOOP’s contractual budget for 2015 was £1,244,074 and the paid amount was £1,197,773 - a variance of 3.7%. Year 5 forecasting should be still tighter having the project management system in place.
Quality of financial management
MOOP delivery continues to benefit from improved financial management systems introduced in Year 3 and has provided regular updates to DFID over the year, advising on latest forecasts in advance of change.
The initial forecast for the year November 2014 - October 2015, including the carry over from Phase 1 project of £181,000, was £1,251,607. The actual spend of £1,197,773 representing a shortfall in the forecast of 4%, falling well within DFIDs forecasting ceiling of 10% variance.
The University of Sussex agrees funding with partners based on workplans, and partner budgets. Workplans and financial reports are scrutinised by MOOP secretariat and payment is made in arrears. DFID payments are made on claims as per the contract on a quarterly basis.
The contract value with the University of Sussex is £6,425,233 m.
Date of last narrative financial report	29/10/15
Date of last audited annual statement	2013/2014 audited annual statement

E: RISK

Overall risk rating: Low (from medium last year).
Overview of programme risk
A number of low- to medium-level risks were identified at design, with overall risk changing little over the review period. From our review of the orginal project document and of additional emerging factors, key risks are:
Policy makers do not take account of findings due to factors outside control of the project. MOOP has engaged policy makers during research definition, production, and with research products- and will maximise dissemination of research and policy engagement.
In the last year, populist debates on migration ‘crises’ have often been uninformed by research evidence. However, media and policy makers’ demands for expert inputs have provided MOOP partners with new opportunities to provide evidence-informed advice. While not all expert advice relates to MOOP research directly, the MOOP partners’ credibility depends on their track record for high quality research.
- Capacity building will not be effective given the lack of evidence of what works and the small scale/scope of the cacpity building initiative – this risk persists and MOOP continues to discuss progress with DFID and – based on learning from experience- revise its approach when required.
- Lack of in-country capacity constrains ability to carry out primary data-gathering as required. This risk delayed data collection in Zimbabwe but, following intense effort by MOOP and partners, data collection is now complete.
Outstanding actions from risk assessment
No outstanding actions. Risks are being monitored and mitigated. This should continue.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
The programme is progressing according to contracted schedule and revised logical framework from 2014 Annual Review. No contract amendments have been issued throughout this review period.
Performance of partnership (s)
The MOOP consortium is a dynamic partnersip, demonstrated by the partners’ meeting in Singapore at which MOOP partners held a discussion with the CAG on the effectiveness of the programme and then provided feedback to the Secretariat.
MOOP’s partnership with DFID is good. MOOP has actively responded to requests for advice related to Mediterranean migration (e.g. Singapore roundtable) and MOOP has engaged with DFID country offices.
Asset monitoring and control
MOOP’s main assets are its staff and partners. Through its efficent management of the programme in 2014-2015, MOOP has ensured that both have been deployed effectively and monitoring tools in place to manage this effectively.
G: CONDITIONALITY

Update on partnership principles
Not applicable. MOOP is a multi-country research programme, which does not provide funding through country-government systems.
H: MONITORING & EVALUATION

Evidence and evaluation: MOOP’s core objective is to to understand the drivers of migration, and the conditions under which the development potential of migration can be fully realised. MOOP has continued to improve its approach to communication and policy engagement to get evidence into action. MOOP’s data collection for logframe monitoring includes routine collecton of data for monitoring progress at outcome and impact level. These are detailed in the logfame reporting section of MOOP’s annual report.
Monitoring progress throughout the review period
DFID’s SRO and MOOP secretariat hold quarterly review meetings by telephone.
This annual review was carried out in Oct 2015 by DFID’s A1 SRO and B2 Programme Manager (PM), with research products reviewed and commented on by a range of DFID country and policy teams. The DFID review team conducted a desk review of key documents, including MOOP’s detailed annual report of programme performance over the review period, and research and communication outputs.
The DFID SRO visited MOOP in Sussex on 20th October and the PM participated by telephone. The MOOP team presented their Annual Report and progress over the review period. Following discussion, MOOP and DFID agreed a commentary on progress against logframe indicators; changes to the logframe; and summary recommendations from this review.
The Annual Review report was shared in draft with MOOP and will be presented at the next CAG meeting, with responses and follow up to be documented.
Quest Documents :
2014 DFID Annual Review Report : Quest no. 4771808
MooP Annual Report Oct 2014- Sep 2015 : Quest no. 5210307