Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Health Partnership Scheme
Programme Value: £30.2m		Review Date: July 2016
Programme Code: 202208	Start Date: Nov 2010	End Date: June 2017

## Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A+	A++	A	A
Risk Rating	L	L	L	L	Moderate

## Summary of progress and lessons learnt since last review
DFID is funding grants to health partnerships between health institutions in the UK and their counterparts in developing countries. The programme is delivered by Tropical Health & Education Trust (THET) to improve human resources for health and health services in developing countries, and to bring benefits back to the UK through NHS staff returning with increased knowledge and skills. There has been strong progress and lessons learnt over the past year; i.e. enhancing data collection, and timing for results reporting on new grants.  The Health Partnership Scheme (HPS) supported over 100 partnerships, and a total of 125 individual projects with health workers receiving training and education across 26 countries, and developed the capacity of over 100 government and civil society institutions across many health themes.
## Summary of recommendations for the next year
- THET to assess the added value of the Uganda office pilot by increasing final logframe targets under Outputs 1and 3 by September 2016 and by collecting and reporting on qualitative evidence of improved alignment and coordination by programme end.
- DFID and THET to change outcome indicator 4 wording and target by September 2016
- DFID and THET to review the end of project targets at regular intervals between September 2016 and January 2017 – see lessons section.
- DFID and THET to reduce Output indicator 1.1 target from 69,000 to 64,000 based on a robust method for setting the target and proactively up-dating DFID on any required adjustments. By September 2016
- THET to continue to support partnerships to improve collection of quality data on number of training places provided, level of improved skills/performance post training, and broken down by gender, cadre and type of training. Ongoing
- DFID and THET agree a standardised method to quantify/assess volunteers’ time spent on projects while in the UK; by September 2016
- THET to provide DFID with a phase-out/ exit strategy, by October 2016. The strategy should include a plan for managing staff resources, a detailed monitoring and evaluation plan with activities to proactively obtain all required data in-time for final HPS analysis/reporting, and activities to support health partnerships to focus further on sustainability in their partnerships and projects.

# A. Introduction and Context (1 page)
DevTracker Link to Business Case:	HPS pre-dates DFID Business Cases
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5382390.xlsx

Background: The Health Partnership Scheme (HPS) is a six year (2011 – 2017) £30m programme which supports the strengthening and sustainability of existing partnerships between UK health institutions and those in low income countries. The HPS is managed by Tropical Health & Education Trust (THET) and programme aims are to:
- improve human resources for health and health services in developing countries through UK health institutions and professionals volunteering their time to build the capacity of their counterparts in developing countries, and
- bring benefits back to the UK through volunteer NHS staff returning with increased knowledge, improved leadership skills and a greater understanding of how to innovatively deliver healthcare with limited resources.
A strong health workforce is an essential component of a functioning health system. Improving access to better basic services requires skilled health workers in the right place and time. DFID makes significant investments in human resources for health in partner countries; including through the HPS.
The HPS has two main components: grants to support partnership projects, and activities to support and develop the health partnership community in the UK and overseas. Furthermore, in March 2016 THET established an office in Uganda (where the largest number of grants operate) to pilot an approach to supporting partnerships at the country level by supporting coordination and inputs of the partnerships to the priorities of the Ministry of Health, promote learning and exchange, and provide support to reduce duplication of effort. Recommend that THET measure the added value of this approach by increasing final logframe targets under Outputs 1, 3 and collect and report on qualitative evidence of improved alignment and coordination.
Gender: The programme has a strong focus on gender equity within training and education opportunities, and THET supports partnerships to provide disaggregated data on gender and other demographic characteristics of health workers (both UK volunteers and developing country health workers) and on the patient populations served through the health partnerships.
Expected results: The impact of the HPS is intended to be more effective and efficient health service provision (with a special interest in MDGs 4, 5 & 6 as well as rural and underserved populations). The intended outcome is more effective and efficient health systems, with an emphasis on the performance of the health workforce in participating countries and the UK.
The original HPS programme was £20m over 4 years (July 2011 – June 2015) referred to as HPS1. In April 2014, a £10m, 2-year cost extension was awarded with a new end date of June 2017; grants awarded under the extension are referred to as HPS1.5. The data reported in this review period (1 May 2015–30 April 2016) comes from 22 new HPS1.5 grants (started between May–October 2015), 48 ongoing HPS1.5 grants, and 23 grants that ended in the review period (mainly HPS1 grants and some HPS1.5 start-up grants). However, some grants have not submitted reports for the whole period due to the timing of their reporting cycles, and 18 grants awarded in this period are not due to report until next period. Final reports for all grants are due at the latest May 2017 so that all HPS results can be reported at the end of the programme.
Wider context: The context of supporting the HPS has changed favourably with the manifesto commitment to boost partnerships between UK institutions and their counterparts in the developing world. A central programme is being designed to support ODA-eligible UK partnership programmes across sectors and to make partnerships a distinctive and innovative part of the overall UKAid offer.
# B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
## Annual outcome assessment
The programme is on-track to meet the outcome of more effective and efficient health systems with an emphasis on the performance of health workers. Outcome indicators assess: 1) improved performance of developing country health workers following training after 3 months; 2) implementation of improved policies and curricula after 12 months, 3) use of and maintenance of improved equipment, ICT, and health information management systems after 12 months; and 4) UK volunteers self-reporting or demonstrating improved clinical/leadership skills.

The logframe outcome milestones and targets for the June 2015 to June 2017 extension period were first established June 2015 on the basis that these would be updated as the HPS1.5 grants were awarded and grantee M&E plans received. 2016 milestones and 2017 targets were updated both in September and December 2015, following the annual review, the 6-month progress report, and new monitoring information provided by HPS1.5 grants. However, the 2016 milestones were marginally missed as revisions to the milestones were too ambitious as progress for start-up of activities under HPS1.5 grants was slower than expected, there were some challenges with data collection, and insufficient time-lag for some improved performance assessments to be completed.

For the final year of the programme, HPS 1.5 projects are now on-track and data collection has improved. However, achievement against outcome 4 target will likely be approximately 70% as the mechanism for data collection was changed in this period to be more robust; i.e. data is now mostly about demonstrating improved competencies, which is a response to demand within the NHS for stronger evidence of the value of volunteering. As this is a measurement metrics issue rather than a performance issue, it is recommended that outcome indicator 4 wording and target be amended accordingly.
## Overall output score and description
The programme continues to perform well and met the majority of Output milestones for 2015/16. While newly established outcome milestones set for the extension period where not met due to time-lag for new HPS1.5 grants to get underway, THET are confident they will achieve the outcome targets by the completion date. There has been a strong focus on enhancing data collection and analysis and THET are further strengthening capacity for this in the final year. For these reasons, the overall output score is an A – programme met expectation.
## Key lessons
Lessons: As grants are awarded at intervals throughout the programme, there is natural variation in the level of project activities and a time-lag for receiving monitoring data and results; these required more analysis and consideration when anticipating and setting the results targets.
THET have found that where partnership grant funding is ending, partners tend to anticipate further collaboration beyond the grant thus seeing the eve of the project as an opportunity to maximise resources rather than simply completing planned activities. This can result in training more people than planned, or diverting resources to a different kind of training, thus impacting the results targets. Therefore, revising logframe targets and capturing and measuring the impact of all activities by the end of the HPS will require careful proactive management by THET and DFID.
Measuring demonstrated improved performance of UK volunteers reflects Health Education England and others’ interest in understanding the impact of health partnerships in the UK. However, for future programmes, THET would like to build direct relationships with UK volunteers in order to better support them and understand their experiences, learning and assessment of improved performance.
Applying and disseminating lessons: For a grants programme where the aim is to support capacity building as identified by the grant holders, every effort should be made to provide grant holders with comprehensive standardised reporting templates to enable aggregation of data. Possibly grant cycles should be carefully scheduled, and timing for achieving and reporting on results should be realistic to enable target setting.
Teams across HMG who are working on the commitment to boost partnerships are already consulting and sharing lessons and information on design and implementation of partnership programmes.

Recommend DFID and THET to review the end of programme targets at agreed intervals between September 2016 and January 2017
## Key actions
None
## Has the logframe been updated since the last review?
Several Outcome and Output 2016 milestones and 2017 targets were amended September 2015 following recommendations from the 2015 Annual Review and M&E plans received from new grant holders. Further amendments where agreed in December 2015 in recognition of : May–October 2015 results reporting; further information received from new grant holders; improved data collection; and review of level of ambition and stretch.

# C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Improved and strengthened knowledge and capability in participating health institutions
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		was Medium	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of training course places or other educational opportunities provided to developing country health workers (directly by project or by trainers trained in project)	59,000	53,871 / [15,170 in this review period] / (26,498 female, 19,935 male, 7,438 no data)
1.2 Percentage of tested trainees showing improved skills or performance immediately after training or education.	93%	92% / [94% (6,790/7,238) in this review period] / (13,385/14,594 female, 9,320/9,947 male, 4,836/5,490 no data)
1.3 Number of developing country institutions with improved medical equipment, ICT or health information management systems.	174	175 / [42 in this review period]

## Key Points
### 1.1. Training course places or other educational opportunities provided
- The 2016 cumulative milestone was missed by 5,129 (9%)
- In this review period, 15,170 course places and educational opportunities were provided; a 25% increase in the number of training places compared to last year
- However, following review of the HPS Progress report (May to October 2015), the 2016 milestone was increased from 50,206 to 59,000, as 95% of the 50,206 milestone was already achieved by Oct 2015. This was due to some large grant projects either expanding their training to medical students or providing more complete counts of training than before, and it was assumed this trend would continue. However, this trend did not continue and THET over-assumed that it would. HPS1 projects that were wrapping-up continued training at a higher rate in the first half of the reporting period than in the second half as they were closing. HPS1.5 projects were not training at this same rate as they were just starting.
- In December 2015, the 2016 milestone and 2017 target were increased from 50,206/61,712 respectively to 59,000/69,000 respectively. THET made an arithmetic error as these should have been set at 54,000/64,000 respectively.
- During the period November 2014–April 2016, of the 19,389 training places where type of trainer is known, 46% were delivered by local trainers, most of whom were trained by UK volunteers in advanced clinical skills and / or teaching methods. 2,368 training places were delivered jointly by UK volunteers and local trainers.

Example: Royal College of Nurses – Zambia Union of Nurses Organisation, a nursing partnership for leadership and improvement on 'safer surgery saves lives has trained 101 staff from 2 hospitals in Zambia to implement the WHO Surgical Safety Checklist. The training and support was delivered by the UK project team and local trainers. As staff capacity has developed, local staff have been able to lead local training in one hospital. After a half-day training workshop, 8 doctors received an additional 58 mentoring days over a 6 month period, some delivered by local trainers.
### 1.2. Tested trainees showing improved skills or performance
- Achievement is 92%, just below the milestone of 93%.
- A breakdown by gender where data is available shows that there is no significant gender difference in terms of reported improved skills, with 94% male and 92% female reporting improved skills.
- Testing is appropriately tailored for the type of training. Methods include test/exam-based assessments and more practical testing, such as trainees using teaching equipment (e.g. mannequins) and trainers observing progress. THET supports grant holders to develop appropriate methods for assessment.
- Grant holders are required to develop detailed monitoring and evaluating plans, outlining the tools and methods they plan to use for data collection and analysis. THET’s Evaluation and Learning team supports each grant holder to strengthen these plans, which includes ensuring that appropriate assessment methods are used to test the improved skills or performance of health workers trained.

Example: University Hospital Southampton NHS Foundation Trust – Gondar University Hospital – Jimma University Hospital - reducing the burden of cardiovascular and chronic respiratory disease in rural Ethiopia. 69 staff across 17 rural health centres in Ethiopia were trained to manage the follow-up of patients with chronic respiratory disease. All were assessed as having a good understanding of the structured follow-up charts and how to complete these through direct observation by the project team during the training, mentoring visits, role-play and review of patient records.
1.3 Improved medical equipment, ICT or HMIS
- A total of 175, against milestone of 174, institutions in developing countries reported having improved medical equipment, ICT or health information management systems (42 in this review period).
- 64% of institutions with improved medical equipment, ICT or HMIS serve all levels of the population, from primary and community care to tertiary level care.
## Summary of responses to issues raised in previous annual reviews (where relevant)
- Milestones for 2016 and 2017 were revised by September 2015
- Previous reviews recommended that THET encourage partnerships to improve data collection on gender and other demographic characteristics of trainees, including developing more explicit guidance and standard training registers for the new grants. THET are supporting partnerships to develop clear monitoring and evaluation plans for each of their objectives and communicated at planning stage how quantitative data, such as number of health workers trained, is to be broken down. However, there are a number of new health partnerships that rely on local teams and trainers to provide training data from the field and the data received is not always broken down appropriately.
- There is no gender data for 14% of the health workers trained in this period, compared with 9% in the last period. The reason for this deterioration is because 72% of health workers trained for whom no gender data was provided were trained by older HPS project grants who have, at times, struggled to provide gender disaggregation. THET have emphasised the importance of gender data and anticipate improved reporting as the HPS1.5 grants become responsible for more of the training. THET continue to support partnerships to collect good quality data on improved skills/performance post training.
## Recommendations
DFID and THET to reduce Output indicator 1.1 target from 69,000 to 64,000 based on a robust method for setting the target and proactively up-dating DFID on any required adjustments. By September 2016
THET to continue to support partnerships to improve collection of quality data on number of training places provided, level of improved skills/performance post training, and broken down by gender, cadre, type of trainer. Ongoing

Output Title	Improved and strengthened policies, protocols and curricula in participating health and health education institutions or across health systems
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		was Medium	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of national and institutional health strategies and professional standards / protocols to which projects have contributed for development, review or update.	447	450 / [40 in this period]
2.2 Number of new or improved policies and professional standards approved and signed off, by end of programme.	311	316 / [30 in this period]
2.3 Number of medical education curricula to which projects have explicitly contributed for development, review or update.	109	104 / [8 in this period]
2.4 Number of new and or improved medical education curricula explicitly approved for teaching.	52	50 / [4 in this period]

## Key Points
### 2.1 and 2.2 Number of health strategies, policies and professional standards; contributed/approved
- Indicators 2.1 and 2.2 have marginally exceeded their milestones by 3 and 5 respectively.
- By April 2016, HPS partnerships contributed to the development, review and update of 450 institutional and national strategies and professional standards/protocols, of which 316 have been formally approved. For the remainder, it is anticipated some will be formally approved by end of the programme, some after programme end, some not at all (this would be because of changes in priorities and leadership or due to lack of resources)

Example: Strengthening eye health systems in Ghana as a model for West Africa (Moorfields Eye Hospital – Korle Bu Hospital, Ghana).
The partnership recently introduced, approved and began using two protocols in eye health clinics at Korle Bu, for infection control (specifically handwashing and sanitisation) and patient consent.
### 2.3 and 2.4 Medical education curricula: contributed/approved
- Indicators 2.3 and 2.4 marginally missed the milestones by 5 and 2 respectively.
- Both indicator milestones overestimated the number of HPS1.5 projects that would have medical curricula development as a measurable component (indicator 2.3), and because the partnerships that have worked on curricula in HPS1.5 projects have not had time to get approval (indicator 2.4).
- By April 2016, HPS partnerships contributed to the development, review and update of 104 medical education curricula, of which 50 have been formally approved for teaching.
- For the remainder, it is anticipated some will be formally approved and some not at all.

Example: The University of Edinburgh, Rwanda Biomedical Centre (RBC), Ministry of Health partnership has developed two courses on palliative care: a 6-month course covering all aspects of non-communicable diseases, including palliative care; and a mentorship and supervision course developed with the support of Makerere Palliative Care Unit. This work supports the development and integration of palliative care curriculum into a range of health and social pastoral pre-service trainings for multidisciplinary groups of health workers.

## Summary of responses to issues raised in previous annual reviews (where relevant)
For Output 2 indicators, 2016 milestones and 2017 targets were adjusted both following the July 2015 annual review recommendations and again following review of the new projects funded in 2015 and are still valid.
## Recommendations
None

Output Title	Stronger and more institutional and country health partnerships that promote and enable mutual learning and skills and technology transfer
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		was Low	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of new institutional health partnership Memoranda of Understanding or other formal written commitments	85	89 / [17 in this review period]
3.2 Number of institutional health partnerships strengthened	78	79 / [21 in this review period]
3.3. Number of UK health professional days spent volunteering overseas and in the UK.	70,886 (63,308 overseas, 7,578 UK)	67,363 / [17,878 in this period (12,364 overseas, 5,514 UK)] / (60,956 overseas, 6,407 recorded since 2015 in the UK) / [Female: 41,956. Male: 19,124. Unknown: 6,283]

## Key Points
3.1 New institutional formal written commitments
By April 2016, 89 new institutional formal written commitments were established against a milestone of 85.
Example: Guys and St Thomas NHS Foundation Trust and Mulungushi University Zambia received a Strategic Start-up grant. As a result of this grant, the partnership signed a formal MoU which sets out: the purpose of the collaboration to improve the quality of training and delivery of health services for adolescents in the Central Region; the intended deliverables; and commitment to alignment with Zambia Ministry of Health and Higher Education priorities and plans.

3.2 Institutional health partnerships strengthened
- To date 79 institutional health partnerships have been strengthened against a milestone of 78.
- In order to measure this indicator, THET take information from grant holders’ progress reports. For the new partnerships, grant holders will report on this indicator through a standardised partnership development plan.

Example: The Royal College of Nurses and Zambia Union of Nurses Organisation have a partnership development plan (PDP) which sets out agreed key areas for improvement. The PDP relates to the relationship/collaboration rather than project activities and includes a commitment to strengthen reflection and learning. To this end, during a visit by UK team members, a strategic project review meeting was held and the team reported on the benefit of having open, face-to-face strategic discussions during the UK visit.

3.3. UK health professional days spent volunteering
- By April 2016, UK volunteers had completed 67,363 days of volunteering (60,956 overseas, 6,407 recorded since 2015 in the UK) against a milestone of 70,886 (63,308 overseas, 7,578 in the UK)
- Progress is 3.7% under the milestone for days spent volunteering overseas and 15% under the milestone for days spent volunteering in the UK. Some HPS1.5 partnerships funded in the last 12 – 18 months have experienced delays to delivering training activities overseas. THET continues to manage delays through their grant management processes ensuring remedial actions / support for off-track performance
- Data collection on days volunteering in the UK started early 2015 and while THET have been working with health partnerships to understand how they can account for their time supporting the project in the UK, it is not often straightforward to quantify volunteers’ contributions; i.e. in part-days, number of hours, and non-consecutive.

Example: The Accra Burns Care project aims to improve the care of burns patients in Accra, Ghana,
by reducing hospital acquired infections and mortality. In the first 6 months of the project, six UK volunteers spent a combined 23 volunteer days on the project in the UK (on project management, training preparation, meetings, events, etc.) and 17 days volunteering in Ghana (on training delivery, meetings with local partners/ stakeholders, and working on guidelines, etc.)
## Summary of responses to issues raised in previous annual reviews (where relevant)
For Output 3 indicators, 2016 milestones and 2017 targets were adjusted both following the July 2015 annual review recommendations and again following review of the May- October 2015 progress report and are still valid.
## Recommendations
DFID and THET agree a standardised method to quantify / assess volunteers’ time spent on projects while in the UK; by September 2016

Output Title	Effective and efficient grant funding and strategic management support to projects and health partnership community by the managing agent
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		was Low	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 The amount of grant funding disbursed within agreed timeframes	£18,873,196	£19,518,358
4.2 % of timely and appropriate provision of technical assistance to grant holders and other eligible stakeholders, in a 12 month period	94%	98% / (96% very satisfied or quite satisfied with quality; 100% very satisfied or quite satisfied with timeliness of THET’s technical assistance)
4.3 Number of advocacy and communication activities undertaken by THET in support of an enabling NHS environment for overseas volunteering	245	251 / [64 in this review period]
4.4 Number of page views for website resource library	59,424	58,777 / [25,858 in this review period]

## Key Points
### 4.1 The amount of grant funding disbursed within agreed timeframes
- Amount of grant funding disbursed exceeded the milestone
- This is due to a THET initiative to reallocate unspent funds from completed HPS1 grants to new grants after June 2015 (the design of each grant round took into account any unallocated funds from previous grant rounds) thus more funds were available than originally forecast.

### 4.2 Timely and appropriate provision of technical assistance to grant holders and eligible stakeholders
- 98% result exceeds the milestone of 94%,
- 92 HPS grant holders were invited to complete an anonymous survey. Survey results and a range of responses to the 2 survey questions in below box.

Q1. How satisfied are you with the quality of THET’s technical assistance in the last 12 months? / 42% very satisfied, 53% quite satisfied, 4% quite unsatisfied, 0% very unsatisfied. Thus, the vast majority of respondents value the quality of THET’s support / ‘The templates to develop project plans, budgets, M&E workplans have been incredibly valuable.’ / ‘THET's expertise in project planning and M&E is superb and their help at an early stage means that projects start off on the right track - essential!’ / ‘We have been very satisfied overall with the technical assistance from THET. However, our M&E manager has changed several times[1]. With the changes we have had vastly differing advice as to how to proceed with setting up project outputs, outcomes and goals. This made the application process challenging at times. All other aspects of technical assistance have been positive and exemplary.’ / Q2. How satisfied are you with the timeliness of THET’s technical assistance in the last twelve months? / 57% very satisfied, 43% quite satisfied, 0% quite unsatisfied, 0% very unsatisfied. / ‘THET make judgement calls, and have a very good sense of when I and others need immediate urgent advice and they have been extraordinarily sensitive about responding to the infrequent but important requests for an immediate response to take actions forward.’ / ‘THET have been exceptionally proactive to seek learning opportunities for teams and have been positive in agreeing to speaking and delivering key talks, workshops, training which is needed to draw academia, government, agency and NGO, civil society together.’ / ‘Some things have been a bit late but no complaints - we are also late at times. Some more help with budgeting would be helpful.’
[1] This is a consequence of people leaving the THET HPS team

### 4.3 Activities undertaken by THET in support of an enabling NHS environment for overseas volunteering
- Milestone exceeded by 6
- Examples of activities include:
  - Launch of the first edition of THET’s special series in Globalization and Health, Health partnerships: An Effective Response to the Global Health Agenda, including 12 peer-reviewed articles and 1 editorial published between December 2015 and April 2016;
  - Launch of the Principles of Partnership on THET’s website which includes tools and illustrative case studies for health partnership practitioners and policy-makers;
  - Participation in regular NHS International Health Group meetings.
### 4.4 Number of page views for website resource library
- There were satisfactory results on the number of page views
- 5 of the 10 most popular resources viewed in this period are: the Principles of Partnership; Guidance on medical equipment donations; Case study: Improving mental health in Uganda; “Managing the Medical Equipment Life Cycle”; “How to start a health partnership”.
## Summary of responses to issues raised in previous annual reviews (where relevant)
In response to July 2015 annual review recommendations the following was agreed and established with the September 2015 logframe revision: output 4 indicators were amended to report to the end of April rather than May (as done in previous years) to align with the rest of the Logframe; a method for consistently measuring indicator 4.2 - see 4.2 above; and 2016 milestone and 2017 target set for indicator 4.3 having achieved competency with using Google analytics for capturing the data
THET also developed and circulated a basic resource and advice pack for long-term volunteers by October 2015.
## Recommendations
None.
# D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
## Key cost drivers and performance
For the review period, the largest costs as a percentage of total costs continue to be the grants themselves, followed by staffing costs, communication & engagement, M&E and travel (ref Table 1). THET overhead costs have decreased from an average 18% at the start of the programme to currently just under 17%.

Table 1: Percentage of total costs
Costs	2014/15 Spend		2015/16 Spend		2016/17 Forecast
Grants	£4,905,701	82.7%	£4,306,374	83.1%	£2,345,355	70.0%
Staff/Consultants	£740,178	12.5%	£613,064	11.8%	£702,805	21.0%
Communication & Engagement	£83,028	1.4%	£61,348	1.2%	£81,085	2.4%
Monitoring & Evaluation	£36,711	0.6%	£45,904	0.9%	£15,000	0.4%
Travel subsistence	£37,601	0.6%	£26,021	0.5%	£40,993	1.2%
Other costs	£127,783	2.2%	£127,244	2.5%	£167,157	5.0%
Total	£5,931,002		£5,179,955		£3,352,395

Spend on grants, as percentage of total, remained relatively the same as the last review period. While long-term staffing costs increased slightly, THET have reduced overall HR costs with the sub-contract with HLSP ending and by covering several staffing gaps within the THET team. Communication & engagement and travel costs decreased due to fewer trips rather than due to changes in cost drivers, as many of the HPS1.5 grants were still in the initial stages so projects visits are planned for the next period (see 2016/17 forecast above). However, M&E costs increased with increased M&E consultancies and activities such as case studies and reviews. All costs to the end of the programme were agreed with the July 2016 contract amendment and are expected to remain within budget; refer 2016/17 forecast above.
The high staff cost of nearly 12% of total costs, reflects the complexity and range of activities undertaken by the programme. Grant management and M&E continue to be significant areas of activity with a high level of interaction with grant holders and the wider health partnerships community. Communication & Engagement are also resource intensive, such as the creation and dissemination of research and learning materials and time spent in non-grant areas such as advocacy and engagement with the UK health sector to create an enabling environment for the partnerships to thrive and help reduce barriers to volunteering.
The largest costs within the grants themselves are travel (average 42%) and training/capacity development (average 23%). Most partnerships deliver activities through a series of short-term visits therefore factors affecting travel and accommodation are key cost drivers. Training/capacity development costs includes venue hire, refreshments, trainee travel and accommodation costs, course materials and resources.
Overall the project is on-track against the original timescale, and on-track to meet end of project spend targets and results.
## VfM performance compared to the original VfM proposition in the business case
The HPS continues to represent VfM at both the individual project level and in THET’s management of the scheme. Delivering a health partnership programme across a highly diverse range of grant projects is a relatively new and challenging area. With ongoing detailed discussions with DFID, THET have undertaken extensive work to develop VfM metrics and to continuously improve VfM in the programme.
For example, many of the HPS1.5 projects incorporate lessons learnt from HPS1 grants which help to improve efficiency and effectiveness, e.g.: more planning and funding for M&E to demonstrate impact; adjusting training courses, teaching methods and logistics in response to trainee feedback; more support (mentoring, funding, incentives) for health workers trained as trainers to help cascade training to others; more emphasis on engaging leaders and / or building leadership skills to create a supportive environment for change; more emphasis on clinical audit to identify problems, measure effectiveness and enhance support.
Economy is being continuously achieved. On travel, grant holders obtain competitive quotes, charity fares, and make advance bookings. Partnerships are encouraged to explore remote ways of working and THET uses Skype as a means of communication with grant applicants/holders to reduce travel costs. On training, where possible, partner institutions are used as training venues and travel/accommodation is booked centrally to limit the need to reimburse trainees.
Efficiency is demonstrated in THET’s regular monitoring of HPS; the grant management group meets regularly to track health partnership performance and moves swiftly to address under-performing projects.
At the level of individual projects, examples of increased efficiency are training of trainers (ToTs) to extend the sustainability and reach of skills transfer, and standardising training. Comparisons of the cost per health worker trained have been carried out for a sample of partnerships that had two similar projects funded by HPS. Comparisons showed that the cost to deliver the same/similar training had increased. Analysis showed that the increased costs were due to factors such as: early stage investment in creating ToTs; country differences in venue/accommodation costs; and differences in match-funding/in-kind contributions between projects. Table 2 sets out costs per health worker trained on stroke care in Ghana by the Wessex–Ghana Stroke Partnership.
Table 2: Cost per health worker trained: Stroke care training in Ghana
Grant	Learning outcome	Health worker cadres	LMIC institution type & country	Duration	Number of health workers trained	Cost per HW	Cost per day	Notes
MPIP40 / 2012	Knowledge and competence in four core stroke skills	Doctors, physiotherapists, nurses, psychologist	Korle Bu Teaching Hospital (KBTH), Accra, Ghana	2 days / (1 day for 52 mixed participants; 1 day for 12 nurses)	64	£11.41	£11.41	Total trip length 7 days. 2 x workshops delivered during trip. / £0 project management.
A11 / 2015	Four core skills plus Intermediate skills	Doctors, Medical students, nurses, health care assistants, dietician, physiotherapists, student nurses, student occupational therapists	Korle Bu Teaching Hospital (KBTH), Accra, Ghana	269 hours equivalent to 34 person days of training	138	£22.70	£92.13	Total trip length 13 nights. Training delivered over 10 days. / Includes a figure of £537.65 which is 35% of total project management spend for the reporting period (7 – 12 months).

Value for money in THET’s management of the HPS was evidenced in the reviews THET commissioned in Malawi and Ghana. The reviews collected views of stakeholders on various aspects of the programme and highlighted: the capacity-building benefits of the HPS; the appetite for partnerships; interventions made possible by HPS funding; and overall satisfaction with the management of individual health partnerships and the HPS as a whole. THET has identified ways to address the concerns raised, such as transparency in grant-making and management.
THET extends its technical support and influence through publication of guidelines, case studies, films and policy briefs, which informs the work of policy-makers and practitioners. THET also supports research into health partnerships through an embryonic research network. This leverages the research skills and enthusiasm of practitioners to develop a rigorous evidence base that both demonstrates and underpins VFM in the HPS. For example, see THET’s series in Globalization and Health and its collaboration with the Institute of Global Health Innovation, Imperial College London, to review the uptake of practices (e.g. procedures, technologies, care models, etc.) from Low- or Middle-Income countries (LMICs) into the UK health system.
Effectiveness is demonstrated in the programme’s delivery against expected outputs. At the project level, 92% of tested trainees showed improved skills or performance immediately after training/education. THET has strengthened data collection through technical support to health partnerships and refinement of reporting systems to increase and improve effectiveness data. Crucially, THET now require that partnerships report quantitative benefits data more clearly and comprehensively, with a focus on changes in health worker performance, which will yield further evidence of effectiveness. In addition to outcomes data on capacity building in LMICs, THET collects data from UK health workers on the value of their volunteering experiences for their work in the UK, in terms of improved competencies and innovative approaches.
Equity is demonstrated in those attending training/educational opportunities and the proportion who show improved skills or performance immediately after training/education.
On assessment of populations served by partnership projects, initial analysis of data provided to-date on populations is provided in table 3 below.

Table 3: Populations served by HPS partnership projects
Population	Projects with data	Projects proportionately reaching population	Projects disproportionately reaching population
The very poor	27	21 (78%)	15 (54%)
Women and girls	38	33 (87%)	23 (61%)
Rural people	39	14 (47%)	11 (39%)
People with disabilities	24	9 (38%)	6 (25%)

## Assessment of whether the programme continues to represent value for money
The programme reached 8 of a total of 14 outputs in this review period, but did not reach the outcome milestones, largely because this has been a transitional period for the programme as HPS1 grants ended and HPS1.5 programmes got underway. THET are confident they will achieve programme targets by the completion date, with the exception of Outcome indicator 4 and Output 1.1, which require some revision (see Annual Outcome Assessment and Output 1 sections above). However, the programme’s theory of change and assumptions will remain valid. The programme also continues to represent value for money, and to this end, THET continues to work with partners to ensure efficient and effective project implementation, and have further strengthened data collection and VFM analysis which is enabling more ways to understand and enhance programme performance.
## Quality of financial management
Of the £30.2 million, 6-year project budget, expenditure stood at around £26 million by June 2016, which represents approximately 86% of the total budget. With only a few small grants to be awarded in the final year, the programme expects to complete within budget.
An extensive reconciliation of THET’s expenditure to-date against their contract budget was undertaken during the review period, and agreement reached on use of remaining funds to strengthen the programme in advance of a contract amendment in July 2016. All financial reports and invoices over the review period were on time and accurate. THET have also proactively maintained accurate and timely forecasting (approximately within 5% accuracy).
In July 2016, the DFID HPS Project Officer carried out a spot check of THET’s internal financial systems and accounting, (reviewed 3 grant payments, international travel, recording of receipts/income, and processes for payments for the programme), HPS staff list, risk register and procedure, fraud and conflict of interest registers and policies. The spot check found processes and adherence to policies to be good. During the annual review visit to Ethiopia in July, the HPS SRO observed THET carry out a routine audit of a 2-year, £244k grant (Strengthening Africa Club Foot treatment at CURE Ethiopia Children’s hospital) where management of the project budget, training expenditure/vouchers, procurement processes, separation of duties for payroll and payments, were scrutinised and found to be robust, accurate and in good order. Menzies LLP, Tavistock Square London, independently audited THET’s accounts for year ended 31st December 2014. The audit report, submitted to DFID in August 2015, clearly accounts for DFID funds and expenditure, including for project grants, and the auditor found THET’s financial statements to be true and fair.

Date of last narrative report / Date of last monthly financial report	3 June 2016 / 25h April 2016
Date of last audited annual statement	For year ending December 2014, received 14 August 2015

# E: RISK (½ page)
## Overall risk rating: Moderate
This programme was approved with a risk rating of Low. Based on DFID’s new risk framework launched in March 2016 (severe, major, moderate, minor) it is now categorised as overall as Moderate risk.
## Overview of programme risk
There has been some change to the risk environment, related to the UK immigration environment and the approaching end of the programme.

There has been a change to the UK immigration environment as some UK grant holders are finding it increasingly difficult to obtain short-term visas for developing country partner visits to the UK which creates the risk that in-country capacity building and training will be undermined by an inability to complete training in the UK. THET are engaging more with partnerships who are struggling to secure visas to help resolve problems; e.g. by securing six month visas. Partnerships have also engaged UK MPs to expedite visas.

The approaching end of the programme in June 2017 has created new risk to the management of the programme as THET staff leave and institutional knowledge is lost. THET Head of Partnerships is proactively managing staff attrition by ensuring key roles are filled by experienced/qualified staff. An experienced Senior Partnerships Manager has committed to a contract to the end of the project, and the M&E team are being strengthened to ensure robust evidenced-based reporting is provided at the end of the programme. Some staff attrition within the grants management team is manageable as there will be few new grant awards with related and inception activities; mainly just regular monitoring of existing projects. While all HPS grant projects are due to complete and report by May 2017, for the ongoing partnerships, the lack of continued funding and technical support risks loss of momentum and potentially missed opportunities to build on existing successes. THET will mitigate risk to the health partnerships by alerting them so they can plan for the future, and by encouraging them to focus further on sustainability in their partnerships and projects.

Review of project-level risks is a standing item at THET’s fortnightly Grants Management Group meeting. Alongside the programme-level risk matrix, the Group maintains a RAG rating on all grants. ‘Red’ grants, and those failing to improve trigger a case review and appropriate plan of action. If severe, cases are reported at Board meetings until satisfactory risk mitigation has been achieved. This has not been needed during this review period.

THET have robust grant award processes which further mitigate against risks for the new grants. This includes detailed discussions with applicants on proposals; focussed monitoring and evaluation support at pre and post selection stage; partnership assessments for shortlisted applications and organisational due diligence assessments for grants over £100k. For live grants, THET carry out ongoing monitoring visits which include financial verification/audit checks of the projects; DFID joined a visit to 7 projects in Ethiopia in July 2016. THET also provide robust Duty of Care, Fraud management and Procurement toolkits to grantees and ensure that these are understood and adhered to.
Recommendation: THET to provide DFID with a phase-out/ exit strategy, by October 2016. The strategy should include a plan for managing staff resources, a detailed monitoring and evaluation plan with activities to proactively obtain all required data in-time for final HPS analysis/reporting, and activities to support health partnerships to focus further on sustainability in their partnerships and projects.
## Outstanding actions from Due Diligence/Fiduciary Risk Assessment /Programme Risk Matrix
There are no outstanding actions.
# F: COMMERCIAL CONSIDERATIONS (½ page)
## Delivery against planned timeframe
THET are on track with delivery of the programme and disbursement of funds by the end of the programme in June 2017. They are making minor reallocations of funds as projects coming to an end defer payments due to under-spend; and are reallocating the under-spend to strengthen programme results, e.g. additional funds being provided to the Knowledge, Sustainability and Exchange grants, THET annual conference, and Uganda office. With the end of the HPS approaching, THET are working with grant holders to ensure projects complete within the timeframe. Given the learning taken from the HPS1 grants, the grant management team are approaching grant-holders currently underspending to enable alterations to be made in good time since the option of providing no-cost extensions, available in previous funding cycles, is no longer available.
## Performance of partnership(s)
Strong productive partnerships exist between DFID and THET and THET with their grant holders. DFID and THET hold regular formal quarterly catch-up meetings, and have ongoing day-to-day informal engagement on delivery of the HPS, and on wider health partnership discussions. DFID and THET also have productive engagement with the health partnership community in the UK and overseas. DFID’s Health Services team engages with DFID country offices on the HPS, including to up-date them on HPS projects operating in their countries. THET staff engage with opinion-formers in many different contexts, such as membership of the NHS International Health Group, and co-chairmanship of the NHS International Volunteering Group.
THET continues to maintain good relationships with grant holders as evidenced by the feedback provided under Output 4 above. In the past year, THET has worked with grantees to strengthen their duty of care /deployment practices and financial/procurement management. THET, who mainly engages with UK partners, have been exploring ways to increase the engagement and support to partners overseas. For example, the opening of the THET Partnerships Office in Uganda (which has the greatest number of HPS projects), is a pilot to explore how greater support and coordination can be provided to partnerships in-country. THET’s webinar presentation series also showcases and connects partnerships working in similar thematic areas.
## Asset monitoring and control
THET purchased office equipment in 2012 and 2013 with HPS funding, which is recorded in THET’s asset register, adjusted to reflect the portion of assets attributable to HPS. All assets are assigned serial numbers and labelled. They are depreciated over three years using the straight line depreciation method. Assets are located in THET’s office which is accessed by code locked door with closed windows reinforced by iron bars. The office is within a secured building with 24-hour security. Assets deemed to be at the end of their useful life will be disposed of by IT Green to comply with the WWE Directive ensuring hard drives are wiped and shredded. A spot check of assets was undertaken by DFID in July 2016: all assets that DFID purchased were identified.
# G: CONDITIONALITY (½ page)
## Update on partnership principles (if relevant)
NA
# H: MONITORING & EVALUATION (½ page)
## Evidence and evaluation
DFID has commissioned an independent evaluation of the HPS, which will be finalised in October 2016. The evaluation will examine the health partnership model that has been implemented in the programme. The focus is on the effectiveness of the programme as a whole, plus learning about what works and what does not work in the current programme’s approach. The evaluation will inform the final stages of the programme and wider lesson learning about volunteering and building health worker capacity in developing countries, and reciprocal benefits of partnerships, and associated volunteering in the UK. The evaluation will also help to inform thinking on any future partnerships work. As part of the inception phase for the evaluation in April, the programme’s Theory of Change (ToC) was updated.
Furthermore, THET commissioned a study which developed a Theory of Change (ToC) for the partnership between the Association of Anaesthetists of Great Britain and Ireland, and the Association of Anaesthesiologists of Uganda. The study’s focus was on the relationships between individuals and between institutions and used a ToC approach to explore these factors. It found many of the characteristics THET expected in strong health partnerships such as institutional relationships, respect, and learning; but it also highlighted aspects that have had less attention in the past, including the importance of individual relationships, the effect of partnership activities on health workers’ motivation, and the flexible development of the partnership. The study has provided more evidence of how health partnerships work, an essential counterpart to THET’s studies of the impact of health partnership projects. Further studies are planned to broaden the evidence base for identifying strong partnerships and support their development.
New evidence: There is a growing quantity of research emerging from health partnerships and published in a range of journals. THET also facilitate meetings bringing together researchers and stakeholders to discuss methods, models and challenges needed to strengthen understanding of health partnerships.
Evidence is disaggregated as far as possible by the following variables, although the quality of the data collected at country level is inconsistent (note, some variables were not specified at the start of the HPS):
- health workers involved in the projects is disaggregated by gender and cadre;
- trained health workers is disaggregated by the trainer type (project team / volunteer or trainers trained as part of the project); health partnerships also now report the number of days of training provided;
- approved protocols is disaggregated by the level at which the protocol is approved;
- health services and health systems strengthening is disaggregated by health theme and level of healthcare;
- health institutions is disaggregated by population served (poor, very poor, women and girls, rural, disability);
- patients is disaggregated by gender.
## Monitoring progress throughout the review period
Beneficiary feedback: Project monitoring visits to Ethiopia in July 2016 included discussions with health workers benefitting from HPS projects in two major rural university hospitals in Gondar and Jimma and in Addis. The majority of health workers described their partnerships with UK institutions as effective, respectful and reciprocal. There was a high level of enthusiasm for the training and capacity development support provided by the UK partners, describing training as highly interactive, with high quality trainers and training materials; one theatre nurse described her UK trainer as ‘awesome’. However, it appeared that some of the newer projects still need to strengthen M&E processes and post training assessments with some health workers still awaiting feedback. These are areas that the evaluation, currently underway, will be able to assess more comprehensively and report on. The evaluation will also assess service users, who are not captured by THET’s monitoring.
Monitoring activities: DFID hold quarterly catch-up meetings with key THET staff to review progress reports, progress against the logframe, financial management and expenditure and to discuss wider health partnerships issues, in addition to frequent informal engagement. Formal 6-monthly progress reports in December and July are reviewed and remedial actions agreed. The 6-monthly reports also feed into the annual review. As part of the annual review, DFID and THET visited seven projects in Ethiopia in July (EB3, F6, A2.14, D2.33, A2.01, D10, and A2.02). The visits confirmed what is reported in the annual review. Projects were strategic and met the identified needs of the overseas partners, health outcomes where evident, and the partnerships were highly valued.
THET support all health partnerships to plan, monitor, evaluate and report on their projects, and use the information they provide to inform this report and sharing and learning activities. THET monitoring activities in this reporting period included: overseas project visits and audits between May – October 2015 to Malawi, India, Uganda and Myanmar, sharing and learning events in London July 2015 and April 2016.
This review was finalised by the SRO for HPS, in consultation with the policy adviser for the programme, based on a self-assessment by THET and the joint visit to Ethiopia, June 2016. The data presented are based on health partnership narrative and financial reports, and health partnership and volunteer surveys.