Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Transparency for Health Outcomes
Programme Value: £1.4m (DFID contribution) / Joint funded project, total value $8.2m		Review Date: May 2016
Programme Code: / 203209-103	Start Date: April 2014	End Date: March 2018

Summary of Programme Performance
Year	2013/14	2014/15	2015/16
Programme Score	A	A	A
Risk Rating	Minor	Minor	Medium

Summary of progress and lessons learnt since last review
Overview: Transparency for Development (T4D) is a five-year (2013-2018) implementation, evaluation and outreach project led by the Harvard Kennedy School in collaboration with the Results for Development Institute. In the year 2015/16 (Year 3), T4D made progress in implementing research activities in Indonesia and Tanzania. This year T4D’s major activities have been:
- Finishing Phase 1 pilots in last two Indonesian villages;
- Completing Phase 1 baseline surveys and analysis;
- Conducting Phase 1 qualitative research (still ongoing);
- Implementing Phase 1 interventions in 200 villages in Tanzania and Indonesia;
- Finishing Phase 1 interventions in 100 villages in Indonesia;
- Revising and beginning to implement the T4D outreach and dissemination strategy, which now includes blogs, videos, guidebooks, and other bespoke outputs;
- Finalising and proposing a research design for Phase 2 that builds on lessons learned.

As shown by the above activities, T4D made relatively more progress in 2015/16 than previous years and is currently on track according to the revised timeline approved in March 2015. However, the overall project is behind schedule and the final analysis of endline data is likely to take place at the end of Year 5 (2018). T4D plans to request donors to allow a no cost extension of the project. DFID will consider this proposal on its merits.
Lessons: T4D’s final research design for Phase 1 combines quantitative and qualitative methods to measure the overall effectiveness of bespoke community-driven interventions and the contexts in which they are achieved. To share lessons learned implementing the research in Tanzania and Indonesia, T4D published a 2016 paper “Transparency for Development Project Intervention Design”[1]. In addition, T4D has made all intervention materials (e.g. scorecards, action stories, facilitator manuals) available online for other researchers.
[1] http://t4dev.org/sites/default/files/file-uploads/Intervention%20Design%20Description%202016%2004_0.pdf
Summary of recommendations for the next year
The T4D logframe should be revised in relation to recent progress refining the Phase 2 design and updated Communications strategy:
1. Ensure Phase 2 does not lose focus on testing the hypothesis of a link between improved transparency and accountability and health outcomes (T4D, ongoing).
2. Ensure that each sub-output has meaningful indicator for each year, drawn from workplan (DFID and T4D agree revised indicators and milestones by July 2016).
3. Update workplan and financial forecast to reflect recent progress and expected completions (by July 2016).
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Quest 3952459
DevTracker Link to Log frame:	Quest 5200465

Outline of the programme
Recent decades have seen a vast expansion of health services across much of the developing world. But the quality of these services is often lacking, due in part to poor governance such as lack of positive incentives for frontline service providers to perform well, poor management (including financial management), and poor training. “Transparency and accountability” (T/A) is seen as one potential solution to some of these problems, working to ensure that citizens and those who represent them have information to hold their governments accountable for better services.
‘Transparency for Health Outcomes’ (generally known as the ‘Transparency for Development’ or T4D) is a five year project (2013-2018) led by the Harvard Kennedy School (HKS) in collaboration with Results for Development Institute (R4D) that seeks to answer the question of whether community-led transparency and accountability interventions can improve health outcomes, and in what contexts.
Project partners include the University of Washington (US), Pattiro (Indonesia), Clinton Health Access Initiative (Tanzania), and Abdul Latif Jameel Poverty Action Lab (J-PAL) SE Asia office (Indonesia).
DFID contributes £1.4m (~25%) to the project which has a total budget of US $8,211,195. The project partners are the Bill and Melinda Gates Foundation; William and Flora Hewlett Foundation; plus the Transparency and Accountability Initiative (T/AI – also co-funded by DFID).
The project has four overlapping phases (currently at the final stage of Phase 1):
1. Design - a community-led project involving local civil society partners, for a mixed method evaluation that incorporates randomized controlled trials (RCTs) and qualitative methodologies.
2. Phase 1 - implementation of the design in two settings – Tanzania and Indonesia.
3. Phase 2 - to address the design and testing of replication studies in other countries.
4. Outreach and Dissemination - across all stages of the project.
The overall expected outcome is that policymakers, donors, practitioners, academics and other experts have access to better evidence and engage in evidence-informed discussions about whether and how T/A can improve health outcomes.
A decade of research into the impact of T/A interventions has produced mixed evidence as to whether these interventions have beneficial impacts, and much less on the extent of these benefits. Furthermore, available research has not provided an empirically verified account of what sorts of T/A strategies are best suited to different conditions and contexts. Reformers, policymakers, donors, and other practitioners lack clear guidance on what sorts of T/A interventions to pursue — or, whether any T/A interventions can ultimately improve service delivery and health outcomes for poor people.
T4D will deliver the following:
- High quality, policy relevant research products on the impact, generalizability, and scalability of T/A interventions being completed (Output One);
- Learning from co-design process is accessible to practitioners (particularly CSOs) that implement T/A interventions (Output Two); and
- Evidence from research products being widely disseminated to T/A practitioners and donors, policymakers, academics, and other experts (Output Three).
Significant progress must be achieved on all of these for the expected outcome to be delivered.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
T4D has made faster progress over the past year than in previous years. The completion of baselines for Phase 1, scale-up of activities, nearly complete Phase 2 research design, and increased efforts to communicate findings are all signs that the slow start is translating into more rapid implementation. Progress towards the two outcome indicators is as follows:
Outcome indicator 1: Number of key stakeholders (as identified in the outreach and dissemination strategy development) attending presentations and/or consultations where study design, results, and the policy implications are discussed. (targets for 2015/16 – 25; 2016/17 -50; 2017/18 -100).
By end of 2015/16, T4D had presented study design and early results to >200 people working on transparency and accountability, health, and related policy areas.
Outcome indicator 2: Number of Google Scholar Citations of T4D papers and research products (2015/26 – 2; 2016/17 – 5; 2017/18 - 20).
- As of 29/04/2016, T4D’s conceptual paper ‘Does Transparency Improve Governance[2]’ published in the Annual Review of Political Science had 26 citations on Google Scholar (an increase of 20 over the past year), exceeding the 2016/17 milestone.
  [2] Kosack, S; and Fung, A (2014) Does Transparency Improve Governance? Annual Review of Political Science, VOL 17.
- In 2016, T4D published a paper entitled ‘Transparency for Development Project Intervention Design’, setting out the final research design and related research tools. In 2015/16, T4D published 4 new blogs and 1 webinar on early lessons learned during research implementation.
Overall output score and description

‘A’ – the iterative process being followed in the design and development of Phase 2 caused delays and a slow start of the project. The project is now on track with the revised schedule and is ‘meeting expectations’ – and exceeding some milestones.

Key lessons

T4D’s progress over the past year has already started to uncover valuable lessons about how to design, implement and evaluate a transparency and accountability project to generate comparable results across contexts, while also capturing the context specific circumstances that can explain any changes measured or observed. Lessons from 2015/16 are numerous and include:
- The value of maintaining flexibility in the qualitative data collection. By staggering data collection T4D was able to improve qualitative data. T4D made adjustments to reporting requirements when they learned what observations ethnographers were making and what information was missing. This resulted in more comprehensive and useful data.
- The value of ethnography. Although the ethnographic component has been challenging, information received is proving valuable. Reports provide a much better overview of the types of cultural, historical, political, and economic context factors that play a role in each intervention. Early qualitative findings have identified that communities are not engaging with governments as expected, which has implications for the overall T/A hypothesis. Despite significant and positive behaviour change amongst local communities, there is little evidence of citizens demanding improved services from district or higher level governments.This information is being used to inform the Phase 2 intervention design. Combining the RCT with ethnographies therefore helps mitigate the risk of any unexplained positive or null effects.

Key actions:	the logframe should be revised to provide more challenging targets e.g. outputs 2.2 (target 100 but achieved 643), 3.2 and 3.3 (both have targets of 50 but 3.2 achieved over 1,000 and 3.3 over 500 – what is a reasonable expectation for Year 4 targets?)

Has the logframe been updated since the last review?

Yes – to reflect the recommendations from the 2015 Annual Review.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	High quality, policy relevant research products on the impact, generalizability, and scalability of T/A interventions are completed.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Progress towards testable theoretical framework for which T/A approaches are appropriate under which conditions.	Brief written and disseminated including how theoretical framework included in intervention (Year 3).	Completed. T4D have effectively used internet blogs to raise awareness with a range of interested parties (CSOs) and have reached over 500views . / T4D are working to further widen the dissemination and specifically target the academic community. This academic dissemination is targeted for the 1st quarter of year 4 of the project. / Milestone to be revised.
1.2 Development of an intervention that can be rigorously evaluated	Intervention design report written and disseminated based on phase 1 intervention (Year 3). / Completion of 2 briefs presenting work from the pilot (Year 3).	Completed – documents available for download from the T4D website and the Harvard Kennedy School Ash Centre blog, and the Results for Development blog
1.3 Number of published, peer-reviewed research papers based on study results and research citations of study results.	None until year 4	Not measured as only in 3rd year of project

The project is on track overall in relation to the revised timeline. Major milestones related to Phase 1 implementation and Phase 2 design have been acieved.
Early quantitative baseline information and qualitative evidence, including in-depth ethnographies, has highlighted promising signs that the flexible approach to design and implementation is having positive results in terms of community behaviours.
One of the early unexpected findings is that despite significant and positive behaviour change amongst local communities, there is little evidence of citizens demanding improved services from district or higher level governments. The design for Phase 2 will reflect this and test new interventions to increase their engagement with the government engagement. However, care will need to be taken not to lose focus on health outcomes.
Recommendation: T4D to ensure that changes to Phase 2 design do not divert attention from testing the main hypothesis: that T/A interventions can have health related outcomes.

Output Title	Learning from co-design process is accessible to practitioners (particularly CSOs) that implement T/A interventions
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of implementing partners that report having benefitted and learned from the co-design process.	6 (Year 5 milestone)	Next milestone due in year 5. / Having already met the year-2 target of 2 partners, T4D are on track to reach 6 partners by year 5. T4D is already interacting with other organisations in the transparency, accountability and health fields. / T4D’s initiatives are already being implemented in project partner’s other projects (Pattiro) and reaching wider audiences in the fields of education and rights of people with disabilities.
2.2 Number of downloads and views of briefs, blog posts, and other practical guides on the tradeoffs, major considerations, and design choices in improving transparency and accountability in health (particularly by women’s empowerment groups).	100	Exceeded – The 4 blogs produced in 2015/16 have had 643 views Blogs have the highest audience numbers . / T4D delivered materials directly to organisations and practitioners focused on women’s empowerment and rights, including PEKKA (Indonesia) and other CSOs. / Milestone to be revised.
(2.3) Number of communities in which the T/A intervention has been successfully implemented.	Launched in 200 villages (Year 3).	Achieved – launched in all 200 villages. / There is a real expectation of meeting the Year 4 target of completing intervention in all 200 villages by September 2016. / 100 villages have already been completed (Indonesia)

As discussed in Output 1, the co-design and implementation process is showing signs of achieving positive behaviour change. DFID collected feedback from T4D’s two NGO partners working on this and noted that the partnerships are mutually beneficial. Despite not always fully agreeing on issues like per diems for local participants, progress was good in both Tanzania and Indonesia.
T4D surpassed exactions for 2015/16 in several areas. New blogs reached a much larger audience than anticipated with a total of 643 views. Because of a failure with the analytics software T4D was unable to capture all downloads in Year 3, but 38 downloads have been tracked in the month prior to this review. T4D was able to reach all 200 villages receiving the intervention, as well as completing interventions in 100 villages.
Recommendation: T4D and DFID should revise log-frame indicators to set stretching but realistic targets for views and downloads.

Output Title	Evidence from research product is widely disseminated to T/A practitioners and donors, policymakers, academics, and other experts.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		Milestones	Progress
3.1 Progress toward the development of an outreach and dissemination strategy including the identification of key stakeholders		Strategy updated to include more detail on results dissemination activities. (Year 3).	Completed. / New milestone to be added.
3.2 Number of downloads of research papers, policy briefs, and other materials on project results.		Number = 50 (Year 3).	Milestone exceeded. / 1058 downloads of the paper in the first year of publication (Annual Review of Political Science website). Due to system failure there has been a loss of analytics but there have been 30 downloads in April 2016. / There have also been 20 Citations (26 in total). / Only one paper available “Does Transparency Improve Governance” - due to the number of sites this is available from and the frequency in which the publishers analyse the data it is difficult to say exactly how many downloads have been taken. / Milestones to be revised.
(3.3) Number of downloads of blogs, thought pieces, podcasts, and other media products on lessons from the research and implementation process	Number = 50 (Year 3)		Milestone exceeded –533 views of the four blogs published in 2015/16. / Note: – the output is defined as downloads of blogs but the data is for views of blogs. / Milestones to be revised.

T4D continually monitors and applies the dissemination strategy by targeting a diverse range of audiences including donors, researchers, implementers, and policymakers in the T/A, health, and evaluation fields and organisations focused on women’s empowerment and rights as well as other programs on gender budgeting (as covered in output 2.2 above).
T4D has widely disseminated the theoretical framework and design process through blogs on their website. Dissemination continues through academic, policy, and practitioner events including:
- Presentation made to the Gates Foundation (June 2015)
- Presentation to members of the Health Governance and Finance team at Abt Associates (June 2015),
- Results for Development internal seminar (July 2015)
- Presentation to the Asia Public Policy Forum (sponsored by USAID, Harvard, Indonesian Ministry of Health, Indonesian Ministry of Finance, and the Health Financing and Governance project): (August 2015)
- Harvard Ash Center seminar (October 2015)
- Seminar for the World Bank and Open Government Partnership (October 2015)
- Presentation to the Primary Health Care Performance Initiative group (including representatives from the Gates Foundation, Ariadne Labs, the World Bank and R4D) (March 2016)
Blogs:
- “How to empower people and save babies” (March 2016 – 250 views):
- “Failing Fast” (March 2016 – 70 views):
- “Does the world need another toolkit?” (March 2016 – 77 views):
- “The surprising power of stories for accountability” (April 2016 – 136 views):
Summary of responses to issues raised in previous annual reviews (where relevant)
The final research design was presented to the Steering Committee as recommended in the 2015 Annual Review. Phase 1 is underway and activities will be completed ontime according to the revised workplan. After a second round of consultations the Phase 2 design is nearly completed and reflects lessons learned from initial Phase 1 findings.
Recommendations
The T4D logframe needs to be updated to set suitable performance targets for subsequent years.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are direct/indirect staff, travel, research consumables and management costs.
The overall DFID budget is £1.4m (towards a joint total fund of US $8.2m) which HKS manages within its own financial regulations. HKS’s good practice standards are passed on to partners and aim to obtain VFM – Economy, Efficiency, and Effectiveness – in spending on all aspects of the project. T4D has confirmed that it adheres to the Counter Fraud and Whistleblowing Unit commitments.
HKS provides a forecast of the projected spend on a rolling annual basis which is supported with a workplan. Payment is made on an annual basis to match the funding mechanism of the other project partners. DFID has just received the revised workplan and forecast for FY 2016/17 and will shortly receive a statement of projected spend for the remainder of the project based on the revised workplan. T4D/HKS have indicated that a request to extend the project, at no additional financial cost, will be submitted to the Steering Committee in the next few months. We will be setting up the budget accordingly.
Payment is made in US dollars. HKS has disbursed an equivalent of £737k in total, including £131k for last FY(compared with £444k in the previous year,and £162k in T4D’s first year). Although HKS has underspent on the project as a whole due to the delays in project activities, the spend of DFID’s funds is currently in line with expectations of the revised workplan and logframe.
T4D has continued to work with partners to find savings in existing budget lines such as linking travel arrangements from their work on other projects to coincide with this project to reduce travel costs, using possible longer term realtionships and commitments with partners to agree lower costs and making use of skype and other internet based systems to maintain contact and open communication between partners.
VfM performance compared to the original VfM proposition in the business case
Overall the programme is still expected to achieve its intended outputs and outcome, and these are still appropriate. However, results will be available slightly later than expected, which will somewhat reduce the overall VFM of the project. The key risk to VFM would be if the project fails to prove or disprove its core hypothesis that T/A interventions can improve health outcomes.

Assessment of whether the programme continues to represent value for money
Yes – the programme continues to represent value for money in economy and efficiency terms. However, ultimate VFM depends on the quality and policy relevance of final research produced and its uptake. Delays could reduce vfm in ‘effectiveness’ terms.This is also referred to in the risk section.
Quality of financial management
The DFID agreement with HKS requires that funds be disbursed directly to them and covers specific budget items by category and has to be supported with an annual statement which minimises any financial risk. HKS is responsible for the overall financial management of the programme and applies its own organisational financial regulations across the program to ensure proper control and efficient use of resources.. The project funds are reported accurately showing spend by each of the 3 individual donors. The workplan for the coming period will take account of the proposed extension period.
Date of last narrative financial report	May 2015 (with email attaching report – to be quested)
Date of last audited annual statement	March 2015 (2016 audited statement yet to be supplied)

## E: RISK (½ page)

Overall risk rating: Major
Delays - including earlier external influences (local elections) –are affecting delivery and this is reflected bythe forthcoming request for a no cost extension request. T4D has to date managed to continue working on other aspects of the project when delays have occured to maintain project momentum.
Overview of programme risk
The programme has completed year 3 and HKS has designed interventions that will engage, improve the debate, and improve the practice of stakeholders in T/A, health, and evaluation fields. Despite delays, progress is advancing more or less as the theory of change anticipated.
The key risk to the projects overall outcome is whether T4D actually delivers evidence that tests the hypothesised link between T/A and health outcomes. Phase 1 suggests that T/A interventions may lead to positive behavior changes in communities without increasing demand for better services. In response to this finding Phase 2 will increase a greater focus on increasing government involvement. It will however be vital to ensure that Phase 2 is still designed in such a way as to test whether T/A interventions impact on health outcomes. Clear evidence that either supports or refutes a link between T/A and health outcomes would be valuable, but if we judge there is a significant risk of failure to robustly test the hypothesis DFID would need to seriously reconsider its funding.
Risk matrix assessments are the same as last year and will be updated as the project progresses, and translated into DFID new 4 point scale. Mitigation factors have also been updated.
HKS is proposing to submit a request to extend the project by a further year, at no additional cost, to allow for the endline data collection for Tanzania that’s timetabled for the second half of Year 5 of the project. As a consequence of this, the RCT analysis will extend beyond the “current” final year of the project. And publication of resultswould fall into the subsequent year.
Outstanding actions from risk assessment
T4D, DFID, Gates and Hewlett should review the implications of the proposed extension period.
DFID’s starting position is that extensions are never truly ‘no cost’ as the budget for core expenses such as salary costs is increased to cover the extension period and there is an opportunity cost in terms of other planned interventions that we are not able to fund during the period of the extension.
There is also a need to ensure that DFID has sufficient resources (financial and administrative capacity) to allow an extension. In order to maximise the efficiency and effectiveness of the use of staff time, Research and Evidence Division is working to reduce the number of small projects that it funds. DFID will therefore need to examine carefully the internal vfm implications of a no cost extension before approving it.
DFID will discuss with the other donors whether DFID funds could be spent out according to the current project period, with other donors covering the spend in any extension period.
F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

As noted above T4D is behind track overall –endline data collection for Tanzania (scheduled for year 5) will be late as a result of early delays. However T4D reports that it is on track to complete all activities in the workplan for Year 4 according to schedule. This includes completion of Phase 1 intervention (already complete in Indonesia), completion of qualitative data collection for Phase 1, and design, partner selection, and intervention and evaluation launch for Phase 2. While they do not currently have major dissemination activities outlined in the workplan for Year 4, they anticipate having several products and events to continue outreach around T4D lessons and experiences in Year 4.

Performance of partnership(s)
We judge that the partnership between T4D’s constituent organisations and its donor partners is working well – contact is regular, business and decisions are presented clearly, and reporting is accurate and timely. UK Aid represents a minority contribution to T4D’s budget, and the Steering Committee is the approval authority. DFID has a seat on the SC but decision making is by consensus.

Asset monitoring and control
A single laptop has been purchased using DFID funds and will HKS retain it on record against this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The four partnership principles are not relevant in this period.
The GCSD team has ensured that T4D’s research in Tanzania and Indonesia is recorded in country by country records of DFID’s centrally managed programmes, and DFID Tanzania in particular has been kept updated of work in country.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
In addition to the ongoing project management, reporting requirements and logframe indicators, T4D continues to monitor intervention implementation and the data collection for evaluation. Intervention monitoring uses a five-pronged approach 1) Facilitator reports, 2) CSO supervision, 3) Team observation (local study coordinators frequently visit the field to observe the intervention progress and quality of facilitation), 4) Qualitative data collection as a means of monitoring, and 5) Phone checks (Tanzania only).
The T4D team worked to ensure successful implementation of the RCT baseline survey and qualitative data collection in both countries. In both Indonesia and Tanzania, project PIs observed the survey piloting activities, and study coordinators and/or team members observed the training of enumerators for both the qualitative and quantitative data collection.

Monitoring progress throughout the review period
This annual review was carried out during April and May 2015, by a team of 4 DFID staff (A2 GA leading, B1 Programme Manager and A2 Quality Assurer).
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and reviewing key research and communication outputs.
The Annual Review report has been shared in with HKS and will be followed up at the next project meeting with responses to the recommendations in this report.
Quest Documents :
HKS Annual Report: Quest Number 5446538
Phase 2 Concept Note: Quest Nnumber 5386787
2015 DFID Annual Review Report : Quest Number 5017901
2014 DFID Annual Review Report : Quest Number 4499764
Logical framework : Quest Number 4997041
Dissemination strategy shown in HKS Report : Quest Number 4997035
Feedback from partners:
PATTIRO : Quest Number 5446472
CHAI : Quest Number 5446434
T4D blog series