ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Foundation for Civil Society Programme
Country or region targeted	Tanzania
Type of cost extension	Cost Scale-Up Extension
Original project budget.	£8.8 million
Original project start and end dates	June 2011 to March 2015
Cost extension value	£1,900,000
New project end date	March 2015
Business Case Quest Document No.	3435802

INFORMATION
What is the project’s purpose?
Project impact: Tanzania is democratically governed and has achieved its 2025 vision in the fight against poverty and a better quality of life for all its citizens. / Project outcome: To empower more citizens (especially the poor and marginalized) to influence and monitor policies that meet their needs and participate in the planning and budgeting processes for improvement of service delivery in Tanzania
What is the objective of the cost extension?
The objective of this cost increase is to enable Foundation for Civil Society provides grants to about 350 civil society organizations to enhance participation of additional 2.4 million citizens (60% women) in governance and accountability processes for improved delivery of basic social and livelihood services including access to land, and women and youth participation in development process
What is the additional and total support the UK will provide?
The UK will provide an additional support of £1,900,000. A new total support by the UK to the Foundation for Civil Society will now be £10.7 million over the lifetime of the project i.e. June 2011 to March 2015
What are the expected results?
DFID’s additional support to the Foundation for Civil Society will contribute to the attainment of the following specific results: / SUMMARY OF KEY RESULTS TO BE DELIVERED AS A RESULT OF OBTAINING EXTRA SUPPORT / STRATEGIC PRIORITY INDICATOR EXPECTED RESULTS / Governance Number of people supported to have choice and control over their own development and hold decision makers to account 501,496 (88% female) empowered to understand their land ownership rights as provided by Land Act No. 5 of 1999. / 1,202,492 elderly people (43% female) empowered to understand their rights as provided in the National Aging Policy 2003. / 93,000 elderly people access free medical services / 184,630 youth (61% female) encouraged to participate in development process at village and ward levels. / 1,500,000 people empowered to understand the importance of demanding and attending village statutory meetings. / 400 villages regularly posted reports on income and expenditure on public notice boards. / 776,388 people (45% female) empowered to understand rights of people living or affected by HIV/AIDS as provided by National Policy on HIV/AIDS 2007. / Wealth creation Rural men and women raise their incomes 600 women economically empowered through obtaining customary certificates of land ownership. / Education Children supported in primary and lower secondary education 249 (46% girls) MVCs enabled to attend school. / 250 school committees formed and their capacity to oversee management of respective schools strengthened.
Impact on Gender Equality / FCS programme is expected to make positive contribution to gender equality through its work to strengthen organizations representing women and marginalized groups, and its work to promote women’s rights and entitlements. FCS will also tackle violence against women and girls. Some of the gender-sensitive performance indicators of the FCS programme during this extension include: number of females empowered to: a) understand and ownership rights as provided by Land Act No. 5 of 1999; and b) participate in development process at village and ward levels. FCS has ongoing interventions that support smaller CSOs to mobilize local communities and campaigns against discriminatory laws; and, prevention and response to gender-based violence. On a more practical level, strengthening the capability of small CSOs should lead to an improvement of accountability processes between the state and citizens and consequently an improvement in the delivery of services for men, women and children. Through this extension, FCS seeks to particularly provide targeted support to 600 women to obtain customary certificate of land ownership, to strengthen their economic position.
What is the approach to implementation?
Foundation for Civil Society will use DFID’s additional funds to provide grants to on-going grantees. These grantees were competitively selected using a transparent process, a clear criteria and upon completing all the required due diligence processes. / FCS will provide DFID with detailed narrative and financial implementation report, as well as independently audited report as already identified in the existing Accountable Grant Letter.
Describe any key changes to the original business case?
Nil